## Code Codes
Code | Name | Qty | UOM | Mhs | Qty/MH | Projected Forecast | Spent? | blank? | Spent to Date | Committed to Date | Qty to Date | Mhs to Date | Labor Rate | Labor | Subcontract | Consumable | Permanent Material | Equipment | Other | System Projected Cost | Variance | november | December | January | February | March | April | May | June | July | August | September | October | Final Cost | Breakdown Type | Cost Category 1 | Cost Category 2 | Equal?
00-0001 | SECOND FLOOR APARTMENT REMOVALS | 7 | EA | 0 | 1 | 14032 | TRUE | FALSE | 14032 | 19333.9 | 0 | 0 | 110 | 0 | 14032 | 0 | 0 | 0 | 0 | 14802 | 770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14032 | SOV | Labor | Change Order | TRUE
00-0002 | SITE 8 SLAB SHORING | 60 | HR | 60 | 1 | 15736.31 | TRUE | FALSE | 15736.31 | 15736.31 | 60 | 60 | 108.6935 | 6521.61 | 0 | 9214.7 | 0 | 0 | 0 | 15736.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15736.31 | SOV | Labor | Change Order | TRUE
00-0003 | OG8 Obstruction Removal | 144 | HR | 155.5 | 0.92605 | 17042.53 | TRUE | FALSE | 17042.53 | 17042.53 | 144 | 155.5 | 109.5983 | 17042.53 | 0 | 0 | 0 | 0 | 0 | 17042.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17042.53 | SOV | Labor | Change Order | TRUE
00-0004 | Floor Drain PCO | 0 | NA | 0 | 1 | 17791.39 | TRUE | FALSE | 17791.39 | 18807.42 | 180.5 | 164.5 | 98.754 | 0 | 0 | 0 | 0 | 0 | 17791.39 | -33.7147 | -17825.1047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17791.39 | SOV | Labor | Change Order | TRUE
00-0005 | Equipment Pad PCO | 100 | CY | 145.28 | 0.68833 | 15000 | FALSE | FALSE | 8025.02 | 8025.02 | 34.02 | 72.5 | 110.6899 | 15000 | 0 | 0 | 0 | 0 | 0 | 18635.2857 | 3635.2857 | 1743.745 | 1743.745 | 1743.745 | 1743.745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | Phased | Labor | Change Order | TRUE
00-0006 | PCO 15 Additional Windows PCO | 2 | EA | 66.67 | 0.029999 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 7333.7 | 7333.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Labor | Change Order | TRUE
00-0007 | IRMA PAGAN APARTMENT MOVE | 0 | NA | 0 | 1 | 2500 | TRUE | FALSE | 2500 | 2500 | 0 | 0 | 110 | 0 | 0 | 2500 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | SOV | Labor | Change Order | TRUE
00-0008 | National Grid Gas Line Relocation | 90.5 | EA | 90.5 | 1 | 11667.88 | TRUE | FALSE | 11667.88 | 11667.88 | 90.5 | 90.5 | 109.6147 | 9920.13 | 0 | 1747.75 | 0 | 0 | 0 | 11667.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11667.88 | SOV | Labor | Change Order | TRUE
00-0009 | Bracing for POE Penetration Through SG4 Wall | 44.5 | EA | 44.5 | 1 | 7468.26 | TRUE | FALSE | 7468.26 | 8688.34 | 44.5 | 44.5 | 111.1519 | 4946.26 | 0 | 2522 | 0 | 0 | 0 | 7468.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7468.26 | SOV | Labor | Change Order | TRUE
00-0010 | SG1 RELOCATE BELONGINGS | 161 | EA | 193 | 0.8342 | 21773.44 | TRUE | FALSE | 21773.44 | 22076.26 | 161 | 193 | 95.137 | 18361.44 | 0 | 3412 | 0 | 0 | 0 | 21773.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21773.44 | SOV | Labor | Change Order | TRUE
00-0011 | PERAMBULATOR ROOM DEMO | 450 | EA | 467.43 | 0.96271 | 18064.37 | TRUE | FALSE | 18064.37 | 18064.37 | 177 | 177 | 102.0586 | 18064.37 | 0 | 0 | 0 | 0 | 0 | 47005.5523 | 28941.1823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18064.37 | SOV | Labor | Change Order | TRUE
00-0012 | OG8 Tank Removal | 1 | EA | 185.26 | 0.0053978 | 20378.14 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 20378.14 | 0 | 0 | 0 | 0 | 0 | 20378.6 | 0.46 | 20378.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20378.14 | Phased | Labor | Change Order | TRUE
00-0013 | Exist Bldgs Bracing due to Penetrations | 0 | NA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Labor | Change Order | TRUE
00-0014 | SG4 DEMO FOR STEEL BEAMS INSTALL | 160 | HR | 160 | 1 | 1285.34 | TRUE | FALSE | 1285.34 | 1285.34 | 13 | 13 | 98.8723 | 1285.34 | 0 | 0 | 0 | 0 | 0 | 15819.5692 | 14534.2292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.34 | SOV | Labor | Change Order | TRUE
00-0015 | SG5 DEMO FOR STEEL BEAMS INSTALL | 17 | HR | 17 | 1 | 1678.93 | TRUE | FALSE | 1678.93 | 1678.93 | 17 | 17 | 98.7606 | 1678.93 | 0 | 0 | 0 | 0 | 0 | 1678.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1678.93 | SOV | Labor | Change Order | TRUE
00-0016 | OG4 BRACING FOR POE PENETRATION | 92.69 | HR | 1503.76 | 0.061639 | 164120.78 | FALSE | FALSE | 25291.89 | 34089.29 | 92.69 | 110.5 | 101.096 | 150000 | 0 | 14120.78 | 0 | 0 | 0 | 25291.89 | -138828.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25291.89 | hold | Contingency |  | FALSE
00-0017 | National Grid Additional Allowance | 1 | LS | 58.5 | 0.017094 | 205770.46 | FALSE | FALSE | 5887.46 | 146714.44 | 1 | 58.5 | 100.6403 | 5887.46 | 199883 | 0 | 0 | 0 | 0 | 5887.46 | -199883 | 0 | 199883 | 49970.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255741.21 | SOV | Labor | Change Order | FALSE
00-0018 | SG6 Additional Strobe | 0 | LS | 0 | 1 | 2387.08 | FALSE | FALSE | 0 | 2387.08 | 0 | 0 | 110 | 0 | 2387.08 | 0 | 0 | 0 | 0 | 0 | -2387.08 | 0 | 2387.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2387.08 | SOV | Labor | Change Order | TRUE
00-0019 | ODWYER FENCE INSTALL | 5000 | LF | 565.41 | 8.8431 | 60000 | FALSE | FALSE | 57179.96 | 64206.75 | 1385.04 | 540 | 105.8888 | 60000 | 0 | 0 | 0 | 0 | 0 | 100465.9211 | 40465.9211 | 0 | 2820.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | SOV | Labor | Change Order | TRUE
00-0021 | MOVE PLAYGROUNDS | 19 | HR | 19 | 1 | 1941.36 | TRUE | FALSE | 1941.36 | 1941.36 | 19 | 19 | 102.1768 | 1941.36 | 0 | 0 | 0 | 0 | 0 | 1941.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1941.36 | SOV | Labor | Change Order | TRUE
00-0022 | SITE 8 CLEANING | 57 | HR | 57 | 1 | 5968.61 | TRUE | FALSE | 5968.61 | 5968.61 | 57 | 57 | 104.7125 | 5968.61 | 0 | 0 | 0 | 0 | 0 | 5968.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5968.61 | SOV | Labor | Change Order | TRUE
00-0023 | S8 FIRE STAND PIPE ACCESS | 610 | HR | 531.21 | 1.1483 | 64306.79 | FALSE | FALSE | 7156.91 | 7156.91 | 61 | 61 | 117.3264 | 64306.79 | 0 | 0 | 0 | 0 | 0 | 63249.3681 | -1057.4219 | 57149.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64306.79 | SOV | Labor | Change Order | TRUE
00-0024 | Boiler Stack Support | 6.5 | HR | 6.5 | 1 | 64820.84 | FALSE | FALSE | 796.41 | 796.41 | 6.5 | 6.5 | 122.5246 | 796.41 | 64024.43 | 0 | 0 | 0 | 0 | 796.41 | -64024.43 | 0 | 0 | 32012.215 | 32012.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64820.84 | SOV | Labor | Change Order | TRUE
00-0025 | Bulletin 1 Civil PCO 44 | 5780 | CY | 501.93 | 11.5155 | 76640 | FALSE | FALSE | 21986.42 | 22370.19 | 187 | 132.5 | 119.5388 | 60000 | 0 | 16640 | 0 | 0 | 0 | 80045.3462 | 3405.3462 | 0 | 10930.716 | 10930.716 | 10930.716 | 10930.716 | 10930.716 | 0 | 0 | 0 | 0 | 0 | 0 | 76640 | SOV | Labor | Change Order | TRUE
00-0026 | DOOR HARDWARE CHANGES | 1 | LS | 199.52 | 0.005012 | 21947.23 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 21947.23 | 0 | 0 | 0 | 0 | 0 | 21947.2 | -0.03 | 0 | 0 | 0 | 0 | 21947.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21947.23 | SOV | Labor | Change Order | TRUE
00-0027 | BOILER ACCESSORY SUPPLY | 1 | LS | 1718.03 | 0.00058206 | 185547.35 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 185547.35 | 0 | 0 | 0 | 0 | 0 | 188983.3 | 3435.95 | 0 | 185547.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185547.35 | SOV | Labor | Change Order | TRUE
00-0028 | SITE 8 ELECTRICAL REPAIRS | 1 | LS | 196.33 | 0.0050935 | 21203.36 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 21203.36 | 0 | 0 | 0 | 0 | 0 | 21596.3 | 392.94 | 0 | 21203.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21203.36 | SOV | Labor | Change Order | TRUE
00-0029 | PCO46 SANITARY VENTING OG5 & OG6 | 1 | LS | 640.82 | 0.0015605 | 69207.97 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 69207.97 | 0 | 0 | 0 | 0 | 0 | 70490.2 | 1282.23 | 0 | 69207.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69207.97 | SOV | Labor | Change Order | TRUE
00-0030 | PCO 54 ACM ABATEMENT MASONRY WATERPROOFING | 1 | NA | 1118.83 | 0.00089379 | 120833.26 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 120833.26 | 0 | 0 | 0 | 0 | 0 | 123071.3 | 2238.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Labor | Change Order | FALSE
00-0031 | PCO 55 ACM ABATEMENT UTILITY WATERPROOF | 1 | LS | 2238.83 | 0.00044666 | 241793.37 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 241793.37 | 0 | 0 | 0 | 0 | 0 | 246271.3 | 4477.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Labor | Change Order | FALSE
00-0032 | PCO 64 OG10 ADDITIONAL SWITCH | 0 | LS | 0 | 1 | 2369.68 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 2369.68 | 0 | 0 | 0 | 0 | 0 | -2369.68 | 0 | 2369.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2369.68 | SOV | Labor | Change Order | TRUE
00-0033 | PCO 66 ELECTRICAL DB FOUNDATION CONFLICT | 1 | LS | 227.82 | 0.0043894 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 25060.2 | 25060.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Labor | Change Order | TRUE
00-0034 | PCO 76 ADDITIONAL FIRE EXTINGUISHERS | 16 | HR | 35.28 | 0.45351 | 3809.76 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 3809.76 | 0 | 0 | 0 | 0 | 0 | 3880.8 | 71.04 | 0 | 0 | 0 | 0 | 3809.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3809.76 | SOV | Labor | Change Order | TRUE
00-0035 | PCO 77 ACM ABATEMENT SGS STEAM PIPE | 1 | LS | 1033.24 | 0.00096783 | 111590.33 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 111590.33 | 0 | 0 | 0 | 0 | 0 | 113656.4 | 2066.07 | 111590.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111590.33 | SOV | Labor | Change Order | TRUE
00-0036 | PCO 99 SG5 APARTMENT RENO | 56.74 | HR | 30.5 | 1.8603 | 9892.17 | TRUE | FALSE | 9892.17 | 9892.17 | 56.74 | 30.5 | 104.8269 | 3197.22 | 0 | 6694.95 | 0 | 0 | 0 | 9892.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9892.17 | SOV | Labor | Change Order | TRUE
00-0037 | JACOBS TRAILER MOVE | 26 | HR | 26 | 1 | 2879.76 | FALSE | FALSE | -30038.69 | -30038.69 | 26 | 26 | 110.76 | 35798.21 | 0 | -32918.45 | 0 | 0 | 0 | -30038.69 | -32918.45 | 32918.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.76 | SOV | Labor | Change Order | TRUE
00-0038 | PCO 59 SGS REDESIGN | 600 | HR | 359.66 | 1.6682 | 557295.88 | FALSE | FALSE | 4726.71 | 4726.71 | 42.5 | 42.5 | 111.2167 | 40000 | 517295.88 | 0 | 0 | 0 | 0 | 41893.5629 | -515402.3171 | 552569.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 557295.88 | SOV | Labor | Change Order | TRUE
00-0039 | AC UNIT DEMO | 74.5 | HR | 74.5 | 1 | 7582.95 | TRUE | FALSE | 7582.95 | 7582.95 | 74.5 | 74.5 | 101.7846 | 7582.95 | 0 | 0 | 0 | 0 | 0 | 7582.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7582.95 | SOV | Labor | Change Order | TRUE
00-0040 | PCO 8 BULLETIN 1 ELECTRICAL | 0 | LS | 0 | 1 | 38953 | FALSE | FALSE | 0 | 38953 | 0 | 0 | 110 | 0 | 38953 | 0 | 0 | 0 | 0 | 0 | -38953 | 38953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38953 | SOV | Labor | Change Order | TRUE
00-0041 | PCO 19 WINDOW INFILL | 0 | LS | 0 | 1 | 5922.43 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 5922.43 | 0 | 0 | 0 | 0 | 0 | -5922.43 | 5922.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5922.43 | SOV | Labor | Change Order | TRUE
00-0042 | PCO 40 SG6 STUD RELOCATION | 0 | LS | 0 | 1 | 10923.98 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 10923.98 | 0 | 0 | 0 | 0 | 0 | -10923.98 | 10923.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10923.98 | SOV | Labor | Change Order | TRUE
00-0043 | PCO 59 SGS ELECTRICAL CHANGES | 2 | NA | 2 | 1 | 0 | FALSE | FALSE | 213.43 | 213.43 | 2 | 2 | 106.715 | 0 | 0 | 0 | 0 | 0 | 0 | 213.43 | 213.43 | -213.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Labor | Change Order | TRUE
00-0044 | PCO 74 OG9 AND S8 GENERATOR SUPPORTS | 0 | LS | 0 | 1 | 60248.81 | FALSE | FALSE | 0 | 60248.81 | 0 | 0 | 110 | 0 | 60248.81 | 0 | 0 | 0 | 0 | 0 | -60248.81 | 60248.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60248.81 | SOV | Labor | Change Order | TRUE
00-0045 | PCO 79 ACM FILING | 0 | LS | 0 | 1 | 4500 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | -4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | SOV | Labor | Change Order | TRUE
00-0046 | PCO 85 OG4 & OG5 TANK INSULATION ACM | 0 | LS | 0 | 1 | 75690.92 | FALSE | FALSE | 0 | 75690.92 | 0 | 0 | 110 | 0 | 75690.92 | 0 | 0 | 0 | 0 | 0 | -75690.92 | 75690.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75690.92 | SOV | Labor | Change Order | TRUE
00-0047 | PCO 90 ODYWER TRAILER POWER | 0 | NA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Labor | Change Order | TRUE
00-0048 | PCO 45 BULLETIN 1 MECHANICAL | 0 | LS | 0 | 1 | 154900.73 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 154900.73 | 0 | 0 | 0 | 0 | 0 | -154900.73 | 154900.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154900.73 | SOV | Labor | Change Order | TRUE
00-0049 | PCO 83 SG6 METAL PANEL SUPPORT | 0 | LS | 0 | 1 | 70919.49 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 70919.49 | 0 | 0 | 0 | 0 | 0 | -70919.49 | 70919.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70919.49 | SOV | Labor | Change Order | TRUE
00-0050 | PCO 63 Conduit Concrete Encasement | 0 | NA | 0 | 1 | 225393.38 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 12847.88 | 212545.5 | 0 | 0 | 0 | 0 | 0 | -225393.38 | 225393.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225393.38 | SOV | Labor | Change Order | TRUE
00-0051 | PCO 49 Electrical Clash with LPS | 0 | LS | 0 | 1 | 9430.53 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 9430.53 | 0 | 0 | 0 | 0 | 0 | -9430.53 | 9430.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9430.53 | SOV | Labor | Change Order | TRUE
00-0052 | PCO 93 Roof Access and ATS Door | 0 | NA | 0 | 1 | 125820.09 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 125820.09 | 0 | 0 | 0 | 0 | 0 | 0 | -125820.09 | 124115.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124115.6 | SOV | Labor | Change Order | FALSE
00-0053 | PCO 100 Exterior Framing OG8, OG9, OG10 | 0 | NA | 0 | 1 | 204711.04 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 204711.04 | 0 | 0 | 0 | 0 | 0 | 0 | -204711.04 | 204711.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204711.04 | SOV | Labor | Change Order | TRUE
00-0054 | PCO 48 Restore Walkways | 54.5 | LS | 54.5 | 1 | 7586.21 | TRUE | FALSE | 7586.21 | 7586.21 | 54.5 | 54.5 | 139.1965 | 7586.21 | 0 | 0 | 0 | 0 | 0 | 7586.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7586.21 | SOV | Labor | Change Order | TRUE
00-0055 | Pit Covers | 0 | NA | 0 | 1 | 0 | TRUE | FALSE | 0 | 10811.29 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Labor | Change Order | TRUE
00-0056 | PCO 27 OG8 Structural Steel | 0 | NA | 0 | 1 | 94993.6 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 94993.6 | 0 | 0 | 0 | 0 | 0 | -94993.6 | 94993.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94993.6 | SOV | Labor | Change Order | TRUE
00-0057 | PCO 80 LPS Reroute OG6 | 0 | NA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Labor | Change Order | TRUE
00-0058 | PCO 98 OG6 Structural Steel | 16 | NA | 16 | 1 | 1612.44 | TRUE | FALSE | 1612.44 | 1612.44 | 16 | 16 | 100.7775 | 1612.44 | 0 | 0 | 0 | 0 | 0 | 1612.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1612.44 | SOV | Labor | Change Order | TRUE
00-0059 | PCO 117 OG1 Ramp Restore | 0 | NA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SOV | Labor | Change Order | TRUE
00-1000 | Revenue | 0 | NA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
01-6000 | BUILDING CONDITIONS SUB | 1 | LS | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
01-6100 | CPM SUB | 37 | MO | 0 | 1 | 73150 | FALSE | FALSE | 58860 | 69685 | 28 | 0 | 110 | 0 | 73150 | 0 | 0 | 0 | 0 | 59850 | -13300 | 0 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 1299.0909 | 73150 | monthly | Sub |  | TRUE
01-6200 | PHOTO SUB | 37 | MO | 0 | 1 | 87990 | FALSE | FALSE | 44170 | 87990 | 28 | 0 | 110 | 0 | 87990 | 0 | 0 | 0 | 0 | 45160 | -42830 | 0 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 3983.6364 | 87990 | monthly | Sub |  | TRUE
01-6300 | OVERHEAD PROTECTION LABOR | 864 | SF | 183.43 | 4.7102 | 1472.69 | TRUE | FALSE | 1472.69 | 7292.69 | 60 | 12 | 122.7242 | 1472.69 | 0 | 0 | 5820 | 0 | -5820 | 22420.6996 | 20948.0096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1472.69 | spent | spent |  | TRUE
01-6310 | OVERHEAD PROTECTION MATERIALS | 239 | LF | 0 | 1 | 4491.11 | TRUE | FALSE | 4491.11 | 5320.77 | 0 | 0 | 110 | 0 | 0 | 3668 | 1652.77 | 0 | -829.66 | 30781.11 | 26290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4491.11 | spent | spent |  | TRUE
01-6320 | OVERHEAD PROTECTION EQUIPMENT | 0 | NA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
01-6400 | RODENT CONTROL SUB | 1 | LS | 0 | 1 | 28596.9 | FALSE | FALSE | 13373.9 | 38642.09 | 0 | 0 | 110 | 0 | 28596.9 | 0 | 0 | 0 | 0 | 13483.9 | -15113 | 0 | 2000 | 2000 | 2000 | 2000 | 1223 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 28596.9 | monthly | Sub |  | TRUE
01-6410 | RODENT CONTROL SUB SUPPORT | 1 | LS | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
02-1000 | EROSION CONTROL FABRIC | 34000 | SF | 97.88 | 347.3641 | 970.55 | TRUE | FALSE | 970.55 | 970.55 | 1200 | 9.5 | 102.1632 | 970.55 | 0 | 0 | 0 | 0 | 0 | 10617.3483 | 9646.7983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 970.55 | spent | spent |  | TRUE
02-1100 | INLET PROTECTION | 0 | EA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
02-1200 | SILT FENCE | 0 | LF | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
02-1300 | STABILIZED CONSTRUCTION ENTRANCE | 0 | SF | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
02-1400 | MANTAIN EROSION CONTROL | 0 | WK | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
02-1500 | REMOVE EROSION CONTROL | 0 | LO | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
02-1600 | STOCKPILE | 6 | EA | 94.25 | 0.06366 | 4496.62 | TRUE | FALSE | 4496.62 | 4496.62 | 2.61 | 41 | 109.6737 | 4496.62 | 0 | 0 | 0 | 0 | 0 | 10336.8794 | 5840.2594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4496.62 | spent | spent |  | TRUE
02-1700 | REMOVE FENCE | 9050 | LF | 581.54 | 15.5621 | 62785.26 | FALSE | FALSE | 22631.82 | 22631.82 | 4580 | 210.5 | 107.5146 | 62785.26 | 0 | 0 | 0 | 0 | 0 | 53513.8554 | -9271.4046 | 0 | 0 | 7879.8 | 7879.8 | 7879.8 | 7879.8 | 7879.8 | 0 | 0 | 0 | 0 | 0 | 62030.82 | Phased | Labor | Site Demo | FALSE
02-1800 | REMOVE/REINSTALL BOLLARDS ODG EAST | 32 | EA | 511.99 | 0.062501 | 51378.15 | FALSE | FALSE | 627.92 | 627.92 | 12 | 6 | 104.6533 | 51378.15 | 0 | 0 | 0 | 0 | 0 | 34116.3326 | -17261.8174 | 0 | 8458.3717 | 8458.3717 | 8458.3717 | 8458.3717 | 8458.3717 | 8458.3717 | 0 | 0 | 0 | 0 | 0 | 51378.15 | Phased | Labor | Site Demo | TRUE
02-1900 | REMOVE FULL DEPTH ASPHALT PVMT | 79200 | SF | 665.48 | 119.0118 | 75977.83 | FALSE | FALSE | 71315.16 | 71315.16 | 64443.38 | 623 | 114.4706 | 75977.83 | 0 | 0 | 0 | 0 | 0 | 85508.6937 | 9530.8637 | 0 | 777.1117 | 777.1117 | 777.1117 | 777.1117 | 777.1117 | 777.1117 | 0 | 0 | 0 | 0 | 0 | 75977.83 | Phased | Labor | Site Demo | TRUE
02-2000 | REMOVE SITE FURNISHING | 117 | EA | 751.43 | 0.1557 | 77397.6 | FALSE | FALSE | 36144.22 | 36144.22 | 90 | 327.5 | 110.364 | 77397.6 | 0 | 0 | 0 | 0 | 0 | 55282.107 | -22115.493 | 0 | 6875.5633 | 6875.5633 | 6875.5633 | 6875.5633 | 6875.5633 | 6875.5633 | 0 | 0 | 0 | 0 | 0 | 77397.6 | Phased | Labor | Site Demo | TRUE
02-2100 | REMOVE CONCRETE CURB & STEPS | 9930 | LF | 838.97 | 11.8359 | 93000 | FALSE | FALSE | 80039.57 | 80039.57 | 8482.4 | 711.5 | 112.4941 | 93000 | 0 | 0 | 0 | 0 | 0 | 93798.2129 | 798.2129 | 0 | 1833.3933 | 1833.3933 | 1833.3933 | 1833.3933 | 1833.3933 | 1833.3933 | 0 | 0 | 0 | 0 | 0 | 91039.93 | Phased | Labor | Site Demo | FALSE
02-2200 | REMOVE PVMTS | 156053 | SF | 967.35 | 161.3201 | 107421.11 | FALSE | FALSE | 80077.9 | 80077.9 | 87283.4 | 702 | 114.0711 | 107421.11 | 0 | 0 | 0 | 0 | 0 | 128705.5828 | 21284.4728 | 0 | 4443.095 | 4443.095 | 4443.095 | 4443.095 | 4443.095 | 4443.095 | 0 | 0 | 0 | 0 | 0 | 106736.47 | Phased | Labor | Site Demo | FALSE
02-2300 | BASEMENT MAINTENANCE | 2112 | HR | 2973.03 | 0.71039 | 312373.79 | FALSE | FALSE | 236562.08 | 236562.08 | 2112 | 2210 | 99.1802 | 295000 | 0 | 17373.79 | 0 | 0 | 0 | 236562.08 | -75811.71 | 0 | 8640 | 8640 | 8640 | 8640 | 8640 | 8640 | 8640 | 4320 | 4320 | 4320 | 2107.71 | 312109.79 | Phased | Labor | Site Maintenance | FALSE
02-3000 | CORE DRILLING | 267.19 | EA | 2237.67 | 0.11941 | 533778.73 | FALSE | FALSE | 503581.03 | 606220.29 | 267.19 | 1976.5 | 102.2696 | 232333.62 | 65285 | 236160.11 | 0 | 0 | 0 | 503581.03 | -30197.7 | 0 | 0 | 5877.702 | 5877.702 | 5877.702 | 5877.702 | 5877.702 | 0 | 0 | 0 | 0 | 0 | 532969.54 | Phased | Labor | Site Demo | FALSE
02-6000 | OG-7 DEMO LABOR | 1 | EA | 116.5 | 0.0085837 | 21560.01 | TRUE | FALSE | 21560.01 | 21560.01 | 1 | 116.5 | 109.5061 | 12757.46 | 0 | 8802.55 | 0 | 0 | 0 | 21560.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21560.01 | spent | spent |  | TRUE
02-6001 | OG-7 DEMO EQUIPMENT | 1 | EA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
02-6002 | OG-7 DEMO MATERIAL | 70 | CY | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
02-6005 | PAINT AND PLASTER REMOVAL IN BASEMENTS | 33320 | SF | 3788.98 | 8.7939 | 373189.17 | FALSE | FALSE | 327967.88 | 327967.88 | 21521.75 | 3326 | 98.145 | 371651.44 | 0 | 1537.73 | 0 | 0 | 0 | 459642.7609 | 86453.5909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327967.88 | hold | labor | Site Demo | FALSE
02-6006 | LEAD CONSULTANT | 1 | LS | 0 | 1 | 19466.75 | TRUE | FALSE | 19466.75 | 38243.07 | 0 | 0 | 110 | 0 | 0 | 19466.75 | 0 | 0 | 0 | 19576.75 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19466.75 | spent | spent |  | TRUE
02-6007 | LEAD DISPOSAL | 13.19 | CY | 0 | 1 | 5400.21 | TRUE | FALSE | 5400.21 | 20005.08 | 0 | 0 | 110 | 0 | 0 | 5400.21 | 0 | 0 | 0 | 6851.11 | 1450.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400.21 | spent | spent |  | TRUE
02-6008 | LEAD TRAINING | 14 | EA | 133.89 | 0.10456 | 8249.33 | TRUE | FALSE | 8249.33 | 10442.93 | 6 | 45 | 95.9407 | 4317.33 | 0 | 3932 | 0 | 0 | 0 | 15589.6133 | 7340.2833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8249.33 | spent | spent |  | TRUE
02-6009 | Paint Removal Elevator Pits | 12 | EA | 671.98 | 0.017858 | 67200 | FALSE | FALSE | 1052.44 | 1052.44 | 0.2 | 10.5 | 100.2324 | 67200 | 0 | 0 | 0 | 0 | 0 | 67284.0261 | 84.0261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1052.44 | hold | labor | Site Demo | FALSE
02-6010 | REMOVE SUMP PUMPS | 36 | EA | 340.56 | 0.10571 | 36030 | FALSE | FALSE | 25020.91 | 25020.91 | 25 | 236.5 | 105.7967 | 36030 | 0 | 0 | 0 | 0 | 0 | 36030.1104 | 0.1104 | 0 | 1805.515 | 1805.515 | 1805.515 | 1805.515 | 1805.515 | 1805.515 | 0 | 0 | 0 | 0 | 0 | 35854 | Phased | Labor | Site Demo | FALSE
02-6015 | DEMO EXISTING VENT, WINDOW, AND FRAME | 185 | EA | 995.56 | 0.18583 | 102770 | FALSE | FALSE | 70550.03 | 70550.03 | 127 | 683 | 103.2943 | 102770 | 0 | 0 | 0 | 0 | 0 | 102790.4138 | 20.4138 | 0 | 5369.995 | 5369.995 | 5369.995 | 5369.995 | 5369.995 | 5369.995 | 0 | 0 | 0 | 0 | 0 | 102770 | Phased | Labor | Site Demo | TRUE
02-6020 | DEMO EXISTING DOOR, FRAME AND HARDWARE | 24 | EA | 208 | 0.11538 | 19766.24 | FALSE | FALSE | 1088.47 | 1088.47 | 1 | 11 | 98.9518 | 19766.24 | 0 | 0 | 0 | 0 | 0 | 20812.8658 | 1046.6258 | 0 | 3112.9617 | 3112.9617 | 3112.9617 | 3112.9617 | 3112.9617 | 3112.9617 | 0 | 0 | 0 | 0 | 0 | 19766.24 | Phased | Labor | Site Demo | TRUE
02-6025 | REMOVE AREAWAYS LABOR | 52.17 | CY | 789.02 | 0.06612 | 82000 | FALSE | FALSE | 68245.4 | 68245.4 | 40.5 | 647 | 105.4798 | 82000 | 0 | 0 | 0 | 0 | 0 | 86862.2901 | 4862.2901 | 0 | 2050.3233 | 2050.3233 | 2050.3233 | 2050.3233 | 2050.3233 | 2050.3233 | 0 | 0 | 0 | 0 | 0 | 80547.34 | Phased | Labor | Site Demo | FALSE
02-6026 | REMOVE AREAWAYS EQUIPMENT | 52.17 | CY | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 5738.7 | 5738.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
02-6030 | PREPARE EXISTING WALL SURFACE FOR PAINT | 9460 | SF | 2363.1 | 4.0032 | 227761.46 | FALSE | FALSE | 385.53 | 385.53 | 880 | 4 | 96.3825 | 227761.46 | 0 | 0 | 0 | 0 | 0 | 206959.9008 | -20801.5592 | 0 | 37895.9883 | 37895.9883 | 37895.9883 | 37895.9883 | 37895.9883 | 37895.9883 | 0 | 0 | 0 | 0 | 0 | 227761.46 | Phased | Labor | Site Demo | TRUE
02-6035 | REMOVE EXISTING PORTION WALL SITE-8 | 0.22 | CY | 16 | 0.01375 | 1520.48 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 1520.48 | 0 | 0 | 0 | 0 | 0 | 1760 | 239.52 | 0 | 253.4133 | 253.4133 | 253.4133 | 253.4133 | 253.4133 | 253.4133 | 0 | 0 | 0 | 0 | 0 | 1520.48 | Phased | Labor | Site Demo | TRUE
02-6040 | SAWCUT OPENINGS THROUGH SLAB FOR CELLAR VENIT | 0.77 | CY | 192 | 0.0040104 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 21120 | 21120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
02-6045 | REMOVE EXISTING AC UNITS AND SLEEVES | 114 | EA | 155.65 | 0.73241 | 15000 | FALSE | FALSE | 3487.09 | 3487.09 | 109 | 34.5 | 101.0751 | 15000 | 0 | 0 | 0 | 0 | 0 | 4177.1047 | -10822.8953 | 0 | 1918.8183 | 1918.8183 | 1918.8183 | 1918.8183 | 1918.8183 | 1918.8183 | 0 | 0 | 0 | 0 | 0 | 15000 | Phased | Labor | Site Demo | TRUE
02-6050 | DEMO STAIRS AND RAMPS LABOR | 15.07 | CY | 168.01 | 0.089697 | 17116.64 | FALSE | FALSE | 12850.76 | 12850.76 | 11.5 | 122 | 105.3341 | 17116.64 | 0 | 0 | 0 | 0 | 0 | 17043.1249 | -73.5151 | 0 | 710.98 | 710.98 | 710.98 | 710.98 | 710.98 | 710.98 | 0 | 0 | 0 | 0 | 0 | 17116.64 | Phased | Labor | Site Demo | TRUE
02-6051 | DEMO STAIRS AND RAMPS EQUIPMENT | 0 | DY | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
02-6055 | SAWCUT SLAB OPENING FOR MECHANICAL | 2.06 | CY | 206 | 0.01 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 22660 | 22660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
02-6060 | DEMO SECOND FLOOR APARTMENTS | 9 | EA | 1486.72 | 0.0060536 | 150000 | FALSE | FALSE | 130767.81 | 130767.81 | 8.71 | 1275.5 | 102.5228 | 150000 | 0 | 0 | 0 | 0 | 0 | 135679.2072 | -14320.7928 | 0 | 4808.0475 | 4808.0475 | 4808.0475 | 4808.0475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | Phased | Labor | Site Demo | TRUE
02-6065 | DEMO FOR MECHANICAL | 2250 | HR | 1999.73 | 1.1252 | 200000 | FALSE | FALSE | 11078.48 | 11078.48 | 107 | 107 | 103.5372 | 200000 | 0 | 0 | 0 | 0 | 0 | 208278.7091 | 8278.7091 | 0 | 0 | 0 | 0 | 0 | 47230.38 | 47230.38 | 47230.38 | 47230.38 | 0 | 0 | 0 | 200000 | Phased | Labor | Site Demo | TRUE
02-6066 | FLOOR DRAIN DEMO | 48 | EA | 725.5 | 0.066161 | 70083.35 | TRUE | FALSE | 70083.35 | 70083.35 | 48 | 725.5 | 96.6001 | 70083.35 | 0 | 0 | 0 | 0 | 0 | 70083.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70083.35 | spent | spent |  | TRUE
02-6070 | DEMO FOR ELECTRICAL | 2213.91 | HR | 2214.2 | 0.99987 | 225000 | FALSE | FALSE | 12339.07 | 12339.07 | 126.5 | 121.5 | 101.5561 | 225000 | 0 | 0 | 0 | 0 | 0 | 224356.1233 | -643.8767 | 0 | 0 | 0 | 0 | 0 | 53077.2325 | 53077.2325 | 53077.2325 | 53077.2325 | 0 | 0 | 0 | 224648 | Phased | Labor | Site Demo | FALSE
02-6075 | DEMO FOR PLUMBING | 2187.94 | HR | 2187.93 | 1 | 211879.62 | FALSE | FALSE | 14739.37 | 14739.37 | 140.5 | 140.5 | 104.9065 | 211879.62 | 0 | 0 | 0 | 0 | 0 | 229528.251 | 17648.631 | 0 | 0 | 0 | 0 | 0 | 49285.0625 | 49285.0625 | 49285.0625 | 49285.0625 | 0 | 0 | 0 | 211879.62 | Phased | Labor | Site Demo | TRUE
02-6080 | ENTRANCE RAMP DEMO | 10 | LO | 1080 | 0.0092593 | 118800 | FALSE | FALSE | 0 | 0 | 0 | 0 | [9 empty] | 29700 | 29700 | 29700 | 27937.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117037.11 | Phased | Labor | Site Demo | FALSE
02-6100 | ASBESTOS SUB | 1 | LS | 0 | 1 | 1554903.14 | FALSE | FALSE | 1263729.48 | 1569944.22 | 0 | 0 | 110 | 0 | 1554903.14 | 0 | 0 | 0 | 0 | 1263839.48 | -291063.66 | 21900 | 30045.3333 | 55216.6667 | 40245.7 | 47319.5 | 34316.6667 | 34316.6667 | 46316.6667 | 13000 | 37000 | 14125 | 0 | 1637531.68 | SOV | Sub |  | FALSE
02-6110 | ASBESTOS SUB SUPPORT | 731 | HR | 734.58 | 0.99513 | 79333.7 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 79333.7 | 0 | 0 | 0 | 0 | 0 | 80803.8 | 1470.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | labor | Sub Support | FALSE
02-6120 | ASEBESTOS CONSULTANT | 9 | EA | 0 | 1 | 23896.55 | TRUE | FALSE | 23896.55 | 84866.98 | 0 | 0 | 110 | 0 | 0 | 23896.55 | 0 | 0 | 0 | 24886.55 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23896.55 | spent | spent |  | TRUE
02-6130 | ASBESTOS SUB ACCESS | 200 | HR | 170 | 1.1765 | 25543.46 | FALSE | FALSE | 21820.5 | 26129.23 | 172 | 170 | 118.2336 | 20099.71 | 0 | 5443.75 | 0 | 0 | 0 | 24634.4594 | -909.0006 | 0 | 0 | 465.37 | 465.37 | 465.37 | 465.37 | 465.37 | 465.37 | 465.37 | 465.37 | 0 | 0 | 25543.46 | Phased | Labor | Sub Support | TRUE
02-7000 | EROSION CONTROL FABRIC CONST MATERIAL | 1 | LS | 0 | 1 | 1900.42 | TRUE | FALSE | 1900.42 | 1900.42 | 0 | 0 | 110 | 0 | 0 | 1900.42 | 0 | 0 | 0 | 2010.42 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1900.42 | spent | spent |  | TRUE
02-7100 | STONE FOR EROSION CONTROL | 405 | CY | 0 | 1 | 32382.03 | TRUE | FALSE | 32382.03 | 47387.21 | 0 | 0 | 110 | 0 | 0 | 32382.03 | 0 | 0 | 0 | 76932.03 | 44550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32382.03 | spent | spent |  | TRUE
02-7200 | SOIL TESTING | 35 | EA | 0 | 1 | 83535 | TRUE | FALSE | 83535 | 93315 | 0 | 0 | 110 | 0 | 0 | 83535 | 0 | 0 | 0 | 87385 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83535 | spent | spent |  | TRUE
03-1000 | FORMWORK NEW BUILDING | 62292 | SF | 19019.7 | 3.2751 | 2150000 | FALSE | FALSE | 2095505.55 | 2095505.55 | 59724.13 | 18548.5 | 112.9744 | 2150000 | 0 | 0 | 0 | 0 | 0 | 2184083.2587 | 34083.2587 | 0 | 0 | 27247.225 | 27247.225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2150000 | Phased | Labor | New Buildings | TRUE
03-1100 | FORMWORK EXIST BLDGS | 23967 | SF | 7605.55 | 3.1513 | 862417.4 | FALSE | FALSE | 494657.54 | 494657.54 | 12223.9 | 4361 | 113.4275 | 862417.4 | 0 | 0 | 0 | 0 | 0 | 917343.9217 | 54926.5217 | 0 | 0 | 59991.8733 | 59991.8733 | 59991.8733 | 59991.8733 | 59991.8733 | 59991.8733 | 0 | 0 | 0 | 0 | 854608.78 | Phased | Labor | Existing Buildings | FALSE
03-1105 | Conduit Encasement | 630 | cy | 1260 | 0.5 | 138600 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 138600 | 138600 | 0 | 34650 | 34650 | 34650 | 30862.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134812.31 | Phased | Labor | Existing Buildings | FALSE
03-1200 | OPERATOR FOR CONCRETE WORK | 993 | CY | 196 | 5.0663 | 29756.82 | TRUE | FALSE | 29756.82 | 29756.82 | 993 | 196 | 151.8205 | 29756.82 | 0 | 0 | 0 | 0 | 0 | 29756.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29756.82 | spent | spent |  | TRUE
03-1300 | SET ANCHOR BOLTS FOR STEEL COLUMNS | 308 | EA | 543 | 0.56722 | 63065.21 | TRUE | FALSE | 63065.21 | 63065.21 | 308 | 543 | 116.1422 | 63065.21 | 0 | 0 | 0 | 0 | 0 | 63065.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63065.21 | spent | spent |  | TRUE
03-1400 | DRILL & GROUT DOWELS | 11714 | EA | 2695.49 | 4.3458 | 274808.11 | FALSE | FALSE | 241327.4 | 241327.4 | 9718 | 2370 | 101.8259 | 274808.11 | 0 | 0 | 0 | 0 | 0 | 288095.6727 | 13287.5627 | 0 | 0 | 6475.152 | 6475.152 | 6475.152 | 6475.152 | 6475.152 | 0 | 0 | 0 | 0 | 0 | 273703.16 | Phased | Labor | Existing Buildings | FALSE
03-1500 | INFILL MASONRY OPENINGS W/ REINFORCED CONCRETE | 164 | CY | 1416.38 | 0.11579 | 162759.19 | FALSE | FALSE | 130598.01 | 130598.01 | 134.7 | 1169 | 111.7177 | 162759.19 | 0 | 0 | 0 | 0 | 0 | 158867.9968 | -3891.1932 | 0 | 0 | 6432.236 | 6432.236 | 6432.236 | 6432.236 | 6432.236 | 0 | 0 | 0 | 0 | 0 | 162759.19 | Phased | Labor | Existing Buildings | TRUE
03-1600 | FORMWORK SITE CONCRETE LABOR | 7400 | SF | 1328.26 | 5.5712 | 150000 | FALSE | FALSE | 83845.85 | 83845.85 | 4290 | 743.5 | 112.7718 | 150000 | 0 | 0 | 0 | 0 | 0 | 146798.2602 | -3201.7398 | 0 | 62266.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146112.22 | Phased | Labor | Site Restoration | FALSE
03-1610 | FORMWORK SITE CONCRETE MATERIAL | 0 | LS | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
03-1700 | CONCRETE REINFORCEMENT NEW BUILDING UNLOAD | 393500 | LB | 487 | 808.0082 | 56763.12 | TRUE | FALSE | 56763.12 | 56763.12 | 393500 | 487 | 116.5567 | 56763.12 | 0 | 0 | 0 | 0 | 0 | 56763.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56763.12 | spent | spent |  | TRUE
03-1800 | CONCRETE REINFORCEMENT BARRIER FOUNDATIONS UNLOAD | 269500 | LB | 395.51 | 681.3987 | 45000 | FALSE | FALSE | 37721.62 | 37721.62 | 269500 | 328 | 115.0049 | 45000 | 0 | 0 | 0 | 0 | 0 | 37721.62 | -7278.38 | 0 | 0 | 1455.676 | 1455.676 | 1455.676 | 1455.676 | 1455.676 | 0 | 0 | 0 | 0 | 0 | 45000 | Phased | Labor | Sub Support | TRUE
03-1900 | POUR CONCRETE NEW BUILDINGS | 4712.2 | CY | 4385 | 1.0746 | 530000 | FALSE | FALSE | 504750.59 | 504750.59 | 4712.2 | 4509.5 | 111.9305 | 530000 | 0 | 0 | 0 | 0 | 0 | 504750.59 | -25249.41 | 0 | 0 | 24623.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529374.1 | Phased | Labor | New Buildings | FALSE
03-2000 | FINISH SLABS - NEW BLDGS | 0 | SF | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
03-2100 | POUR CONC EXIST BLDGS | 1039.5 | CY | 1624.85 | 0.63975 | 170000 | FALSE | FALSE | 173021.93 | 173021.93 | 620.43 | 1630.5 | 106.1159 | 170000 | 0 | 0 | 0 | 0 | 0 | 242533.2766 | 72533.2766 | 0 | 0 | -8512.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164509.72 | Phased | Labor | Existing Buildings | FALSE
03-2110 | SHOTCRETE SUB | 0 | LS | 0 | 1 | 166500 | FALSE | FALSE | 90593.84 | 166500 | 0 | 0 | 110 | 0 | 166500 | 0 | 0 | 0 | 0 | 90593.84 | -75906.16 | 0 | 0 | 25302.0533 | 25302.0533 | 25302.0533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166500 | Phased | Sub |  | TRUE
03-2120 | SHOTCRETE SUB CLEANUP | 277 | HR | 274.2 | 1.0102 | 30000 | FALSE | FALSE | 23324.48 | 23324.48 | 219.94 | 215 | 108.486 | 30000 | 0 | 0 | 0 | 0 | 0 | 29452.116 | -547.884 | 0 | 0 | 2225.1733 | 2225.1733 | 2225.1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | Phased | Labor | Sub Support | TRUE
03-2200 | CONCRETE FOOTING FOR SITE FURNISHING | 150 | CY | 144 | 1.0417 | 13759.32 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 13759.32 | 0 | 0 | 0 | 0 | 0 | 15840 | 2080.68 | 0 | 0 | 0 | 0 | 3439.83 | 3439.83 | 3439.83 | 3439.83 | 0 | 0 | 0 | 0 | 13759.32 | Phased | Labor | Site Restoration | TRUE
03-2300 | CONCRETE DUCTBANKS | 1091 | CY | 2014.27 | 0.54164 | 225000 | FALSE | FALSE | 218768.34 | 218768.34 | 1091 | 1959.5 | 111.645 | 225000 | 0 | 0 | 0 | 0 | 0 | 218768.34 | -6231.66 | 0 | 0 | 6231.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225000 | Phased | Labor | Site Utilities | TRUE
03-2400 | CONCRETE SITE RETAINING WALL AND FOOTINGS | 275 | CY | 356.34 | 0.77173 | 36435.9 | FALSE | FALSE | 15459.02 | 15459.02 | 181 | 133 | 116.2332 | 36435.9 | 0 | 0 | 0 | 0 | 0 | 29616.6335 | -6819.2665 | 0 | 0 | 20976.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36435.9 | Phased | Labor | Site Restoration | TRUE
03-2500 | CONCRETE SHELF AND BOND BEAM EXTG BL (INCL FORMS) | 265 | CY | 952.09 | 0.27834 | 108745 | FALSE | FALSE | 98112.12 | 98112.12 | 265 | 868 | 113.0324 | 108745 | 0 | 0 | 0 | 0 | 0 | 98112.12 | -10632.88 | 0 | 2658.22 | 2658.22 | 2658.22 | 2658.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108745 | Phased | Labor | Existing Buildings | TRUE
03-2600 | PATCH AND REPAIR CONCRETE SUBSTRATE AND MAKE LEVEL | 6650 | SF | 114.33 | 58.165 | 13834.32 | FALSE | FALSE | 726.04 | 726.04 | 0 | 6 | 121.0067 | 13834.32 | 0 | 0 | 0 | 0 | 0 | 14560.7322 | 726.4122 | 0 | 0 | 0 | 0 | 0 | 0 | 3277.07 | 3277.07 | 3277.07 | 3277.07 | 0 | 0 | 13834.32 | Phased | Labor | Existing Buildings | TRUE
03-2700 | EXISTING BLDGS EQUIPMENT PAD WORK | 1 | CY | 1 | 1 | 95.84 | TRUE | FALSE | 95.84 | 95.84 | 0 | 1 | 95.84 | 95.84 | 0 | 0 | 0 | 0 | 0 | 191.68 | 95.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95.84 | spent | spent |  | TRUE
03-5000 | FURNISH CONCRETE | 6563 | CY | 0 | 1 | 1603745.65 | FALSE | FALSE | 1322825.88 | 1603745.65 | 6563 | 0 | 110 | 0 | 0 | 0 | 1603745.65 | 0 | 0 | 1322825.88 | -280919.77 | 63479.445 | 63479.445 | 31739.7225 | 31739.7225 | 31739.7225 | 15869.8612 | 15869.8612 | 0 | 0 | 0 | 0 | 0 | 1576743.66 | phased | Material |  | FALSE
03-5100 | FURNISH INSULATION | 19200 | SF | 0 | 1 | 39414.64 | TRUE | FALSE | 39414.64 | 50669.81 | 14912 | 0 | 110 | 0 | 0 | 0 | 39414.64 | 0 | 0 | 511094.64 | 471680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39414.64 | spent | spent |  | TRUE
03-5200 | FURNISH REBAR | 1714793 | LB | 0 | 1 | 14662.42 | FALSE | FALSE | 13710.55 | 14651.47 | 0 | 0 | 110 | 0 | 0 | 4368.48 | 10293.94 | 0 | 0 | 188640940.55 | 188626278.13 | 237.9675 | 237.9675 | 118.9838 | 118.9838 | 118.9838 | 59.4919 | 59.4919 | 0 | 0 | 0 | 0 | 0 | 14662.42 | phased | Material |  | TRUE
03-5250 | FURNISH WIREMESH | 51750 | SF | 0 | 1 | 47762.13 | FALSE | FALSE | 35283.88 | 50998.16 | 0 | 0 | 110 | 0 | 0 | 0 | 47762.13 | 0 | 0 | 5727783.88 | 5680021.75 | 3119.5625 | 3119.5625 | 1559.7812 | 1559.7812 | 1559.7812 | 779.8906 | 779.8906 | 0 | 0 | 0 | 0 | 0 | 47762.13 | phased | Material |  | TRUE
03-5400 | FURNISH SAKCRETE | 12100 | BG | 0 | 1 | 181500 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 181500 | 0 | 0 | 1331000 | 1149500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material |  | FALSE
03-5500 | FURNISH CONC PATCH MATERIAL | 6650 | SF | 0 | 1 | 9174.5 | TRUE | FALSE | 9174.5 | 9627.4 | 0 | 0 | 110 | 0 | 0 | 0 | 9174.5 | 0 | 0 | 740674.5 | 731500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9174.5 | spent | spent |  | TRUE
03-6000 | FRP WORK | 9064.75 | SF | 2509.22 | 3.6126 | 420253.96 | FALSE | FALSE | 396888.19 | 407921.25 | 9064.75 | 2360 | 99.8666 | 250739.42 | 0 | 0 | 169514.54 | 0 | 0 | 396888.19 | -23365.77 | 0 | 19490.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416379.07 | Phased | Labor | Existing Buildings | FALSE
03-6010 | FRP Self Perform | 0 | HR | 3 | 1 | 33860.62 | TRUE | FALSE | 33860.62 | 35095.13 | 0 | 3 | 127.9767 | 383.93 | 0 | 34711.2 | 0 | 0 | -1234.51 | 33860.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33860.62 | spent | spent |  | TRUE
03-6100 | REBAR SUB | 1 | LS | 0 | 1 | 1494408.08 | FALSE | FALSE | 1201115.52 | 1420047.7 | 0 | 0 | 110 | 0 | 1494408.08 | 0 | 0 | 0 | 0 | 1201225.52 | -293182.56 | 41898.9371 | 41898.9371 | 41898.9371 | 41898.9371 | 41898.9371 | 41898.9371 | 41898.9371 | 0 | 0 | 0 | 0 | 0 | 1494408.08 | phased | Sub |  | TRUE
03-6110 | REBAR SUB SUPPORT | 1 | LS | 41.76 | 0.023946 | 4416.84 | FALSE | FALSE | 347.15 | 347.15 | 0 | 3 | 115.7167 | 4416.84 | 0 | 0 | 0 | 0 | 0 | 5179.478 | 762.638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347.15 | hold | labor | Sub Support | FALSE
03-6120 | REBAR DELIVERY SUPPORT | 36660 | LB | 35 | 1047.4286 | 4041.34 | TRUE | FALSE | 4041.34 | 4041.34 | 36660 | 35 | 115.4669 | 4041.34 | 0 | 0 | 0 | 0 | 0 | 4041.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4041.34 | spent | spent |  | TRUE
03-7000 | FORMWORK MATERIAL | 92612 | SF | 76.82 | 1205.5715 | 709305.66 | FALSE | FALSE | 532783.94 | 631194.62 | 37044.59 | 1 | 1687.22 | 9305.66 | 0 | 700000 | 0 | 0 | 0 | 610551.5781 | -98754.0819 | 44130.43 | 44130.43 | 22065.215 | 22065.215 | 22065.215 | 11032.6075 | 11032.6075 | 0 | 0 | 0 | 0 | 0 | 709305.66 | phased | Material |  | TRUE
03-7100 | MATERIAL FOR FLOWABLE FILL BACKFILL | 920 | CY | 0 | 1 | 152745.59 | TRUE | FALSE | 152745.59 | 196356.98 | 920 | 0 | 110 | 0 | 0 | 152745.59 | 0 | 0 | 0 | 152745.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152745.59 | spent | spent |  | TRUE
04-1000 | CLEAN CONC SURF FOUND WALL/PATCH VOIDS W/MORTAR | 995 | SF | 72 | 13.8194 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 7920 | 7920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
04-6000 | GROUT INJECTION SUB | 1 | LS | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
04-6100 | MASONRY SUB | 1 | LS | 0 | 1 | 9090000 | FALSE | FALSE | 5912809.56 | 9090000 | 0 | 0 | 110 | 0 | 8578380 | 0 | 511620 | 0 | 0 | 5912919.56 | -3177080.44 | 611947.2553 | 383342.623 | 395445.3676 | 489738.8079 | 481858.6487 | 309367.1187 | 390550.1788 | 0 | 0 | 0 | 0 | 0 | 8975059.56 | SOV | Sub |  | FALSE
04-6110 | MASONRY SUB SUPPORT | 1 | LS | 230.34 | 0.0043414 | 69431.6 | FALSE | FALSE | 25393.2 | 126966 | 0 | 0 | 110 | 23034 | 46397.6 | 0 | 0 | 0 | 0 | 50730.6 | -18701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25393.2 | hold | labor | Sub Support | FALSE
04-6120 | MASON EUIP SUPPORT | 462.5 | HR | 473 | 0.9778 | 62569.54 | TRUE | FALSE | 62569.54 | 62569.54 | 462.5 | 473 | 132.2823 | 62569.54 | 0 | 0 | 0 | 0 | 0 | 62569.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62569.54 | spent | spent |  | TRUE
04-6130 | ANGLE FOR FACADE | 786 | LF | 882.05 | 0.89111 | 103266.58 | FALSE | FALSE | 65935.69 | 66701.18 | 786 | 546.5 | 110.099 | 97500 | 0 | 5766.58 | 0 | 0 | 0 | 65935.69 | -37330.89 | 0 | 9088.2475 | 9088.2475 | 9088.2475 | 9088.2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102288.68 | Phased | Labor | Existing Buildings | FALSE
04-6200 | STONE SUB | 1 | LS | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
04-7000 | MASONRY CLEANER | 995 | SF | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 109450 | 109450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
05-6000 | STRUCTURAL STEEL SUB | 1 | LS | 0 | 1 | 5918133.95 | FALSE | FALSE | 5876727.32 | 5983580.98 | 0 | 0 | 110 | 0 | 5866168.95 | 51965 | 0 | 0 | 0 | 5876837.32 | -41296.63 | 53000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5984727.32 | SOV | Sub |  | FALSE
05-6010 | STRUCTURAL STEEL SUB SUPPORT | 176 | HR | 183.72 | 0.95798 | 19997.99 | FALSE | FALSE | 15158.89 | 15158.89 | 116.66 | 140 | 108.2778 | 19997.99 | 0 | 0 | 0 | 0 | 0 | 21865.9266 | 1867.9366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15158.89 | hold | labor | Sub Support | FALSE
05-6020 | GROUT STEEL COLUMNS | 99 | EA | 286.97 | 0.34498 | 30000 | FALSE | FALSE | 24803.43 | 24803.43 | 92.6 | 235 | 105.5465 | 30000 | 0 | 0 | 0 | 0 | 0 | 26761.4862 | -3238.5138 | 0 | 2070.285 | 2070.285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28944 | Phased | Labor | Existing Buildings | FALSE
05-6030 | STEEL & CRANE DELIVERIES | 58.5 | HR | 58.5 | 1 | 9097.96 | TRUE | FALSE | 9097.96 | 9097.96 | 58.16 | 58.5 | 155.5207 | 9097.96 | 0 | 0 | 0 | 0 | 0 | 9150.837 | 52.877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9097.96 | spent | spent |  | TRUE
05-6040 | Ground Prep For Crane | 76.5 | HR | 75 | 1.02 | 8898.32 | TRUE | FALSE | 8898.32 | 8898.32 | 76.5 | 75 | 118.6443 | 8898.32 | 0 | 0 | 0 | 0 | 0 | 8898.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8898.32 | spent | spent |  | TRUE
05-6050 | PREP COLUMNS FOR STEEL INSTALL | 45 | HR | 45.24 | 0.99469 | 2237.81 | TRUE | FALSE | 2237.81 | 2237.81 | 10 | 21 | 106.5624 | 5000 | 0 | 0 | 0 | 0 | -2762.19 | 5987.385 | 3749.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2237.81 | spent | spent |  | TRUE
05-6100 | MISC METALS SUB | 1 | LS | 0 | 1 | 2010175 | FALSE | FALSE | 651253.92 | 2042542.67 | 0 | 0 | 110 | 0 | 2010175 | 0 | 0 | 0 | 0 | 651363.92 | -1358811.08 | 20458.9241 | 218220.9253 | 131968.6753 | 141683.8253 | 88634.25 | 155988 | 103992 | 12999 | 38997 | 0 | 0 | 0 | 1564196.52 | SOV | Sub |  | FALSE
05-6110 | MISC METALS SUB SUPPORT | 1 | LS | 384.64 | 0.0025998 | 100040.22 | FALSE | FALSE | 6694.55 | 16294.55 | 0.15 | 51.5 | 129.9913 | 50000 | 50040.22 | 0 | 0 | 0 | 0 | 49194.4132 | -50845.8068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6694.55 | hold | labor | Sub Support | FALSE
05-6120 | BACKCHARGE E&Y | 0 | NA | 8 | 1 | 1174.65 | TRUE | FALSE | 1174.65 | 1174.65 | 0 | 8 | 146.8313 | 1174.65 | 0 | 0 | 0 | 0 | 0 | 1174.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174.65 | spent | spent |  | TRUE
05-6200 | SIGNAGE SUB | 1 | LS | 0 | 1 | 138024 | FALSE | FALSE | 21000 | 138024 | 0 | 0 | 110 | 0 | 138024 | 0 | 0 | 0 | 0 | 21110 | -116914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 | SOV | Sub |  | FALSE
05-6210 | SIGNAGE SUB SUPPORT | 0 | LS | 0 | 1 | 10000 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | labor | Sub Support | FALSE
06-6000 | CARPENTRY SUB | 1 | LS | 0 | 1 | 1840000 | FALSE | FALSE | 1476182 | 1840000 | 0 | 0 | 110 | 0 | 1840000 | 0 | 0 | 0 | 0 | 1476292 | -363708 | 185498.949 | 77657.5342 | 96839.196 | 73116.8842 | 68855.8756 | 101775.2295 | 105521.171 | 57710.5855 | 0 | 0 | 0 | 0 | 2243157.425 | SOV | Sub |  | FALSE
06-6010 | CARPENTRY SUB SUPPORT | 0 | LS | 0 | 1 | 50000 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | -50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | labor | Sub Support | FALSE
07-1000 | HIGH DENSITY STYROFOAM INFILL NEW BLDGS | 30 | CF | 14 | 2.1429 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 1540 | 1540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
07-1100 | 3 RIGID INSULATION UNDER GRADE NEW BLDGS | 19200 | SF | 329 | 58.3587 | 34098.54 | TRUE | FALSE | 34098.54 | 34165.69 | 19200 | 329 | 103.643 | 34098.54 | 0 | 0 | 0 | 0 | 0 | 34098.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34098.54 | spent | spent |  | TRUE
07-1200 | PENETRATION FIRESTOPPING EXTG BLDGS | 12 | BL | 576 | 0.020833 | 55337.28 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 55337.28 | 0 | 0 | 0 | 0 | 0 | 63360 | 8022.72 | 0 | 0 | 0 | 0 | 9222.88 | 9222.88 | 9222.88 | 9222.88 | 9222.88 | 9222.88 | 0 | 0 | 55337.28 | Phased | Labor | Existing Buildings | TRUE
07-1300 | PENETRATION FIRESTOPPING NEW BLDGS | 6 | BL | 288 | 0.020833 | 27668.64 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 27668.64 | 0 | 0 | 0 | 0 | 0 | 31680 | 4011.36 | 0 | 0 | 0 | 0 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 0 | 0 | 27668.64 | Phased | Labor | New Buildings | TRUE
07-1400 | JOINT SEALANTS EXTG BLDGS | 12 | BL | 576 | 0.020833 | 55337.28 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 55337.28 | 0 | 0 | 0 | 0 | 0 | 63360 | 8022.72 | 0 | 0 | 0 | 0 | 9094.7133 | 9094.7133 | 9094.7133 | 9094.7133 | 9094.7133 | 9094.7133 | 0 | 0 | 54568.28 | Phased | Labor | Existing Buildings | FALSE
07-1500 | JOINT SEALANTS NEW BLDGS | 6 | BL | 288 | 0.020833 | 27668.64 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 27668.64 | 0 | 0 | 0 | 0 | 0 | 31680 | 4011.36 | 0 | 0 | 0 | 0 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 4611.44 | 0 | 0 | 27668.64 | Phased | Labor | New Buildings | TRUE
07-2000 | INSTALL WATERSTOP | 313 | HR | 34 | 9.2059 | 3491.54 | TRUE | FALSE | 3491.54 | 3491.54 | 313 | 34 | 102.6924 | 3491.54 | 0 | 0 | 0 | 0 | 0 | 3491.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3491.54 | spent | spent |  | TRUE
07-5000 | FURNISH FIRESTOPPING | 18 | BL | 0 | 1 | 90000 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 90000 | 0 | 0 | 1980 | -88020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material |  | FALSE
07-5100 | FURNISH JOINT SEALANT | 18 | BL | 0 | 1 | 90000 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 90000 | 0 | 0 | 1980 | -88020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material |  | FALSE
07-6000 | WATERPROOFING SUB | 140655 | SF | 0 | 1 | 1007406.25 | FALSE | FALSE | 27305.01 | 907406.25 | 0 | 0 | 110 | 0 | 1007406.25 | 0 | 0 | 0 | 0 | 15499355.01 | 14491948.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27305.01 | SOV | Sub |  | FALSE
07-6010 | WATERPROOFING SUB SUPPORT | 14065.5 | SF | 1017.55 | 13.8229 | 103780.13 | FALSE | FALSE | 1172.93 | 1172.93 | 0 | 11.5 | 101.9939 | 103780.13 | 0 | 0 | 0 | 0 | 0 | 104956.8362 | 1176.7062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1172.93 | hold | labor | Sub Support | FALSE
07-6020 | PREP SURFACE FOR WATERPROOFING | 474.5 | HR | 507.13 | 0.93566 | 51250.23 | FALSE | FALSE | 51520.23 | 51520.23 | 474.5 | 512 | 100.6254 | 51250.23 | 0 | 0 | 0 | 0 | 0 | 51520.23 | 270 | 0 | -270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51250.23 | Phased | Labor | New Buildings | TRUE
07-6100 | METAL PANELS SUB | 38765 | SF | 0 | 1 | 3381506.41 | FALSE | FALSE | 1472118.91 | 3350000 | 0 | 0 | 110 | 0 | 3381506.41 | 0 | 0 | 0 | 0 | 5736268.91 | 2354762.5 | 297591.4 | 181743.2797 | 651626.3402 | 306637.0016 | 26629.1786 | 51389 | 33581.1429 | 15642.8571 | 0 | 0 | 0 | 0 | 3036959.11 | SOV | Sub |  | FALSE
07-6110 | METAL PANELS SUB SUPPORT | 575 | HR | 573.64 | 1.0024 | 68493.59 | FALSE | FALSE | 9269.14 | 9269.14 | 372.45 | 76.5 | 121.1652 | 68493.59 | 0 | 0 | 0 | 0 | 0 | 33753.1099 | -34740.4801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9269.14 | hold | labor | Sub Support | FALSE
07-6200 | ROOFING SUB | 21000 | SF | 0 | 1 | 1135000 | FALSE | FALSE | 572194.78 | 1135000 | 0 | 0 | 110 | 0 | 1135000 | 0 | 0 | 0 | 0 | 2882194.78 | 1747194.78 | 6078.6291 | 145814.3709 | 0 | 355028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1079115.78 | SOV | Sub |  | FALSE
07-6210 | ROOFING SUB SUPPORT | 10 | LS | 10 | 1 | 60000 | FALSE | FALSE | 1171.78 | 1171.78 | 10 | 10 | 117.178 | 60000 | 0 | 0 | 0 | 0 | 0 | 1171.78 | -58828.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1171.78 | hold | labor | Sub Support | FALSE
07-6220 | PREP ROOF SURFACE FOR WORK | 6 | EA | 399.33 | 0.015025 | 40000 | FALSE | FALSE | 22460.72 | 22460.72 | 4 | 224 | 100.2711 | 40000 | 0 | 0 | 0 | 0 | 0 | 35807.8023 | -4192.1977 | 0 | 8769.64 | 8769.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | Phased | Labor | New Buildings | TRUE
07-6300 | SPRAY ON FIREPROOFING SUB | 67690 | SF | 0 | 1 | 254755.38 | FALSE | FALSE | 184755.38 | 254755.38 | 0 | 0 | 110 | 0 | 254755.38 | 0 | 0 | 0 | 0 | 7630655.38 | 7375900 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254755.38 | Phased | Sub |  | TRUE
07-6310 | SPRAY ON FIREPROOFING SUB SUPPORT | 180 | HR | 180 | 1 | 21837.92 | FALSE | FALSE | 1377.92 | 1377.92 | 9.5 | 9.5 | 145.0442 | 21837.92 | 0 | 0 | 0 | 0 | 0 | 26107.9579 | 4270.0379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1377.92 | hold | sub |  | FALSE
07-6320 | Maintain heat for Fireproofers | 75.64 | HR | 91.5 | 0.82667 | 9196.97 | TRUE | FALSE | 9196.97 | 9196.97 | 75.64 | 91.5 | 100.5133 | 9196.97 | 0 | 0 | 0 | 0 | 0 | 9196.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9196.97 | spent | spent |  | TRUE
07-6330 | FIREPROOFING CLEANUP | 45 | HR | 45 | 1 | 2771.84 | TRUE | FALSE | 2771.84 | 2771.84 | 25 | 25 | 110.8736 | 2771.84 | 0 | 0 | 0 | 0 | 0 | 4989.312 | 2217.472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2771.84 | spent | spent |  | TRUE
08-1600 | ACCESS HATCH | 36 | EA | 1008 | 0.035714 | 114418.44 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 114418.44 | 0 | 0 | 0 | 0 | 0 | 110880 | -3538.44 | 0 | 0 | 0 | 19069.74 | 19069.74 | 19069.74 | 19069.74 | 19069.74 | 19069.74 | 0 | 0 | 0 | 114418.44 | Phased | Labor | Existing Buildings | TRUE
08-1700 | (1''4WX8H) S.S. FLOOD VENTS NEW BL (153) | 33 | EA | 168 | 0.19643 | 19069.74 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 19069.74 | 0 | 0 | 0 | 0 | 0 | 18480 | -589.74 | 0 | 0 | 0 | 3178.29 | 3178.29 | 3178.29 | 3178.29 | 3178.29 | 3178.29 | 0 | 0 | 0 | 19069.74 | Phased | Labor | Existing Buildings | TRUE
08-1800 | 2'9"x8" SS FLOOD VENT W/SS SCRN NEW BLDG(8.06) | 17 | EA | 56 | 0.30357 | 6356.58 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 6356.58 | 0 | 0 | 0 | 0 | 0 | 6160 | -196.58 | 0 | 0 | 0 | 1059.43 | 1059.43 | 1059.43 | 1059.43 | 1059.43 | 1059.43 | 0 | 0 | 0 | 6356.58 | Phased | Labor | Existing Buildings | TRUE
08-5000 | FURNISH HM DOORS | 96 | EA | 0 | 1 | 191266.4 | FALSE | FALSE | 83834.36 | 131759.13 | 32 | 0 | 110 | 0 | 0 | 0 | 191266.4 | 0 | 0 | 90874.36 | -100392.04 | 0 | 0 | 26858.01 | 26858.01 | 26858.01 | 26858.01 | 0 | 0 | 0 | 0 | 0 | 0 | 191266.4 | phased | Material |  | TRUE
08-5010 | HM DOOR SUPPORT | 0 | LS | 0 | 1 | 50000 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | -50000 | 0 | 0 | 0 | 8333.3333 | 8333.3333 | 8333.3333 | 8333.3333 | 8333.3333 | 8333.3333 | 0 | 0 | 0 | 50000 | Phased | Labor | Existing Buildings | TRUE
08-5100 | FURNISH ACCESS HATCHES | 36 | EA | 0 | 1 | 91781 | TRUE | FALSE | 91781 | 99876.64 | 0 | 0 | 110 | 0 | 0 | 0 | 91781 | 0 | 0 | 95741 | 3960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91781 | spent | spent |  | TRUE
08-6000 | OVERHEAD DOORS SUB | 2 | EA | 0 | 1 | 22632 | FALSE | FALSE | 5658 | 22632 | 0 | 0 | 110 | 0 | 22632 | 0 | 0 | 0 | 0 | 5878 | -16754 | 0 | 0 | 22632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28290 | SOV | Sub |  | FALSE
08-6010 | OVERHEAD DOORS SUB SUPPORT | 0 | LS | 0 | 1 | 5000 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | -5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | sub |  | FALSE
08-6100 | GLAZING SUB | 2 | EA | 0 | 1 | 28000 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 28000 | 0 | 0 | 0 | 0 | 220 | -27780 | 0 | 0 | 0 | 0 | 0 | 9333.3333 | 9333.3333 | 9333.3333 | 0 | 0 | 0 | 0 | 28000 | Phased | Sub |  | TRUE
08-6200 | LOUVERS SUB | 1 | LS | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
09-6000 | STUCCO SUB | 5060 | SF | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 556600 | 556600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
09-6100 | TILE SUB | 246 | SF | 0 | 1 | 34200 | FALSE | FALSE | 0 | 23820 | 0 | 0 | 110 | 0 | 34200 | 0 | 0 | 0 | 0 | 27060 | -7140 | 0 | 0 | 0 | 11400 | 11400 | 11400 | 0 | 0 | 0 | 0 | 0 | 0 | 34200 | Phased | Sub |  | TRUE
09-6110 | TILING SUB SUPPORT | 0 | LS | 0 | 1 | 5000 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | -5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | sub |  | FALSE
09-6200 | VCT FLOORING SUB | 173 | SF | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 19030 | 19030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
09-6300 | PAINT SUB | 1 | LS | 0 | 1 | 533755 | FALSE | FALSE | 0 | 330000 | 0 | 0 | 110 | 0 | 533755 | 0 | 0 | 0 | 0 | 110 | -533645 | 27500 | 27500 | 0 | 0 | 23571.4286 | 141428.5714 | 17500 | 75000 | 17500 | 0 | 0 | 0 | 330000 | SOV | Sub |  | FALSE
09-6310 | PAINTING SUB SUPPORT | 0 | LS | 0 | 1 | 40000 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | -40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | sub |  | FALSE
10-1000 | FIRE EXTINGUISHERS NEW BLDGS | 7 | EA | 24 | 0.29167 | 2772.14 | FALSE | FALSE | 935.19 | 935.19 | 0 | 8 | 116.8988 | 2772.14 | 0 | 0 | 0 | 0 | 0 | 3740.76 | 968.62 | 0 | 0 | 0 | 306.1583 | 306.1583 | 306.1583 | 306.1583 | 306.1583 | 306.1583 | 0 | 0 | 0 | 2772.14 | Phased | Labor | New Buildings | TRUE
10-1100 | TOILET ACCESSORIES NEW BLDGS | 15 | EA | 96 | 0.15625 | 11021.7 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 11021.7 | 0 | 0 | 0 | 0 | 0 | 10560 | -461.7 | 0 | 0 | 0 | 1836.95 | 1836.95 | 1836.95 | 1836.95 | 1836.95 | 1836.95 | 0 | 0 | 0 | 11021.7 | Phased | Labor | New Buildings | TRUE
10-1200 | AQUAFENCE FLOOD BARRIER W/ STEEL CHANNEL (8.03) | 930 | LF | 2815.99 | 0.33026 | 289147.86 | FALSE | FALSE | 14136.86 | 14136.86 | 30 | 133 | 106.2922 | 289147.86 | 0 | 0 | 0 | 0 | 0 | 303799.167 | 14651.307 | 0 | 0 | 0 | 0 | 45835.1667 | 45835.1667 | 45835.1667 | 45835.1667 | 45835.1667 | 45835.1667 | 0 | 0 | 289147.86 | Phased | Labor | Existing Buildings | TRUE
10-1300 | MULTIPLE PANEL VSL FLOODGATE SYSTEM (8.11) | 14 | EA | 128.88 | 0.10863 | 22248.03 | FALSE | FALSE | 431.58 | 431.58 | 0 | 2.5 | 172.632 | 22248.03 | 0 | 0 | 0 | 0 | 0 | 22680.3922 | 432.3622 | 0 | 0 | 0 | 0 | 3548.4217 | 3548.4217 | 3548.4217 | 3548.4217 | 3548.4217 | 3548.4217 | 0 | 0 | 21722.11 | Phased | Labor | Existing Buildings | FALSE
10-1400 | WINDOW FLOODGATES (8.06 AND 8.14) | 387 | LF | 440.49 | 0.87857 | 50000.29 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 50000.29 | 0 | 0 | 0 | 0 | 0 | 48453.9 | -1546.39 | 0 | 0 | 0 | 0 | 8333.3817 | 8333.3817 | 8333.3817 | 8333.3817 | 8333.3817 | 8333.3817 | 0 | 0 | 50000.29 | Phased | Labor | Existing Buildings | TRUE
10-1500 | MANUALLY INSTALLED SLIM-LINE PEDESTRIAN FLOODGATE | 80 | LF | 189.9 | 0.42127 | 19069.74 | FALSE | FALSE | 5523.22 | 5523.22 | 46.75 | 55 | 100.4222 | 19069.74 | 0 | 0 | 0 | 0 | 0 | 13449.2604 | -5620.4796 | 0 | 0 | 0 | 0 | 2257.7533 | 2257.7533 | 2257.7533 | 2257.7533 | 2257.7533 | 2257.7533 | 0 | 0 | 19069.74 | Phased | Labor | Existing Buildings | TRUE
10-5000 | FURNISH TOILET ACCESSORIES | 15 | EA | 0 | 1 | 1488.1 | FALSE | FALSE | 0 | 1488.1 | 0 | 0 | 110 | 0 | 0 | 0 | 1488.1 | 0 | 0 | 1650 | 161.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material |  | FALSE
10-5100 | FURNISH FIRE EXTINGUISHERS | 7 | EA | 0 | 1 | 2450 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 2450 | 0 | 0 | 770 | -1680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material |  | FALSE
10-5200 | FURNISH AQUA FLOOD BARRIERS | 930 | LF | 0 | 1 | 1682724.63 | FALSE | FALSE | 938308 | 1532090 | 0 | 0 | 110 | 0 | 0 | 0 | 1682724.63 | 0 | 0 | 1040608 | -642116.63 | 0 | 0 | 186104.1575 | 186104.1575 | 186104.1575 | 186104.1575 | 0 | 0 | 0 | 0 | 0 | 0 | 1682724.63 | phased | Material |  | TRUE
10-5300 | FURNISH 8.08 FLOOD DOORS | 30 | EA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
10-5400 | FURNISH FLOOD ITEMS (153, 8.06 / 8.14, 8.11, 8.15) | 1 | LS | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
11-1000 | EXCAVATE & POUR CONCRETE FOOTINGS | 7 | EA | 336 | 0.020833 | 35505.12 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 35505.12 | 0 | 0 | 0 | 0 | 0 | 36960 | 1454.88 | 0 | 5917.52 | 5917.52 | 5917.52 | 0 | 0 | 0 | 5917.52 | 5917.52 | 5917.52 | 0 | 0 | 35505.12 | Phased | Labor | Site Restoration | TRUE
11-6000 | PLAY AREA ITEMS SUB | 7 | EA | 0 | 1 | 426718.49 | FALSE | FALSE | 224018 | 224018 | 0 | 0 | 110 | 0 | 202700.49 | 0 | 224018 | 0 | 0 | 224788 | -201930.49 | 0 | 0 | 50675.1225 | 50675.1225 | 0 | 0 | 0 | 0 | 50675.1225 | 50675.1225 | 0 | 0 | 426718.49 | Phased | Sub |  | TRUE
11-6010 | SUPPORT PLAY AREA | 6 | NA | 448.35 | 0.013382 | 50000 | FALSE | FALSE | 10004.56 | 10004.56 | 1 | 87.5 | 114.3378 | 50000 | 0 | 0 | 0 | 0 | 0 | 52724.0312 | 2724.0312 | 0 | 6411.3733 | 6411.3733 | 6411.3733 | 0 | 0 | 0 | 6411.3733 | 6411.3733 | 6411.3733 | 0 | 0 | 48472.8 | Phased | Labor | Sub Support | FALSE
14-6000 | ELEVATOR SUB | 1 | LS | 0 | 1 | 1027903.5 | FALSE | FALSE | 31860 | 34687.58 | 0 | 0 | 110 | 0 | 1027903.5 | 0 | 0 | 0 | 0 | 31970 | -995933.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31860 | hold | sub |  | FALSE
14-6010 | ELEVATOR JUNCTION BOXES | 36 | EA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 3960 | 3960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
22-5000 | Purchase Yard Pumps | 16 | EA | 0 | 1 | 99876.64 | FALSE | FALSE | 0 | 90656 | 0 | 0 | 110 | 0 | 0 | 0 | 99876.64 | 0 | 0 | 1760 | -98116.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material |  | FALSE
22-6000 | PLUMBING SUB | 1 | LS | 0 | 1 | 13100000 | FALSE | FALSE | 8426271.83 | 13099982.4 | 0 | 0 | 110 | 0 | 13100000 | 0 | 0 | 0 | 0 | 8426381.83 | -4673618.17 | 400898.86 | 540179.4201 | 537959.6175 | 462423.214 | 427905.5184 | 430513.1662 | 517329.072 | 204644.0318 | 0 | 0 | 0 | 0 | 11948124.73 | SOV | Sub |  | FALSE
22-6010 | PLUMBING BOND | 1 | LS | 0 | 1 | 125426 | TRUE | FALSE | 125426 | 125426 | 1 | 0 | 110 | 0 | 0 | 125426 | 0 | 0 | 0 | 125426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125426 | spent | spent |  | TRUE
22-6020 | PIPE INSULATION | 0 | LS | 0 | 1 | 450000 | FALSE | FALSE | 82255 | 400000 | 0 | 0 | 110 | 0 | 450000 | 0 | 0 | 0 | 0 | 82255 | -367745 | 2510 | 1520 | 41647.0455 | 89437.9545 | 91050 | 34350 | 0 | 0 | 0 | 0 | 0 | 0 | 342770 | SOV | Sub |  | FALSE
22-6025 | PLUMBING INSULATION REMOVAL | 2000 | LF | 250 | 8 | 25000 | FALSE | FALSE | 8405.69 | 8405.69 | 670 | 84 | 100.0677 | 25000 | 0 | 0 | 0 | 0 | 0 | 25041.9515 | 41.9515 | 0 | 2765.7183 | 2765.7183 | 2765.7183 | 2765.7183 | 2765.7183 | 2765.7183 | 0 | 0 | 0 | 0 | 0 | 25000 | Phased | Labor | Sub Support | TRUE
22-6030 | YARD PUMP SUPPLY | 0 | NA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
22-6040 | YARD PUMP INSTALL | 16 | EA | 1938.37 | 0.0082544 | 209344 | FALSE | FALSE | 21676.9 | 21676.9 | 4 | 203 | 106.7828 | 209344 | 0 | 0 | 0 | 0 | 0 | 176915.2719 | -32428.7281 | 0 | 30562.2767 | 30562.2767 | 30562.2767 | 30562.2767 | 30562.2767 | 30562.2767 | 0 | 0 | 0 | 0 | 0 | 205050.56 | Phased | Labor | Existing Buildings | FALSE
22-6050 | SPRAY SHOWER AND DRINKING FOUNTAIN | 21 | EA | 0 | 1 | 41078 | TRUE | FALSE | 41078 | 44723.67 | 0 | 0 | 110 | 0 | 0 | 0 | 41078 | 0 | 0 | 43388 | 2310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41078 | spent | spent |  | TRUE
22-6060 | PLUMBING SUB SUPPORT | 29.5 | NA | 29.5 | 1 | 3359.95 | TRUE | FALSE | 3359.95 | 3359.95 | 29.5 | 29.5 | 113.8966 | 3359.95 | 0 | 0 | 0 | 0 | 0 | 3359.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3359.95 | spent | spent |  | TRUE
22-6070 | PLUMBING SCAFFOLD | 80 | HR | 83.34 | 0.95992 | 10000 | FALSE | FALSE | 8249.4 | 8249.4 | 72.5 | 71 | 116.1887 | 10000 | 0 | 0 | 0 | 0 | 0 | 9157.1971 | -842.8029 | 0 | 291.7667 | 291.7667 | 291.7667 | 291.7667 | 291.7667 | 291.7667 | 0 | 0 | 0 | 0 | 0 | 10000 | Phased | Labor | Sub Support | TRUE
23-6000 | HVAC SUB | 1 | LS | 0 | 1 | 24100000 | FALSE | FALSE | 16961353.61 | 22562297.4 | 0 | 0 | 110 | 0 | 24100000 | 0 | 0 | 0 | 0 | 16961463.61 | -7138536.39 | 941127 | 940236.2987 | 1002551.8553 | 1079113.5837 | 1321452.3226 | 775396.3526 | 339918.2092 | 293738.6746 | 101849.6999 | 24200 | 0 | 0 | 23780937.6067 | SOV | Sub |  | FALSE
23-6010 | HVAC SUB SUPPORT | 0 | NA | 0 | 1 | 200000 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | -200000 | 33333.3333 | 33333.3333 | 33333.3333 | 33333.3333 | 33333.3333 | 33333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | phased | sub |  | TRUE
23-6020 | MECHANICAL LOUVERS | 0 | NA | 0 | 1 | 0 | TRUE | FALSE | 0 | 20490.93 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
26-6000 | ELECTRICAL SUB | 1 | LS | 0 | 1 | 50186995.05 | FALSE | FALSE | 24286356.65 | 50099472.19 | 0 | 0 | 110 | 0 | 50186995.05 | 0 | 0 | 0 | 0 | 24286466.65 | -25900528.4 | 2410925 | 2653514.4095 | 2095145.1938 | 2497093.6894 | 2227210.3282 | 3294050.9786 | 2996338.6923 | 2813600.5971 | 2180880.9988 | 1342400.5128 | 1389477.9995 | 0 | 50186995.05 | SOV | Sub |  | TRUE
26-6010 | TEMP ELECTRIC | 18 | EA | 0 | 1 | 2449.46 | TRUE | FALSE | 2449.46 | 2449.46 | 0 | 0 | 110 | 0 | 0 | 2449.46 | 0 | 0 | 0 | 4429.46 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2449.46 | spent | spent |  | TRUE
26-6020 | ELECTRICAL SUB SUPPORT | 0 | NA | 0 | 1 | 50000 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | -50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | sub |  | FALSE
26-6030 | EQUIPMENT INSTALLATION SUPPORT | 280 | HR | 241.04 | 1.1616 | 30000 | FALSE | FALSE | 22091.48 | 22091.48 | 159.54 | 177.5 | 124.459 | 30000 | 0 | 0 | 0 | 0 | 0 | 34997.7397 | 4997.7397 | 0 | 988.565 | 988.565 | 988.565 | 988.565 | 988.565 | 988.565 | 988.565 | 988.565 | 0 | 0 | 0 | 30000 | Phased | Labor | Sub Support | TRUE
31-1000 | EXCAVATION FOR FLOOD BARRIER FOOTINGS AND CONCRETE | 6738 | CY | 2264.77 | 2.9751 | 250000 | FALSE | FALSE | 184612.63 | 184612.63 | 4745 | 1654 | 111.6159 | 250000 | 0 | 0 | 0 | 0 | 0 | 259382.4439 | 9382.4439 | 0 | 10897.895 | 10897.895 | 10897.895 | 10897.895 | 10897.895 | 10897.895 | 0 | 0 | 0 | 0 | 0 | 250000 | Phased | Labor | Existing Buildings | TRUE
31-1100 | BACKFILL FOR FLOOD BARRIER FFTGS & CONCRETE SHELF | 4447.3 | CY | 1323.07 | 3.3613 | 152500 | FALSE | FALSE | 104184.46 | 104184.46 | 3037.18 | 901.5 | 115.5679 | 152500 | 0 | 0 | 0 | 0 | 0 | 152666.3656 | 166.3656 | 0 | 7727.625 | 7727.625 | 7727.625 | 7727.625 | 7727.625 | 7727.625 | 0 | 0 | 0 | 0 | 0 | 150550.21 | Phased | Labor | Existing Buildings | FALSE
31-1200 | INFILL AREAWAY W/ GRAVEL/TOPSOIL - ALL EXIST BLDGS | 161 | CY | 42.94 | 3.7494 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 4723.4 | 4723.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
31-1300 | EXCAVATION NEW BLDGS | 7992.55 | CY | 1841 | 4.3414 | 205909.86 | TRUE | FALSE | 205909.86 | 205909.86 | 7989.55 | 1841 | 111.8467 | 205909.86 | 0 | 0 | 0 | 0 | 0 | 205987.1482 | 77.2882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205909.86 | spent | spent |  | TRUE
31-1400 | BACKFILL NEW BLDGS | 3481.25 | CY | 1381.55 | 2.5198 | 150000 | FALSE | FALSE | 148114.7 | 148114.7 | 3481.25 | 1337.5 | 110.74 | 150000 | 0 | 0 | 0 | 0 | 0 | 148114.7 | -1885.3 | 0 | 942.65 | 942.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | Phased | Labor | New Buildings | TRUE
31-1500 | BACKFILL STONE/GRAVEL/CRUSHED STONE - ALL | 303 | CY | 222.98 | 1.3589 | 25000 | FALSE | FALSE | 23506.32 | 23506.32 | 233 | 218.5 | 107.5804 | 25000 | 0 | 0 | 0 | 0 | 0 | 29048.1669 | 4048.1669 | 0 | 746.84 | 746.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | Phased | Labor | New Buildings | TRUE
31-1600 | PUMP OPERATOR FOR FLOOD BARRIERS | 0 | MO | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
31-1700 | DEWATER NEW BLDGS | 1066.55 | HR | 962.5 | 1.1081 | 140469.48 | TRUE | FALSE | 140469.48 | 140469.48 | 1066.55 | 962.5 | 145.9423 | 140469.48 | 0 | 0 | 0 | 0 | 0 | 140469.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140469.48 | spent | spent |  | TRUE
31-1800 | INSTALL H PILES | 280 | LF | 223 | 1.2556 | 26802.94 | TRUE | FALSE | 26802.94 | 26802.94 | 280 | 223 | 120.1926 | 26802.94 | 0 | 0 | 0 | 0 | 0 | 26802.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26802.94 | spent | spent |  | TRUE
31-1810 | SOE MATERIAL | 1 | LS | 10 | 0.1 | 445577.25 | TRUE | FALSE | 445577.25 | 489937.63 | 0 | 10 | 133.944 | 1339.44 | 0 | 439637.81 | 4600 | 0 | 0 | 446916.69 | 1339.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 445577.25 | spent | spent |  | TRUE
31-1820 | INSTALL SHEETING | 8691.99 | SF | 1738.42 | 4.9999 | 210938.15 | FALSE | FALSE | 208728.89 | 208728.89 | 8691.99 | 1725 | 121.0023 | 210938.15 | 0 | 0 | 0 | 0 | 0 | 208728.89 | -2209.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208728.89 | hold | labor | New Buildings | FALSE
31-1830 | INSTALL LAGGING | 8318.5 | SF | 465 | 17.8892 | 55626.32 | TRUE | FALSE | 55626.32 | 55626.32 | 8318.5 | 465 | 115.8175 | 53855.12 | 0 | 0 | 0 | 0 | 1771.2 | 55626.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55626.32 | spent | spent |  | TRUE
31-1840 | MUD SLAB | 1110 | CY | 495 | 2.2424 | 55578.77 | TRUE | FALSE | 55578.77 | 55578.77 | 863 | 495 | 112.2803 | 55578.77 | 0 | 0 | 0 | 0 | 0 | 67946.2981 | 12367.5281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55578.77 | spent | spent |  | TRUE
31-1850 | SOE Sub | 836 | HR | 988.5 | 0.84573 | 402338.93 | TRUE | FALSE | 402338.93 | 402338.93 | 836 | 988.5 | 134.6012 | 133053.32 | 269285.61 | 0 | 0 | 0 | 0 | 402338.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 402338.93 | spent | spent |  | TRUE
31-1860 | SOE Sub Support | 12 | SH | 143 | 0.083916 | 15201.85 | TRUE | FALSE | 15201.85 | 15201.85 | 11.91 | 143 | 106.3066 | 15201.85 | 0 | 0 | 0 | 0 | 0 | 15315.8639 | 114.0139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15201.85 | spent | spent |  | TRUE
31-1900 | TREE PROTECTION | 135 | EA | 450.15 | 0.2999 | 50000 | FALSE | FALSE | 44097.39 | 44097.39 | 135 | 403.5 | 109.2872 | 50000 | 0 | 0 | 0 | 0 | 0 | 44097.39 | -5902.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44097.39 | hold | labor | Site Utilities | FALSE
31-2000 | TEST PIT SUPPORT | 1650 | CY | 792.5 | 2.082 | 83241.53 | TRUE | FALSE | 83241.53 | 83241.53 | 1620.62 | 792.5 | 105.0366 | 83241.53 | 0 | 0 | 0 | 0 | 0 | 84723.7337 | 1482.2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83241.53 | spent | spent |  | TRUE
31-2010 | HAND EXCAVATION SUPPORT | 5.87 | CY | 18 | 0.32611 | 1978.47 | TRUE | FALSE | 1978.47 | 1978.47 | 5.87 | 18 | 109.915 | 1978.47 | 0 | 0 | 0 | 0 | 0 | 1978.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1978.47 | spent | spent |  | TRUE
31-2100 | EXCAVATION FOR SITE FURNISHING FOOTINGS | 410 | CY | 329.32 | 1.245 | 40000 | FALSE | FALSE | 17989.24 | 17989.24 | 272 | 143.5 | 125.3606 | 40000 | 0 | 0 | 0 | 0 | 0 | 31884.7423 | -8115.2577 | 0 | 3668.46 | 3668.46 | 3668.46 | 3668.46 | 3668.46 | 3668.46 | 0 | 0 | 0 | 0 | 0 | 40000 | Phased | Labor | Site Restoration | TRUE
31-2200 | BACKFILL UTILITIES | 27415 | CY | 3302.81 | 8.3005 | 383288.4 | FALSE | FALSE | 282371.95 | 282371.95 | 23632.73 | 2414.5 | 116.9484 | 383288.4 | 0 | 0 | 0 | 0 | 0 | 335661.5195 | -47626.8805 | 0 | 15940.65 | 15940.65 | 15940.65 | 15940.65 | 15940.65 | 15940.65 | 0 | 0 | 0 | 0 | 0 | 378015.85 | Phased | Labor | Site Utilities | FALSE
31-2300 | EXCAVATION FOR PAVEMENTS | 700 | CY | 93.89 | 7.4555 | 10328.22 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 10328.22 | 0 | 0 | 0 | 0 | 0 | 10327.9 | -0.32 | 0 | 1721.37 | 1721.37 | 1721.37 | 1721.37 | 1721.37 | 1721.37 | 0 | 0 | 0 | 0 | 0 | 10328.22 | Phased | Labor | Site Restoration | TRUE
31-2400 | BACKFILL AND COMPACTION FOR PAVEMENTS | 435 | CY | 64.92 | 6.7006 | 7141.61 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 7141.61 | 0 | 0 | 0 | 0 | 0 | 7141.2 | -0.41 | 0 | 1190.2683 | 1190.2683 | 1190.2683 | 1190.2683 | 1190.2683 | 1190.2683 | 0 | 0 | 0 | 0 | 0 | 7141.61 | Phased | Labor | Site Restoration | TRUE
31-2500 | DENSE GRADED STONE BASE | 1680 | CY | 627.2 | 2.6786 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 68992 | 68992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
31-2600 | SITE FURNISHINGS | 117 | EA | 357.95 | 0.32686 | 38534.4 | FALSE | FALSE | 2691.34 | 2691.34 | 9 | 25 | 107.6536 | 38534.4 | 0 | 0 | 0 | 0 | 0 | 38261.7456 | -272.6544 | 0 | 0 | 0 | 0 | 0 | 8891.0525 | 8891.0525 | 8891.0525 | 8891.0525 | 0 | 0 | 0 | 38255.55 | Phased | Labor | Site Restoration | FALSE
31-2700 | BOLLARDS | 8 | EA | 48 | 0.16667 | 4816.8 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 4816.8 | 0 | 0 | 0 | 0 | 0 | 5280 | 463.2 | 0 | 0 | 0 | 0 | 0 | 2408.4 | 2408.4 | 0 | 0 | 0 | 0 | 0 | 4816.8 | Phased | Labor | Site Restoration | TRUE
31-2800 | DRINKING FOUNTAIN | 6 | EA | 298.95 | 0.02007 | 30000 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 30000 | 0 | 0 | 0 | 0 | 0 | 32884.5 | 2884.5 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 30000 | Phased | Labor | Site Restoration | TRUE
31-2900 | LANDSCAPE BOULDERS | 148 | EA | 330.68 | 0.44756 | 80000 | FALSE | FALSE | 59019.92 | 62658.67 | 72 | 154.5 | 116.6338 | 39000 | 0 | 41000 | 0 | 0 | 0 | 78825.3457 | -1174.6543 | 0 | 9849.01 | 9849.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78717.94 | Phased | Labor | Site Restoration | FALSE
31-3000 | BASKETBALL BACKSTOP | 2 | EA | 32 | 0.0625 | 3296.32 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 3296.32 | 0 | 0 | 0 | 0 | 0 | 3520 | 223.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1648.16 | 1648.16 | 0 | 0 | 0 | 3296.32 | Phased | Labor | Site Restoration | TRUE
31-4000 | VAC TRUCKING SUB | 30 | DY | 0 | 1 | 130000 | FALSE | FALSE | 112290.76 | 114830 | 0 | 0 | 110 | 0 | 130000 | 0 | 0 | 0 | 0 | 115590.76 | -14409.24 | 0 | 5000 | 5000 | 5000 | 2500 | 209.24 | 0 | 0 | 0 | 0 | 0 | 0 | 130000 | Phased | Sub |  | TRUE
31-5000 | FURNISH GRAVEL | 637.2 | CY | 0 | 1 | 12744 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 12744 | 0 | 0 | 70092 | 57348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material |  | FALSE
31-5100 | FURNISH CLEAN FILL | 8681 | CY | 0 | 1 | 60000 | FALSE | FALSE | 7761.75 | 7761.75 | 0 | 0 | 110 | 0 | 0 | 0 | 60000 | 0 | 0 | 962671.75 | 902671.75 | 0 | 0 | 13059.5625 | 13059.5625 | 13059.5625 | 13059.5625 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | phased | Material |  | TRUE
31-6000 | DISPOSAL & TRUCKING SUB | 1 | LS | 0 | 1 | 1710399 | FALSE | FALSE | 1449641.33 | 1814355.74 | 0 | 0 | 110 | 0 | 110399 | 1600000 | 0 | 0 | 0 | 1449751.33 | -260647.67 | 0 | 40000 | 40000 | 40000 | 40000 | 40000 | 20000 | 20000 | 10000 | 10757.67 | 0 | 0 | 1710399 | Phased | Sub |  | TRUE
31-6100 | DEWATERING SUB | 1 | LS | 0 | 1 | 38820 | TRUE | FALSE | 38820 | 38820 | 0 | 0 | 110 | 0 | 38820 | 0 | 0 | 0 | 0 | 38930 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38820 | spent | spent |  | TRUE
31-6110 | FURNISH SETTLING TANK AND DISCHARGE PIPING BEYOND | 16 | UM | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 1760 | 1760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
31-6120 | INSTALL SETTLING TANK AND DISCHARGE PIPING BEYOND | 16 | DY | 48 | 0.33333 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 5280 | 5280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
31-6130 | DISCHARGE LOCATIONS NOT INCLUDED WITHIN DEWATERING | 0 | EA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
31-6140 | DEEP WELL INSTALL SUPPORT & CLEANUP LABOR | 180 | DY | 439.02 | 0.41 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 48292.2 | 48292.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
31-6150 | DEEP WELL INSTALL SUPPORT & CLEANUP EQUIPMENT | 60 | DY | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
31-6160 | DEEP WELL INSTALL SUPPORT & CLEANUP CONSUMABLES | 400 | CY | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 44000 | 44000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
31-6170 | REMOVE AND REINSTALL PUMPS & PIPING | 30 | DY | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
31-6180 | WATER TREATMENT | 1 | LS | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
31-6190 | ELECTRIC SERVICE | 1 | LS | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
31-6200 | DUMPSTERS FOR DEWATERING | 0 | NA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
31-6210 | DEWATERING DISCHARGE | 1 | LS | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
31-7000 | LUMBER - TREE PROTECTION | 9.34 | MB | 4 | 2.335 | 22925.01 | TRUE | FALSE | 22925.01 | 22925.01 | 9.34 | 4 | 248.5725 | 994.29 | 0 | 21930.72 | 0 | 0 | 0 | 22925.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22925.01 | spent | spent |  | TRUE
31-7100 | DEWATERING PUMPS | 10 | MO | 0 | 1 | 14.07 | TRUE | FALSE | 14.07 | 14.07 | 0 | 0 | 110 | 14.07 | 0 | 0 | 0 | 0 | 0 | 1114.07 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.07 | spent | spent |  | TRUE
31-7200 | SOLDIER PILE & LAGGING BLDGS | 1 | LS | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
31-7300 | TRENCH BOX - UTILITY TRENCHES | 1 | LS | 0 | 1 | 256261.83 | FALSE | FALSE | 186979.41 | 353111.2 | 0.1 | 0 | 110 | 0 | 0 | 256261.83 | 0 | 0 | 0 | 187078.41 | -69183.42 | 0 | 25000 | 12500 | 12500 | 12500 | 6782.42 | 0 | 0 | 0 | 0 | 0 | 0 | 256261.83 | Phased | Labor | Site Utilities | TRUE
31-7400 | PLATES - UTILITY TRENCHES | 3000 | SF | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 330000 | 330000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
31-7500 | LUMBER - UTILITY TRENCHES | 11.25 | MB | 0 | 1 | 16396.43 | TRUE | FALSE | 16396.43 | 21915.27 | 0 | 0 | 110 | 0 | 0 | 16396.43 | 0 | 0 | 0 | 17633.93 | 1237.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16396.43 | spent | spent |  | TRUE
32-5000 | FURNISH BOLLARDS | 8 | EA | 0 | 1 | 10010 | TRUE | FALSE | 10010 | 10010 | 0 | 0 | 110 | 0 | 0 | 0 | 10010 | 0 | 0 | 10890 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10010 | spent | spent |  | TRUE
32-5100 | FURNISH SUBBASE | 2268 | CY | 0 | 1 | 56700 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 56700 | 0 | 0 | 249480 | 192780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material |  | FALSE
32-5200 | FURNISH BENCHES & TABLES | 106 | EA | 0 | 1 | 393000 | FALSE | FALSE | 190392.5 | 380865 | 0 | 0 | 110 | 0 | 0 | 0 | 393000 | 0 | 0 | 202052.5 | -190947.5 | 0 | 0 | 50651.875 | 50651.875 | 50651.875 | 50651.875 | 0 | 0 | 0 | 0 | 0 | 0 | 393000 | phased | Material |  | TRUE
32-5300 | FURNISH PING PONG TABLE | 3 | EA | 0 | 1 | 32700 | FALSE | FALSE | 22413 | 22413 | 0 | 0 | 110 | 0 | 0 | 0 | 32700 | 0 | 0 | 22743 | -9957 | 0 | 0 | 2571.75 | 2571.75 | 2571.75 | 2571.75 | 0 | 0 | 0 | 0 | 0 | 0 | 32700 | phased | Material |  | TRUE
32-5400 | FURNISH BIKE RACK | 8 | EA | 0 | 1 | 2400 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 2400 | 0 | 0 | 880 | -1520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material |  | FALSE
32-5500 | FURNISH DRINKING FOUNTAIN | 6 | EA | 0 | 1 | 9000 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 9000 | 0 | 0 | 660 | -8340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material |  | FALSE
32-5600 | FURNISH SHOWER EQUIPMENT | 6 | EA | 0 | 1 | 26188.02 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 26188.02 | 0 | 0 | 660 | -25528.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material |  | FALSE
32-5700 | FURNISH LANDSCAPE BOULDERS | 148 | EA | 0 | 1 | 191092.5 | TRUE | FALSE | 191092.5 | 221092.5 | 0 | 0 | 110 | 0 | 0 | 0 | 191092.5 | 0 | 0 | 207372.5 | 16280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191092.5 | spent | spent |  | TRUE
32-5800 | FURNISH BASKETBALL BOARD AND POST | 2 | EA | 0 | 1 | 5340 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 5340 | 0 | 0 | 220 | -5120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material |  | FALSE
32-6000 | SAWCUTTING | 1200 | EA | 10922.95 | 0.10986 | 131611.18 | TRUE | FALSE | 131611.18 | 131611.18 | 122 | 1110.5 | 102.6082 | 113946.43 | 0 | 17664.75 | 0 | 0 | 0 | 1138449.2318 | 1006838.0518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131611.18 | spent | spent |  | TRUE
32-6100 | ASPHALT SUB | 1 | LS | 0 | 1 | 210269.79 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 210269.79 | 0 | 0 | 0 | 0 | 110 | -210159.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70089.93 | 70089.93 | 70089.93 | 0 | 0 | 210269.79 | Phased | Sub |  | TRUE
32-6200 | FLATWORK SUB | 1 | LS | 0 | 1 | 3075000 | FALSE | FALSE | 243350 | 3075000 | 0 | 0 | 110 | 0 | 3075000 | 0 | 0 | 0 | 0 | 243460 | -2831540 | 416113.452 | 268894.1807 | 162546.4822 | 256599.4565 | 247182.1429 | 399457.1429 | 194757.1429 | 165700 | 29095.2381 | 381936.6667 | 309368.0952 | 0 | 3075000 | SOV | Sub |  | TRUE
32-6210 | FLATWORK SUB SUPPORT | 1 | LS | 1078.78 | 0.00092697 | 134287 | FALSE | FALSE | 1157.89 | 1157.89 | 0 | 9 | 128.6544 | 134287 | 0 | 0 | 0 | 0 | 0 | 139947.7316 | 5660.7316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157.89 | Hold | labor | Sub Support | FALSE
32-6220 | JMC EQUIP BACKCHARGE | 47.4 | HR | 53.5 | 0.88598 | 6698.28 | TRUE | FALSE | 6698.28 | 6698.28 | 47.4 | 53.5 | 125.2015 | 6698.28 | 0 | 0 | 0 | 0 | 0 | 6698.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6698.28 | spent | spent |  | TRUE
32-6230 | GRADING FOR RESTORATION | 5 | EA | 1668.29 | 0.0029971 | 200000 | FALSE | FALSE | 53939.6 | 53939.6 | 1.45 | 452 | 119.3354 | 200000 | 0 | 0 | 0 | 0 | 0 | 195290.6966 | -4709.3034 | 0 | 35366.595 | 35366.595 | 35366.595 | 35366.595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195405.98 | Phased | Labor | Site Restoration | FALSE
32-6300 | ASPHALT- PAVEMENT MARKINGS SUB | 10500 | LF | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 1155000 | 1155000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
32-6400 | COURT SURFACES SUB | 8500 | SF | 0 | 1 | 425000 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 425000 | 0 | 0 | 0 | 0 | 935000 | 510000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141666.6667 | 141666.6667 | 141666.6667 | 0 | 0 | 425000 | Phased | Sub |  | TRUE
32-6500 | FENCING SUB | 1 | LS | 0 | 1 | 1318652.5 | FALSE | FALSE | 757678.8 | 1036387.5 | 0 | 0 | 110 | 0 | 1318652.5 | 0 | 0 | 0 | 0 | 757788.8 | -560863.7 | 0 | 0 | 0 | 0 | 0 | 67720.9302 | 42461.9638 | 23636.4858 | 373930.6202 | 189250 | 0 | 0 | 1454678.8 | SOV | Sub |  | FALSE
32-6510 | FENCE MESH INSTALL | 15000 | LF | 871.57 | 17.2103 | 99496.11 | FALSE | FALSE | 90775.64 | 91826.29 | 14604.82 | 847 | 101.504 | 88394.5 | 0 | 11101.61 | 0 | 0 | 0 | 93106.3554 | -6389.7546 | 0 | 1453.4117 | 1453.4117 | 1453.4117 | 1453.4117 | 1453.4117 | 1453.4117 | 0 | 0 | 0 | 0 | 0 | 99496.11 | Phased | Labor | Site Maintenance | TRUE
32-6520 | FENCE INSTALL SELF PERFORM | 6845.65 | LF | 3984.47 | 1.7181 | 507000 | FALSE | FALSE | 337289.32 | 360416.61 | 6845.65 | 2414.5 | 104.9678 | 417000 | 0 | 90000 | 0 | 0 | 0 | 337289.32 | -169710.68 | 0 | 24244.3829 | 24244.3829 | 24244.3829 | 24244.3829 | 24244.3829 | 24244.3829 | 24244.3829 | 0 | 0 | 0 | 0 | 507000 | Phased | Labor | Site Maintenance | TRUE
32-6600 | LANDSCAPING SUB | 1 | LS | 0 | 1 | 635225.54 | FALSE | FALSE | 31172.29 | 638633.25 | 0 | 0 | 110 | 0 | 635225.54 | 0 | 0 | 0 | 0 | 31282.29 | -603943.25 | 1727.7481 | 11197.2479 | 10715.6822 | 9678.6807 | 10715.6822 | 50221.7089 | 0 | 0 | 0 | 214669.3285 | 295127.1713 | 0 | 635225.54 | SOV | Sub |  | TRUE
32-6610 | CLEAR AND GRUB | 137053 | SF | 754.13 | 181.7366 | 87764.08 | TRUE | FALSE | 87764.08 | 87764.08 | 125991.99 | 753 | 116.5526 | 87764.08 | 0 | 0 | 0 | 0 | 0 | 94857.804 | 7093.724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87764.08 | spent | spent |  | TRUE
32-6620 | SELF PERFORM TREE REMOVAL | 58 | EA | 243.75 | 0.23795 | 25000 | FALSE | FALSE | 24373.2 | 24373.2 | 58 | 236.5 | 103.0579 | 25000 | 0 | 0 | 0 | 0 | 0 | 24373.2 | -626.8 | 0 | 125.36 | 125.36 | 125.36 | 125.36 | 125.36 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | Phased | Labor | Site Restoration | TRUE
32-6630 | LANDSCAPING SUB SUPPORT | 489.56 | HR | 489.56 | 1 | 50000 | FALSE | FALSE | 23531.37 | 23531.37 | 235.5 | 235.5 | 99.9209 | 50000 | 0 | 0 | 0 | 0 | 0 | 48917.2718 | -1082.7282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23531.37 | hold | labor | Sub Support | FALSE
32-6700 | Arbor Consultant | 0 | HR | 0 | 1 | 960 | TRUE | FALSE | 960 | 1134.2 | 0 | 0 | 110 | 0 | 960 | 0 | 0 | 0 | 0 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | spent | spent |  | TRUE
33-1000 | MAINT & PROT EXIST PRIVATELY OWNED UTILITIES | 5 | LO | 428.02 | 0.011682 | 51626.6 | FALSE | FALSE | 43707.83 | 43707.83 | 3.8 | 378.5 | 115.4764 | 51626.6 | 0 | 0 | 0 | 0 | 0 | 55570.1235 | 3943.5235 | 0 | 1131.2529 | 1131.2529 | 1131.2529 | 1131.2529 | 1131.2529 | 1131.2529 | 1131.2529 | 0 | 0 | 0 | 0 | 51626.6 | Phased | Labor | Site Utilities | TRUE
33-1100 | TERMINATE AND DEMOLISH EXISTING UTILITIES | 3300 | LF | 527.97 | 6.2504 | 56789.26 | FALSE | FALSE | 13848.58 | 13848.58 | 595.63 | 111 | 124.762 | 56789.26 | 0 | 0 | 0 | 0 | 0 | 67829.9225 | 11040.6625 | 0 | 6134.3829 | 6134.3829 | 6134.3829 | 6134.3829 | 6134.3829 | 6134.3829 | 6134.3829 | 0 | 0 | 0 | 0 | 56789.26 | Phased | Labor | Site Utilities | TRUE
33-1200 | WATER | 0 | LF | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
33-1300 | WELDING OF WATER PIPE | 383.28 | LF | 1735.36 | 0.22086 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 190889.6 | 190889.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
33-1310 | WATER PIPE FIT UP | 0 | EA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
33-1400 | INSTALL JOJNT INSULATORS | 0 | EA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
33-1500 | PRESSURE & AIR TEST | 0 | EA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
33-1600 | FIX 10% FAILURE PIPE | 0 | LF | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
33-1700 | PRESSURE & AIR RE-TEST | 2 | EA | 25 | 0.08 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 2750 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
33-1800 | CONDENSATE & STEAM PIPE | 0 | LF | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
33-1900 | WELDING OF STEAM AND CONDENSATE PIPE | 0 | LF | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
33-1910 | STEAM AND CONDENSATE PIPE FIT UP | 0 | EA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
33-2000 | INSTALL JOJNT INSULATORS | 0 | EA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
33-2100 | PRESSURE & AIR TEST | 0 | EA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
33-2200 | FIX 10% FAILURE PIPE | 0 | LF | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
33-2210 | EXCAVATE UTILITIES | 8515 | CY | 16 | 532.1875 | 1849.67 | TRUE | FALSE | 1849.67 | 1849.67 | 25 | 16 | 115.6044 | 1849.67 | 0 | 0 | 0 | 0 | 0 | 3693.9094 | 1844.2394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1849.67 | spent | spent |  | TRUE
33-2300 | PRESSURE & AIR RE-TEST | 0 | EA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
33-2400 | DEWATER UTILITIES | 3.08 | MO | 341.17 | 0.0090278 | 55000 | FALSE | FALSE | 53037.69 | 53037.69 | 1.38 | 329 | 161.2088 | 55000 | 0 | 0 | 0 | 0 | 0 | 83394.6126 | 28394.6126 | 0 | 280.33 | 280.33 | 280.33 | 280.33 | 280.33 | 280.33 | 280.33 | 0 | 0 | 0 | 0 | 55000 | Phased | Labor | Site Utilities | TRUE
33-2500 | DUCTILE IRON PIPE SEWERS | 4768 | LF | 2328.82 | 2.0474 | 276988.13 | FALSE | FALSE | 179784.77 | 179784.77 | 3013 | 1524 | 117.969 | 276988.13 | 0 | 0 | 0 | 0 | 0 | 280906.5552 | 3918.4252 | 0 | 18158.716 | 18158.716 | 18158.716 | 18158.716 | 18158.716 | 0 | 0 | 0 | 0 | 0 | 0 | 270578.35 | Phased | Labor | Site Utilities | FALSE
33-2510 | SEWER LINE WORK | 200 | LF | 1680.85 | 0.11899 | 200000 | FALSE | FALSE | 55983.71 | 55983.71 | 30 | 470.5 | 118.9877 | 200000 | 0 | 0 | 0 | 0 | 0 | 225984.1056 | 25984.1056 | 0 | 28803.258 | 28803.258 | 28803.258 | 28803.258 | 28803.258 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | Phased | Labor | Site Utilities | TRUE
33-2600 | CATCH BASIN CONNECTIONS | 180 | EA | 2824.51 | 0.063728 | 313516.44 | FALSE | FALSE | 152601.14 | 152601.14 | 94.7 | 1282.5 | 118.9872 | 313516.44 | 0 | 0 | 0 | 0 | 0 | 311866.0304 | -1650.4096 | 0 | 31159 | 31159 | 31159 | 31159 | 31159 | 0 | 0 | 0 | 0 | 0 | 0 | 308396.14 | Phased | Labor | Site Utilities | FALSE
33-2700 | STORM DETENTION TANK (I DON'T THINK THIS EXISTS) | 1 | EA | 64 | 0.015625 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 7040 | 7040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
33-2800 | DRAINAGE MANHOLES | 3 | EA | 192 | 0.015625 | 21873.24 | FALSE | FALSE | 552.53 | 552.53 | 0.3 | 5 | 110.506 | 21873.24 | 0 | 0 | 0 | 0 | 0 | 19647.9668 | -2225.2732 | 0 | 4264.142 | 4264.142 | 4264.142 | 4264.142 | 4264.142 | 0 | 0 | 0 | 0 | 0 | 0 | 21873.24 | Phased | Labor | Site Utilities | TRUE
33-2900 | REMOVE AREA DRAINS | 22 | EA | 262.9 | 0.083682 | 32809.86 | FALSE | FALSE | 25193.4 | 25193.4 | 18 | 206.5 | 122.0019 | 32809.86 | 0 | 0 | 0 | 0 | 0 | 31025.0926 | -1784.7674 | 0 | 1357.084 | 1357.084 | 1357.084 | 1357.084 | 1357.084 | 0 | 0 | 0 | 0 | 0 | 0 | 31978.82 | Phased | Labor | Site Utilities | FALSE
33-3000 | ELECTRICAL MANHOLES | 0 | EA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
33-3100 | UTILITY TRENCHES | 28875 | CY | 6345.51 | 4.5505 | 717840.82 | FALSE | FALSE | 670161.71 | 670161.71 | 24889 | 5898 | 113.6252 | 717840.82 | 0 | 0 | 0 | 0 | 0 | 769692.3225 | 51851.5025 | 0 | 8955.502 | 8955.502 | 8955.502 | 8955.502 | 8955.502 | 0 | 0 | 0 | 0 | 0 | 0 | 714939.22 | Phased | Labor | Site Utilities | FALSE
33-3200 | FENCES & PLATES @ TRENCHES (THIS WILL BE DIFFERENT | 0 | EA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
33-3300 | ADD''L CRANE FOR SUBCONTRACTORS SUPPORT | 12 | MO | 2112 | 0.0056818 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 232320 | 232320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
33-5000 | FURNISH CW, HW, STEAM & CONDENSATE PIPE | 7796 | LF | 19.5 | 399.7949 | 881653.58 | FALSE | FALSE | 717720.89 | 915894.53 | 0 | 19.5 | 116.4497 | 2270.77 | 0 | 0 | 879382.81 | 0 | 0 | 719991.66 | -161661.92 | 0 | 0 | 40767.885 | 40767.885 | 40767.885 | 40767.885 | 0 | 0 | 0 | 0 | 0 | 0 | 880792.43 | phased | Material |  | FALSE
33-5100 | FURNISH 2 COPPER WATER PIPE | 675 | LF | 0 | 1 | 115654.5 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 115654.5 | 0 | 0 | 74250 | -41404.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | phased | Material |  | FALSE
33-5200 | FURNISH DIP DRAINAGE PIPE | 3799 | LF | 0 | 1 | 264282 | TRUE | FALSE | 264282 | 286251.61 | 0 | 0 | 110 | 0 | 0 | 0 | 264282 | 0 | 0 | 682172 | 417890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264282 | spent | spent |  | TRUE
33-5300 | FURNISH PRECAST AREA DRAINS & MHS | 89 | EA | 0 | 1 | 126016 | FALSE | FALSE | 74171.81 | 97977.83 | 0 | 0 | 110 | 0 | 0 | 0 | 126016 | 0 | 0 | 83961.81 | -42054.19 | 0 | 0 | 12961.0475 | 12961.0475 | 12961.0475 | 12961.0475 | 0 | 0 | 0 | 0 | 0 | 0 | 126016 | phased | Material |  | TRUE
33-5400 | FURNISH PRECAST ELECTRICAL MANHOLES | 6 | EA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
33-5500 | FURNISH DETENTION TANK | 1 | EA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
33-5600 | CHLORINATION | 0 | LS | 0 | 1 | 100000 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | -100000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 100000 | Phased | Labor | Site Utilities | TRUE
33-6000 | UNDERGROUND UTILITY MATERIAL DELIVERY | 8000 | LF | 214.98 | 37.2128 | 25000 | FALSE | FALSE | 20750.65 | 20750.65 | 7300.5 | 182 | 114.0146 | 25000 | 0 | 0 | 0 | 0 | 0 | 22893.8175 | -2106.1825 | 0 | 607.05 | 607.05 | 607.05 | 607.05 | 607.05 | 607.05 | 607.05 | 0 | 0 | 0 | 0 | 25000 | Phased | Labor | Site Utilities | TRUE
33-6010 | UTILITY PIPE PLACEMENT IN TRENCH | 8000 | LF | 905.83 | 8.8317 | 115000 | FALSE | FALSE | 104182.59 | 104182.59 | 6104 | 818 | 127.3626 | 115000 | 0 | 0 | 0 | 0 | 0 | 131525.0063 | 16525.0063 | 0 | 1545.3443 | 1545.3443 | 1545.3443 | 1545.3443 | 1545.3443 | 1545.3443 | 1545.3443 | 0 | 0 | 0 | 0 | 115000 | Phased | Labor | Site Utilities | TRUE
33-7000 | WELDING MATERIALS | 1 | LS | 0 | 1 | 32664 | FALSE | FALSE | 13246.13 | 24753.89 | 0.29 | 0 | 110 | 0 | 0 | 32664 | 0 | 0 | 0 | 13324.23 | -19339.77 | 0 | 2758.8171 | 2758.8171 | 2758.8171 | 2758.8171 | 2758.8171 | 2758.8171 | 2758.8171 | 0 | 0 | 0 | 0 | 32557.85 | Phased | Labor | Site Utilities | FALSE
33-9000 | GAS LINE DAMAGE | 14 | HR | 14 | 1 | 110287.72 | FALSE | FALSE | 83073.27 | 115156.02 | 14 | 14 | 114.85 | 1607.9 | 27214.45 | 81465.37 | 0 | 0 | 0 | 83073.27 | -27214.45 | 0 | 0 | 27214.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110287.72 | Phased | Labor | Site Utilities | TRUE
97-6000 | Bulk ACM removal, hose wire insulation | 1 | LF | 0 | 1 | 25 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 25 | 0 | 0 | 0 | 0 | 110 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | hold | Labor | Change Order | TRUE
97-6100 | Bulk ACM removal, pipe mold joint and pipe insulat | 1 | LF | 0 | 1 | 74 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 74 | 0 | 0 | 0 | 0 | 110 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 74 | hold | Labor | Change Order | TRUE
97-6200 | Bulk ACM removal, pipe insulation and assoc jack | 1 | LF | 0 | 1 | 42 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 42 | 0 | 0 | 0 | 0 | 110 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 42 | hold | Labor | Change Order | TRUE
97-6300 | Bulk ACM removal, pipe insulation and braided wire | 1 | LF | 0 | 1 | 42 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 42 | 0 | 0 | 0 | 0 | 110 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 42 | hold | Labor | Change Order | TRUE
97-6400 | Bulk ACM removal, ACM Contamined Debris | 1 | SF | 0 | 1 | 25 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 25 | 0 | 0 | 0 | 0 | 110 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | hold | Labor | Change Order | TRUE
97-6500 | Bulk ACM removal, ACM Contamined Debris at Pump an | 1 | SF | 0 | 1 | 30 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 30 | 0 | 0 | 0 | 0 | 110 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | hold | Labor | Change Order | TRUE
97-6600 | Hazardous waste cleanup/pickup/disposal, solid pic | 1 | CY | 0 | 1 | 400 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 400 | 0 | 0 | 0 | 0 | 110 | -290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | hold | Labor | Change Order | TRUE
97-6700 | Bulk ACM removal, ACM Fibrous un-identified gasket | 1 | SF | 0 | 1 | 750 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 750 | 0 | 0 | 0 | 0 | 110 | -640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 750 | hold | Labor | Change Order | TRUE
97-6800 | Bulk ACM removal, ACM Fibrous Slate at Window Sill | 1 | SF | 0 | 1 | 85 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 85 | 0 | 0 | 0 | 0 | 110 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 85 | hold | Labor | Change Order | TRUE
97-7000 | TESTING, HANDLING, DISPOSAL OF PETROLIUM CONT SOIL | 1 | CY | 0 | 1 | 60 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 60 | 0 | 0 | 0 | 0 | 110 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | hold | Labor | Change Order | TRUE
98-1000 | ALLOWANCE -CON EDISON ELEC UTILITY SERVICE FEE | 1 | LS | 0 | 1 | 51926.66 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 51926.66 | 0 | 0 | 0 | 0 | 110 | -51816.66 | 0 | 51926.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51926.66 | Phased | Labor | Site Utilities | TRUE
98-1100 | ALLOWANCE - NATIONAL GRID GAS UTILITY SERVICE FEE | 1 | LS | 0 | 1 | 141408 | FALSE | FALSE | 140826.98 | 140826.98 | 0 | 0 | 110 | 0 | 141408 | 0 | 0 | 0 | 0 | 140936.98 | -471.02 | 0 | 581.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141408 | Phased | Labor | Site Utilities | TRUE
99-1000 | Supervision | 37 | MO | 86521.03 | 0.00042764 | 7270000 | FALSE | FALSE | 5245922.41 | 5261591.97 | 28 | 61793.63 | 82.0014 | 7070000 | 0 | 200000 | 0 | 0 | 0 | 6971696.0528 | -298303.9472 | 0 | 200000 | 220000 | 220000 | 242000 | 220000 | 220000 | 175000 | 175000 | 150000 | 100000 | 67763.55 | 7235685.96 | Phased | overhead |  | FALSE
99-1010 | CLAIMS CONSULTANT | 0 | NA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
99-1020 | LEGAL COSTS | 0 | LS | 0 | 1 | 50000 | FALSE | FALSE | 5030 | 5030 | 0 | 0 | 110 | 0 | 0 | 50000 | 0 | 0 | 0 | 5030 | -44970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4970 | 10000 | 10000 | 10000 | 10000 | 50000 | Phased | overhead |  | TRUE
99-1100 | TEAMSTER | 12 | MO | 3150 | 0.0038095 | 315000 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 315000 | 0 | 0 | 0 | 0 | 0 | 346500 | 31500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency |  | FALSE
99-1200 | OPER ENG MASTER MECH | 12 | MO | 1697.26 | 0.0070702 | 270000 | FALSE | FALSE | 70524.91 | 70524.91 | 2.94 | 468 | 150.6943 | 270000 | 0 | 0 | 0 | 0 | 0 | 263629.2414 | -6370.7586 | 0 | 27974.1557 | 27974.1557 | 27974.1557 | 27974.1557 | 27974.1557 | 27974.1557 | 27974.1557 | 0 | 0 | 0 | 0 | 266344 | Phased | Labor | Site Maintenance | FALSE
99-1300 | OPER ENG MECH | 12 | MO | 1793.1 | 0.0066923 | 260000 | FALSE | FALSE | 63513.14 | 63513.14 | 3.03 | 462.5 | 137.3257 | 260000 | 0 | 0 | 0 | 0 | 0 | 247576.5886 | -12423.4114 | 0 | 27641.78 | 27641.78 | 27641.78 | 27641.78 | 27641.78 | 27641.78 | 27641.78 | 0 | 0 | 0 | 0 | 257005.6 | Phased | Labor | Site Maintenance | FALSE
99-2000 | SURVEY SUB | 9 | EA | 0 | 1 | 521300 | FALSE | FALSE | 468449 | 555038.25 | 0 | 0 | 110 | 0 | 500000 | 21300 | 0 | 0 | 0 | 469439 | -51861 | 0 | 5872.3333 | 5872.3333 | 5872.3333 | 5872.3333 | 5872.3333 | 5872.3333 | 5872.3333 | 5872.3333 | 5872.3333 | 0 | 0 | 521300 | Phased | Sub |  | TRUE
99-3000 | SECURITY SUB | 37 | MO | 0 | 1 | 648295.5 | FALSE | FALSE | 0 | 0 | 27 | 0 | 110 | 0 | 648295.5 | 0 | 0 | 0 | 0 | 1100 | -647195.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency |  | FALSE
99-3100 | CONTAINERS - 30 CY | 400 | EA | 0 | 1 | 1150000 | FALSE | FALSE | 710968.41 | 892165.6 | 80 | 0 | 110 | 0 | 0 | 1150000 | 0 | 0 | 0 | 746168.41 | -403831.59 | 0 | 80000 | 80000 | 80000 | 50000 | 50000 | 30000 | 30000 | 20000 | 10000 | 9031.59 | 0 | 1150000 | Phased | Material |  | TRUE
99-4000 | YARD W/ TEMP ELECT | 74.02 | HR | 535.04 | 0.13834 | 138034 | FALSE | FALSE | 119118.41 | 119118.41 | 74.02 | 382 | 107.4891 | 55815.7 | 0 | 82218.3 | 0 | 0 | 0 | 119118.41 | -18915.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 8915.59 | 138034 | Phased | Labor | Closeout | TRUE
99-4050 | COMPUTER/SOFTWARE | 8 | EA | 0 | 1 | 90000 | FALSE | FALSE | 80136.51 | 80136.51 | 0 | 0 | 110 | 0 | 0 | 90000 | 0 | 0 | 0 | 81016.51 | -8983.49 | 0 | 896.6809 | 896.6809 | 896.6809 | 896.6809 | 896.6809 | 896.6809 | 896.6809 | 896.6809 | 896.6809 | 896.6809 | 896.6809 | 90000 | monthly | overhead |  | TRUE
99-4100 | STATIONWORK DESK | 8 | EA | 0 | 1 | 8710.4 | FALSE | FALSE | 6193.68 | 6193.68 | 7 | 0 | 110 | 0 | 0 | 8710.4 | 0 | 0 | 0 | 6303.68 | -2406.72 | 0 | 228.7927 | 228.7927 | 228.7927 | 228.7927 | 228.7927 | 228.7927 | 228.7927 | 228.7927 | 228.7927 | 228.7927 | 228.7927 | 8710.4 | monthly | overhead |  | TRUE
99-4150 | IT SUPPORT | 37 | MO | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 27 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
99-4200 | PHONE EQUIPMENT | 8 | EA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 7 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
99-4250 | PHONE SYSTEM | 271 | UM | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 50.65 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 24238.5 | 24238.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
99-4300 | PRINTERS/PLOTTER | 37 | MO | 0 | 1 | 55000 | FALSE | FALSE | 41223.99 | 41223.99 | 28 | 0 | 110 | 0 | 0 | 55000 | 0 | 0 | 0 | 42213.99 | -12786.01 | 0 | 1250.1373 | 1250.1373 | 1250.1373 | 1250.1373 | 1250.1373 | 1250.1373 | 1250.1373 | 1250.1373 | 1250.1373 | 1250.1373 | 1250.1373 | 54975.5 | monthly | overhead |  | FALSE
99-4350 | SUPPLIES | 271 | UM | 0 | 1 | 90000 | FALSE | FALSE | 59051.92 | 59051.93 | 14.65 | 0 | 110 | 0 | 0 | 90000 | 0 | 0 | 0 | 87250.42 | -2749.58 | 0 | 2760.43 | 2760.43 | 2760.43 | 2760.43 | 2760.43 | 2760.43 | 2760.43 | 2760.43 | 2760.43 | 2760.43 | 2760.43 | 89416.65 | monthly | overhead |  | FALSE
99-4400 | TELEPHONE | 37 | MO | 0 | 1 | 18500 | FALSE | FALSE | 0 | 0 | 28 | 0 | 110 | 0 | 0 | 18500 | 0 | 0 | 0 | 990 | -17510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency |  | FALSE
99-4450 | CELL PHONES | 271 | UM | 0 | 1 | 29506.48 | FALSE | FALSE | 19721.09 | 19721.09 | 14.65 | 0 | 110 | 0 | 0 | 29506.48 | 0 | 0 | 0 | 47919.59 | 18413.11 | 0 | 889.5809 | 889.5809 | 889.5809 | 889.5809 | 889.5809 | 889.5809 | 889.5809 | 889.5809 | 889.5809 | 889.5809 | 889.5809 | 29506.48 | monthly | overhead |  | TRUE
99-4500 | ELECTRIC | 37 | MO | 0 | 1 | 18500 | FALSE | FALSE | 0 | 0 | 28 | 0 | 110 | 0 | 0 | 18500 | 0 | 0 | 0 | 990 | -17510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency |  | FALSE
99-4550 | SANITATION | 37 | MO | 0 | 1 | 305000 | FALSE | FALSE | 154554.47 | 303221.25 | 28 | 0 | 110 | 0 | 0 | 305000 | 0 | 0 | 0 | 155544.47 | -149455.53 | 0 | 20445.53 | 20000 | 20000 | 20000 | 20000 | 10000 | 10000 | 10000 | 10000 | 5000 | 5000 | 305000 | Phased | overhead |  | TRUE
99-4560 | SITE MAINTENANCE | 11240 | HR | 10642.56 | 1.0561 | 1110000 | FALSE | FALSE | 840936.12 | 840936.12 | 6146.5 | 8073.5 | 104.16 | 1110000 | 0 | 0 | 0 | 0 | 0 | 1343275.5445 | 233275.5445 | 0 | 35173.33 | 34560 | 34560 | 34560 | 34560 | 17280 | 17280 | 17280 | 17280 | 15000 | 10000 | 1108469.45 | Phased | Labor | Site Maintenance | FALSE
99-4570 | BASEMENT MAINTENANCE | 960 | HR | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 105600 | 105600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
99-4600 | VEHICLES | 180 | MO | 27.33 | 6.5862 | 160347.74 | FALSE | FALSE | 81071.28 | 106502.01 | 28 | 3 | 248.6533 | 2871.76 | 0 | 137371.42 | 0 | 0 | 20104.56 | 86809.8674 | -73537.8726 | 0 | 10000 | 10000 | 10000 | 10000 | 10000 | 5000 | 5000 | 5000 | 5000 | 5000 | 2988.36 | 159059.64 | Phased | Equipment |  | FALSE
99-4650 | FUEL | 180 | MO | 0 | 1 | 160000 | FALSE | FALSE | 118312.29 | 204535.66 | 28 | 0 | 110 | 0 | 0 | 160000 | 0 | 0 | 0 | 135032.29 | -24967.71 | 0 | 10000 | 10000 | 10000 | 5000 | 2500 | 2500 | 1500 | 0 | 0 | 0 | 0 | 159812.29 | Phased | Equipment |  | FALSE
99-4700 | PETTY CASH | 37 | MO | 0 | 1 | 111000 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 111000 | 0 | 0 | 0 | 4070 | -106930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency |  | FALSE
99-5000 | OFFICE RENT | 222 | UM | 0 | 1 | 561000 | FALSE | FALSE | 439507.07 | 447640.03 | 22 | 0 | 110 | 0 | 0 | 561000 | 0 | 0 | 0 | 461507.07 | -99492.93 | 0 | 13499.2144 | 13499.2144 | 13499.2144 | 13499.2144 | 13499.2144 | 13499.2144 | 13499.2144 | 13499.2144 | 13499.2144 | 0 | 0 | 561000 | Phased | overhead |  | TRUE
99-5100 | NYCHA OFFICE FURNITURE | 1 | LS | 65.5 | 0.015267 | 55000 | FALSE | FALSE | 38878.87 | 40158.87 | 0.72 | 65.5 | 85.8261 | 5621.61 | 0 | 49378.39 | 0 | 0 | 0 | 40452.9208 | -14547.0792 | 0 | 1465.5573 | 1465.5573 | 1465.5573 | 1465.5573 | 1465.5573 | 1465.5573 | 1465.5573 | 1465.5573 | 1465.5573 | 1465.5573 | 1465.5573 | 55000 | monthly | overhead |  | TRUE
99-6000 | SMALL TOOLS | 37 | MO | 0 | 1 | 640000 | FALSE | FALSE | 516443.35 | 742548.63 | 28 | 0 | 110 | 0 | 0 | 640000 | 0 | 0 | 0 | 517433.35 | -122566.65 | 0 | 10174.4045 | 10174.4045 | 10174.4045 | 10174.4045 | 10174.4045 | 10174.4045 | 10174.4045 | 10174.4045 | 10174.4045 | 10174.4045 | 10174.4045 | 628361.8 | monthly | Material |  | FALSE
99-7000 | LABOR ESCAL | 1 | LS | 10000 | 0.0001 | 1000000 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 1000000 | 0 | 0 | 0 | 0 | 0 | 1100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency |  | FALSE
99-7100 | PREMIUM COST | 1 | LS | 5000 | 0.0002 | 500000 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 500000 | 0 | 0 | 0 | 0 | 0 | 550000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | hold | Contingency |  | FALSE
99-7200 | HOLIDAY PAY | 1.19 | LS | 1469 | 0.00081007 | 265289.81 | FALSE | FALSE | 203649.81 | 203649.81 | 1.19 | 1787 | 113.7198 | 325000 | 0 | 432.56 | 0 | 0 | -60142.75 | 203649.81 | -61640 | 0 | 18400 | 18400 | 9200 | 0 | 0 | 6440 | 0 | 4600 | 0 | 4600 | 0 | 265289.81 | Phased | overhead |  | TRUE
99-7210 | PAID TIME OFF | 480 | NA | 588.1 | 0.81619 | 68000 | FALSE | FALSE | 26257.59 | 26257.59 | 296.6 | 240 | 109.4066 | 68000 | 0 | 0 | 0 | 0 | 0 | 50841.6097 | -17158.3903 | 0 | 3750.2845 | 3750.2845 | 3750.2845 | 3750.2845 | 3750.2845 | 3750.2845 | 3750.2845 | 3750.2845 | 3750.2845 | 3750.2845 | 3750.2845 | 67510.72 | monthly | overhead |  | FALSE
99-7300 | LOST TIME | 1 | LS | 1500 | 0.00066667 | 150000 | FALSE | FALSE | 49377.75 | 49377.75 | 0.31 | 399 | 123.7538 | 150000 | 0 | 0 | 0 | 0 | 0 | 177462.891 | 27462.891 | 0 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 9147.4773 | 150000 | hold | overhead |  | TRUE
99-7400 | PERMITS | 1 | LS | 0 | 1 | 30000 | FALSE | FALSE | 18673.7 | 20998.7 | 0.79 | 0 | 110 | 0 | 0 | 30000 | 0 | 0 | 0 | 18696.8 | -11303.2 | 0 | 1415.7875 | 1415.7875 | 1415.7875 | 1415.7875 | 1415.7875 | 1415.7875 | 1415.7875 | 1415.7875 | 0 | 0 | 0 | 30000 | Phased | overhead |  | TRUE
99-7500 | ENGINEERING SUB | 1 | LS | 0 | 1 | 183350 | FALSE | FALSE | 171007.28 | 178984.95 | 0.86 | 0 | 110 | 0 | 183350 | 0 | 0 | 0 | 0 | 171022.68 | -12327.32 | 0 | 1542.84 | 1542.84 | 1542.84 | 1542.84 | 1542.84 | 1542.84 | 1542.84 | 1542.84 | 0 | 0 | 0 | 183350 | Phased | Sub |  | TRUE
99-7510 | CADD SERVICES | 9 | EA | 0 | 1 | 20000 | FALSE | FALSE | 12795.69 | 14453.39 | 0 | 0 | 110 | 0 | 0 | 20000 | 0 | 0 | 0 | 13785.69 | -6214.31 | 0 | 900.5387 | 900.5387 | 900.5387 | 900.5387 | 900.5387 | 900.5387 | 900.5387 | 900.5387 | 0 | 0 | 0 | 20000 | Phased | overhead |  | TRUE
99-7600 | SECTION 3 ADMINISTRATOR SUB | 1 | LS | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
99-8000 | EQUIPMENT | 1 | LS | 0 | 1 | 1549124.28 | FALSE | FALSE | 1027952.62 | 1406424.72 | 0.38 | 0 | 110 | 0 | 0 | 93736.6 | 0 | 1430043.14 | 25344.54 | 1028020.82 | -521103.46 | 0 | 80000 | 80000 | 80000 | 60000 | 50000 | 40000 | 30000 | 20000 | 10000 | 5134.01 | 0 | 1483086.63 | Phased | overhead |  | FALSE
99-8050 | AID TO SUBS | 1 | LS | 2500 | 0.0004 | 250000 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 250000 | 0 | 0 | 0 | 0 | 0 | 275000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 250000 | Phased | Sub |  | TRUE
99-8100 | PROJECT SIGNS | 1 | EA | 0 | 1 | 4000 | FALSE | FALSE | 3181.22 | 3181.23 | 0 | 0 | 110 | 0 | 0 | 4000 | 0 | 0 | 0 | 3291.22 | -708.78 | 0 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 74.4345 | 4000 | monthly | Material |  | TRUE
99-8200 | PUNCH LIST | 1 | LS | 2500 | 0.0004 | 250000 | FALSE | FALSE | 0 | 0 | 0 | 0 | 110 | 250000 | 0 | 0 | 0 | 0 | 0 | 275000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 50000 | 250000 | Phased | Labor | Closeout | TRUE
99-9000 | BOND | 1 | LS | 0 | 1 | 1170144 | FALSE | FALSE | 948765.41 | 948765.41 | 0.48 | 0 | 110 | 0 | 0 | 1170144 | 0 | 0 | 0 | 948822.61 | -221321.39 | 0 | 20125.3264 | 20125.3264 | 20125.3264 | 20125.3264 | 20125.3264 | 20125.3264 | 20125.3264 | 20125.3264 | 20125.3264 | 20125.3264 | 20125.3264 | 1170144 | monthly | overhead |  | TRUE
99-9100 | INSURANCE | 1 | LS | 0 | 1 | 3248000 | FALSE | FALSE | 1762491.35 | 1762491.35 | 0.2 | 0 | 110 | 0 | 0 | 45902 | 0 | 0 | 3202098 | 1762579.35 | -1485420.65 | 0 | 122433.7864 | 122433.7864 | 122433.7864 | 122433.7864 | 122433.7864 | 122433.7864 | 122433.7864 | 122433.7864 | 122433.7864 | 122433.7864 | 122433.7864 | 3109263 | monthly | overhead |  | FALSE
99-9999 | Accruals | 0 | NA | 0 | 1 | 0 | TRUE | FALSE | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | spent | spent |  | TRUE
99-NY0001 | Supervision- Do Not Use | 0 | NA | 248 | 1 | 22408.12 | TRUE | FALSE | 22408.12 | 22408.12 | 0 | 248 | 65.3553 | 16208.12 | 0 | 6200 | 0 | 0 | 0 | 22408.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22408.12 | spent | spent |  | TRUE