## Activities
Activity Status | WBS Code | Building/Area | ID1 | ID2 | ID3 | ID4 | Activity ID | Type | (*)WBS Name | (*)WBS Path | Activity Name | Original Duration(h) | Remaining Duration(h) | Activity % Complete | (*)Start | (*)Finish | (*)Total Float(h) | Sub | Actvity Category 1 | Actvity Category 2 | Cost Code | Sub-Cost Code
Completed | CI NYCHA Update #22.Milestones | 0 | M000 | 0 | 0 | 0 | M000 | Milestones | Milestones | Milestones | Notice of Award | 0 | 0 | 100% | 2020-02-27 17:00 |  |  | MLJ | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Milestones.6 | S82 | M170 | 0 | 0 | 0 | M170 | Milestones | Phase 6 Construction (Site 8) | Milestones.6 | Start Building S8-1 - Addition | 0 | 0 | 100% | 2022-04-20 |  |  | MLJ | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Milestones.6 | S82 | M175 | 0 | 0 | 0 | M175 | Milestones | Phase 6 Construction (Site 8) | Milestones.6 | Complete Building S8-1 - Addition | 0 | 0 | 0% |  | 2024-05-08 17:00 | -348 | MLJ | MILESTONE | 0 | NA | NA-S82
Completed | CI NYCHA Update #22.Milestones.6 | S82 | M180 | 0 | 0 | 0 | M180 | Milestones | Phase 6 Construction (Site 8) | Milestones.6 | Start Building S8-1 - Existing | 0 | 0 | 100% | 2022-04-20 |  |  | MLJ | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Milestones.6 | S82 | M185 | 0 | 0 | 0 | M185 | Milestones | Phase 6 Construction (Site 8) | Milestones.6 | Complete Building S8-1 - Existing | 0 | 0 | 0% |  | 2024-05-08 17:00 | -348 | MLJ | MILESTONE | 0 | NA | NA-S82
Completed | CI NYCHA Update #22.Milestones.3 | OG2 | M090 | 0 | 0 | 0 | M090 | Milestones | Phase 3 Construction (Odwyer Gardens West - OG-9, OG-2, OG-3) | Milestones.3 | Start Building OG-2 | 0 | 0 | 100% | 2021-03-13 |  |  | MLJ | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Milestones.3 | OG2 | M095 | 0 | 0 | 0 | M095 | Milestones | Phase 3 Construction (Odwyer Gardens West - OG-9, OG-2, OG-3) | Milestones.3 | Complete Building OG-2 | 0 | 0 | 0% |  | 2023-07-28 17:00 | -63 | MLJ | MILESTONE | 0 | NA | NA-OG2
Completed | CI NYCHA Update #22.Milestones.3 | OG3 | M080 | 0 | 0 | 0 | M080 | Milestones | Phase 3 Construction (Odwyer Gardens West - OG-9, OG-2, OG-3) | Milestones.3 | Start Building OG-3 | 0 | 0 | 100% | 2021-05-12 08:00 |  |  | MLJ | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Milestones.3 | OG3 | M085 | 0 | 0 | 0 | M085 | Milestones | Phase 3 Construction (Odwyer Gardens West - OG-9, OG-2, OG-3) | Milestones.3 | Complete Building OG-3 | 0 | 0 | 0% |  | 2024-01-15 17:00 | -234 | MLJ | MILESTONE | 0 | NA | NA-OG3
Completed | CI NYCHA Update #22.Milestones.2 | OG4 | M050 | 0 | 0 | 0 | M050 | Milestones | Phase 2 Construction (Odwyer Gardens Part 1 - OG-8, OG-4, OG-5) | Milestones.2 | Start Building OG-4 | 0 | 0 | 100% | 2021-09-20 08:00 |  |  | MLJ | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Milestones.2 | OG4 | M055 | 0 | 0 | 0 | M055 | Milestones | Phase 2 Construction (Odwyer Gardens Part 1 - OG-8, OG-4, OG-5) | Milestones.2 | Complete Building OG-4 | 0 | 0 | 0% |  | 2023-09-11 17:00 | -108 | MLJ | MILESTONE | 0 | NA | NA-OG4
Completed | CI NYCHA Update #22.Milestones.2 | OG8 | M040 | 0 | 0 | 0 | M040 | Milestones | Phase 2 Construction (Odwyer Gardens Part 1 - OG-8, OG-4, OG-5) | Milestones.2 | Start Building OG-8 | 0 | 0 | 100% | 2021-07-12 08:00 |  |  | MLJ | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Milestones.2 | OG8 | M045 | 0 | 0 | 0 | M045 | Milestones | Phase 2 Construction (Odwyer Gardens Part 1 - OG-8, OG-4, OG-5) | Milestones.2 | Complete Building OG-8 | 0 | 0 | 0% |  | 2023-08-15 17:00 | -81 | MLJ | MILESTONE | 0 | NA | NA-OG8
Completed | CI NYCHA Update #22.Milestones.3 | OG9 | M070 | 0 | 0 | 0 | M070 | Milestones | Phase 3 Construction (Odwyer Gardens West - OG-9, OG-2, OG-3) | Milestones.3 | Start Building OG-9 | 0 | 0 | 100% | 2021-08-10 08:00 |  |  | MLJ | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Milestones.3 | OG9 | M075 | 0 | 0 | 0 | M075 | Milestones | Phase 3 Construction (Odwyer Gardens West - OG-9, OG-2, OG-3) | Milestones.3 | Complete Building OG-9 | 0 | 0 | 0% |  | 2024-01-03 17:00 | -222 | MLJ | MILESTONE | 0 | NA | NA-OG9
Completed | CI NYCHA Update #22.Milestones.4 | OG1 | M120 | 0 | 0 | 0 | M120 | Milestones | Phase 4 Construction (Odwyer Gardens East - OG-10, OG-1, OG-6) | Milestones.4 | Start Building OG-1 | 0 | 0 | 100% | 2021-05-17 08:00 |  |  | MLJ | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Milestones.4 | OG1 | M125 | 0 | 0 | 0 | M125 | Milestones | Phase 4 Construction (Odwyer Gardens East - OG-10, OG-1, OG-6) | Milestones.4 | Complete Building OG-1 | 0 | 0 | 0% |  | 2024-01-22 17:00 | -241 | MLJ | MILESTONE | 0 | NA | NA-OG1
Completed | CI NYCHA Update #22.Milestones.2 | OG5 | M060 | 0 | 0 | 0 | M060 | Milestones | Phase 2 Construction (Odwyer Gardens Part 1 - OG-8, OG-4, OG-5) | Milestones.2 | Start Building OG-5 | 0 | 0 | 100% | 2021-04-21 08:00 |  |  | MLJ | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Milestones.2 | OG5 | M065 | 0 | 0 | 0 | M065 | Milestones | Phase 2 Construction (Odwyer Gardens Part 1 - OG-8, OG-4, OG-5) | Milestones.2 | Complete Building OG-5 | 0 | 0 | 0% |  | 2024-01-08 17:00 | -227 | MLJ | MILESTONE | 0 | NA | NA-OG5
Completed | CI NYCHA Update #22.Milestones.4 | OG6 | M110 | 0 | 0 | 0 | M110 | Milestones | Phase 4 Construction (Odwyer Gardens East - OG-10, OG-1, OG-6) | Milestones.4 | Start Building OG-6 | 0 | 0 | 100% | 2021-05-03 |  |  | MLJ | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Milestones.4 | OG6 | M115 | 0 | 0 | 0 | M115 | Milestones | Phase 4 Construction (Odwyer Gardens East - OG-10, OG-1, OG-6) | Milestones.4 | Complete Building OG-6 | 0 | 0 | 0% |  | 2024-02-13 17:00 | -263 | MLJ | MILESTONE | 0 | NA | NA-OG6
Completed | CI NYCHA Update #22.Milestones.4 | OG10 | M100 | 0 | 0 | 0 | M100 | Milestones | Phase 4 Construction (Odwyer Gardens East - OG-10, OG-1, OG-6) | Milestones.4 | Start Building OG-10 | 0 | 0 | 100% | 2021-06-30 08:00 |  |  | MLJ | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Milestones.4 | OG10 | M105 | 0 | 0 | 0 | M105 | Milestones | Phase 4 Construction (Odwyer Gardens East - OG-10, OG-1, OG-6) | Milestones.4 | Complete Building OG-10 | 0 | 0 | 0% |  | 2024-01-24 17:00 | -243 | MLJ | MILESTONE | 0 | NA | NA-OG10
Completed | CI NYCHA Update #22.Milestones.1 | SG4 | M020 | 0 | 0 | 0 | M020 | Milestones | Phase 1 Construction (Surfside North - SG-6, SG-4, SG-5) | Milestones.1 | Start Building SG-4 | 0 | 0 | 100% | 2021-09-13 08:00 |  |  | MLJ | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Milestones.1 | SG4 | M025 | 0 | 0 | 0 | M025 | Milestones | Phase 1 Construction (Surfside North - SG-6, SG-4, SG-5) | Milestones.1 | Complete Building SG-4 | 0 | 0 | 0% |  | 2023-07-05 17:00 | -40 | MLJ | MILESTONE | 0 | NA | NA-SG4
Completed | CI NYCHA Update #22.Milestones.1 | SG5 | M030 | 0 | 0 | 0 | M030 | Milestones | Phase 1 Construction (Surfside North - SG-6, SG-4, SG-5) | Milestones.1 | Start Building SG-5 | 0 | 0 | 100% | 2021-06-14 08:00 |  |  | MLJ | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Milestones.1 | SG5 | M035 | 0 | 0 | 0 | M035 | Milestones | Phase 1 Construction (Surfside North - SG-6, SG-4, SG-5) | Milestones.1 | Complete Building SG-5 | 0 | 0 | 0% |  | 2023-07-25 17:00 | -60 | MLJ | MILESTONE | 0 | NA | NA-SG5
Completed | CI NYCHA Update #22.Milestones.1 | SG6 | M010 | 0 | 0 | 0 | M010 | Milestones | Phase 1 Construction (Surfside North - SG-6, SG-4, SG-5) | Milestones.1 | Start Building SG-6 | 0 | 0 | 100% | 2021-03-25 |  |  | MLJ | 0 | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Milestones.1 | SG6 | M015 | 0 | 0 | 0 | M015 | Milestones | Phase 1 Construction (Surfside North - SG-6, SG-4, SG-5) | Milestones.1 | Complete Building SG-6 | 0 | 0 | 0% |  | 2023-06-22 17:00 | -27 | MLJ | MILESTONE | 0 | NA | NA-SG6
Completed | CI NYCHA Update #22.Milestones.5 | SG1 | M150 | 0 | 0 | 0 | M150 | Milestones | Phase 5 Construction (Surfside Gardens South - SG-7, SG-1, SG-2, SG-3) | Milestones.5 | Start Building SG-1 | 0 | 0 | 100% | 2021-03-08 |  |  | MLJ | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Milestones.5 | SG1 | M155 | 0 | 0 | 0 | M155 | Milestones | Phase 5 Construction (Surfside Gardens South - SG-7, SG-1, SG-2, SG-3) | Milestones.5 | Complete Building SG-1 | 0 | 0 | 0% |  | 2023-11-15 17:00 | -173 | MLJ | MILESTONE | 0 | NA | NA-SG1
Completed | CI NYCHA Update #22.Milestones.5 | SG2 | M160 | 0 | 0 | 0 | M160 | Milestones | Phase 5 Construction (Surfside Gardens South - SG-7, SG-1, SG-2, SG-3) | Milestones.5 | Start Building SG-2 | 0 | 0 | 100% | 2021-05-18 08:00 |  |  | MLJ | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Milestones.5 | SG2 | M165 | 0 | 0 | 0 | M165 | Milestones | Phase 5 Construction (Surfside Gardens South - SG-7, SG-1, SG-2, SG-3) | Milestones.5 | Complete Building SG-2 | 0 | 0 | 0% |  | 2023-11-15 17:00 | -173 | MLJ | MILESTONE | 0 | NA | NA-SG2
Completed | CI NYCHA Update #22.Milestones.5 | SG3 | M145 | 0 | 0 | 0 | M145 | Milestones | Phase 5 Construction (Surfside Gardens South - SG-7, SG-1, SG-2, SG-3) | Milestones.5 | Start Building SG-3 | 0 | 0 | 100% | 2021-05-06 08:00 |  |  | MLJ | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Milestones.5 | SG3 | M140 | 0 | 0 | 0 | M140 | Milestones | Phase 5 Construction (Surfside Gardens South - SG-7, SG-1, SG-2, SG-3) | Milestones.5 | Complete Building SG-3 | 0 | 0 | 0% |  | 2023-11-21 17:00 | -179 | MLJ | MILESTONE | 0 | NA | NA-SG3
Completed | CI NYCHA Update #22.Milestones.5 | SG7 | M130 | 0 | 0 | 0 | M130 | Milestones | Phase 5 Construction (Surfside Gardens South - SG-7, SG-1, SG-2, SG-3) | Milestones.5 | Start Building SG-7 | 0 | 0 | 100% | 2021-04-28 08:00 |  |  | MLJ | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Milestones.5 | SG7 | M135 | 0 | 0 | 0 | M135 | Milestones | Phase 5 Construction (Surfside Gardens South - SG-7, SG-1, SG-2, SG-3) | Milestones.5 | Complete Building SG-7 | 0 | 0 | 0% |  | 2024-05-08 17:00 | -348 | MLJ | MILESTONE | 0 | NA | NA-SG7
Completed | CI NYCHA Update #22.Procurement.Div 1.GENRAL | 0 | 01500 | 0 | 0 | 0 | 01500 | Procurement | General | Procurement.Div 1.GENRAL | Prepare & Submit Safety Plan | 25 | 0 | 100% | 2020-07-13 | 2020-08-14 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.GENRAL | 0 | 01510 | 0 | 0 | 0 | 01510 | Procurement | General | Procurement.Div 1.GENRAL | Initial Review of Safety Plan | 10 | 0 | 100% | 2020-08-15 | 2020-09-15 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.GENRAL | 0 | 01520 | 0 | 0 | 0 | 01520 | Procurement | General | Procurement.Div 1.GENRAL | Prepare & Submit Safety Engineer | 30 | 0 | 100% | 2020-07-13 | 2020-09-30 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.GENRAL | 0 | 01530 | 0 | 0 | 0 | 01530 | Procurement | General | Procurement.Div 1.GENRAL | Review & Approve Safety Engineer | 10 | 0 | 100% | 2020-09-30 | 2020-10-19 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.GENRAL | 0 | 01540 | 0 | 0 | 0 | 01540 | Procurement | General | Procurement.Div 1.GENRAL | Prepare & Submit Quality Plan | 20 | 0 | 100% | 2020-07-13 | 2020-09-01 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.GENRAL | 0 | 01550 | 0 | 0 | 0 | 01550 | Procurement | General | Procurement.Div 1.GENRAL | Review & Approve Quality Plan | 10 | 0 | 100% | 2020-09-01 | 2021-01-04 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 2 | 0 | 02020 | 0 | 0 | 0 | 02020 | Procurement | Div. 2 - Existing Conditions | Procurement.Div. 2 | Prepare & Submit Pre-construction As Built Sewer and Water Main Documentation | 20 | 0 | 100% | 2020-12-21 | 2021-01-20 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 2 | 0 | 02030 | 0 | 0 | 0 | 02030 | Procurement | Div. 2 - Existing Conditions | Procurement.Div. 2 | Review & Approve Pre-construction As Built Sewer and Water Main Documentation | 10 | 0 | 100% | 2021-01-20 | 2021-06-22 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 2 | 0 | 02040 | 0 | 0 | 0 | 02040 | Procurement | Div. 2 - Existing Conditions | Procurement.Div. 2 | Prepare & Submit Testing, Handling, and of Contaminated Soils Plan | 60 | 0 | 100% | 2020-07-13 | 2020-10-26 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 2 | 0 | 02050 | 0 | 0 | 0 | 02050 | Procurement | Div. 2 - Existing Conditions | Procurement.Div. 2 | Review & Approve Testing, Handling, and of Contaminated Soils Plan | 10 | 0 | 100% | 2020-10-26 | 2020-12-23 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 2 | 0 | 02060 | 0 | 0 | 0 | 02060 | Procurement | Div. 2 - Existing Conditions | Procurement.Div. 2 | Prepare & Submit Site Demolition Plan | 40 | 0 | 100% | 2020-10-01 | 2020-10-30 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 2 | 0 | 02070 | 0 | 0 | 0 | 02070 | Procurement | Div. 2 - Existing Conditions | Procurement.Div. 2 | Review & Approve Site Demolition Plan | 10 | 0 | 100% | 2020-10-30 | 2020-11-16 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 2 | 0 | 02080 | 0 | 0 | 0 | 02080 | Procurement | Div. 2 - Existing Conditions | Procurement.Div. 2 | Prepare & Submit Selective Demolition Plan | 40 | 0 | 100% | 2020-10-01 | 2020-10-30 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 2 | 0 | 02090 | 0 | 0 | 0 | 02090 | Procurement | Div. 2 - Existing Conditions | Procurement.Div. 2 | Review & Approve Selective Demolition Plan | 10 | 0 | 100% | 2020-10-30 | 2020-11-16 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 2 | 0 | 02100 | 0 | 0 | 0 | 02100 | Procurement | Div. 2 - Existing Conditions | Procurement.Div. 2 | Prepare & Submit Interior Asbestos Abatement Plan | 40 | 0 | 100% | 2020-08-03 | 2020-09-02 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 2 | 0 | 02110 | 0 | 0 | 0 | 02110 | Procurement | Div. 2 - Existing Conditions | Procurement.Div. 2 | Review & Approve Interior Asbestos Abatement Plan | 10 | 0 | 100% | 2020-09-02 | 2021-02-08 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 2 | 0 | 02120 | 0 | 0 | 0 | 02120 | Procurement | Div. 2 - Existing Conditions | Procurement.Div. 2 | Prepare & Submit Asbestos Abatement - Masonry Removals Plan | 40 | 0 | 100% | 2020-08-03 | 2020-09-02 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 2 | 0 | 02130 | 0 | 0 | 0 | 02130 | Procurement | Div. 2 - Existing Conditions | Procurement.Div. 2 | Review & Approve Asbestos Abatement - Masonry Removals Plan | 10 | 0 | 100% | 2020-09-02 | 2021-02-08 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 2 | 0 | 02140 | 0 | 0 | 0 | 02140 | Procurement | Div. 2 - Existing Conditions | Procurement.Div. 2 | Prepare & Submit Asbestos Abatement - Site Work (Underground Utilities) Plan | 40 | 0 | 100% | 2020-08-03 | 2020-09-02 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 2 | 0 | 02150 | 0 | 0 | 0 | 02150 | Procurement | Div. 2 - Existing Conditions | Procurement.Div. 2 | Review & Approve Asbestos Abatement - Site Work (Underground Utilities) Plan | 10 | 0 | 100% | 2020-09-02 | 2021-11-05 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 2 | 0 | 02160 | 0 | 0 | 0 | 02160 | Procurement | Div. 2 - Existing Conditions | Procurement.Div. 2 | Prepare & Submit Lead Safe Work Practices Plan | 20 | 0 | 100% | 2020-11-10 | 2020-12-10 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 2 | 0 | 02170 | 0 | 0 | 0 | 02170 | Procurement | Div. 2 - Existing Conditions | Procurement.Div. 2 | Review & Approve Lead Safe Work Practices Plan | 10 | 0 | 100% | 2020-12-11 | 2021-03-23 |  | 0 | 0 | 0 | 0 | 0-0
Not Started | CI NYCHA Update #22.Procurement.Div. 2 | NA | 02180 | 0 | 0 | 0 | 02180 | Procurement | Div. 2 - Existing Conditions | Procurement.Div. 2 | Obtain Lead Placards | 20 | 20 | 0% | 2022-11-25 08:00 | 2022-12-22 17:00 | 65 | MLJ | PROCUREMENT | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div. 3 | 0 | 03000 | 0 | 0 | 0 | 03000 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Prepare & Submit Strengthening of Concrete with FRP Product Data | 100 | 0 | 100% | 2020-12-28 | 2021-01-28 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 3 | 0 | 03010 | 0 | 0 | 0 | 03010 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Review & Approve Strengthening of Concrete with FRP Product Data | 10 | 0 | 100% | 2021-01-29 | 2021-05-25 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 3 | 0 | 03020 | 0 | 0 | 0 | 03020 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Del. Strengthening of Concrete with FRP | 5 | 0 | 100% | 2022-02-01 | 2022-02-04 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 3 | 0 | 03030 | 0 | 0 | 0 | 03030 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Prepare & Submit Concrete Formwork | 80 | 0 | 100% | 2020-10-05 | 2021-02-22 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 3 | 0 | 03040 | 0 | 0 | 0 | 03040 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Review & Approve Concrete Formwork | 10 | 0 | 100% | 2021-02-23 | 2021-03-23 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 3 | 0 | 03050 | 0 | 0 | 0 | 03050 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Fab/Del. Concrete Formwork | 5 | 0 | 100% | 2021-03-29 | 2021-04-05 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 3 | 0 | 03060 | 0 | 0 | 0 | 03060 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Prepare & Submit Concrete Reinforcement | 80 | 0 | 100% | 2020-07-13 | 2020-10-22 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 3 | 0 | 03070 | 0 | 0 | 0 | 03070 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Review & Approve Concrete Reinforcement | 10 | 0 | 100% | 2020-10-22 | 2021-03-22 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 3 | 0 | 03080 | 0 | 0 | 0 | 03080 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Fab/Del. Concrete Reinforcement | 5 | 0 | 100% | 2021-04-06 | 2021-04-13 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 3 | 0 | 03090 | 0 | 0 | 0 | 03090 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Prepare & Submit Cast In Place Concrete Mix Design | 80 | 0 | 100% | 2020-07-13 | 2020-09-02 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 3 | 0 | 03100 | 0 | 0 | 0 | 03100 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Review & Approve Cast In Place Concrete Mix Design | 10 | 0 | 100% | 2020-09-02 | 2020-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 3 | 0 | 03120 | 0 | 0 | 0 | 03120 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Prepare & Submit Grouting | 100 | 0 | 100% | 2021-01-04 | 2021-06-16 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 3 | 0 | 03130 | 0 | 0 | 0 | 03130 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Review & Approve Grouting | 10 | 0 | 100% | 2021-06-16 | 2021-06-18 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 3 | 0 | 03140 | 0 | 0 | 0 | 03140 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Fab/Del. Grouting | 10 | 0 | 100% | 2022-02-01 | 2022-02-04 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 3 | 0 | 03150 | 0 | 0 | 0 | 03150 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Prepare & Submit Concrete Repair Shop Drawings | 80 | 0 | 100% | 2021-01-01 | 2021-05-25 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 3 | 0 | 03160 | 0 | 0 | 0 | 03160 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Review & Approve Concrete Repair Shop Drawings | 10 | 0 | 100% | 2021-05-25 | 2021-05-26 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 4 | 0 | 04000 | 0 | 0 | 0 | 04000 | Procurement | Div. 4 - Masonry | Procurement.Div 4 | Prepare & Submit Unit Masonry | 100 | 0 | 100% | 2020-12-14 | 2021-09-22 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 4 | 0 | 04010 | 0 | 0 | 0 | 04010 | Procurement | Div. 4 - Masonry | Procurement.Div 4 | Review & Approve Unit Masonry | 10 | 0 | 100% | 2021-09-23 | 2021-12-26 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 4 | 0 | 04020 | 0 | 0 | 0 | 04020 | Procurement | Div. 4 - Masonry | Procurement.Div 4 | Fab/Del. Unit Masonry | 10 | 0 | 100% | 2021-12-26 | 2022-01-05 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 4 | 0 | 04030 | 0 | 0 | 0 | 04030 | Procurement | Div. 4 - Masonry | Procurement.Div 4 | Prepare & Submit Cast Stone | 150 | 0 | 100% | 2020-11-09 | 2021-07-08 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 4 | 0 | 04040 | 0 | 0 | 0 | 04040 | Procurement | Div. 4 - Masonry | Procurement.Div 4 | Review & Approve Cast Stone | 10 | 0 | 100% | 2021-07-09 08:00 | 2021-08-06 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 4 | 0 | 04050 | 0 | 0 | 0 | 04050 | Procurement | Div. 4 - Masonry | Procurement.Div 4 | Fab/Del. Cast Stone | 60 | 0 | 100% | 2022-01-03 08:00 | 2022-09-10 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | S82 | 05000 | 0 | 0 | 0 | 05000 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Structural Steel - S8-1 - Addition | 100 | 0 | 100% | 2020-11-05 | 2021-11-22 17:00 |  | 0 | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Procurement.div. 5 | S82 | 05010 | 0 | 0 | 0 | 05010 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Structural Steel - S8-1 - Addition | 10 | 0 | 100% | 2021-11-23 08:00 | 2022-03-31 |  | 0 | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Procurement.div. 5 | S82 | 05020 | 0 | 0 | 0 | 05020 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Structural Steel - S8-1 - Addition | 50 | 0 | 100% | 2022-01-10 | 2022-07-25 |  | 0 | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Procurement.div. 5 | S82 | 05030 | 0 | 0 | 0 | 05030 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Structural Steel - S8 Existing - N/A | 100 | 0 | 100% | 2020-11-05 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Procurement.div. 5 | S82 | 05040 | 0 | 0 | 0 | 05040 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Structural Steel - S8 Existing - N/A | 10 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Procurement.div. 5 | S82 | 05050 | 0 | 0 | 0 | 05050 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Structural Steel - S8 Existing - N/A | 50 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG2 | 05060 | 0 | 0 | 0 | 05060 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Structural Steel - OG-2 | 100 | 0 | 100% | 2020-11-05 | 2021-06-09 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG2 | 05070 | 0 | 0 | 0 | 05070 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Structural Steel - OG-2 | 10 | 0 | 100% | 2021-06-10 08:00 | 2021-06-18 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG2 | 05080 | 0 | 0 | 0 | 05080 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Structural Steel - OG-2 | 50 | 0 | 100% | 2022-01-10 | 2022-04-04 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG3 | 05090 | 0 | 0 | 0 | 05090 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Structural Steel - OG-3 | 100 | 0 | 100% | 2020-11-05 | 2021-06-09 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG3 | 05100 | 0 | 0 | 0 | 05100 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Structural Steel - OG-3 | 10 | 0 | 100% | 2021-06-10 08:00 | 2021-06-18 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG3 | 05110 | 0 | 0 | 0 | 05110 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Structural Steel - OG-3 | 50 | 0 | 100% | 2022-01-10 | 2022-04-05 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG4 | 05120 | 0 | 0 | 0 | 05120 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Structural Steel - OG-4 | 100 | 0 | 100% | 2020-11-05 | 2021-06-09 17:00 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG4 | 05130 | 0 | 0 | 0 | 05130 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Structural Steel - OG-4 | 10 | 0 | 100% | 2021-06-10 08:00 | 2021-06-18 17:00 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG4 | 05140 | 0 | 0 | 0 | 05140 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Structural Steel - OG-4 | 50 | 0 | 100% | 2022-01-10 | 2022-04-06 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG8 | 05150 | 0 | 0 | 0 | 05150 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Structural Steel - OG-8 (RFI #130) | 100 | 0 | 100% | 2020-11-12 | 2021-01-27 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG8 | 05160 | 0 | 0 | 0 | 05160 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Structural Steel - OG-8 (RFI 130) | 10 | 0 | 100% | 2021-01-28 | 2021-05-13 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG8 | 05170 | 0 | 0 | 0 | 05170 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Structural Steel - OG-8 | 50 | 0 | 100% | 2021-05-14 | 2021-06-02 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG9 | 05180 | 0 | 0 | 0 | 05180 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Structural Steel - OG-9 (RFI #127) | 100 | 0 | 100% | 2020-11-12 | 2021-05-18 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG9 | 05190 | 0 | 0 | 0 | 05190 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Structural Steel - OG-9 | 10 | 0 | 100% | 2021-05-19 | 2021-06-16 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG9 | 05200 | 0 | 0 | 0 | 05200 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Structural Steel - OG-9 | 30 | 0 | 100% | 2021-09-01 | 2021-10-01 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG1 | 05210 | 0 | 0 | 0 | 05210 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Structural Steel - OG -1 | 100 | 0 | 100% | 2020-11-05 | 2021-06-09 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05220 | 0 | 0 | 0 | 05220 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Structural Steel - OG -1 | 10 | 0 | 100% | 2021-06-10 | 2021-06-18 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05230 | 0 | 0 | 0 | 05230 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Structural Steel - OG -1 | 50 | 0 | 100% | 2022-01-10 | 2022-04-07 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG5 | 05240 | 0 | 0 | 0 | 05240 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Structural Steel - OG-5 | 100 | 0 | 100% | 2020-11-05 | 2021-06-09 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG5 | 05250 | 0 | 0 | 0 | 05250 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Structural Steel - OG-5 | 10 | 0 | 100% | 2021-06-10 | 2021-06-18 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG5 | 05260 | 0 | 0 | 0 | 05260 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Structural Steel - OG-5 | 50 | 0 | 100% | 2022-01-10 | 2022-04-08 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG6 | 05270 | 0 | 0 | 0 | 05270 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Structural Steel - OG-6 | 100 | 0 | 100% | 2020-11-05 | 2022-06-14 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG6 | 05280 | 0 | 0 | 0 | 05280 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Structural Steel - OG-6 | 10 | 0 | 100% | 2022-06-15 | 2022-08-30 |  | 0 | 0 | ENG | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG6 | 05290 | 0 | 0 | 0 | 05290 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Structural Steel - OG-6 | 20 | 0 | 100% | 2022-08-31 | 2022-09-12 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG10 | 05300 | 0 | 0 | 0 | 05300 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Structural Steel - OG-10 (RFI #131, 167 & 335) | 100 | 0 | 100% | 2020-11-12 | 2021-09-14 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG10 | 05310 | 0 | 0 | 0 | 05310 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Structural Steel - OG-10 | 10 | 0 | 100% | 2021-09-15 | 2021-09-15 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.div. 5 | OG10 | 05320 | 0 | 0 | 0 | 05320 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Structural Steel - OG-10 | 40 | 0 | 100% | 2021-09-16 08:00 | 2021-10-23 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.div. 5 | SG4 | 05330 | 0 | 0 | 0 | 05330 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Structural Steel - SG-4 | 100 | 0 | 100% | 2020-11-05 | 2021-10-18 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.div. 5 | SG4 | 05340 | 0 | 0 | 0 | 05340 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Structural Steel - SG-4 | 10 | 0 | 100% | 2021-10-19 | 2021-10-26 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.div. 5 | SG4 | 05350 | 0 | 0 | 0 | 05350 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Structural Steel - SG-4 | 20 | 0 | 100% | 2021-10-10 | 2021-10-18 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.div. 5 | SG5 | 05360 | 0 | 0 | 0 | 05360 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Structural Steel - SG-5 | 100 | 0 | 100% | 2020-11-05 | 2021-11-09 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.div. 5 | SG5 | 05370 | 0 | 0 | 0 | 05370 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Structural Steel - SG-5 | 10 | 0 | 100% | 2021-11-10 08:00 | 2021-11-10 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.div. 5 | SG5 | 05380 | 0 | 0 | 0 | 05380 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Structural Steel - SG-5 | 50 | 0 | 100% | 2021-11-11 08:00 | 2021-12-16 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.div. 5 | SG6 | 05390 | 0 | 0 | 0 | 05390 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Structural Steel - SG-6 | 100 | 0 | 100% | 2020-11-03 | 2021-01-13 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.div. 5 | SG6 | 05400 | 0 | 0 | 0 | 05400 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Structural Steel - SG-6 (Clash with Breaching Stack) | 10 | 0 | 100% | 2021-01-14 | 2021-04-13 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.div. 5 | SG6 | 05410 | 0 | 0 | 0 | 05410 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Structural Steel - SG-6 | 50 | 0 | 100% | 2021-04-14 | 2021-05-31 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.div. 5 | SG1 | 05420 | 0 | 0 | 0 | 05420 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Structural Steel - SG-1 - N/A | 100 | 0 | 100% | 2020-11-05 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.div. 5 | SG1 | 05430 | 0 | 0 | 0 | 05430 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Structural Steel - SG-1 - N/A | 10 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.div. 5 | SG1 | 05440 | 0 | 0 | 0 | 05440 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Structural Steel - SG-1 - N/A | 50 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.div. 5 | SG2 | 05450 | 0 | 0 | 0 | 05450 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Structural Steel - SG-2 - N/A | 100 | 0 | 100% | 2020-11-05 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.div. 5 | SG2 | 05460 | 0 | 0 | 0 | 05460 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Structural Steel - SG-2 - N/A | 10 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.div. 5 | SG2 | 05470 | 0 | 0 | 0 | 05470 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Structural Steel - SG-2 - N/A | 50 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.div. 5 | SG3 | 05510 | 0 | 0 | 0 | 05510 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Structural Steel - SG-3 | 100 | 0 | 100% | 2020-11-05 | 2022-06-14 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.div. 5 | SG3 | 05520 | 0 | 0 | 0 | 05520 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Structural Steel - SG-3 | 10 | 0 | 100% | 2022-06-15 | 2022-09-01 |  | 0 | 0 | ENG | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.div. 5 | SG3 | 05530 | 0 | 0 | 0 | 05530 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Structural Steel - SG-3 | 50 | 0 | 100% | 2022-09-02 | 2022-09-12 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.div. 5 | SG7 | 05540 | 0 | 0 | 0 | 05540 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Structural Steel - SG-7 | 100 | 0 | 100% | 2020-11-05 | 2021-09-09 17:00 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.div. 5 | SG7 | 05550 | 0 | 0 | 0 | 05550 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Structural Steel - SG-7 | 10 | 0 | 100% | 2021-09-10 08:00 | 2021-11-16 17:00 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.div. 5 | SG7 | 05560 | 0 | 0 | 0 | 05560 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Structural Steel - SG-7 | 50 | 0 | 100% | 2021-09-26 | 2021-10-18 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05570 | 0 | 0 | 0 | 05570 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Metal Deck | 100 | 0 | 100% | 2020-10-07 | 2021-05-05 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05580 | 0 | 0 | 0 | 05580 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Metal Deck | 10 | 0 | 100% | 2021-06-22 | 2021-07-06 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05590 | 0 | 0 | 0 | 05590 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Metal Deck | 30 | 0 | 100% | 2021-07-26 08:00 | 2021-08-12 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05600 | 0 | 0 | 0 | 05600 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Metal Fabrications - N/A | 100 | 0 | 100% | 2020-10-05 | 2021-07-24 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05610 | 0 | 0 | 0 | 05610 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Metal Fabrications - N/A | 10 | 0 | 100% | 2021-07-24 | 2021-07-24 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05620 | 0 | 0 | 0 | 05620 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Metal Fabrications - N/A | 30 | 0 | 100% | 2021-07-24 | 2021-07-24 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05630 | 0 | 0 | 0 | 05630 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Metal Stairs | 100 | 0 | 100% | 2020-11-02 | 2021-06-14 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05640 | 0 | 0 | 0 | 05640 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Metal Stairs | 10 | 0 | 100% | 2021-06-15 | 2021-09-01 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05650 | 0 | 0 | 0 | 05650 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Metal Stairs | 40 | 0 | 100% | 2021-10-01 08:00 | 2021-10-17 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05660 | 0 | 0 | 0 | 05660 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Metal Railings | 100 | 0 | 100% | 2021-01-04 | 2021-05-07 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05670 | 0 | 0 | 0 | 05670 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Metal Railings | 10 | 0 | 100% | 2021-05-08 | 2021-05-24 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05680 | 0 | 0 | 0 | 05680 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Metal Railings | 50 | 0 | 100% | 2022-01-03 | 2022-02-28 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05690 | 0 | 0 | 0 | 05690 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Pipe and Tube Railings | 100 | 0 | 100% | 2021-01-04 | 2021-05-07 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05700 | 0 | 0 | 0 | 05700 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Pipe and Tube Railings | 10 | 0 | 100% | 2021-05-08 | 2021-05-21 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05710 | 0 | 0 | 0 | 05710 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Pipe and Tube Railings | 50 | 0 | 100% | 2022-01-03 | 2022-02-28 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05720 | 0 | 0 | 0 | 05720 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Metal Castings (RFI #165) | 100 | 0 | 100% | 2020-11-02 | 2021-07-14 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05730 | 0 | 0 | 0 | 05730 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Metal Castings | 10 | 0 | 100% | 2021-07-15 | 2021-08-10 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05740 | 0 | 0 | 0 | 05740 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Metal Castings | 50 | 0 | 100% | 2021-07-26 08:00 | 2022-02-28 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05750 | 0 | 0 | 0 | 05750 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare & Submit Decorative Metal Railings - N/A | 100 | 0 | 100% | 2021-01-04 | 2021-04-25 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05760 | 0 | 0 | 0 | 05760 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Decorative Metal Railings - N/A | 10 | 0 | 100% | 2021-04-25 | 2021-04-25 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05770 | 0 | 0 | 0 | 05770 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Fab/Del. Decorative Metal Railings - N/A | 50 | 0 | 100% | 2021-04-25 | 2021-04-25 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07000 | 0 | 0 | 0 | 07000 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Prepare & Submit Foundation Waterproofing | 80 | 0 | 100% | 2020-10-05 | 2020-12-31 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07010 | 0 | 0 | 0 | 07010 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Review & Approve Foundation Waterproofing | 10 | 0 | 100% | 2021-01-01 | 2021-05-04 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07020 | 0 | 0 | 0 | 07020 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Fab/Del. Foundation Waterproofing - N/A | 10 | 0 | 100% | 2021-03-01 | 2021-03-01 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07030 | 0 | 0 | 0 | 07030 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Prepare & Submit Crystalline Waterproofing | 80 | 0 | 100% | 2020-12-01 | 2020-12-07 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07040 | 0 | 0 | 0 | 07040 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Review & Approve Crystalline Waterproofing | 10 | 0 | 100% | 2020-12-07 | 2021-01-12 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07050 | 0 | 0 | 0 | 07050 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Fab/Del. Crystalline Waterproofing | 20 | 0 | 100% | 2022-01-26 | 2022-02-15 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07060 | 0 | 0 | 0 | 07060 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Prepare & Submit Thermal Insulation | 80 | 0 | 100% | 2020-09-06 | 2020-10-06 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07070 | 0 | 0 | 0 | 07070 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Review & Approve Thermal Insulation | 10 | 0 | 100% | 2020-10-07 | 2020-10-30 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07080 | 0 | 0 | 0 | 07080 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Fab/Del. Thermal Insulation | 10 | 0 | 100% | 2022-02-28 | 2022-03-07 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07090 | 0 | 0 | 0 | 07090 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Prepare & Submit Spray Applied Insulation | 100 | 0 | 100% | 2021-01-04 | 2022-09-16 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07100 | 0 | 0 | 0 | 07100 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Review & Approve Spray Applied Insulation | 10 | 0 | 100% | 2022-09-17 | 2022-10-07 17:00 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07110 | 0 | 0 | 0 | 07110 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Fab/Del. Spray Applied Insulation | 10 | 0 | 100% | 2022-10-10 08:00 | 2022-10-14 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07120 | 0 | 0 | 0 | 07120 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Prepare & Submit Fluid Applied Membrane Air Barriers | 100 | 0 | 100% | 2021-01-04 | 2022-02-24 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07130 | 0 | 0 | 0 | 07130 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Review & Approve Fluid Applied Membrane Air Barriers | 10 | 0 | 100% | 2022-02-25 | 2022-07-07 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07140 | 0 | 0 | 0 | 07140 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Fab/Del. Fluid Applied Membrane Air Barriers | 10 | 0 | 100% | 2022-09-08 | 2022-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07150 | 0 | 0 | 0 | 07150 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Prepare & Submit Insulated Metal Wall Panels | 180 | 0 | 100% | 2020-08-31 | 2021-06-15 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07160 | 0 | 0 | 0 | 07160 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Review & Approve Insulated Metal Wall Panels | 10 | 0 | 100% | 2021-06-16 | 2021-09-13 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07170 | 0 | 0 | 0 | 07170 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Fab/Del. Insulated Metal Wall Panels | 50 | 0 | 100% | 2022-02-15 | 2022-05-13 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07180 | 0 | 0 | 0 | 07180 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Prepare & Submit SBS Modified Bituminous Membrane Roofing | 150 | 0 | 100% | 2020-11-30 | 2020-12-30 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07190 | 0 | 0 | 0 | 07190 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Review & Approve SBS Modified Bituminous Membrane Roofing | 10 | 0 | 100% | 2020-12-30 | 2021-03-01 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07200 | 0 | 0 | 0 | 07200 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Fab/Del. SBS Modified Bituminous Membrane Roofing | 20 | 0 | 100% | 2022-06-27 08:00 | 2022-07-07 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07210 | 0 | 0 | 0 | 07210 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Prepare & Submit Sheet Metal Flashing and Trim | 150 | 0 | 100% | 2021-01-04 | 2022-09-06 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07220 | 0 | 0 | 0 | 07220 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Review & Approve Sheet Metal Flashing and Trim | 10 | 0 | 100% | 2022-09-07 | 2022-11-09 |  | 0 | 0 | ENG | 0 | 0-0
Not Started | CI NYCHA Update #22.Procurement.Div. 7 | NA | 07230 | 0 | 0 | 0 | 07230 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Fab/Del. Sheet Metal Flashing and Trim | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | 10 | TRIANGLE | 0 | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07240 | 0 | 0 | 0 | 07240 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Prepare & Submit Applied Fireproofing | 100 | 0 | 100% | 2020-11-25 | 2021-08-27 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07250 | 0 | 0 | 0 | 07250 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Review & Approve Applied Fireproofing | 10 | 0 | 100% | 2021-08-30 08:00 | 2021-10-07 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07260 | 0 | 0 | 0 | 07260 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Fab/Del. Applied Fireproofing | 20 | 0 | 100% | 2021-12-01 08:00 | 2021-12-22 17:00 |  | 0 | 0 | 0 | 0 | 0-0
In Progress | CI NYCHA Update #22.Procurement.Div. 7 | NA | 07270 | 0 | 0 | 0 | 07270 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Prepare & Submit Penetration Firestopping | 180 | 10 | 94% | 2020-11-02 | 2022-12-08 17:00 | 26 | MLJ | FIRESTOPPING | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 7 | NA | 07280 | 0 | 0 | 0 | 07280 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Review & Approve Penetration Firestopping | 10 | 10 | 0% | 2022-12-09 08:00 | 2022-12-22 17:00 | 26 | MLJ | FIRESTOPPING | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 7 | NA | 07290 | 0 | 0 | 0 | 07290 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Fab/Del. Penetration Firestopping | 20 | 20 | 0% | 2022-12-23 08:00 | 2023-01-24 17:00 | 26 | MLJ | FIRESTOPPING | PROCUREMENT | 07-5000 | 07-5000-NA
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07300 | 0 | 0 | 0 | 07300 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Prepare & Submit Joint Sealants | 180 | 0 | 100% | 2020-11-02 | 2021-05-13 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07310 | 0 | 0 | 0 | 07310 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Review & Approve Joint Sealants | 10 | 0 | 100% | 2021-05-14 | 2021-05-21 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07320 | 0 | 0 | 0 | 07320 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Fab/Del. Joint Sealants | 20 | 0 | 100% | 2022-08-01 08:00 | 2022-08-05 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08000 | 0 | 0 | 0 | 08000 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Prepare & Submit Hollow Metal Doors and Frames | 120 | 0 | 100% | 2020-07-13 | 2020-10-22 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08010 | 0 | 0 | 0 | 08010 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Review & Approve Hollow Metal Doors and Frames | 10 | 0 | 100% | 2020-10-22 | 2020-12-03 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08020 | 0 | 0 | 0 | 08020 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Fab/Del. Hollow Metal Doors and Frames | 50 | 0 | 100% | 2021-11-01 08:00 | 2022-02-04 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08030 | 0 | 0 | 0 | 08030 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Prepare & Submit Access Doors and Frames | 120 | 0 | 100% | 2020-12-01 | 2021-02-10 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08040 | 0 | 0 | 0 | 08040 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Review & Approve Access Doors and Frames | 10 | 0 | 100% | 2021-02-11 | 2021-12-03 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08050 | 0 | 0 | 0 | 08050 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Fab/Del. Access Doors and Frames | 50 | 0 | 100% | 2022-02-01 08:00 | 2022-04-05 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08060 | 0 | 0 | 0 | 08060 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Prepare & Submit Sectional Overhead Doors | 180 | 0 | 100% | 2020-10-05 | 2021-11-29 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08070 | 0 | 0 | 0 | 08070 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Review & Approve Sectional Overhead Doors | 10 | 0 | 100% | 2021-11-30 08:00 | 2021-12-17 17:00 |  | 0 | 0 | 0 | 0 | 0-0
In Progress | CI NYCHA Update #22.Procurement.Div. 8 | NA | 08080 | 0 | 0 | 0 | 08080 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Fab/Del. Sectional Overhead Doors | 50 | 30 | 40% | 2021-12-20 08:00 | 2023-01-09 17:00 | -25 | LOADING DOCK | 0 | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08090 | 0 | 0 | 0 | 08090 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Prepare & Submit Flood Doors and Panels | 80 | 0 | 100% | 2020-12-01 | 2021-10-22 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08100 | 0 | 0 | 0 | 08100 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Review & Approve Flood Doors and Panels | 10 | 0 | 100% | 2021-10-23 | 2021-10-26 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08110 | 0 | 0 | 0 | 08110 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Fab/Del. Flood Doors and Panels | 50 | 0 | 100% | 2021-10-27 08:00 | 2022-06-30 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08120 | 0 | 0 | 0 | 08120 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Prepare & Submit Aluminum Windows - N/A | 60 | 0 | 100% | 2021-01-04 | 2022-07-25 17:00 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08130 | 0 | 0 | 0 | 08130 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Review & Approve Aluminum Windows - N/A | 10 | 0 | 100% | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08140 | 0 | 0 | 0 | 08140 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Fab/Del. Aluminum Windows - N/A | 40 | 0 | 100% | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08150 | 0 | 0 | 0 | 08150 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Prepare & Submit Finish Hardware | 80 | 0 | 100% | 2020-07-13 | 2020-10-20 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08160 | 0 | 0 | 0 | 08160 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Review & Approve Finish Hardware | 10 | 0 | 100% | 2020-10-20 | 2020-12-03 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08170 | 0 | 0 | 0 | 08170 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Fab/Del. Finish Hardware | 50 | 0 | 100% | 2021-11-01 08:00 | 2022-10-17 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08180 | 0 | 0 | 0 | 08180 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Prepare & Submit Glazing - N/A | 60 | 0 | 100% | 2021-01-04 | 2022-07-25 17:00 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08190 | 0 | 0 | 0 | 08190 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Review & Approve Glazing - N/A | 10 | 0 | 100% | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08200 | 0 | 0 | 0 | 08200 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Fab/Del. Glazing - N/A | 40 | 0 | 100% | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08210 | 0 | 0 | 0 | 08210 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Prepare & Submit Fixed Louvers | 180 | 0 | 100% | 2020-11-02 | 2022-04-01 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08220 | 0 | 0 | 0 | 08220 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Review & Approve Fixed Louvers | 10 | 0 | 100% | 2022-04-02 | 2022-06-08 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 8 | 0 | 08230 | 0 | 0 | 0 | 08230 | Procurement | Div. 8 - Openings | Procurement.Div. 8 | Fab/Del. Fixed Louvers | 40 | 0 | 100% | 2022-06-09 | 2022-11-24 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09000 | 0 | 0 | 0 | 09000 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Prepare & Submit Non Structural Metal Framing | 100 | 0 | 100% | 2021-01-04 | 2022-03-18 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09010 | 0 | 0 | 0 | 09010 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Review & Approve Non Structural Metal Framing | 10 | 0 | 100% | 2022-03-19 | 2022-04-11 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09020 | 0 | 0 | 0 | 09020 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Fab/Del. Non Structural Metal Framing | 30 | 0 | 100% | 2022-04-12 | 2022-05-12 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09030 | 0 | 0 | 0 | 09030 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Prepare & Submit Cement Plastering | 80 | 0 | 100% | 2021-01-04 | 2022-08-11 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09040 | 0 | 0 | 0 | 09040 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Review & Approve Cement Plastering | 10 | 0 | 100% | 2022-08-12 | 2022-08-12 17:00 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09050 | 0 | 0 | 0 | 09050 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Fab/Del. Cement Plastering | 10 | 0 | 100% | 2022-08-13 08:00 | 2022-08-19 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09060 | 0 | 0 | 0 | 09060 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Prepare & Submit Gypsum Board | 80 | 0 | 100% | 2021-01-04 | 2022-04-01 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09070 | 0 | 0 | 0 | 09070 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Review & Approve Gypsum Board | 10 | 0 | 100% | 2022-04-02 | 2022-04-14 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09080 | 0 | 0 | 0 | 09080 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Fab/Del. Gypsum Board | 10 | 0 | 100% | 2022-06-01 | 2022-06-16 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09090 | 0 | 0 | 0 | 09090 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Prepare & Submit Tiling | 80 | 0 | 100% | 2022-07-25 08:00 | 2022-08-19 17:00 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09100 | 0 | 0 | 0 | 09100 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Review & Approve Tiling | 10 | 0 | 100% | 2022-08-22 08:00 | 2022-09-13 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09110 | 0 | 0 | 0 | 09110 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Fab/Del. Tiling | 10 | 0 | 100% | 2022-11-01 | 2022-11-17 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09120 | 0 | 0 | 0 | 09120 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Prepare & Submit Acoustical Panel Ceilings | 80 | 0 | 100% | 2021-08-25 08:00 | 2022-07-07 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09130 | 0 | 0 | 0 | 09130 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Review & Approve Acoustical Panel Ceilings | 10 | 0 | 100% | 2022-07-08 | 2022-07-19 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09140 | 0 | 0 | 0 | 09140 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Fab/Del. Acoustical Panel Ceilings | 10 | 0 | 100% | 2022-11-01 | 2022-11-07 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09150 | 0 | 0 | 0 | 09150 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Prepare & Submit Resilient Flooring | 80 | 0 | 100% | 2022-04-25 08:00 | 2022-05-12 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09160 | 0 | 0 | 0 | 09160 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Review & Approve Resilient Flooring | 10 | 0 | 100% | 2022-05-13 | 2022-07-20 |  | 0 | 0 | ENG | 0 | 0-0
Not Started | CI NYCHA Update #22.Procurement.Div. 9 | NA | 09170 | 0 | 0 | 0 | 09170 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Fab/Del. Resilient Flooring | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | 85 | FLOORING | 0 | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09180 | 0 | 0 | 0 | 09180 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Prepare & Submit Paint | 60 | 0 | 100% | 2020-10-01 | 2020-11-13 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09190 | 0 | 0 | 0 | 09190 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Review & Approve Paint | 10 | 0 | 100% | 2020-11-13 | 2021-09-03 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09200 | 0 | 0 | 0 | 09200 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Fab/Del. Paint | 10 | 0 | 100% | 2021-05-25 | 2022-04-29 |  | 0 | 0 | 0 | 0 | 0-0
In Progress | CI NYCHA Update #22.Procurement.Div. 9 | NA | 09210 | 0 | 0 | 0 | 09210 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Prepare & Submit Penetrating Concrete Sealer | 60 | 1 | 98% | 2021-01-04 | 2022-11-25 17:00 | 106 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 9 | NA | 09220 | 0 | 0 | 0 | 09220 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Review & Approve Penetrating Concrete Sealer | 10 | 10 | 0% | 2022-11-28 08:00 | 2022-12-09 17:00 | 106 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 9 | NA | 09230 | 0 | 0 | 0 | 09230 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Fab/Del. Penetrating Concrete Sealer | 10 | 10 | 0% | 2022-12-12 08:00 | 2022-12-23 17:00 | 106 | MLJ | PROCUREMENT | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div. 10 | 0 | 10000 | 0 | 0 | 0 | 10000 | Procurement | Div. 10 - Specialties | Procurement.Div. 10 | Prepare & Submit Toilet Accessories | 80 | 0 | 100% | 2022-03-07 08:00 | 2022-05-12 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 10 | 0 | 10010 | 0 | 0 | 0 | 10010 | Procurement | Div. 10 - Specialties | Procurement.Div. 10 | Review & Approve Toilet Accessories | 10 | 0 | 100% | 2022-05-13 | 2022-06-14 |  | 0 | 0 | ENG | 0 | 0-0
Not Started | CI NYCHA Update #22.Procurement.Div. 10 | NA | 10020 | 0 | 0 | 0 | 10020 | Procurement | Div. 10 - Specialties | Procurement.Div. 10 | Fab/Del. Toilet Accessories | 30 | 30 | 0% | 2022-11-25 08:00 | 2023-01-09 17:00 | 40 | MLJ | PROCUREMENT | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div. 10 | 0 | 10030 | 0 | 0 | 0 | 10030 | Procurement | Div. 10 - Specialties | Procurement.Div. 10 | Prepare & Submit Flood Control System - Aquafence/Floodbreak | 80 | 0 | 100% | 2020-11-11 | 2021-03-04 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 10 | 0 | 10040 | 0 | 0 | 0 | 10040 | Procurement | Div. 10 - Specialties | Procurement.Div. 10 | Review & Approve Flood Control System - Aquafence/Floodbreak | 10 | 0 | 100% | 2021-03-05 | 2021-03-08 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 10 | 0 | 10090 | 0 | 0 | 0 | 10090 | Procurement | Div. 10 - Specialties | Procurement.Div. 10 | Fab/Del. Flood Control System - Aquafence/Floodbreak | 80 | 0 | 100% | 2021-09-06 | 2022-09-01 |  | 0 | 0 | AQUAFENCE | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 11 | 0 | 11000 | 0 | 0 | 0 | 11000 | Procurement | Div. 11 - Equipment | Procurement.Div. 11 | Prepare & Submit Play Equipment | 180 | 0 | 100% | 2021-07-26 08:00 | 2021-08-06 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 11 | 0 | 11010 | 0 | 0 | 0 | 11010 | Procurement | Div. 11 - Equipment | Procurement.Div. 11 | Review & Approve Play Equipment | 10 | 0 | 100% | 2021-08-09 08:00 | 2021-12-17 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 11 | 0 | 11020 | 0 | 0 | 0 | 11020 | Procurement | Div. 11 - Equipment | Procurement.Div. 11 | Fab/Del. Play Equipment | 30 | 0 | 100% | 2022-06-01 | 2022-09-23 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 11 | 0 | 11030 | 0 | 0 | 0 | 11030 | Procurement | Div. 11 - Equipment | Procurement.Div. 11 | Prepare & Submit Spray Shower Equipment | 180 | 0 | 100% | 2021-07-26 08:00 | 2021-08-18 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 11 | 0 | 11040 | 0 | 0 | 0 | 11040 | Procurement | Div. 11 - Equipment | Procurement.Div. 11 | Review & Approve Spray Shower Equipment | 10 | 0 | 100% | 2021-08-19 08:00 | 2021-11-08 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 11 | 0 | 11050 | 0 | 0 | 0 | 11050 | Procurement | Div. 11 - Equipment | Procurement.Div. 11 | Fab/Del. Spray Shower Equipment | 30 | 0 | 100% | 2022-06-01 | 2022-09-01 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 14 | 0 | 14000 | 0 | 0 | 0 | 14000 | Procurement | Div. 14 - Conveying Equipment | Procurement.Div. 14 | Prepare & Submit Limited Elevator Upgrades (RFI 161, 162, 163, 164) | 120 | 0 | 100% | 2020-12-07 | 2021-06-18 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 14 | 0 | 14010 | 0 | 0 | 0 | 14010 | Procurement | Div. 14 - Conveying Equipment | Procurement.Div. 14 | Review & Approve Limited Elevator Upgrades (Omitted PCOCO 69) | 10 | 0 | 100% | 2021-06-21 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 14 | 0 | 14020 | 0 | 0 | 0 | 14020 | Procurement | Div. 14 - Conveying Equipment | Procurement.Div. 14 | Fab/Del. Limited Elevator Upgrade Materials (Omitted PCOCO 69) | 80 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | S82 | 22000 | 0 | 0 | 0 | 22000 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Plumbing Layout - S8-1 - Addition | 27 | 0 | 100% | 2021-11-15 08:00 | 2021-11-24 17:00 |  | 0 | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Procurement.Div. 22 | S82 | 22010 | 0 | 0 | 0 | 22010 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Plumbing Layout - S8-1 - Addition | 10 | 0 | 100% | 2021-11-25 08:00 | 2021-12-14 17:00 |  | 0 | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Procurement.Div. 22 | S81 | 22020 | 0 | 0 | 0 | 22020 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Plumbing Layout - S8 Existing | 27 | 0 | 100% | 2021-11-15 08:00 | 2021-11-25 |  | 0 | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Procurement.Div. 22 | S81 | 22030 | 0 | 0 | 0 | 22030 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Plumbing Layout - S8 Existing | 10 | 0 | 100% | 2021-11-26 | 2021-12-13 |  | 0 | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Procurement.Div. 22 | OG2 | 22040 | 0 | 0 | 0 | 22040 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Plumbing Layout - OG-2 | 27 | 0 | 100% | 2021-07-02 | 2021-07-16 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.Div. 22 | OG2 | 22050 | 0 | 0 | 0 | 22050 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Plumbing Layout - OG-2 | 10 | 0 | 100% | 2021-07-19 08:00 | 2021-08-16 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.Div. 22 | OG3 | 22060 | 0 | 0 | 0 | 22060 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Plumbing Layout - OG-3 | 27 | 0 | 100% | 2021-07-02 | 2021-07-16 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.Div. 22 | OG3 | 22070 | 0 | 0 | 0 | 22070 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Plumbing Layout - OG-3 | 10 | 0 | 100% | 2021-07-19 08:00 | 2021-08-16 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.Div. 22 | OG4 | 22080 | 0 | 0 | 0 | 22080 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Plumbing Layout - OG-4 | 27 | 0 | 100% | 2021-05-17 | 2021-08-18 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.Div. 22 | OG4 | 22090 | 0 | 0 | 0 | 22090 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Plumbing Layout - OG-4 | 10 | 0 | 100% | 2021-08-19 | 2021-09-04 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.Div. 22 | OG8 | 22100 | 0 | 0 | 0 | 22100 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Plumbing Layout - OG-8 | 27 | 0 | 100% | 2021-01-20 | 2021-08-26 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.Div. 22 | OG8 | 22110 | 0 | 0 | 0 | 22110 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Plumbing Layout - OG-8 | 10 | 0 | 100% | 2021-08-27 08:00 | 2021-10-08 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.Div. 22 | OG9 | 22120 | 0 | 0 | 0 | 22120 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Plumbing Layout - OG-9 | 27 | 0 | 100% | 2021-06-17 | 2021-08-26 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.Div. 22 | OG9 | 22130 | 0 | 0 | 0 | 22130 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Plumbing Layout - OG-9 | 10 | 0 | 100% | 2021-08-27 08:00 | 2021-10-08 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22140 | OG1 | 0 | 0 | 22140 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Plumbing Layout - OG -1 | 27 | 0 | 100% | 2021-07-02 | 2021-07-16 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22150 | 0 | 0 | 0 | 22150 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Plumbing Layout - OG -1 | 10 | 0 | 100% | 2021-07-19 08:00 | 2021-08-16 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | OG5 | 22160 | 0 | 0 | 0 | 22160 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Plumbing Layout - OG-5 | 27 | 0 | 100% | 2021-05-17 | 2021-06-16 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.Div. 22 | OG5 | 22170 | 0 | 0 | 0 | 22170 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Plumbing Layout - OG-5 | 10 | 0 | 100% | 2021-06-17 | 2021-07-26 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.Div. 22 | OG6 | 22180 | 0 | 0 | 0 | 22180 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Plumbing Layout - OG-6 | 27 | 0 | 100% | 2021-05-27 | 2021-06-16 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.Div. 22 | OG6 | 22190 | 0 | 0 | 0 | 22190 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Plumbing Layout - OG-6 | 10 | 0 | 100% | 2021-06-17 | 2021-07-26 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.Div. 22 | OG10 | 22200 | 0 | 0 | 0 | 22200 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Plumbing Layout - OG-10 | 27 | 0 | 100% | 2021-06-17 | 2021-09-01 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.Div. 22 | OG10 | 22210 | 0 | 0 | 0 | 22210 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Plumbing Layout - OG-10 | 10 | 0 | 100% | 2021-09-02 | 2021-10-08 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.Div. 22 | SG4 | 22220 | 0 | 0 | 0 | 22220 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Plumbing Layout - SG-4 | 27 | 0 | 100% | 2021-04-15 | 2021-05-03 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.Div. 22 | SG4 | 22230 | 0 | 0 | 0 | 22230 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Plumbing Layout - SG-4 | 10 | 0 | 100% | 2021-05-04 | 2021-05-19 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.Div. 22 | SG5 | 22240 | 0 | 0 | 0 | 22240 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Plumbing Layout - SG-5 | 27 | 0 | 100% | 2021-04-20 | 2021-07-16 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.Div. 22 | SG5 | 22250 | 0 | 0 | 0 | 22250 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Plumbing Layout - SG-5 | 10 | 0 | 100% | 2021-07-19 | 2021-08-16 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.Div. 22 | SG6 | 22260 | 0 | 0 | 0 | 22260 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Plumbing Layout - SG-6 | 27 | 0 | 100% | 2020-12-21 | 2021-05-07 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.Div. 22 | SG6 | 22270 | 0 | 0 | 0 | 22270 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Plumbing Layout - SG-6 | 10 | 0 | 100% | 2021-05-08 | 2021-05-19 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.Div. 22 | SG1 | 22280 | 0 | 0 | 0 | 22280 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Plumbing Layout - SG-1 | 27 | 0 | 100% | 2021-07-26 08:00 | 2021-08-13 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.Div. 22 | SG1 | 22290 | 0 | 0 | 0 | 22290 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Plumbing Layout - SG-1 | 10 | 0 | 100% | 2021-08-16 08:00 | 2021-09-08 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.Div. 22 | SG2 | 22300 | 0 | 0 | 0 | 22300 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Plumbing Layout - SG-2 | 27 | 0 | 100% | 2021-07-26 08:00 | 2021-08-13 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.Div. 22 | SG2 | 22310 | 0 | 0 | 0 | 22310 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Plumbing Layout - SG-2 | 10 | 0 | 100% | 2021-08-16 08:00 | 2021-09-08 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.Div. 22 | SG3 | 22340 | 0 | 0 | 0 | 22340 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Plumbing Layout - SG-3 | 27 | 0 | 100% | 2021-07-26 08:00 | 2021-08-13 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.Div. 22 | SG3 | 22350 | 0 | 0 | 0 | 22350 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Plumbing Layout - SG-3 | 10 | 0 | 100% | 2021-08-16 08:00 | 2021-09-08 17:00 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.Div. 22 | SG7 | 22360 | 0 | 0 | 0 | 22360 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Plumbing Layout - SG-7 | 27 | 0 | 100% | 2021-09-26 | 2021-10-06 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.Div. 22 | SG7 | 22370 | 0 | 0 | 0 | 22370 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Plumbing Layout - SG-7 | 10 | 0 | 100% | 2021-10-07 | 2021-11-05 17:00 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22380 | 0 | 0 | 0 | 22380 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Sleeves and Seals for Plumbing Piping | 27 | 0 | 100% | 2020-09-08 | 2020-10-20 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22390 | 0 | 0 | 0 | 22390 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Sleeves and Seals for Plumbing Piping | 10 | 0 | 100% | 2020-10-20 | 2021-03-19 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22400 | 0 | 0 | 0 | 22400 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. Sleeves and Seals for Plumbing Piping | 5 | 0 | 100% | 2021-04-14 | 2021-05-21 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22410 | 0 | 0 | 0 | 22410 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Escutcheons for Plumbing Piping | 27 | 0 | 100% | 2020-09-08 | 2020-10-20 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22420 | 0 | 0 | 0 | 22420 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Escutcheons for Plumbing Piping | 10 | 0 | 100% | 2020-10-20 | 2020-12-22 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22430 | 0 | 0 | 0 | 22430 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. Escutcheons for Plumbing Piping | 5 | 0 | 100% | 2021-08-02 08:00 | 2021-08-06 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22440 | 0 | 0 | 0 | 22440 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit General Duty Valves | 27 | 0 | 100% | 2020-09-08 | 2020-09-24 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22450 | 0 | 0 | 0 | 22450 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve General Duty Valves | 10 | 0 | 100% | 2020-09-24 | 2020-10-14 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22460 | 0 | 0 | 0 | 22460 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. General Duty Valves | 5 | 0 | 100% | 2021-08-02 08:00 | 2021-08-06 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22470 | 0 | 0 | 0 | 22470 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Plumbing Hangers and Supports | 27 | 0 | 100% | 2020-10-22 | 2020-11-05 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22480 | 0 | 0 | 0 | 22480 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Plumbing Hangers and Supports | 10 | 0 | 100% | 2020-11-05 | 2020-11-11 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22490 | 0 | 0 | 0 | 22490 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. Plumbing Hangers and Supports | 5 | 0 | 100% | 2020-10-22 | 2021-02-08 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22500 | 0 | 0 | 0 | 22500 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Heat Tracing for Plumbing Piping | 27 | 0 | 100% | 2020-09-08 | 2020-10-27 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22510 | 0 | 0 | 0 | 22510 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Heat Tracing for Plumbing Piping | 10 | 0 | 100% | 2020-10-27 | 2020-11-03 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22520 | 0 | 0 | 0 | 22520 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. Heat Tracing for Plumbing Piping | 20 | 0 | 100% | 2022-05-27 | 2022-06-20 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22530 | 0 | 0 | 0 | 22530 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Identification for Plumbing Piping and Equipment | 27 | 0 | 100% | 2021-01-04 | 2021-06-25 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22540 | 0 | 0 | 0 | 22540 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Identification for Plumbing Piping and Equipment | 10 | 0 | 100% | 2021-06-28 08:00 | 2021-07-19 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22550 | 0 | 0 | 0 | 22550 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. Identification for Plumbing Piping and Equipment | 5 | 0 | 100% | 2022-05-27 | 2022-06-20 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22560 | 0 | 0 | 0 | 22560 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Plumbing Piping Insulation | 27 | 0 | 100% | 2021-01-04 | 2021-06-30 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22570 | 0 | 0 | 0 | 22570 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Plumbing Piping Insulation | 10 | 0 | 100% | 2021-07-01 | 2021-07-27 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22580 | 0 | 0 | 0 | 22580 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. Plumbing Piping Insulation | 20 | 0 | 100% | 2022-05-27 | 2022-06-20 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22590 | 0 | 0 | 0 | 22590 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Domestic Water Piping | 27 | 0 | 100% | 2020-09-08 | 2020-11-05 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22600 | 0 | 0 | 0 | 22600 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Domestic Water Piping | 10 | 0 | 100% | 2020-11-05 | 2020-12-17 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22610 | 0 | 0 | 0 | 22610 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. Domestic Water Piping | 10 | 0 | 100% | 2020-12-17 | 2021-08-02 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22620 | 0 | 0 | 0 | 22620 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Domestic Water Piping Specialties | 27 | 0 | 100% | 2020-09-08 | 2020-11-10 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22630 | 0 | 0 | 0 | 22630 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Domestic Water Piping Specialties | 10 | 0 | 100% | 2020-11-10 | 2020-12-03 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22640 | 0 | 0 | 0 | 22640 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. Domestic Water Piping Specialties | 10 | 0 | 100% | 2021-07-26 08:00 | 2021-08-02 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22650 | 0 | 0 | 0 | 22650 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Domestic Water Pumping System | 27 | 0 | 100% | 2020-09-08 | 2020-09-28 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22660 | 0 | 0 | 0 | 22660 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Domestic Water Pumping System | 10 | 0 | 100% | 2020-09-28 | 2020-11-05 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22670 | 0 | 0 | 0 | 22670 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. Domestic Water Pumping System | 10 | 0 | 100% | 2021-07-26 08:00 | 2021-08-02 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22680 | 0 | 0 | 0 | 22680 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Sanitary Waste Piping | 27 | 0 | 100% | 2020-09-08 | 2020-11-05 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22690 | 0 | 0 | 0 | 22690 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Sanitary Waste Piping | 10 | 0 | 100% | 2020-11-05 | 2021-02-18 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22700 | 0 | 0 | 0 | 22700 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. Sanitary Waste Piping | 10 | 0 | 100% | 2021-07-26 08:00 | 2021-08-02 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22710 | 0 | 0 | 0 | 22710 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Sanitary Waste Piping Specialties | 27 | 0 | 100% | 2020-10-04 | 2020-11-04 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22720 | 0 | 0 | 0 | 22720 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Sanitary Waste Piping Specialties | 10 | 0 | 100% | 2020-11-04 | 2021-02-18 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22730 | 0 | 0 | 0 | 22730 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. Sanitary Waste Piping Specialties | 10 | 0 | 100% | 2021-07-26 08:00 | 2021-08-02 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22740 | 0 | 0 | 0 | 22740 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Storm Drainage Piping Specialties | 27 | 0 | 100% | 2020-09-08 | 2020-11-04 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22750 | 0 | 0 | 0 | 22750 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Storm Drainage Piping Specialties | 10 | 0 | 100% | 2020-11-04 | 2020-11-19 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22760 | 0 | 0 | 0 | 22760 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. Storm Drainage Piping Specialties | 10 | 0 | 100% | 2021-07-26 08:00 | 2021-08-02 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22770 | 0 | 0 | 0 | 22770 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Ejector Pumps, Sump Pumps and Hot Water Circulation Pumps | 27 | 0 | 100% | 2020-09-08 | 2020-11-13 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22780 | 0 | 0 | 0 | 22780 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Ejector Pumps, Sump Pumps and Hot Water Circulation Pumps | 10 | 0 | 100% | 2020-11-13 | 2021-02-25 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22790 | 0 | 0 | 0 | 22790 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. Ejector Pumps, Sump Pumps and Hot Water Circulation Pumps | 30 | 0 | 100% | 2021-11-10 08:00 | 2022-01-05 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22800 | 0 | 0 | 0 | 22800 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Domestic - Steam to Water Semi-Instantaneous Heater | 27 | 0 | 100% | 2020-09-08 | 2020-11-02 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22810 | 0 | 0 | 0 | 22810 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Domestic - Steam to Water Semi-Instantaneous Heater | 10 | 0 | 100% | 2020-11-02 | 2020-11-06 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22820 | 0 | 0 | 0 | 22820 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. Domestic - Steam to Water Semi-Instantaneous Heater | 30 | 0 | 100% | 2021-11-10 08:00 | 2022-01-05 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22830 | 0 | 0 | 0 | 22830 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Gas Service and Piping | 27 | 0 | 100% | 2020-09-08 | 2020-11-05 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22840 | 0 | 0 | 0 | 22840 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Gas Service and Piping | 10 | 0 | 100% | 2020-11-05 | 2020-12-01 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22850 | 0 | 0 | 0 | 22850 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. Gas Service and Piping | 20 | 0 | 100% | 2022-02-04 | 2022-02-24 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22860 | 0 | 0 | 0 | 22860 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Plumbing Fixtures | 27 | 0 | 100% | 2020-09-08 | 2020-11-11 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22870 | 0 | 0 | 0 | 22870 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Plumbing Fixtures | 10 | 0 | 100% | 2020-11-11 | 2020-11-16 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22880 | 0 | 0 | 0 | 22880 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. Plumbing Fixtures | 20 | 0 | 100% | 2021-07-26 08:00 | 2021-08-15 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22890 | 0 | 0 | 0 | 22890 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Prepare & Submit Underground Domestic Cold and Hot Water Distribution Piping | 27 | 0 | 100% | 2020-09-08 | 2020-11-05 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22900 | 0 | 0 | 0 | 22900 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Review & Approve Underground Domestic Cold and Hot Water Distribution Piping | 10 | 0 | 100% | 2020-11-05 | 2021-08-11 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | SGN | 22910 | 0 | 0 | 0 | 22910 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. Underground Domestic Cold and Hot Water Distribution Piping - SGN | 40 | 0 | 100% | 2021-06-21 | 2021-08-05 17:00 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Procurement.Div. 23 | S81 | 23000 | 0 | 0 | 0 | 23000 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Ductwork Shop Drawings for All Levels of S8 | 30 | 0 | 100% | 2021-10-25 08:00 | 2021-11-09 17:00 |  | 0 | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Procurement.Div. 23 | S81 | 23010 | 0 | 0 | 0 | 23010 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Ductwork Shop Drawings for All Levels of S8 | 10 | 0 | 100% | 2021-11-10 08:00 | 2021-11-23 |  | 0 | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG1 | 23020 | 0 | 0 | 0 | 23020 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Ductwork Shop Drawings for All Levels of OG-1 | 30 | 0 | 100% | 2021-04-25 | 2021-05-11 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG1 | 23030 | 0 | 0 | 0 | 23030 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Ductwork Shop Drawings for All Levels of OG-1 | 10 | 0 | 100% | 2021-05-12 | 2021-05-19 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG2 | 23040 | 0 | 0 | 0 | 23040 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Ductwork Shop Drawings for All Levels of OG-2 | 30 | 0 | 100% | 2021-11-15 08:00 | 2021-11-24 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG2 | 23050 | 0 | 0 | 0 | 23050 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Ductwork Shop Drawings for All Levels of OG-2 | 10 | 0 | 100% | 2021-11-25 | 2021-12-21 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG3 | 23060 | 0 | 0 | 0 | 23060 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Ductwork Shop Drawings for All Levels of OG-3 | 30 | 0 | 100% | 2021-10-25 08:00 | 2021-11-03 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG3 | 23070 | 0 | 0 | 0 | 23070 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Ductwork Shop Drawings for All Levels of OG-3 | 10 | 0 | 100% | 2021-11-04 08:00 | 2021-11-15 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG4 | 23080 | 0 | 0 | 0 | 23080 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Ductwork Shop Drawings for All Levels of OG-4 | 30 | 0 | 100% | 2021-05-17 | 2021-11-05 17:00 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG4 | 23090 | 0 | 0 | 0 | 23090 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Ductwork Shop Drawings for All Levels of OG-4 | 10 | 0 | 100% | 2021-11-08 08:00 | 2021-11-15 17:00 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG5 | 23100 | 0 | 0 | 0 | 23100 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Ductwork Shop Drawings for All Levels of OG-5 | 30 | 0 | 100% | 2021-05-17 | 2021-11-17 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG5 | 23110 | 0 | 0 | 0 | 23110 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Ductwork Shop Drawings for All Levels of OG-5 | 10 | 0 | 100% | 2021-11-18 08:00 | 2021-12-09 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG6 | 23120 | 0 | 0 | 0 | 23120 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Ductwork Shop Drawings for All Levels of OG-6 | 30 | 0 | 100% | 2021-05-17 | 2021-11-09 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG6 | 23130 | 0 | 0 | 0 | 23130 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Ductwork Shop Drawings for All Levels of OG-6 | 10 | 0 | 100% | 2021-11-10 | 2021-12-27 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG8 | 23140 | 0 | 0 | 0 | 23140 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Ductwork Shop Drawings for All Levels of OG-8 | 30 | 0 | 100% | 2021-01-11 | 2021-10-06 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG8 | 23150 | 0 | 0 | 0 | 23150 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Ductwork Shop Drawings for All Levels of OG-8 | 10 | 0 | 100% | 2021-10-07 | 2021-10-22 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG9 | 23160 | 0 | 0 | 0 | 23160 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Ductwork Shop Drawings for All Levels of OG-9 | 30 | 0 | 100% | 2021-09-26 | 2021-10-14 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG9 | 23170 | 0 | 0 | 0 | 23170 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Ductwork Shop Drawings for All Levels of OG-9 | 10 | 0 | 100% | 2021-10-15 | 2021-10-22 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG10 | 23180 | 0 | 0 | 0 | 23180 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Ductwork Shop Drawings for All Levels of OG-10 | 30 | 0 | 100% | 2021-06-30 08:00 | 2021-07-14 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG10 | 23190 | 0 | 0 | 0 | 23190 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Ductwork Shop Drawings for All Levels of OG-10 | 10 | 0 | 100% | 2021-07-15 08:00 | 2021-07-29 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG1 | 23200 | 0 | 0 | 0 | 23200 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Ductwork Shop Drawings for All Levels of SG-1 | 30 | 0 | 100% | 2021-08-26 08:00 | 2021-09-16 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG1 | 23210 | 0 | 0 | 0 | 23210 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Ductwork Shop Drawings for All Levels of SG-1 | 10 | 0 | 100% | 2021-09-17 08:00 | 2021-10-22 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG2 | 23220 | 0 | 0 | 0 | 23220 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Ductwork Shop Drawings for All Levels of SG-2 | 30 | 0 | 100% | 2021-11-15 08:00 | 2021-11-30 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG2 | 23230 | 0 | 0 | 0 | 23230 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Ductwork Shop Drawings for All Levels of SG-2 | 10 | 0 | 100% | 2021-12-01 | 2021-12-21 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG3 | 23240 | 0 | 0 | 0 | 23240 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Ductwork Shop Drawings for All Levels of SG-3 | 30 | 0 | 100% | 2021-11-15 08:00 | 2021-11-30 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG3 | 23250 | 0 | 0 | 0 | 23250 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Ductwork Shop Drawings for All Levels of SG-3 | 10 | 0 | 100% | 2021-12-01 | 2021-12-14 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG4 | 23260 | 0 | 0 | 0 | 23260 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Ductwork Shop Drawings for All Levels of SG-4 | 30 | 0 | 100% | 2021-02-20 | 2021-03-24 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG4 | 23270 | 0 | 0 | 0 | 23270 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Ductwork Shop Drawings for All Levels of SG-4 | 10 | 0 | 100% | 2021-03-25 | 2022-07-05 |  | 0 | 0 | ENG | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG5 | 23280 | 0 | 0 | 0 | 23280 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Ductwork Shop Drawings for All Levels of SG-5 | 30 | 0 | 100% | 2021-06-07 | 2021-07-08 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG5 | 23290 | 0 | 0 | 0 | 23290 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Ductwork Shop Drawings for All Levels of SG-5 | 10 | 0 | 100% | 2021-07-09 | 2021-07-19 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG6 | 23300 | 0 | 0 | 0 | 23300 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Ductwork Shop Drawings for All Levels of SG-6 | 30 | 0 | 100% | 2020-12-21 | 2021-07-08 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG6 | 23310 | 0 | 0 | 0 | 23310 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Ductwork Shop Drawings for All Levels of SG-6 | 10 | 0 | 100% | 2021-07-09 | 2021-07-19 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG7 | 23320 | 0 | 0 | 0 | 23320 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Ductwork Shop Drawings for All Levels of SG-7 | 30 | 0 | 100% | 2021-11-15 | 2021-11-30 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG7 | 23330 | 0 | 0 | 0 | 23330 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Ductwork Shop Drawings for All Levels of SG-7 | 10 | 0 | 100% | 2021-12-01 | 2021-12-21 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.Div. 23 | S81 | 23340 | 0 | 0 | 0 | 23340 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Piping Shop Drawings for All Levels of S8 | 30 | 0 | 100% | 2022-01-10 | 2022-06-15 |  | 0 | 0 | ENG | 0 | 0-S81
Completed | CI NYCHA Update #22.Procurement.Div. 23 | S81 | 23350 | 0 | 0 | 0 | 23350 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Piping Shop Drawings for All Levels of S8 | 10 | 0 | 100% | 2022-06-16 | 2022-06-29 |  | 0 | 0 | ENG | 0 | 0-S81
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG1 | 23360 | 0 | 0 | 0 | 23360 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Piping Shop Drawings for All Levels of OG-1 | 30 | 0 | 100% | 2021-03-26 | 2021-04-23 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG1 | 23370 | 0 | 0 | 0 | 23370 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Piping Shop Drawings for All Levels of OG-1 | 10 | 0 | 100% | 2021-04-23 | 2021-05-19 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG2 | 23380 | 0 | 0 | 0 | 23380 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Piping Shop Drawings for All Levels of OG-2 | 30 | 0 | 100% | 2021-06-25 08:00 | 2021-06-29 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG2 | 23390 | 0 | 0 | 0 | 23390 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Piping Shop Drawings for All Levels of OG-2 | 10 | 0 | 100% | 2021-06-30 08:00 | 2021-07-12 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG3 | 23400 | 0 | 0 | 0 | 23400 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Piping Shop Drawings for All Levels of OG-3 | 30 | 0 | 100% | 2021-09-26 | 2021-10-20 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG3 | 23410 | 0 | 0 | 0 | 23410 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Piping Shop Drawings for All Levels of OG-3 | 10 | 0 | 100% | 2021-10-21 | 2021-11-09 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG4 | 23420 | 0 | 0 | 0 | 23420 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Piping Shop Drawings for All Levels of OG-4 | 30 | 0 | 100% | 2021-05-17 | 2022-02-18 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG4 | 23430 | 0 | 0 | 0 | 23430 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Piping Shop Drawings for All Levels of OG-4 | 10 | 0 | 100% | 2022-02-19 | 2022-04-05 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG5 | 23440 | 0 | 0 | 0 | 23440 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Piping Shop Drawings for All Levels of OG-5 | 30 | 0 | 100% | 2021-05-17 | 2022-03-30 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG5 | 23450 | 0 | 0 | 0 | 23450 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Piping Shop Drawings for All Levels of OG-5 | 10 | 0 | 100% | 2022-03-31 | 2022-04-05 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG6 | 23460 | 0 | 0 | 0 | 23460 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Piping Shop Drawings for All Levels of OG-6 | 30 | 0 | 100% | 2021-05-17 | 2022-03-09 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG6 | 23470 | 0 | 0 | 0 | 23470 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Piping Shop Drawings for All Levels of OG-6 | 10 | 0 | 100% | 2022-03-10 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG8 | 23480 | 0 | 0 | 0 | 23480 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Piping Shop Drawings for All Levels of OG-8 | 30 | 0 | 100% | 2020-12-21 | 2021-11-09 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG8 | 23490 | 0 | 0 | 0 | 23490 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Piping Shop Drawings for All Levels of OG-8 | 10 | 0 | 100% | 2021-11-10 | 2021-12-09 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG9 | 23500 | 0 | 0 | 0 | 23500 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Piping Shop Drawings for All Levels of OG-9 | 30 | 0 | 100% | 2021-10-15 | 2022-01-20 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG9 | 23510 | 0 | 0 | 0 | 23510 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Piping Shop Drawings for All Levels of OG-9 | 10 | 0 | 100% | 2022-01-21 | 2022-01-21 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG10 | 23520 | 0 | 0 | 0 | 23520 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Piping Shop Drawings for All Levels of OG-10 | 30 | 0 | 100% | 2021-10-15 | 2021-11-03 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OG10 | 23530 | 0 | 0 | 0 | 23530 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Piping Shop Drawings for All Levels of OG-10 | 10 | 0 | 100% | 2021-11-04 | 2021-11-29 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG1 | 23540 | 0 | 0 | 0 | 23540 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Piping Shop Drawings for All Levels of SG-1 | 30 | 0 | 100% | 2021-05-24 | 2021-06-03 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG1 | 23550 | 0 | 0 | 0 | 23550 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Piping Shop Drawings for All Levels of SG-1 | 10 | 0 | 100% | 2021-06-04 | 2021-07-26 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG2 | 23560 | 0 | 0 | 0 | 23560 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Piping Shop Drawings for All Levels of SG-2 | 30 | 0 | 100% | 2021-09-26 | 2021-10-06 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG2 | 23570 | 0 | 0 | 0 | 23570 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Piping Shop Drawings for All Levels of SG-2 | 10 | 0 | 100% | 2021-10-07 | 2021-10-08 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG3 | 23580 | 0 | 0 | 0 | 23580 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Piping Shop Drawings for All Levels of SG-3 | 30 | 0 | 100% | 2022-04-04 | 2022-04-13 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG3 | 23590 | 0 | 0 | 0 | 23590 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Piping Shop Drawings for All Levels of SG-3 | 10 | 0 | 100% | 2022-04-21 | 2022-05-03 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG4 | 23600 | 0 | 0 | 0 | 23600 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Piping Shop Drawings for All Levels of SG-4 | 30 | 0 | 100% | 2021-01-11 | 2021-03-14 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG4 | 23610 | 0 | 0 | 0 | 23610 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Piping Shop Drawings for All Levels of SG-4 | 10 | 0 | 100% | 2021-03-15 | 2021-05-25 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG5 | 23620 | 0 | 0 | 0 | 23620 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Piping Shop Drawings for All Levels of SG-5 | 30 | 0 | 100% | 2021-05-14 | 2021-05-17 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG5 | 23630 | 0 | 0 | 0 | 23630 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Piping Shop Drawings for All Levels of SG-5 | 10 | 0 | 100% | 2021-05-18 | 2021-05-19 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG6 | 23640 | 0 | 0 | 0 | 23640 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Piping Shop Drawings for All Levels of SG-6 | 30 | 0 | 100% | 2021-01-04 | 2021-07-08 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG6 | 23650 | 0 | 0 | 0 | 23650 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Piping Shop Drawings for All Levels of SG-6 | 10 | 0 | 100% | 2021-07-09 | 2021-07-21 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG7 | 23660 | 0 | 0 | 0 | 23660 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Piping Shop Drawings for All Levels of SG-7 | 30 | 0 | 100% | 2022-03-21 | 2022-09-21 |  | 0 | 0 | ENG | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SG7 | 23670 | 0 | 0 | 0 | 23670 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Piping Shop Drawings for All Levels of SG-7 | 10 | 0 | 100% | 2022-09-22 | 2022-10-05 |  | 0 | 0 | ENG | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23680 | 0 | 0 | 0 | 23680 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Expansion Fittings and Loops for HVAC Piping | 30 | 0 | 100% | 2021-01-04 | 2021-12-30 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23690 | 0 | 0 | 0 | 23690 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Expansion Fittings and Loops for HVAC Piping | 10 | 0 | 100% | 2021-12-31 | 2022-08-02 17:00 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23700 | 0 | 0 | 0 | 23700 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Expansion Fittings and Loops for HVAC Piping | 10 | 0 | 100% | 2022-09-25 08:00 | 2022-10-05 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23710 | 0 | 0 | 0 | 23710 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Sleeves and Sleeve Seals for HVAC Piping | 30 | 0 | 100% | 2020-10-18 | 2020-11-18 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23720 | 0 | 0 | 0 | 23720 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Sleeves and Sleeve Seals for HVAC Piping | 10 | 0 | 100% | 2020-11-18 | 2020-12-04 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23730 | 0 | 0 | 0 | 23730 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Sleeves and Sleeve Seals for HVAC Piping | 10 | 0 | 100% | 2021-08-03 08:00 | 2021-08-13 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23740 | 0 | 0 | 0 | 23740 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Meters and Gages for HVAC Piping | 30 | 0 | 100% | 2020-08-03 | 2020-09-02 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23750 | 0 | 0 | 0 | 23750 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Meters and Gages for HVAC Piping | 10 | 0 | 100% | 2020-09-02 | 2020-10-06 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23760 | 0 | 0 | 0 | 23760 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Meters and Gauges for HVAC Piping | 10 | 0 | 100% | 2021-11-22 08:00 | 2021-11-26 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23770 | 0 | 0 | 0 | 23770 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit meters and gauges for HVAC piping | 30 | 0 | 100% | 2020-08-03 | 2020-09-02 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23780 | 0 | 0 | 0 | 23780 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve meters and gauges for HVAC piping | 10 | 0 | 100% | 2020-09-02 | 2020-10-06 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23790 | 0 | 0 | 0 | 23790 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. meters and gages for HVAC piping | 10 | 0 | 100% | 2021-11-22 08:00 | 2021-11-26 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23800 | 0 | 0 | 0 | 23800 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit General Duty Valves for HVAC Piping Facility Fuel Oil Piping Steam and Condensate Piping | 30 | 0 | 100% | 2020-08-03 | 2020-09-04 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23810 | 0 | 0 | 0 | 23810 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve General Duty Valves for HVAC Piping Facility Fuel Oil Piping Steam and Condensate Piping | 10 | 0 | 100% | 2020-09-04 | 2020-09-28 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23820 | 0 | 0 | 0 | 23820 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. General Duty Valves for HVAC Piping Facility Fuel Oil Piping Steam and Condensate Piping | 45 | 0 | 100% | 2021-04-25 | 2021-08-03 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23830 | 0 | 0 | 0 | 23830 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Facility Fuel Oil Piping | 30 | 0 | 100% | 2020-10-01 | 2020-10-29 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23840 | 0 | 0 | 0 | 23840 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Facility Fuel Oil Piping | 10 | 0 | 100% | 2020-10-29 | 2020-11-16 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23850 | 0 | 0 | 0 | 23850 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Facility Fuel Oil Piping | 45 | 0 | 100% | 2021-09-01 08:00 | 2022-03-04 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23860 | 0 | 0 | 0 | 23860 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Hangers and Supports for HVAC Piping and Equipment | 30 | 0 | 100% | 2020-08-03 | 2020-09-04 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23870 | 0 | 0 | 0 | 23870 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Hangers and Supports for HVAC Piping and Equipment | 10 | 0 | 100% | 2020-09-04 | 2020-10-29 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23880 | 0 | 0 | 0 | 23880 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Hangers and Supports for HVAC Piping and Equipment | 10 | 0 | 100% | 2021-04-25 | 2021-05-05 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23890 | 0 | 0 | 0 | 23890 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Seismic Restraints and Vibration Isolation | 30 | 0 | 100% | 2020-12-08 | 2022-08-01 17:00 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23900 | 0 | 0 | 0 | 23900 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Seismic Restraints and Vibration Isolation | 10 | 0 | 100% | 2022-08-02 08:00 | 2022-08-02 17:00 |  | 0 | 0 | ENG | 0 | 0-0
Not Started | CI NYCHA Update #22.Procurement.Div. 23 | NA | 23910 | 0 | 0 | 0 | 23910 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Seismic Restraints and Vibration Isolation | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | -32 | WELKIN | 0 | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23920 | 0 | 0 | 0 | 23920 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit HVAC Testing, Adjusting, Balancing Plan | 30 | 0 | 100% | 2020-08-17 | 2020-08-17 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23930 | 0 | 0 | 0 | 23930 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve HVAC Testing, Adjusting, Balancing Plan | 10 | 0 | 100% | 2020-08-17 | 2020-09-30 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23940 | 0 | 0 | 0 | 23940 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit HVAC Piping Insulation & Equipment Insulation Duct Insulation | 30 | 0 | 100% | 2020-11-25 | 2020-12-14 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23950 | 0 | 0 | 0 | 23950 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve HVAC Piping Insulation & Equipment Insulation Duct Insulation | 10 | 0 | 100% | 2020-12-14 | 2021-02-26 |  | 0 | 0 | 0 | 0 | 0-0
In Progress | CI NYCHA Update #22.Procurement.Div. 23 | NA | 23960 | 0 | 0 | 0 | 23960 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. HVAC Piping Insulation & Equipment Insulation Duct Insulation | 20 | 5 | 75% | 2022-07-22 | 2022-12-01 17:00 | -17 | WELKIN | 0 | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23970 | 0 | 0 | 0 | 23970 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Metal Ducts | 30 | 0 | 100% | 2020-12-17 | 2020-12-17 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23980 | 0 | 0 | 0 | 23980 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Metal Ducts | 10 | 0 | 100% | 2020-12-17 | 2021-01-22 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 23990 | 0 | 0 | 0 | 23990 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Metal Ducts | 20 | 0 | 100% | 2021-05-21 | 2021-05-25 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24000 | 0 | 0 | 0 | 24000 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Duplex Condensate Return Pumps | 30 | 0 | 100% | 2020-08-03 | 2020-09-01 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24010 | 0 | 0 | 0 | 24010 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Duplex Condensate Return Pumps | 10 | 0 | 100% | 2020-09-01 | 2020-11-27 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24020 | 0 | 0 | 0 | 24020 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Duplex Condensate Return Pumps | 45 | 0 | 100% | 2021-03-26 | 2022-02-02 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24030 | 0 | 0 | 0 | 24030 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit HVAC Power Ventilators | 30 | 0 | 100% | 2020-07-01 | 2020-07-01 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24040 | 0 | 0 | 0 | 24040 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve HVAC Power Ventilators | 10 | 0 | 100% | 2020-07-01 | 2021-01-21 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24050 | 0 | 0 | 0 | 24050 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. HVAC Power Ventilators | 45 | 0 | 100% | 2021-03-26 | 2022-06-01 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24060 | 0 | 0 | 0 | 24060 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Air Duct Accessories Diffusers, Registers, and Grilles | 30 | 0 | 100% | 2020-08-03 | 2020-09-21 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24070 | 0 | 0 | 0 | 24070 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Air Duct Accessories Diffusers, Registers, and Grilles | 10 | 0 | 100% | 2020-09-21 | 2020-10-01 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24080 | 0 | 0 | 0 | 24080 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Air Duct Accessories Diffusers, Registers, and Grilles | 20 | 0 | 100% | 2021-10-10 | 2022-06-01 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24090 | 0 | 0 | 0 | 24090 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Vacuum Pump Units | 30 | 0 | 100% | 2020-02-09 | 2020-10-14 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24100 | 0 | 0 | 0 | 24100 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Vacuum Pump Units | 10 | 0 | 100% | 2020-10-14 | 2020-11-30 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24110 | 0 | 0 | 0 | 24110 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Vacuum Pump Units | 40 | 0 | 100% | 2021-03-26 | 2021-08-03 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24120 | 0 | 0 | 0 | 24120 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Boiler Feedwater Pumps | 30 | 0 | 100% | 2020-08-03 | 2020-09-09 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24130 | 0 | 0 | 0 | 24130 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Boiler Feedwater Pumps | 10 | 0 | 100% | 2020-09-09 | 2020-09-29 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24140 | 0 | 0 | 0 | 24140 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Boiler Feedwater Pumps | 70 | 0 | 100% | 2021-10-10 | 2021-10-21 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24150 | 0 | 0 | 0 | 24150 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Unit Heaters | 30 | 0 | 100% | 2020-07-20 | 2020-07-20 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24160 | 0 | 0 | 0 | 24160 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Unit Heaters | 10 | 0 | 100% | 2020-07-20 | 2020-09-20 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24170 | 0 | 0 | 0 | 24170 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Unit Heaters | 25 | 0 | 100% | 2021-10-10 | 2022-06-01 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24180 | 0 | 0 | 0 | 24180 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Steam and Condensate Piping | 30 | 0 | 100% | 2020-08-03 | 2020-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24190 | 0 | 0 | 0 | 24190 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Steam and Condensate Piping | 10 | 0 | 100% | 2020-09-12 | 2020-10-14 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SGN | 24200 | 0 | 0 | 0 | 24200 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Steam and Condensate Piping - SGN | 35 | 0 | 100% | 2021-03-25 08:00 | 2021-08-03 17:00 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24210 | 0 | 0 | 0 | 24210 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Facility Fuel Oil Piping | 30 | 0 | 100% | 2020-08-03 | 2020-10-29 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24220 | 0 | 0 | 0 | 24220 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Facility Fuel Oil Piping | 10 | 0 | 100% | 2020-10-29 | 2020-11-16 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24230 | 0 | 0 | 0 | 24230 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Facility Fuel Oil Piping | 65 | 0 | 100% | 2021-07-12 08:00 | 2021-10-22 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24240 | 0 | 0 | 0 | 24240 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Water Treatment for Steam System | 30 | 0 | 100% | 2021-03-25 08:00 | 2021-09-26 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24250 | 0 | 0 | 0 | 24250 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Water Treatment for Steam System | 10 | 0 | 100% | 2021-09-27 | 2021-11-17 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24260 | 0 | 0 | 0 | 24260 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Water Treatment for Steam System | 70 | 0 | 100% | 2022-06-14 | 2022-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24270 | 0 | 0 | 0 | 24270 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Commissioning of HVAC Plan | 30 | 0 | 100% | 2022-06-15 | 2022-09-23 17:00 |  | 0 | 0 | ENG | 0 | 0-0
Not Started | CI NYCHA Update #22.Procurement.Div. 23 | NA | 24280 | 0 | 0 | 0 | 24280 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Commissioning of HVAC Plan | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | -32 | WELKIN | 0 | ENG | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24290 | 0 | 0 | 0 | 24290 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Prefabricated Breechings and Stacks | 30 | 0 | 100% | 2020-08-03 | 2020-10-13 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24300 | 0 | 0 | 0 | 24300 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Prefabricated Breechings and Stacks | 10 | 0 | 100% | 2020-10-13 | 2021-03-08 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24310 | 0 | 0 | 0 | 24310 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Prefabricated Breechings and Stacks | 30 | 0 | 100% | 2022-01-16 | 2022-02-15 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24320 | 0 | 0 | 0 | 24320 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Fire Tube Boilers | 30 | 0 | 100% | 2020-08-03 | 2020-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24330 | 0 | 0 | 0 | 24330 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Fire Tube Boilers | 10 | 0 | 100% | 2020-09-23 | 2021-01-06 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24340 | 0 | 0 | 0 | 24340 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Fire Tube Boilers | 60 | 0 | 100% | 2022-01-28 | 2022-03-03 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24350 | 0 | 0 | 0 | 24350 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit HVAC Controls | 30 | 0 | 100% | 2021-01-11 | 2021-02-11 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24360 | 0 | 0 | 0 | 24360 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve HVAC Controls | 10 | 0 | 100% | 2021-02-12 | 2021-02-18 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24370 | 0 | 0 | 0 | 24370 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. HVAC Controls | 40 | 0 | 100% | 2021-03-26 | 2022-06-16 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24380 | 0 | 0 | 0 | 24380 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit CO & Natural Gas Sensors | 30 | 0 | 100% | 2020-07-29 | 2020-07-29 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24390 | 0 | 0 | 0 | 24390 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve CO & Natural Gas Sensors | 10 | 0 | 100% | 2020-07-29 | 2021-03-05 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24400 | 0 | 0 | 0 | 24400 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. CO & Natural Gas Sensors | 30 | 0 | 100% | 2022-07-25 08:00 | 2022-08-01 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 28 | 0 | 28000 | 0 | 0 | 0 | 28000 | Procurement | Div. 28 - Electronic Safety & Security | Procurement.Div. 28 | Prepare & Submit Smoke Detection System (Duplicate with 283100-01005) | 80 | 0 | 100% | 2020-11-16 | 2020-12-24 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 28 | 0 | 28010 | 0 | 0 | 0 | 28010 | Procurement | Div. 28 - Electronic Safety & Security | Procurement.Div. 28 | Review & Approve Smoke Detection System (Duplicate with 283100-01010) | 10 | 0 | 100% | 2020-12-24 | 2020-12-24 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 28 | 0 | 28020 | 0 | 0 | 0 | 28020 | Procurement | Div. 28 - Electronic Safety & Security | Procurement.Div. 28 | Fab/Del. Smoke Detection System | 60 | 0 | 100% | 2022-03-25 08:00 | 2022-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 28 | 0 | 28030 | 0 | 0 | 0 | 28030 | Procurement | Div. 28 - Electronic Safety & Security | Procurement.Div. 28 | Prepare & Submit Carbon-Monoxide & Natural Gas Detection Sensors | 80 | 0 | 100% | 2021-02-01 | 2021-02-25 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 28 | 0 | 28040 | 0 | 0 | 0 | 28040 | Procurement | Div. 28 - Electronic Safety & Security | Procurement.Div. 28 | Review & Approve Carbon-Monoxide & Natural Gas Detection Sensors | 10 | 0 | 100% | 2021-02-26 | 2021-03-17 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 28 | 0 | 28050 | 0 | 0 | 0 | 28050 | Procurement | Div. 28 - Electronic Safety & Security | Procurement.Div. 28 | Fab/Del. Carbon-Monoxide & Natural Gas Detection Sensors | 60 | 0 | 100% | 2022-07-25 08:00 | 2022-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32000 | 0 | 0 | 0 | 32000 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare & Submit Dense Graded Stone Base | 150 | 0 | 100% | 2020-11-10 | 2020-12-10 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32010 | 0 | 0 | 0 | 32010 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Dense Graded Stone Base | 10 | 0 | 100% | 2020-12-10 | 2020-12-29 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32020 | 0 | 0 | 0 | 32020 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Del. Dense Graded Stone Base | 1 | 0 | 100% | 2021-09-26 | 2021-09-26 |  | 0 | 0 | 0 | 0 | 0-0
In Progress | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32030 | 0 | 0 | 0 | 32030 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare & Submit Concrete Base for Pavement | 150 | 20 | 86% | 2022-01-26 | 2022-12-22 17:00 | -27 | ASPHALT | 0 | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32040 | 0 | 0 | 0 | 32040 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Concrete Base for Pavement | 10 | 10 | 0% | 2022-12-23 08:00 | 2023-01-09 17:00 | -27 | ASPHALT | 0 | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32050 | 0 | 0 | 0 | 32050 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Del. Concrete Base for Pavement | 1 | 1 | 0% | 2023-01-10 08:00 | 2023-01-10 17:00 | -27 | ASPHALT | 0 | 0 | 0 | 0-NA
In Progress | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32060 | 0 | 0 | 0 | 32060 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare & Submit Asphaltic Concrete | 150 | 20 | 86% | 2022-01-26 | 2022-12-22 17:00 | 13 | ASPHALT | 0 | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32070 | 0 | 0 | 0 | 32070 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Asphaltic Concrete | 10 | 10 | 0% | 2022-12-23 08:00 | 2023-01-09 17:00 | 13 | ASPHALT | 0 | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32260 | 0 | 0 | 0 | 32260 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Del. Asphaltic Concrete | 1 | 1 | 0% | 2023-01-10 08:00 | 2023-01-10 17:00 | 13 | ASPHALT | 0 | 0 | 0 | 0-NA
In Progress | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32270 | 0 | 0 | 0 | 32270 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare & Submit Tack Coat | 150 | 20 | 86% | 2022-01-26 | 2022-12-22 17:00 | 13 | ASPHALT | 0 | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32280 | 0 | 0 | 0 | 32280 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Tack Coat | 10 | 10 | 0% | 2022-12-23 08:00 | 2023-01-09 17:00 | 13 | ASPHALT | 0 | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32290 | 0 | 0 | 0 | 32290 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Fab/Del. Tack Coat | 1 | 1 | 0% | 2023-01-10 08:00 | 2023-01-10 17:00 | 13 | MLJ | PROCUREMENT | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32300 | 0 | 0 | 0 | 32300 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare & Submit Concrete Sidewalk Plan | 150 | 0 | 100% | 2021-09-10 08:00 | 2021-09-26 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32310 | 0 | 0 | 0 | 32310 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Concrete Sidewalk Plan | 10 | 0 | 100% | 2021-09-27 | 2021-11-18 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32320 | 0 | 0 | 0 | 32320 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare & Submit Porous Concrete Pavement | 150 | 0 | 100% | 2021-09-10 08:00 | 2022-11-03 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32330 | 0 | 0 | 0 | 32330 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Porous Concrete Pavement | 10 | 0 | 100% | 2022-10-04 | 2022-10-24 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32340 | 0 | 0 | 0 | 32340 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Del. Porous Concrete Pavement | 1 | 0 | 100% | 2022-10-25 | 2022-10-25 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32350 | 0 | 0 | 0 | 32350 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare & Submit Integrally Colored Concrete | 150 | 0 | 100% | 2021-09-01 08:00 | 2021-09-24 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32360 | 0 | 0 | 0 | 32360 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Integrally Colored Concrete | 10 | 0 | 100% | 2021-09-24 | 2022-05-03 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32370 | 0 | 0 | 0 | 32370 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Del. Integrally Colored Concrete | 1 | 0 | 100% | 2022-08-29 | 2022-08-29 |  | 0 | 0 | 0 | 0 | 0-0
In Progress | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32380 | 0 | 0 | 0 | 32380 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare & Submit Expansion Joints | 150 | 10 | 93% | 2021-08-26 | 2022-12-08 17:00 | 14 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32390 | 0 | 0 | 0 | 32390 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Expansion Joints | 10 | 10 | 0% | 2022-12-09 08:00 | 2022-12-22 17:00 | 14 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32400 | 0 | 0 | 0 | 32400 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Fab/Del. Expansion Joints | 10 | 10 | 0% | 2022-12-23 08:00 | 2023-01-09 17:00 | 14 | MLJ | PROCUREMENT | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32410 | 0 | 0 | 0 | 32410 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare & Submit Concrete Curbs Plan | 150 | 0 | 100% | 2021-09-01 08:00 | 2021-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32420 | 0 | 0 | 0 | 32420 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Concrete Curbs Plan | 10 | 0 | 100% | 2021-09-24 08:00 | 2022-04-25 |  | 0 | 0 | 0 | 0 | 0-0
In Progress | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32430 | 0 | 0 | 0 | 32430 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare & Submit Steel Faced Concrete Curbs | 150 | 4 | 97% | 2021-09-26 | 2022-11-30 17:00 | -30 | JMC | 0 | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32440 | 0 | 0 | 0 | 32440 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Steel Faced Concrete Curbs | 10 | 10 | 0% | 2022-12-01 08:00 | 2022-12-14 17:00 | -30 | JMC | 0 | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32450 | 0 | 0 | 0 | 32450 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Fab/Del. Steel Faced Concrete Curbs | 20 | 20 | 0% | 2022-12-15 08:00 | 2023-01-13 17:00 | -30 | JMC | 0 | 0 | 0 | 0-NA
In Progress | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32460 | 0 | 0 | 0 | 32460 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare & Submit Pavement Markings | 150 | 10 | 93% | 2022-01-26 | 2022-12-08 17:00 | 47 | ASPHALT | 0 | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32470 | 0 | 0 | 0 | 32470 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Pavement Markings | 10 | 10 | 0% | 2022-12-09 08:00 | 2022-12-22 17:00 | 47 | ASPHALT | 0 | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32480 | 0 | 0 | 0 | 32480 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Fab/Del. Pavement Markings | 10 | 10 | 0% | 2022-12-23 08:00 | 2023-01-09 17:00 | 47 | ASPHALT | 0 | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32490 | 0 | 0 | 0 | 32490 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare & Submit Safety Surfacing | 150 | 0 | 100% | 2022-01-26 | 2022-11-02 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32500 | 0 | 0 | 0 | 32500 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Safety Surfacing | 10 | 0 | 100% | 2022-11-02 | 2022-11-02 |  | 0 | 0 | ENG | 0 | 0-0
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32510 | 0 | 0 | 0 | 32510 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Fab/Del. Safety Surfacing | 20 | 20 | 0% | 2022-11-25 08:00 | 2022-12-22 17:00 | 24 | PLAYGROUND | 0 | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32520 | 0 | 0 | 0 | 32520 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare & Submit Chain Link Fences and Gates | 150 | 0 | 100% | 2020-09-22 | 2020-10-12 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32530 | 0 | 0 | 0 | 32530 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Chain Link Fences and Gates | 10 | 0 | 100% | 2021-01-21 | 2021-02-04 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32540 | 0 | 0 | 0 | 32540 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Fab/Del. Chain Link Fences and Gates | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 79 | ATLAS | 0 | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32550 | 0 | 0 | 0 | 32550 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare & Submit Site Furnishings | 150 | 0 | 100% | 2021-09-01 08:00 | 2022-11-02 |  | 0 | 0 | ENG | 0 | 0-0
In Progress | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32560 | 0 | 0 | 0 | 32560 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Site Furnishings | 10 | 1 | 90% | 2022-11-02 | 2022-11-25 17:00 | 48 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32570 | 0 | 0 | 0 | 32570 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Fab/Del. Site Furnishings | 40 | 40 | 0% | 2022-11-28 08:00 | 2023-01-25 17:00 | 48 | MLJ | PROCUREMENT | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32580 | 0 | 0 | 0 | 32580 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare & Submit Topsoil | 150 | 0 | 100% | 2021-09-01 08:00 | 2022-07-21 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32590 | 0 | 0 | 0 | 32590 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Topsoil | 10 | 0 | 100% | 2022-07-22 | 2022-08-10 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32600 | 0 | 0 | 0 | 32600 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Del. Topsoil | 1 | 0 | 100% | 2022-10-17 08:00 | 2022-10-17 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32610 | 0 | 0 | 0 | 32610 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare & Submit Seeded Lawn | 150 | 0 | 100% | 2022-01-26 | 2022-09-06 17:00 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32620 | 0 | 0 | 0 | 32620 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Seeded Lawn | 10 | 0 | 100% | 2022-09-07 08:00 | 2022-09-16 17:00 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32630 | 0 | 0 | 0 | 32630 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Del. Seeded Lawn | 5 | 0 | 100% | 2022-10-03 08:00 | 2022-10-07 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32640 | 0 | 0 | 0 | 32640 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare & Submit Plant Materials | 150 | 0 | 100% | 2022-01-26 | 2022-07-21 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32650 | 0 | 0 | 0 | 32650 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Plant Materials | 10 | 0 | 100% | 2022-07-22 | 2022-08-10 |  | 0 | 0 | ENG | 0 | 0-0
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32660 | 0 | 0 | 0 | 32660 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Del. Plant Materials | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | 92 | ASPEN | 0 | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32670 | 0 | 0 | 0 | 32670 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare & Submit Landscape Boulders | 150 | 0 | 100% | 2020-07-13 | 2020-11-13 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32680 | 0 | 0 | 0 | 32680 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Landscape Boulders | 10 | 0 | 100% | 2020-11-13 | 2021-03-05 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32690 | 0 | 0 | 0 | 32690 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Del. Landscape Boulders | 5 | 0 | 100% | 2022-09-23 | 2022-10-26 |  | 0 | 0 | 0 | 0 | 0-0
In Progress | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32700 | 0 | 0 | 0 | 32700 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare & Submit Metal Edging | 150 | 10 | 93% | 2022-01-26 | 2022-12-08 17:00 | 82 | JMC | 0 | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32710 | 0 | 0 | 0 | 32710 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Metal Edging | 10 | 10 | 0% | 2022-12-09 08:00 | 2022-12-22 17:00 | 82 | JMC | 0 | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32720 | 0 | 0 | 0 | 32720 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Fab/Del. Metal Edging | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | 82 | JMC | 0 | 0 | 0 | 0-NA
In Progress | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32730 | 0 | 0 | 0 | 32730 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare & Submit Basketball Backstop | 150 | 20 | 86% | 2022-01-26 | 2022-12-22 17:00 | 29 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32740 | 0 | 0 | 0 | 32740 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Basketball Backstop | 10 | 10 | 0% | 2022-12-23 08:00 | 2023-01-09 17:00 | 29 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32750 | 0 | 0 | 0 | 32750 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Fab/Del. Basketball Backstop | 30 | 30 | 0% | 2023-01-10 08:00 | 2023-02-22 17:00 | 29 | MLJ | PROCUREMENT | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33000 | 0 | 0 | 0 | 33000 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Prepare & Submit Maint. & Protect Existing Privately Owned Utilities Plan - N/A | 20 | 0 | 100% | 2021-03-01 | 2021-03-01 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33010 | 0 | 0 | 0 | 33010 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Review & Approve Maint. & Protect Existing Privately Owned Utilities Plan - N/A | 10 | 0 | 100% | 2021-03-01 | 2021-03-01 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33020 | 0 | 0 | 0 | 33020 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Prepare & Submit Terminate & Demo. Existing Utilities Plan - N/A | 20 | 0 | 100% | 2021-03-01 | 2021-03-01 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33030 | 0 | 0 | 0 | 33030 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Review & Approve Terminate & Demo. Existing Utilities Plan - N/A | 10 | 0 | 100% | 2021-03-01 | 2021-03-01 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33040 | 0 | 0 | 0 | 33040 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Prepare & Submit Cleaning & Disinfecting Water Mains Plan - N/A | 20 | 0 | 100% | 2021-03-01 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33050 | 0 | 0 | 0 | 33050 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Review & Approve Cleaning & Disinfecting Water Mains Plan - N/A | 10 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33060 | 0 | 0 | 0 | 33060 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Prepare & Submit Cement Lined Ductile Iron Pipe & Fitting for Water Main | 20 | 0 | 100% | 2020-10-09 | 2020-11-09 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33070 | 0 | 0 | 0 | 33070 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Review & Approve Cement Lined Ductile Iron Pipe & Fitting for Water Main | 10 | 0 | 100% | 2020-11-09 | 2020-12-15 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33080 | 0 | 0 | 0 | 33080 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Fab/Del. Cement Lined Ductile Iron Pipe & Fitting for Water Main | 20 | 0 | 100% | 2021-06-21 08:00 | 2021-08-05 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33090 | 0 | 0 | 0 | 33090 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Prepare & Submit Water Main & Appurtenances - N/A | 20 | 0 | 100% | 2021-07-12 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33100 | 0 | 0 | 0 | 33100 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Review & Approve Water Main & Appurtenances - N/A | 10 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33110 | 0 | 0 | 0 | 33110 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Fab/Del. Water Main & Appurtenances - N/A | 20 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33120 | 0 | 0 | 0 | 33120 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Prepare & Submit Filter Fabric for Utility Pipes | 20 | 0 | 100% | 2020-11-21 | 2020-12-21 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33130 | 0 | 0 | 0 | 33130 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Review & Approve Filter Fabric for Utility Pipes | 10 | 0 | 100% | 2020-12-21 | 2020-12-24 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33140 | 0 | 0 | 0 | 33140 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Fab/Del. Filter Fabric for Utility Pipes | 20 | 0 | 100% | 2021-06-21 08:00 | 2021-08-05 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33150 | 0 | 0 | 0 | 33150 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Prepare & Submit Polyethylene Sleeve | 20 | 0 | 100% | 2020-12-28 | 2021-01-11 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33160 | 0 | 0 | 0 | 33160 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Review & Approve Polyethylene Sleeve | 10 | 0 | 100% | 2021-01-11 | 2021-02-08 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33170 | 0 | 0 | 0 | 33170 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Fab/Del. Polyethylene Sleeve | 20 | 0 | 100% | 2021-06-21 08:00 | 2021-08-05 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33180 | 0 | 0 | 0 | 33180 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Prepare & Submit Wet & Dry Connections to Existing Water Main Procedure - N/A | 20 | 0 | 100% | 2021-08-02 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33190 | 0 | 0 | 0 | 33190 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Review & Approve Wet & Dry Connections to Existing Water Main Procedure - N/A | 10 | 0 | 100% | 2021-08-02 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33200 | 0 | 0 | 0 | 33200 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Prepare & Submit Water Main Valves - N/A | 20 | 0 | 100% | 2021-07-24 | 2021-07-24 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33210 | 0 | 0 | 0 | 33210 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Review & Approve Water Main Valvess - N/A | 10 | 0 | 100% | 2021-07-24 | 2021-07-24 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33220 | 0 | 0 | 0 | 33220 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Fab/Del. Water Main Valvess - N/A | 20 | 0 | 100% | 2021-07-24 | 2021-07-24 |  | 0 | 0 | 0 | 0 | 0-0
In Progress | CI NYCHA Update #22.Procurement.Div. 33 | NA | 33230 | 0 | 0 | 0 | 33230 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Prepare & Submit Cleaning of Drainage Structures Procedures | 20 | 1 | 95% | 2022-07-25 08:00 | 2022-11-25 17:00 | -16 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 33 | NA | 33240 | 0 | 0 | 0 | 33240 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Review & Approve Cleaning of Drainage Structures Procedures | 10 | 10 | 0% | 2022-11-28 08:00 | 2022-12-09 17:00 | -16 | MLJ | PROCUREMENT | ENG | NA | NA-NA
In Progress | CI NYCHA Update #22.Procurement.Div. 33 | NA | 33250 | 0 | 0 | 0 | 33250 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Prepare & Submit Expansion Joints for Utility | 20 | 1 | 95% | 2021-11-22 08:00 | 2022-11-25 17:00 | -27 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 33 | NA | 33260 | 0 | 0 | 0 | 33260 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Review & Approve Expansion Joints for Utility | 10 | 10 | 0% | 2022-11-28 08:00 | 2022-12-09 17:00 | -27 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 33 | NA | 33270 | 0 | 0 | 0 | 33270 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Fab/Del. Expansion Joints for Utility | 20 | 20 | 0% | 2022-12-12 08:00 | 2023-01-10 17:00 | -27 | MLJ | PROCUREMENT | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33280 | 0 | 0 | 0 | 33280 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Prepare & Submit Ductile Iron Pipe Sewers | 20 | 0 | 100% | 2020-11-09 | 2020-12-03 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33290 | 0 | 0 | 0 | 33290 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Review & Approve Ductile Iron Pipe Sewers | 10 | 0 | 100% | 2020-12-03 | 2020-12-15 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33300 | 0 | 0 | 0 | 33300 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Fab/Del. Ductile Iron Pipe Sewers | 20 | 0 | 100% | 2021-07-28 | 2021-08-17 |  | 0 | 0 | 0 | 0 | 0-0
In Progress | CI NYCHA Update #22.Procurement.Div. 33 | NA | 33310 | 0 | 0 | 0 | 33310 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Prepare & Submit Catch Basin Connections | 20 | 1 | 95% | 2022-08-22 08:00 | 2022-11-25 17:00 | -5 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 33 | NA | 33320 | 0 | 0 | 0 | 33320 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Review & Approve Catch Basin Connections | 10 | 10 | 0% | 2022-11-28 08:00 | 2022-12-09 17:00 | -5 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 33 | NA | 33330 | 0 | 0 | 0 | 33330 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Fab/Del. Catch Basin Connections | 20 | 20 | 0% | 2022-12-12 08:00 | 2023-01-10 17:00 | -5 | MLJ | PROCUREMENT | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33340 | 0 | 0 | 0 | 33340 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Prepare & Submit Structures for Sewers | 20 | 0 | 100% | 2020-08-30 | 2020-09-30 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33350 | 0 | 0 | 0 | 33350 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Review & Approve Structures for Sewers | 10 | 0 | 100% | 2020-10-01 | 2021-04-25 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 33 | 0 | 33360 | 0 | 0 | 0 | 33360 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Fab/Del. Structures for Sewers | 20 | 0 | 100% | 2022-03-01 | 2022-03-11 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01600 | 0 | 0 | 0 | 01600 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Prepare & Submit Electrical Subcontractor | 5 | 0 | 100% | 2020-03-16 | 2020-03-16 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01610 | 0 | 0 | 0 | 01610 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Review & Approve Electrical Subcontractor | 10 | 0 | 100% | 2020-03-16 | 2020-11-06 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01620 | 0 | 0 | 0 | 01620 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Prepare & Submit Plumbing Subcontractor | 5 | 0 | 100% | 2020-03-16 | 2020-03-16 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01630 | 0 | 0 | 0 | 01630 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Review & Approve Plumbing Subcontractor | 10 | 0 | 100% | 2020-03-16 | 2020-09-08 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01640 | 0 | 0 | 0 | 01640 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Prepare & Submit HVAC Subcontractor | 5 | 0 | 100% | 2020-03-16 | 2020-03-16 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01650 | 0 | 0 | 0 | 01650 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Review & Approve HVAC Subcontractor | 10 | 0 | 100% | 2020-03-16 | 2020-12-16 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01660 | 0 | 0 | 0 | 01660 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Site Survey, Prepare & Submit Elevator Subcontractor | 60 | 0 | 100% | 2020-07-13 | 2020-11-10 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01670 | 0 | 0 | 0 | 01670 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Review & Approve Elevator Subcontractor | 10 | 0 | 100% | 2020-11-10 | 2021-07-23 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 31 | 0 | 31000 | 0 | 0 | 0 | 31000 | Procurement | Div. 31 - Earthwork | Procurement.Div. 31 | Prepare & Submit Geotectile - Drainage | 20 | 0 | 100% | 2020-09-26 | 2020-10-26 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 31 | 0 | 31010 | 0 | 0 | 0 | 31010 | Procurement | Div. 31 - Earthwork | Procurement.Div. 31 | Review & Approve Geotectile - Drainage | 10 | 0 | 100% | 2020-10-26 | 2020-11-02 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 31 | 0 | 31020 | 0 | 0 | 0 | 31020 | Procurement | Div. 31 - Earthwork | Procurement.Div. 31 | Fab/Del. Geotectile - Drainage | 5 | 0 | 100% | 2022-03-07 08:00 | 2022-03-07 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 31 | 0 | 31030 | 0 | 0 | 0 | 31030 | Procurement | Div. 31 - Earthwork | Procurement.Div. 31 | Prepare & Submit Geotectile - Separation & Stabilization | 20 | 0 | 100% | 2020-09-22 | 2020-10-22 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 31 | 0 | 31040 | 0 | 0 | 0 | 31040 | Procurement | Div. 31 - Earthwork | Procurement.Div. 31 | Review & Approve Geotectile - Separation & Stabilization | 10 | 0 | 100% | 2020-10-22 | 2020-12-15 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 31 | 0 | 31050 | 0 | 0 | 0 | 31050 | Procurement | Div. 31 - Earthwork | Procurement.Div. 31 | Fab/Del. Geotectile - Separation & Stabilization | 5 | 0 | 100% | 2022-03-07 08:00 | 2022-03-07 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 31 | 0 | 31060 | 0 | 0 | 0 | 31060 | Procurement | Div. 31 - Earthwork | Procurement.Div. 31 | Prepare & Submit Clearing & Grubbing Plan | 20 | 0 | 100% | 2020-07-13 | 2020-11-11 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 31 | 0 | 31070 | 0 | 0 | 0 | 31070 | Procurement | Div. 31 - Earthwork | Procurement.Div. 31 | Review & Approve Clearing & Grubbing Plan | 10 | 0 | 100% | 2020-11-11 | 2020-12-15 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 31 | 0 | 31080 | 0 | 0 | 0 | 31080 | Procurement | Div. 31 - Earthwork | Procurement.Div. 31 | Prepare & Submit Tree Protection Plan | 20 | 0 | 100% | 2020-07-13 | 2020-10-19 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 31 | 0 | 31090 | 0 | 0 | 0 | 31090 | Procurement | Div. 31 - Earthwork | Procurement.Div. 31 | Review & Approve Tree Protection Plan | 10 | 0 | 100% | 2020-10-19 | 2020-10-27 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 31 | 0 | 31100 | 0 | 0 | 0 | 31100 | Procurement | Div. 31 - Earthwork | Procurement.Div. 31 | Prepare & Submit Selective Tree Removal Plan | 20 | 0 | 100% | 2020-07-13 | 2020-10-19 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 31 | 0 | 31110 | 0 | 0 | 0 | 31110 | Procurement | Div. 31 - Earthwork | Procurement.Div. 31 | Review & Approve Selective Tree Removal Plan | 10 | 0 | 100% | 2020-10-19 | 2020-10-27 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 31 | 0 | 31120 | 0 | 0 | 0 | 31120 | Procurement | Div. 31 - Earthwork | Procurement.Div. 31 | Prepare & Submit Dewatering Plan | 20 | 0 | 100% | 2020-08-20 | 2020-09-03 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 31 | 0 | 31130 | 0 | 0 | 0 | 31130 | Procurement | Div. 31 - Earthwork | Procurement.Div. 31 | Review & Approve Dewatering Plan | 10 | 0 | 100% | 2020-09-03 | 2021-02-12 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 31 | 0 | 31140 | 0 | 0 | 0 | 31140 | Procurement | Div. 31 - Earthwork | Procurement.Div. 31 | Prepare & Submit Excavating Backfill & Compaction for Pipes & Utility Trenches Procedure | 20 | 0 | 100% | 2021-01-04 | 2021-02-05 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 31 | 0 | 31150 | 0 | 0 | 0 | 31150 | Procurement | Div. 31 - Earthwork | Procurement.Div. 31 | Review & Approve Excavating Backfill & Compaction for Pipes & Utility Trenches Procedure | 10 | 0 | 100% | 2021-02-06 | 2021-02-19 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 31 | 0 | 31160 | 0 | 0 | 0 | 31160 | Procurement | Div. 31 - Earthwork | Procurement.Div. 31 | Prepare & Submit Excavating Backfill & Compaction for Pavements Plan Procedure | 20 | 0 | 100% | 2021-01-04 | 2021-02-05 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 31 | 0 | 31170 | 0 | 0 | 0 | 31170 | Procurement | Div. 31 - Earthwork | Procurement.Div. 31 | Review & Approve Excavating Backfill & Compaction for Pavements Plan Procedure | 10 | 0 | 100% | 2021-02-06 | 2021-02-19 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01680 | 0 | 0 | 0 | 01680 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Prepare & Submit Structural Steel Subcontractor | 5 | 0 | 100% | 2020-05-18 | 2020-05-18 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01690 | 0 | 0 | 0 | 01690 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Review & Approve Structural Steel Subcontractor | 10 | 0 | 100% | 2020-05-18 | 2020-10-06 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01700 | 0 | 0 | 0 | 01700 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Prepare & Submit Misc. Metal Subcontractor | 5 | 0 | 100% | 2020-05-18 | 2020-05-18 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01710 | 0 | 0 | 0 | 01710 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Review & Approve Misc. Metal Subcontractor | 10 | 0 | 100% | 2020-05-18 | 2022-05-20 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01720 | 0 | 0 | 0 | 01720 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Prepare & Submit Masonry Subcontractor | 5 | 0 | 100% | 2020-07-07 | 2020-07-07 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01730 | 0 | 0 | 0 | 01730 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Review & Approve Masonry Subcontractor | 10 | 0 | 100% | 2020-07-07 | 2021-11-16 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01740 | 0 | 0 | 0 | 01740 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Prepare & Submit Waterproofer Subcontractor | 5 | 0 | 100% | 2020-07-13 | 2020-11-10 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01750 | 0 | 0 | 0 | 01750 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Review & Approve Waterproofer Subcontractor | 10 | 0 | 100% | 2020-11-10 | 2021-04-21 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01760 | 0 | 0 | 0 | 01760 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Prepare & Submit Painting Subcontractor | 5 | 0 | 100% | 2020-05-18 | 2020-05-18 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01770 | 0 | 0 | 0 | 01770 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Review & Approve Painting Subcontractor | 10 | 0 | 100% | 2020-05-18 | 2021-03-16 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01780 | 0 | 0 | 0 | 01780 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Prepare & Submit Hazardous Waste Subcontractor | 5 | 0 | 100% | 2020-03-16 | 2020-03-16 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01790 | 0 | 0 | 0 | 01790 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Review & Approve Hazardous Waste Subcontractor | 10 | 0 | 100% | 2020-03-16 | 2020-08-21 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01800 | 0 | 0 | 0 | 01800 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Prepare & Submit Roofing Subcontractor | 5 | 0 | 100% | 2020-05-27 | 2020-05-28 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01810 | 0 | 0 | 0 | 01810 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Review & Approve Roofing Subcontractor | 10 | 0 | 100% | 2020-05-28 | 2021-06-07 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01820 | 0 | 0 | 0 | 01820 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Prepare & Submit Fire Proofing Subcontractor | 5 | 0 | 100% | 2020-07-10 | 2020-07-10 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01830 | 0 | 0 | 0 | 01830 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Review & Approve Fire Proofing Subcontractor | 10 | 0 | 100% | 2020-07-10 | 2020-08-27 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24410 | 0 | 0 | 0 | 24410 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Fuel Oil Tanks | 30 | 0 | 100% | 2020-09-29 | 2020-10-29 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24420 | 0 | 0 | 0 | 24420 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Fuel Oil Tanks | 10 | 0 | 100% | 2020-10-29 | 2020-11-16 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24430 | 0 | 0 | 0 | 24430 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Fuel Oil Tanks | 75 | 0 | 100% | 2021-04-12 | 2021-09-26 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24440 | 0 | 0 | 0 | 24440 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Prepare & Submit Fuel Pumps | 30 | 0 | 100% | 2020-09-29 | 2020-10-29 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24450 | 0 | 0 | 0 | 24450 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Review & Approve Fuel Pumps | 10 | 0 | 100% | 2020-10-29 | 2020-11-16 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24460 | 0 | 0 | 0 | 24460 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Fuel Pumps | 75 | 0 | 100% | 2021-07-26 08:00 | 2021-10-24 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Construction.2.1 | SGN | SURV | SGN | G | 01005 | SURV-SGN-G-01005 | Construction | Survey & Mobilization | Construction.2.1 | Perform Survey of Site/Building - Surfside - North | 10 | 0 | 100% | 2020-10-19 | 2020-10-26 17:00 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.5.1 | OGW | SURV | OGW | G | 01010 | SURV-OGW-G-01010 | Construction | Mobilization & Survey | Construction.5.1 | Perform Survey of Site/Building - O'Dwyer Garden - West (OG-2, OG-3 & OG-9) | 10 | 0 | 100% | 2020-11-05 | 2020-11-17 17:00 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.1.1 | OGE | SURV | OGE | 01015 | 0 | SURV-OGE-01015 | Construction | Mobilization & Survey | Construction.1.1 | Perform Survey of Site/Building - O'Dwyer Garden - East (OG-1, OG-6 & OG-10) | 10 | 0 | 100% | 2020-11-05 | 2020-11-17 17:00 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.4.1 | SGS | SURV | SGS | G | 01020 | SURV-SGS-G-01020 | Construction | Mobilization & Survey | Construction.4.1 | Perform Survey of Site/Building - Surfside - South (SG-1, SG-2, SG-3 & SG-7) | 10 | 0 | 100% | 2020-10-26 | 2020-11-05 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.8.4 | S8 | SURV | S8 | G | 01005 | SURV-S8-G-01005 | Construction | Mobilization & Survey | Construction.8.4 | Perform Survey of Site/Building - Site 8 (S8 & S8-1) | 10 | 0 | 100% | 2020-10-26 | 2020-11-05 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.Mob | 0 | MOBE | 01005 | 0 | 0 | MOBE-01005 | Construction | Survey & Mobilization | Construction.Mob | Project Mobilization | 20 | 0 | 100% | 2020-07-13 | 2020-08-07 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Construction.2.5.Removals | SGN | SGN | 01005 | 0 | 0 | SGN-01005 | Construction | Site Protection & Removals | Construction.2.5.Removals | Install Site Fencing - Surfside Gardens - North | 10 | 0 | 100% | 2020-12-15 | 2021-01-08 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Procurement.Div 1.GENRAL | 0 | 01560 | 0 | 0 | 0 | 01560 | Procurement | General | Procurement.Div 1.GENRAL | NYCHA files TR's | 67 | 0 | 100% | 2020-07-13 | 2020-09-22 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 01005 | 0 | 0 | PERMIT-01005 | Procurement | Permits | Procurement.Div 1.Permits | File for DOT Sidewalk Permits | 10 | 0 | 100% | 2020-10-01 | 2020-10-01 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Milestones | 0 | M005 | 0 | 0 | 0 | M005 | Milestones | Milestones | Milestones | Notice to Proceed (July 13, 2020) | 0 | 0 | 100% | 2020-07-13 17:00 |  |  | 0 | 0 | 0 | 0 | 0-0
Not Started | CI NYCHA Update #22.Milestones | NA | M900 | 0 | 0 | 0 | M900 | Milestones | Milestones | Milestones | Substantial Completion (NTP+1047d) - May 26, 2023 | 0 | 0 | 0% |  | 2024-05-08 17:00 | -348 | MLJ | MILESTONE | 0 | NA | NA-NA
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 01010 | 0 | 0 | PERMIT-01010 | Procurement | Permits | Procurement.Div 1.Permits | DOT Issue Sidewalk Permits | 20 | 0 | 100% | 2020-09-02 | 2020-10-06 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Not Started | CI NYCHA Update #22.Milestones | NA | M999 | 0 | 0 | 0 | M999 | Milestones | Milestones | Milestones | Final Completion (NTP+1137d) - August 24, 2023 | 0 | 0 | 0% |  | 2024-08-06 17:00 | -348 | MLJ | MILESTONE | 0 | NA | NA-NA
Completed | CI NYCHA Update #22.Construction.2.1 | SGN | SURV | SGN | E | 01000 | SURV-SGN-E-01000 | Construction | Survey & Mobilization | Construction.2.1 | Conduct Electrical Site Survey - Surfside Gardens North (SG-4, SG-5) | 20 | 0 | 100% | 2020-08-13 | 2020-12-23 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.5.1 | OGW | SURV | OGW | E | 01015 | SURV-OGW-E-01015 | Construction | Mobilization & Survey | Construction.5.1 | Conduct Electrical Site Survey - O'Dwyer Garden - Part 2 (OG-3) | 15 | 0 | 100% | 2020-09-08 | 2021-07-16 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.1.1 | OGE | SURV | OGE | 01020 | 0 | SURV-OGE-01020 | Construction | Mobilization & Survey | Construction.1.1 | Conduct Electrical Site Survey - O'Dwyer Garden - East (OG-1, OG-6 & OG-10) | 15 | 0 | 100% | 2021-02-24 | 2021-06-30 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.4.1 | SGS | SURV | SGS | E | 01030 | SURV-SGS-E-01030 | Construction | Mobilization & Survey | Construction.4.1 | Conduct Electrical Site Survey - Surfside Gardens South (SG-1) | 10 | 0 | 100% | 2021-06-01 | 2021-07-21 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.8.4 | S8 | SURV | S8 | E | 01015 | SURV-S8-E-01015 | Construction | Mobilization & Survey | Construction.8.4 | Conduct Electrical Site Survey - Site 8 (S8 & S8-1) | 10 | 0 | 100% | 2022-02-22 08:00 | 2022-03-04 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01905 | 0 | 0 | 0 | 01905 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Procure Vendor - Switchboard/Panelboard & GCB/Disconnect Switches | 30 | 0 | 100% | 2020-07-13 | 2020-08-07 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01910 | 0 | 0 | 0 | 01910 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Procure Vendor - ACTTS | 30 | 0 | 100% | 2020-07-13 | 2020-08-20 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01915 | 0 | 0 | 0 | 01915 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Procure Installer - Lightning Protection | 50 | 0 | 100% | 2020-07-13 | 2020-09-02 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01920 | 0 | 0 | 0 | 01920 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Procure Vendor - Generator | 20 | 0 | 100% | 2020-11-02 | 2020-11-13 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01925 | 0 | 0 | 0 | 01925 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Procure Installer - Smoke Detection System | 50 | 0 | 100% | 2020-07-13 | 2020-08-31 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01930 | 0 | 0 | 0 | 01930 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Procure Vendor - Lighting & Vacancy/Occupancy Sensors | 50 | 0 | 100% | 2020-07-13 | 2020-09-22 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01935 | 0 | 0 | 0 | 01935 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Procure Vendor - Seismic Restraint & Vibration Isolation | 50 | 0 | 100% | 2021-04-05 | 2021-04-12 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01940 | 0 | 0 | 0 | 01940 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Procure Vendor - Heat Tracing | 50 | 0 | 100% | 2020-07-13 | 2020-07-27 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.2 | 0 | 260519 | 01000 | 0 | 0 | 260519-01000 | Procurement | 26 05 19 - Wire & Cable (600 V) | Procurement.ElecEng.2 | Prep/Submit Product Submittals - Wire & Cable (600 V) | 40 | 0 | 100% | 2020-04-15 | 2020-05-13 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.2 | 0 | 260519 | 01010 | 0 | 0 | 260519-01010 | Procurement | 26 05 19 - Wire & Cable (600 V) | Procurement.ElecEng.2 | Rev/Apprv. Product Submittals - Wire & Cable (600 V) | 10 | 0 | 100% | 2020-05-14 | 2020-11-09 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.2 | 0 | 260519 | 01015 | 0 | 0 | 260519-01015 | Procurement | 26 05 19 - Wire & Cable (600 V) | Procurement.ElecEng.2 | Fabricate & Deliver Material - Wire & Cable (600 V) | 35 | 0 | 100% | 2022-03-25 08:00 | 2022-06-03 17:00 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.3 | 0 | 260526 | 01010 | 0 | 0 | 260526-01010 | Procurement | 26 05 26 - Grounding & Bonding | Procurement.ElecEng.3 | Prep/Submit Product Submittals - Grounding & Bonding Equipment | 40 | 0 | 100% | 2020-06-17 | 2020-11-05 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.3 | 0 | 260526 | 01020 | 0 | 0 | 260526-01020 | Procurement | 26 05 26 - Grounding & Bonding | Procurement.ElecEng.3 | Rev/Apprv. Product Submittals - Grounding & Bonding Equipment | 10 | 0 | 100% | 2020-11-06 | 2020-12-14 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.3 | 0 | 260526 | 01025 | 0 | 0 | 260526-01025 | Procurement | 26 05 26 - Grounding & Bonding | Procurement.ElecEng.3 | Fabricate & Deliver Material - Grounding & Bonding | 35 | 0 | 100% | 2022-05-01 | 2022-09-23 10:00 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.4 | 0 | 260533 | 01005 | 0 | 0 | 260533-01005 | Procurement | 26 05 33 - Raceways & Installation Components | Procurement.ElecEng.4 | Prep/Submit Product Submittals - Conduits (Rigid, EMT & Flexible) | 40 | 0 | 100% | 2020-04-15 | 2020-05-14 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.4 | 0 | 260533 | 01010 | 0 | 0 | 260533-01010 | Procurement | 26 05 33 - Raceways & Installation Components | Procurement.ElecEng.4 | Rev/Apprv. Product Submittals - Conduits (Rigid, EMT & Flexible) | 10 | 0 | 100% | 2020-05-15 | 2020-12-03 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.4 | 0 | 260533 | 01015 | 0 | 0 | 260533-01015 | Procurement | 26 05 33 - Raceways & Installation Components | Procurement.ElecEng.4 | Prep/Submit Product Submittals - Junction & Pull Boxes | 40 | 0 | 100% | 2020-04-15 | 2020-05-14 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.4 | 0 | 260533 | 01020 | 0 | 0 | 260533-01020 | Procurement | 26 05 33 - Raceways & Installation Components | Procurement.ElecEng.4 | Rev/Apprv. Product Submittals - Junction & Pull Boxes | 10 | 0 | 100% | 2020-05-15 | 2021-02-18 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.4 | 0 | 260533 | 01025 | 0 | 0 | 260533-01025 | Procurement | 26 05 33 - Raceways & Installation Components | Procurement.ElecEng.4 | Fabricate & Deliver Material - Raceway Conduits & Installation Components | 25 | 0 | 100% | 2021-06-25 08:00 | 2022-08-31 17:00 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.5 | 0 | 260534 | 01005 | 0 | 0 | 260534-01005 | Procurement | 26 05 34 - Fire Stopping for Electrical Systems | Procurement.ElecEng.5 | Prep/Submit Product Submittals - Fire Stopping | 40 | 0 | 100% | 2020-04-15 | 2020-06-09 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.5 | 0 | 260534 | 01010 | 0 | 0 | 260534-01010 | Procurement | 26 05 34 - Fire Stopping for Electrical Systems | Procurement.ElecEng.5 | Rev/Apprv. Product Submittals - Fire Stopping | 10 | 0 | 100% | 2020-06-10 | 2020-11-24 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.5 | 0 | 260534 | 01015 | 0 | 0 | 260534-01015 | Procurement | 26 05 34 - Fire Stopping for Electrical Systems | Procurement.ElecEng.5 | Fabricate & Deliver Material - Fire Stopping | 25 | 0 | 100% | 2022-03-01 | 2022-09-02 12:00 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.6 | 0 | 260543 | 01005 | 0 | 0 | 260543-01005 | Procurement | 26 05 43 - Underground Ducts for Electrical Systems | Procurement.ElecEng.6 | Prep/Submit Product Submittals - High Density Polyethylene Conduit (HDPE) | 40 | 0 | 100% | 2020-04-15 | 2020-06-29 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.6 | 0 | 260543 | 01010 | 0 | 0 | 260543-01010 | Procurement | 26 05 43 - Underground Ducts for Electrical Systems | Procurement.ElecEng.6 | Rev/Apprv. Product Submittals - High Density Polyethylene Conduit (HDPE) | 10 | 0 | 100% | 2020-06-30 | 2021-02-09 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.6 | 0 | 260543 | 01015 | 0 | 0 | 260543-01015 | Procurement | 26 05 43 - Underground Ducts for Electrical Systems | Procurement.ElecEng.6 | Prep/Submit Product Submittals - Fiber Reinforced Epoxy Utility Duct (FRE) - N/A | 40 | 0 | 100% | 2020-11-24 | 2020-11-24 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.6 | 0 | 260543 | 01020 | 0 | 0 | 260543-01020 | Procurement | 26 05 43 - Underground Ducts for Electrical Systems | Procurement.ElecEng.6 | Rev/Apprv. Product Submittals - Fiber Reinforced Epoxy Utility Duct (FRE) | 10 | 0 | 100% | 2020-11-24 | 2020-11-24 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.6 | 0 | 260543 | 01025 | 0 | 0 | 260543-01025 | Procurement | 26 05 43 - Underground Ducts for Electrical Systems | Procurement.ElecEng.6 | Fabricate & Deliver Material - Underground Ducts for Electrical Systems (HDPE & FRE) | 25 | 0 | 100% | 2021-04-01 | 2022-03-02 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.7 | 0 | 260548 | 01005 | 0 | 0 | 260548-01005 | Procurement | 26 05 48 - Seismic Vibration & Isolation Equipment | Procurement.ElecEng.7 | Prep/Submit Product Submittals - Vibration Isolation Devices | 40 | 0 | 100% | 2020-10-10 | 2020-10-21 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.7 | 0 | 260548 | 01010 | 0 | 0 | 260548-01010 | Procurement | 26 05 48 - Seismic Vibration & Isolation Equipment | Procurement.ElecEng.7 | Rev/Apprv. Product Submittals - Vibration Isolation Devices | 10 | 0 | 100% | 2020-10-22 | 2020-11-11 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.7 | 0 | 260548 | 01015 | 0 | 0 | 260548-01015 | Procurement | 26 05 48 - Seismic Vibration & Isolation Equipment | Procurement.ElecEng.7 | Prep/Submit Product Submittals - Seismic Restraints | 40 | 0 | 100% | 2021-07-26 08:00 | 2021-11-15 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.7 | 0 | 260548 | 01020 | 0 | 0 | 260548-01020 | Procurement | 26 05 48 - Seismic Vibration & Isolation Equipment | Procurement.ElecEng.7 | Rev/Apprv. Product Submittals - Seismic Restraints | 10 | 0 | 100% | 2021-11-16 | 2021-12-08 17:00 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.7 | 0 | 260548 | 01025 | 0 | 0 | 260548-01025 | Procurement | 26 05 48 - Seismic Vibration & Isolation Equipment | Procurement.ElecEng.7 | Fabricate & Deliver Equipment - Seismic Vibration & Isolation - N/A | 45 | 0 | 100% | 2022-01-01 08:00 | 2022-01-01 17:00 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.8 | 0 | 260553 | 01005 | 0 | 0 | 260553-01005 | Procurement | 26 05 53 - Identification for Electrical Systems | Procurement.ElecEng.8 | Prep/Submit Product Submittals - Identification Labels & Tags | 40 | 0 | 100% | 2020-08-20 | 2020-10-20 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.8 | 0 | 260553 | 01010 | 0 | 0 | 260553-01010 | Procurement | 26 05 53 - Identification for Electrical Systems | Procurement.ElecEng.8 | Rev/Apprv. Product Submittals - Identification Labels & Tags | 10 | 0 | 100% | 2020-10-21 | 2020-11-16 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.8 | 0 | 260553 | 01015 | 0 | 0 | 260553-01015 | Procurement | 26 05 53 - Identification for Electrical Systems | Procurement.ElecEng.8 | Fabricate & Deliver Material - Identification Labels & Tags | 25 | 0 | 100% | 2022-07-01 | 2022-09-23 12:00 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.9 | 0 | 260573 | 01005 | 0 | 0 | 260573-01005 | Procurement | 26 05 73 - Short Circuit Analysis Studies | Procurement.ElecEng.9 | Prep/Submit Report - Short Circuit Analysis Studies | 60 | 0 | 100% | 2020-11-02 | 2022-05-06 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.9 | 0 | 260573 | 01010 | 0 | 0 | 260573-01010 | Procurement | 26 05 73 - Short Circuit Analysis Studies | Procurement.ElecEng.9 | Rev/Appr. Report - Short Circuit Analysis Studies - (Coordinate w/ CON-ED) | 40 | 0 | 100% | 2021-04-22 | 2022-05-03 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.10 | 0 | 260923 | 01005 | 0 | 0 | 260923-01005 | Procurement | 26 09 23 - Vacancy & Occupancy Sensors | Procurement.ElecEng.10 | Prep/Submit Product Submittals - Room Controller | 40 | 0 | 100% | 2020-08-10 | 2021-02-05 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.10 | 0 | 260923 | 01010 | 0 | 0 | 260923-01010 | Procurement | 26 09 23 - Vacancy & Occupancy Sensors | Procurement.ElecEng.10 | Rev/Apprv. Product Submittals - Room Controller | 10 | 0 | 100% | 2020-10-09 | 2021-03-01 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.10 | 0 | 260923 | 01015 | 0 | 0 | 260923-01015 | Procurement | 26 09 23 - Vacancy & Occupancy Sensors | Procurement.ElecEng.10 | Prep/Submit Product Submittals - Occupancy/Vacancy Sensors (Rev 1) | 40 | 0 | 100% | 2020-08-10 | 2021-09-03 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.10 | 0 | 260923 | 01020 | 0 | 0 | 260923-01020 | Procurement | 26 09 23 - Vacancy & Occupancy Sensors | Procurement.ElecEng.10 | Rev/Apprv. Product Submittals - Occupancy/Vacancy Sensors (Rev 1) | 10 | 0 | 100% | 2021-09-06 | 2021-09-20 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.10 | 0 | 260923 | 01025 | 0 | 0 | 260923-01025 | Procurement | 26 09 23 - Vacancy & Occupancy Sensors | Procurement.ElecEng.10 | Prep/Submit Product Submittals - Wall Switches | 40 | 0 | 100% | 2020-08-10 | 2021-02-05 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.10 | 0 | 260923 | 01030 | 0 | 0 | 260923-01030 | Procurement | 26 09 23 - Vacancy & Occupancy Sensors | Procurement.ElecEng.10 | Rev/Apprv. Product Submittals - Wall Switches | 10 | 0 | 100% | 2020-10-09 | 2021-03-01 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.10 | 0 | 260923 | 01035 | 0 | 0 | 260923-01035 | Procurement | 26 09 23 - Vacancy & Occupancy Sensors | Procurement.ElecEng.10 | Fabricate & Deliver Equipment - Vacancy & Occupancy Sensors | 25 | 0 | 100% | 2022-04-25 08:00 | 2022-05-13 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.11 | 0 | 260924 | 01005 | 0 | 0 | 260924-01005 | Procurement | 26 09 24 - Exterior Lighting Controls | Procurement.ElecEng.11 | Prep/Submit Product Submittals - Lighting Contactors | 40 | 0 | 100% | 2020-09-01 | 2021-02-05 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.11 | 0 | 260924 | 01010 | 0 | 0 | 260924-01010 | Procurement | 26 09 24 - Exterior Lighting Controls | Procurement.ElecEng.11 | Rev/Apprv. Product Submittals - Lighting Contactors | 10 | 0 | 100% | 2020-10-09 | 2021-03-01 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.11 | 0 | 260924 | 01015 | 0 | 0 | 260924-01015 | Procurement | 26 09 24 - Exterior Lighting Controls | Procurement.ElecEng.11 | Prep/Submit Product Submittals - Time Switches | 40 | 0 | 100% | 2020-09-01 | 2021-02-05 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.11 | 0 | 260924 | 01020 | 0 | 0 | 260924-01020 | Procurement | 26 09 24 - Exterior Lighting Controls | Procurement.ElecEng.11 | Rev/Apprv. Product Submittals - Time Switches | 10 | 0 | 100% | 2020-10-09 | 2021-03-01 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.11 | 0 | 260924 | 01025 | 0 | 0 | 260924-01025 | Procurement | 26 09 24 - Exterior Lighting Controls | Procurement.ElecEng.11 | Prep/Submit Product Submittals - Outdoor Photoelectric Switches | 40 | 0 | 100% | 2020-09-01 | 2021-02-05 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.11 | 0 | 260924 | 01030 | 0 | 0 | 260924-01030 | Procurement | 26 09 24 - Exterior Lighting Controls | Procurement.ElecEng.11 | Rev/Apprv. Product Submittals - Outdoor Photoelectric Switches | 10 | 0 | 100% | 2020-10-09 | 2021-03-01 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.12 | 0 | 265600 | 01005 | 0 | 0 | 265600-01005 | Procurement | 26 56 00 - Exterior Lighting | Procurement.ElecEng.12 | Prep/Submit Product Submittals - Exterior Lighting Fixtures | 30 | 0 | 100% | 2020-09-22 | 2020-12-14 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.12 | 0 | 265600 | 01010 | 0 | 0 | 265600-01010 | Procurement | 26 56 00 - Exterior Lighting | Procurement.ElecEng.12 | Rev/Apprv. Product Submittals - Exterior Lighting Fixtures | 10 | 0 | 100% | 2020-12-15 | 2021-01-26 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.13 | 0 | 265100 | 01005 | 0 | 0 | 265100-01005 | Procurement | 26 51 00 - Lighting Fixtures | Procurement.ElecEng.13 | Prep/Submit Product Submittals - Lighting Fixtures | 30 | 0 | 100% | 2020-08-03 | 2020-12-23 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.13 | 0 | 265100 | 01010 | 0 | 0 | 265100-01010 | Procurement | 26 51 00 - Lighting Fixtures | Procurement.ElecEng.13 | Rev/Apprv. Product Submittals - Lighting Fixtures | 10 | 0 | 100% | 2020-12-03 | 2021-01-11 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.13 | 0 | 265100 | 01015 | 0 | 0 | 265100-01015 | Procurement | 26 51 00 - Lighting Fixtures | Procurement.ElecEng.13 | Provide Samples - Lighting Fixtures | 10 | 0 | 100% | 2021-10-18 08:00 | 2021-12-01 17:00 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.20 | 0 | 262416 | 01005 | 0 | 0 | 262416-01005 | Procurement | 26 24 16 - Panelboards & Circuit Breakers (GCB) for Generators | Procurement.ElecEng.20 | Prep/Submit Product Submittals - Panelboards | 20 | 0 | 100% | 2020-08-24 | 2021-01-13 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.20 | 0 | 262416 | 01010 | 0 | 0 | 262416-01010 | Procurement | 26 24 16 - Panelboards & Circuit Breakers (GCB) for Generators | Procurement.ElecEng.20 | Rev/Apprv. Product Submittals - Panelboards | 10 | 0 | 100% | 2020-09-24 | 2021-02-08 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.20 | 0 | 262416 | 01015 | 0 | 0 | 262416-01015 | Procurement | 26 24 16 - Panelboards & Circuit Breakers (GCB) for Generators | Procurement.ElecEng.20 | Prep/Submit Product Submittals - Generator Circuit Breaker | 20 | 0 | 100% | 2020-08-24 | 2021-01-13 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.20 | 0 | 262416 | 01020 | 0 | 0 | 262416-01020 | Procurement | 26 24 16 - Panelboards & Circuit Breakers (GCB) for Generators | Procurement.ElecEng.20 | Rev/Apprv. Product Submittals - Generator Circuit Breaker | 10 | 0 | 100% | 2020-09-24 | 2021-02-08 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.16 | 0 | 283100 | 01005 | 0 | 0 | 283100-01005 | Procurement | 28 31 00 - Smoke Detetction Systems | Procurement.ElecEng.16 | Prep/Submit Product Submittals - Smoke Detection Panels (SDP) | 30 | 0 | 100% | 2020-09-01 | 2021-01-05 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.16 | 0 | 283100 | 01010 | 0 | 0 | 283100-01010 | Procurement | 28 31 00 - Smoke Detetction Systems | Procurement.ElecEng.16 | Rev/Apprv. Product Submittals - Smoke Detection Panels (SDP) | 10 | 0 | 100% | 2021-01-06 | 2021-02-22 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.16 | 0 | 283100 | 01015 | 0 | 0 | 283100-01015 | Procurement | 28 31 00 - Smoke Detetction Systems | Procurement.ElecEng.16 | Prep/Submit Product Submittals - Smoke Detectors | 30 | 0 | 100% | 2020-09-01 | 2021-01-05 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.16 | 0 | 283100 | 01020 | 0 | 0 | 283100-01020 | Procurement | 28 31 00 - Smoke Detetction Systems | Procurement.ElecEng.16 | Rev/Apprv. Product Submittals - Smoke Detectors | 10 | 0 | 100% | 2021-01-06 | 2021-02-22 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.16 | 0 | 283100 | 01025 | 0 | 0 | 283100-01025 | Procurement | 28 31 00 - Smoke Detetction Systems | Procurement.ElecEng.16 | Prep/Submit Product Submittals - Horns/Strobes | 30 | 0 | 100% | 2020-09-01 | 2021-01-05 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.16 | 0 | 283100 | 01030 | 0 | 0 | 283100-01030 | Procurement | 28 31 00 - Smoke Detetction Systems | Procurement.ElecEng.16 | Rev/Apprv. Product Submittals - Horns/Strobes | 10 | 0 | 100% | 2021-01-06 | 2021-02-22 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.16 | 0 | 283100 | 01035 | 0 | 0 | 283100-01035 | Procurement | 28 31 00 - Smoke Detetction Systems | Procurement.ElecEng.16 | Prep/Submit Product Submittals - Monitor & Circuit Modules | 30 | 0 | 100% | 2020-09-01 | 2021-01-05 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.16 | 0 | 283100 | 01040 | 0 | 0 | 283100-01040 | Procurement | 28 31 00 - Smoke Detetction Systems | Procurement.ElecEng.16 | Rev/Apprv. Product Submittals - Monitor & Circuit Modules | 10 | 0 | 100% | 2021-01-06 | 2021-02-22 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.16 | 0 | 283100 | 01045 | 0 | 0 | 283100-01045 | Procurement | 28 31 00 - Smoke Detetction Systems | Procurement.ElecEng.16 | Prep/Submit Product Submittals - Fire Smoke Dampers (FSD) | 30 | 0 | 100% | 2020-09-01 | 2021-01-05 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.16 | 0 | 283100 | 01050 | 0 | 0 | 283100-01050 | Procurement | 28 31 00 - Smoke Detetction Systems | Procurement.ElecEng.16 | Rev/Apprv. Product Submittals - Fire Smoke Dampers (FSD) | 10 | 0 | 100% | 2021-01-06 | 2021-02-22 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.16 | 0 | 283100 | 01055 | 0 | 0 | 283100-01055 | Procurement | 28 31 00 - Smoke Detetction Systems | Procurement.ElecEng.16 | Prep/Submit Product Submittals - Pull Station | 30 | 0 | 100% | 2020-09-01 | 2021-01-05 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.16 | 0 | 283100 | 01060 | 0 | 0 | 283100-01060 | Procurement | 28 31 00 - Smoke Detetction Systems | Procurement.ElecEng.16 | Rev/Apprv. Product Submittals - Pull Station | 10 | 0 | 100% | 2021-01-06 | 2021-02-22 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.17 | 0 | 264100 | 01005 | 0 | 0 | 264100-01005 | Procurement | 26 41 00 - Lightning Protection Systems | Procurement.ElecEng.17 | Prep/Submit Product Submittals - Lightning Protection Equipment | 60 | 0 | 100% | 2020-08-03 | 2020-12-08 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.17 | 0 | 264100 | 01010 | 0 | 0 | 264100-01010 | Procurement | 26 41 00 - Lightning Protection Systems | Procurement.ElecEng.17 | Rev/Apprv. Product Submittals - Lightning Protection Equipment | 10 | 0 | 100% | 2020-09-01 | 2021-01-29 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.22 | 0 | 262813 | 01005 | 0 | 0 | 262813-01005 | Procurement | 26 28 13 - 600 Volt Fuses | Procurement.ElecEng.22 | Prep/Submit Product Submittals - 600 Volt Fuse (Submitted with disconnect switches) | 20 | 0 | 100% | 2020-08-24 | 2020-09-08 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.22 | 0 | 262813 | 01010 | 0 | 0 | 262813-01010 | Procurement | 26 28 13 - 600 Volt Fuses | Procurement.ElecEng.22 | Rev/Apprv. Product Submittals - 600 Volt Fuse | 10 | 0 | 100% | 2020-09-09 | 2020-12-01 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.22 | 0 | 262813 | 01015 | 0 | 0 | 262813-01015 | Procurement | 26 28 13 - 600 Volt Fuses | Procurement.ElecEng.22 | Fabricate - 600 Volt Fuse | 40 | 0 | 100% | 2021-12-01 08:00 | 2021-12-20 17:00 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.22 | 0 | 262813 | 01020 | 0 | 0 | 262813-01020 | Procurement | 26 28 13 - 600 Volt Fuses | Procurement.ElecEng.22 | Deliver - 600 Volt Fuse | 5 | 0 | 100% | 2021-12-27 08:00 | 2021-12-31 17:00 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.23 | 0 | 262816 | 01005 | 0 | 0 | 262816-01005 | Procurement | 26 28 16 - Safety & Disconnect Switches | Procurement.ElecEng.23 | Prep/Submit Product Submittals - Fused Disconnect Switches | 20 | 0 | 100% | 2020-08-24 | 2020-09-08 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.23 | 0 | 262816 | 01010 | 0 | 0 | 262816-01010 | Procurement | 26 28 16 - Safety & Disconnect Switches | Procurement.ElecEng.23 | Rev/Apprv. Product Submittals - Fused Disconnect Switches | 10 | 0 | 100% | 2020-09-09 | 2020-12-01 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.23 | 0 | 262816 | 01015 | 0 | 0 | 262816-01015 | Procurement | 26 28 16 - Safety & Disconnect Switches | Procurement.ElecEng.23 | Prep/Submit Product Submittals - Switch Enclosures | 20 | 0 | 100% | 2020-08-24 | 2020-09-08 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.23 | 0 | 262816 | 01020 | 0 | 0 | 262816-01020 | Procurement | 26 28 16 - Safety & Disconnect Switches | Procurement.ElecEng.23 | Rev/Apprv. Product Submittals - Switch Enclosures | 10 | 0 | 100% | 2020-09-09 | 2020-12-01 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.23 | 0 | 262816 | 01025 | 0 | 0 | 262816-01025 | Procurement | 26 28 16 - Safety & Disconnect Switches | Procurement.ElecEng.23 | Fabricate - Fused Disconnect Switches | 40 | 0 | 100% | 2021-06-25 08:00 | 2022-04-15 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.23 | 0 | 262816 | 01030 | 0 | 0 | 262816-01030 | Procurement | 26 28 16 - Safety & Disconnect Switches | Procurement.ElecEng.23 | Deliver - Fused Disconnect Switches | 5 | 0 | 100% | 2022-04-18 | 2022-04-20 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.24 | 0 | 263213 | 01005 | 0 | 0 | 263213-01005 | Procurement | 26 32 13 - Natural Gas Generators | Procurement.ElecEng.24 | Prep/Submit Product Submittals - Generator (450 Kw) | 40 | 0 | 100% | 2020-07-13 | 2020-08-04 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.24 | 0 | 263213 | 01010 | 0 | 0 | 263213-01010 | Procurement | 26 32 13 - Natural Gas Generators | Procurement.ElecEng.24 | Rev/Apprv. Product Submittals - Generator (450 Kw) | 10 | 0 | 100% | 2020-08-05 | 2020-11-19 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.24 | 0 | 263213 | 01015 | 0 | 0 | 263213-01015 | Procurement | 26 32 13 - Natural Gas Generators | Procurement.ElecEng.24 | Prep/Submit Product Submittals - Acoustic Generator Enclosure | 40 | 0 | 100% | 2020-07-13 | 2020-09-02 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.24 | 0 | 263213 | 01020 | 0 | 0 | 263213-01020 | Procurement | 26 32 13 - Natural Gas Generators | Procurement.ElecEng.24 | Rev/Apprv. Product Submittals - Acoustic Generator Enclosure | 10 | 0 | 100% | 2020-09-03 | 2020-11-19 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.24 | 0 | 263213 | 01025 | 0 | 0 | 263213-01025 | Procurement | 26 32 13 - Natural Gas Generators | Procurement.ElecEng.24 | Prep/Submit Product Submittals - Generator (350 Kw) | 40 | 0 | 100% | 2020-07-13 | 2020-08-04 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.24 | 0 | 263213 | 01030 | 0 | 0 | 263213-01030 | Procurement | 26 32 13 - Natural Gas Generators | Procurement.ElecEng.24 | Rev/Apprv. Product Submittals - Generator (350 Kw) | 10 | 0 | 100% | 2020-08-05 | 2020-11-19 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.24 | 0 | 263213 | 01035 | 0 | 0 | 263213-01035 | Procurement | 26 32 13 - Natural Gas Generators | Procurement.ElecEng.24 | Prep/Submit Product Submittals - Generator (500 Kw) | 40 | 0 | 100% | 2020-07-13 | 2020-08-04 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.24 | 0 | 263213 | 01040 | 0 | 0 | 263213-01040 | Procurement | 26 32 13 - Natural Gas Generators | Procurement.ElecEng.24 | Rev/Apprv. Product Submittals - Generator (500 Kw) | 10 | 0 | 100% | 2020-08-05 | 2020-11-19 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.24 | 0 | 263213 | 01045 | 0 | 0 | 263213-01045 | Procurement | 26 32 13 - Natural Gas Generators | Procurement.ElecEng.24 | Prep/Submit Product Submittals - Generator (400 Kw) | 40 | 0 | 100% | 2020-07-13 | 2020-08-04 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.24 | 0 | 263213 | 01050 | 0 | 0 | 263213-01050 | Procurement | 26 32 13 - Natural Gas Generators | Procurement.ElecEng.24 | Rev/Apprv. Product Submittals - Generator (400 Kw) | 10 | 0 | 100% | 2020-08-04 | 2020-11-19 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.21 | 0 | 263623 | 01005 | 0 | 0 | 263623-01005 | Procurement | 26 36 23 - Automatic Closed Transition Transfer Switches (ATS, ACTTS, CTTS) | Procurement.ElecEng.21 | Prep/Submit Product Submittals - ACTTS (200A) | 30 | 0 | 100% | 2020-08-24 | 2020-09-16 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.21 | 0 | 263623 | 01010 | 0 | 0 | 263623-01010 | Procurement | 26 36 23 - Automatic Closed Transition Transfer Switches (ATS, ACTTS, CTTS) | Procurement.ElecEng.21 | Rev/Apprv. Product Submittals - ACTTS (200A) | 10 | 0 | 100% | 2020-09-17 | 2020-12-21 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.21 | 0 | 263623 | 01015 | 0 | 0 | 263623-01015 | Procurement | 26 36 23 - Automatic Closed Transition Transfer Switches (ATS, ACTTS, CTTS) | Procurement.ElecEng.21 | Prep/Submit Product Submittals - ACTTS (400A) | 30 | 0 | 100% | 2020-08-24 | 2020-09-16 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.21 | 0 | 263623 | 01020 | 0 | 0 | 263623-01020 | Procurement | 26 36 23 - Automatic Closed Transition Transfer Switches (ATS, ACTTS, CTTS) | Procurement.ElecEng.21 | Rev/Apprv. Product Submittals - ACTTS (400A) | 10 | 0 | 100% | 2020-09-17 | 2020-12-21 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.21 | 0 | 263623 | 01025 | 0 | 0 | 263623-01025 | Procurement | 26 36 23 - Automatic Closed Transition Transfer Switches (ATS, ACTTS, CTTS) | Procurement.ElecEng.21 | Prep/Submit Product Submittals - ACTTS (600A) | 30 | 0 | 100% | 2020-08-24 | 2020-09-16 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.21 | 0 | 263623 | 01030 | 0 | 0 | 263623-01030 | Procurement | 26 36 23 - Automatic Closed Transition Transfer Switches (ATS, ACTTS, CTTS) | Procurement.ElecEng.21 | Rev/Apprv. Product Submittals - ACTTS (600A) | 10 | 0 | 100% | 2020-09-17 | 2020-12-21 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.21 | 0 | 263623 | 01035 | 0 | 0 | 263623-01035 | Procurement | 26 36 23 - Automatic Closed Transition Transfer Switches (ATS, ACTTS, CTTS) | Procurement.ElecEng.21 | Prep/Submit Product Submittals - ACTTS (800A) | 30 | 0 | 100% | 2020-08-24 | 2020-09-16 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.21 | 0 | 263623 | 01040 | 0 | 0 | 263623-01040 | Procurement | 26 36 23 - Automatic Closed Transition Transfer Switches (ATS, ACTTS, CTTS) | Procurement.ElecEng.21 | Rev/Apprv. Product Submittals - ACTTS (800A) | 10 | 0 | 100% | 2020-09-17 | 2020-12-21 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.21 | 0 | 263623 | 01045 | 0 | 0 | 263623-01045 | Procurement | 26 36 23 - Automatic Closed Transition Transfer Switches (ATS, ACTTS, CTTS) | Procurement.ElecEng.21 | Prep/Submit Product Submittals - ACTTS (1000A) | 30 | 0 | 100% | 2020-08-24 | 2020-09-16 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.21 | 0 | 263623 | 01050 | 0 | 0 | 263623-01050 | Procurement | 26 36 23 - Automatic Closed Transition Transfer Switches (ATS, ACTTS, CTTS) | Procurement.ElecEng.21 | Rev/Apprv. Product Submittals - ACTTS (1000A) | 10 | 0 | 100% | 2020-08-17 | 2020-12-21 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.14 | 0 | 220533 | 01005 | 0 | 0 | 220533-01005 | Procurement | 22 05 33 - Heat Tracing | Procurement.ElecEng.14 | Prep/Submit Product Submittals - Heating Cables | 30 | 0 | 100% | 2020-07-28 | 2020-08-28 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.14 | 0 | 220533 | 01010 | 0 | 0 | 220533-01010 | Procurement | 22 05 33 - Heat Tracing | Procurement.ElecEng.14 | Rev/Apprv. Product Submittals - Heating Cables | 10 | 0 | 100% | 2020-08-31 | 2020-11-04 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.14 | 0 | 220533 | 01015 | 0 | 0 | 220533-01015 | Procurement | 22 05 33 - Heat Tracing | Procurement.ElecEng.14 | Prep/Submit Product Submittals - Temperature Sensors | 30 | 0 | 100% | 2020-07-28 | 2020-08-28 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.14 | 0 | 220533 | 01020 | 0 | 0 | 220533-01020 | Procurement | 22 05 33 - Heat Tracing | Procurement.ElecEng.14 | Rev/Apprv. Product Submittals - Temperature Sensors | 10 | 0 | 100% | 2020-08-31 | 2020-11-04 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.14 | 0 | 220533 | 01025 | 0 | 0 | 220533-01025 | Procurement | 22 05 33 - Heat Tracing | Procurement.ElecEng.14 | Prep/Submit Product Submittals - Heat Trace Controls | 30 | 0 | 100% | 2020-07-28 | 2020-08-28 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.14 | 0 | 220533 | 01030 | 0 | 0 | 220533-01030 | Procurement | 22 05 33 - Heat Tracing | Procurement.ElecEng.14 | Rev/Apprv. Product Submittals - Heat Trace Controls | 10 | 0 | 100% | 2020-08-31 | 2020-11-04 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.14 | 0 | 220533 | 01035 | 0 | 0 | 220533-01035 | Procurement | 22 05 33 - Heat Tracing | Procurement.ElecEng.14 | Fabricate & Deliver Equipment - Heat Tracing - N/A | 75 | 0 | 100% | 2021-06-15 | 2022-09-01 15:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.26 | 0 | 262726 | 01005 | 0 | 0 | 262726-01005 | Procurement | 26 27 26 - Wiring & Installation Devices | Procurement.ElecEng.26 | Prep/Submit Product Submittals - Switches & Receptacles | 20 | 0 | 100% | 2020-04-15 | 2020-06-09 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.26 | 0 | 262726 | 01010 | 0 | 0 | 262726-01010 | Procurement | 26 27 26 - Wiring & Installation Devices | Procurement.ElecEng.26 | Rev/Apprv. Product Submittals - Switches & Receptacles | 10 | 0 | 100% | 2020-06-10 | 2020-11-16 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.26 | 0 | 262726 | 01015 | 0 | 0 | 262726-01015 | Procurement | 26 27 26 - Wiring & Installation Devices | Procurement.ElecEng.26 | Fabricate & Deliver Equipment - Switches & Receptacles | 25 | 0 | 100% | 2022-04-15 | 2022-09-02 17:00 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.1 | OG1 | 262413 | 01315 | 0 | 0 | 262413-01315 | Procurement | O'Dwyer Gardens East (OG-1, OG-5, OG-6 & OG-10) | Procurement.ElecEng.27.1 | Prep/Submit Product Submittals - OG1 Switchboard (MSSB-OG-1) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.1 | OG1 | 262413 | 01320 | 0 | 0 | 262413-01320 | Procurement | O'Dwyer Gardens East (OG-1, OG-5, OG-6 & OG-10) | Procurement.ElecEng.27.1 | Rev/Apprv. Product Submittals - OG1 Switchboard (MSSB-OG-1) | 10 | 0 | 100% | 2021-02-24 | 2021-11-12 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.1 | OG1 | 262413 | 01325 | 0 | 0 | 262413-01325 | Procurement | O'Dwyer Gardens East (OG-1, OG-5, OG-6 & OG-10) | Procurement.ElecEng.27.1 | Prep/Submit Product Submittals - OG10 Switchboard (DB-OG-10) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.1 | OG1 | 262413 | 01330 | 0 | 0 | 262413-01330 | Procurement | O'Dwyer Gardens East (OG-1, OG-5, OG-6 & OG-10) | Procurement.ElecEng.27.1 | Rev/Apprv. Product Submittals - OG10 Switchboard (DB-OG-10) | 10 | 0 | 100% | 2021-02-24 | 2021-11-15 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.1 | OG1 | 262413 | 01305 | 0 | 0 | 262413-01305 | Procurement | O'Dwyer Gardens East (OG-1, OG-5, OG-6 & OG-10) | Procurement.ElecEng.27.1 | Prep/Submit Product Submittals - OG1 Switchboard (ESB) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.1 | OG1 | 262413 | 01310 | 0 | 0 | 262413-01310 | Procurement | O'Dwyer Gardens East (OG-1, OG-5, OG-6 & OG-10) | Procurement.ElecEng.27.1 | Rev/Apprv. Product Submittals - OG1 Switchboard (ESB) | 10 | 0 | 100% | 2021-02-24 | 2021-11-15 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.1 | OG6 | 262413 | 01365 | 0 | 0 | 262413-01365 | Procurement | O'Dwyer Gardens East (OG-1, OG-5, OG-6 & OG-10) | Procurement.ElecEng.27.1 | Prep/Submit Product Submittals - OG6 Switchboard (MSSB-OG-6) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.1 | OG6 | 262413 | 01370 | 0 | 0 | 262413-01370 | Procurement | O'Dwyer Gardens East (OG-1, OG-5, OG-6 & OG-10) | Procurement.ElecEng.27.1 | Rev/Apprv. Product Submittals - OG6 Switchboard (MSSB-OG-6) | 10 | 0 | 100% | 2021-02-24 | 2021-11-15 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.1 | OG6 | 262413 | 01355 | 0 | 0 | 262413-01355 | Procurement | O'Dwyer Gardens East (OG-1, OG-5, OG-6 & OG-10) | Procurement.ElecEng.27.1 | Prep/Submit Product Submittals - OG6 Switchboard (ESB) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.1 | OG6 | 262413 | 01360 | 0 | 0 | 262413-01360 | Procurement | O'Dwyer Gardens East (OG-1, OG-5, OG-6 & OG-10) | Procurement.ElecEng.27.1 | Rev/Apprv. Product Submittals - OG6 Switchboard (ESB) | 10 | 0 | 100% | 2021-02-24 | 2021-11-15 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.1 | OG5 | 262413 | 01345 | 0 | 0 | 262413-01345 | Procurement | O'Dwyer Gardens East (OG-1, OG-5, OG-6 & OG-10) | Procurement.ElecEng.27.1 | Prep/Submit Product Submittals - OG5 Switchboard (MSSB-OG-5) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.1 | OG5 | 262413 | 01350 | 0 | 0 | 262413-01350 | Procurement | O'Dwyer Gardens East (OG-1, OG-5, OG-6 & OG-10) | Procurement.ElecEng.27.1 | Rev/Apprv. Product Submittals - OG5 Switchboard (MSSB-OG-5) | 10 | 0 | 100% | 2021-02-24 | 2021-07-08 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.1 | OG5 | 262413 | 01335 | 0 | 0 | 262413-01335 | Procurement | O'Dwyer Gardens East (OG-1, OG-5, OG-6 & OG-10) | Procurement.ElecEng.27.1 | Prep/Submit Product Submittals - OG5 Switchboard (ESB) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.1 | OG5 | 262413 | 01340 | 0 | 0 | 262413-01340 | Procurement | O'Dwyer Gardens East (OG-1, OG-5, OG-6 & OG-10) | Procurement.ElecEng.27.1 | Rev/Apprv. Product Submittals - OG5 Switchboard (ESB) | 10 | 0 | 100% | 2021-02-24 | 2021-07-08 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.2 | OG2 | 262413 | 01115 | 0 | 0 | 262413-01115 | Procurement | O'Dwyer Gardens West (OG-2, OG-3, OG-4, OG-8 & OG-9) | Procurement.ElecEng.27.2 | Prep/Submit Product Submittals - OG2 Switchboard (MSSB-OG-2) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.2 | OG2 | 262413 | 01120 | 0 | 0 | 262413-01120 | Procurement | O'Dwyer Gardens West (OG-2, OG-3, OG-4, OG-8 & OG-9) | Procurement.ElecEng.27.2 | Rev/Apprv. Product Submittals - OG2 Switchboard (MSSB) | 10 | 0 | 100% | 2021-02-24 | 2021-03-08 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.2 | OG2 | 262413 | 01105 | 0 | 0 | 262413-01105 | Procurement | O'Dwyer Gardens West (OG-2, OG-3, OG-4, OG-8 & OG-9) | Procurement.ElecEng.27.2 | Prep/Submit Product Submittals - OG2 Switchboard (ESB) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.2 | OG2 | 262413 | 01110 | 0 | 0 | 262413-01110 | Procurement | O'Dwyer Gardens West (OG-2, OG-3, OG-4, OG-8 & OG-9) | Procurement.ElecEng.27.2 | Rev/Apprv. Product Submittals - OG2 Switchboard (ESB) | 10 | 0 | 100% | 2021-02-24 | 2021-03-08 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.2 | OG9 | 262413 | 01195 | 0 | 0 | 262413-01195 | Procurement | O'Dwyer Gardens West (OG-2, OG-3, OG-4, OG-8 & OG-9) | Procurement.ElecEng.27.2 | Prep/Submit Product Submittals - OG9 Switchboard (ESB-OG-2) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.2 | OG9 | 262413 | 01200 | 0 | 0 | 262413-01200 | Procurement | O'Dwyer Gardens West (OG-2, OG-3, OG-4, OG-8 & OG-9) | Procurement.ElecEng.27.2 | Rev/Apprv. Product Submittals - OG9 Switchboard (ESB-OG-2) | 10 | 0 | 100% | 2021-02-24 | 2021-04-01 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.2 | OG9 | 262413 | 01185 | 0 | 0 | 262413-01185 | Procurement | O'Dwyer Gardens West (OG-2, OG-3, OG-4, OG-8 & OG-9) | Procurement.ElecEng.27.2 | Prep/Submit Product Submittals - OG9 Switchboard (DB-OG-9) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.2 | OG9 | 262413 | 01190 | 0 | 0 | 262413-01190 | Procurement | O'Dwyer Gardens West (OG-2, OG-3, OG-4, OG-8 & OG-9) | Procurement.ElecEng.27.2 | Rev/Apprv. Product Submittals - OG9 Switchboard (DB-OG-9) | 10 | 0 | 100% | 2021-02-24 | 2021-04-01 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.2 | OG3 | 262413 | 01135 | 0 | 0 | 262413-01135 | Procurement | O'Dwyer Gardens West (OG-2, OG-3, OG-4, OG-8 & OG-9) | Procurement.ElecEng.27.2 | Prep/Submit Product Submittals - OG3 Switchboard (MSSB-OG-3) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.2 | OG3 | 262413 | 01140 | 0 | 0 | 262413-01140 | Procurement | O'Dwyer Gardens West (OG-2, OG-3, OG-4, OG-8 & OG-9) | Procurement.ElecEng.27.2 | Rev/Apprv. Product Submittals - OG3 Switchboard (MSSB-OG-3) | 10 | 0 | 100% | 2021-02-24 | 2021-03-08 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.2 | OG3 | 262413 | 01125 | 0 | 0 | 262413-01125 | Procurement | O'Dwyer Gardens West (OG-2, OG-3, OG-4, OG-8 & OG-9) | Procurement.ElecEng.27.2 | Prep/Submit Product Submittals - OG3 Switchboard (ESB) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.2 | OG3 | 262413 | 01130 | 0 | 0 | 262413-01130 | Procurement | O'Dwyer Gardens West (OG-2, OG-3, OG-4, OG-8 & OG-9) | Procurement.ElecEng.27.2 | Rev/Apprv. Product Submittals - OG3 Switchboard (ESB) | 10 | 0 | 100% | 2021-02-24 | 2021-03-08 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.2 | OG4 | 262413 | 01165 | 0 | 0 | 262413-01165 | Procurement | O'Dwyer Gardens West (OG-2, OG-3, OG-4, OG-8 & OG-9) | Procurement.ElecEng.27.2 | Prep/Submit Product Submittals - OG4 Switchboard (MSSB-OG-4) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.2 | OG4 | 262413 | 01170 | 0 | 0 | 262413-01170 | Procurement | O'Dwyer Gardens West (OG-2, OG-3, OG-4, OG-8 & OG-9) | Procurement.ElecEng.27.2 | Rev/Apprv. Product Submittals - OG4 Switchboard (MSSB-OG-4) | 10 | 0 | 100% | 2021-02-24 | 2021-07-15 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.2 | OG4 | 262413 | 01145 | 0 | 0 | 262413-01145 | Procurement | O'Dwyer Gardens West (OG-2, OG-3, OG-4, OG-8 & OG-9) | Procurement.ElecEng.27.2 | Prep/Submit Product Submittals - OG4 Switchboard (ESB) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.2 | OG4 | 262413 | 01150 | 0 | 0 | 262413-01150 | Procurement | O'Dwyer Gardens West (OG-2, OG-3, OG-4, OG-8 & OG-9) | Procurement.ElecEng.27.2 | Rev/Apprv. Product Submittals - OG4 Switchboard (ESB) | 10 | 0 | 100% | 2021-02-24 | 2021-07-15 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.2 | OG4 | 262413 | 01155 | 0 | 0 | 262413-01155 | Procurement | O'Dwyer Gardens West (OG-2, OG-3, OG-4, OG-8 & OG-9) | Procurement.ElecEng.27.2 | Prep/Submit Product Submittals - OG4 Switchboard (ESB-G) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.2 | OG4 | 262413 | 01160 | 0 | 0 | 262413-01160 | Procurement | O'Dwyer Gardens West (OG-2, OG-3, OG-4, OG-8 & OG-9) | Procurement.ElecEng.27.2 | Rev/Apprv. Product Submittals - OG4 Switchboard (ESB-G) | 10 | 0 | 100% | 2021-02-24 | 2021-07-15 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.2 | OG8 | 262413 | 01175 | 0 | 0 | 262413-01175 | Procurement | O'Dwyer Gardens West (OG-2, OG-3, OG-4, OG-8 & OG-9) | Procurement.ElecEng.27.2 | Prep/Submit Product Submittals - OG8 Switchboard (DB-OG-8) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.2 | OG8 | 262413 | 01180 | 0 | 0 | 262413-01180 | Procurement | O'Dwyer Gardens West (OG-2, OG-3, OG-4, OG-8 & OG-9) | Procurement.ElecEng.27.2 | Rev/Apprv. Product Submittals - OG8 Switchboard (DB-OG-8) | 10 | 0 | 100% | 2021-02-24 | 2021-07-15 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.3 | SG1 | 262413 | 01445 | 0 | 0 | 262413-01445 | Procurement | Surfside Gardens South (SG-1, SG-2, SG-3 & SG-7) | Procurement.ElecEng.27.3 | Prep/Submit Product Submittals - SG1 Switchboard (MSSB-SG-1) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.3 | SG1 | 262413 | 01450 | 0 | 0 | 262413-01450 | Procurement | Surfside Gardens South (SG-1, SG-2, SG-3 & SG-7) | Procurement.ElecEng.27.3 | Rev/Apprv. Product Submittals - SG1 Switchboard (MSSB-SG-1) | 10 | 0 | 100% | 2021-02-24 | 2022-05-12 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.3 | SG1 | 262413 | 01425 | 0 | 0 | 262413-01425 | Procurement | Surfside Gardens South (SG-1, SG-2, SG-3 & SG-7) | Procurement.ElecEng.27.3 | Prep/Submit Product Submittals - SG1 Switchboard (ESB) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.3 | SG1 | 262413 | 01430 | 0 | 0 | 262413-01430 | Procurement | Surfside Gardens South (SG-1, SG-2, SG-3 & SG-7) | Procurement.ElecEng.27.3 | Rev/Apprv. Product Submittals - SG1 Switchboard (ESB) | 10 | 0 | 100% | 2021-02-24 | 2022-05-12 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.3 | SG2 | 262413 | 01455 | 0 | 0 | 262413-01455 | Procurement | Surfside Gardens South (SG-1, SG-2, SG-3 & SG-7) | Procurement.ElecEng.27.3 | Prep/Submit Product Submittals - SG2 Switchboard (MSSB-SG-2) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.3 | SG2 | 262413 | 01460 | 0 | 0 | 262413-01460 | Procurement | Surfside Gardens South (SG-1, SG-2, SG-3 & SG-7) | Procurement.ElecEng.27.3 | Rev/Apprv. Product Submittals - SG2 Switchboard (MSSB-SG-2) | 10 | 0 | 100% | 2021-02-24 | 2022-05-12 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.3 | SG2 | 262413 | 01435 | 0 | 0 | 262413-01435 | Procurement | Surfside Gardens South (SG-1, SG-2, SG-3 & SG-7) | Procurement.ElecEng.27.3 | Prep/Submit Product Submittals - SG2 Switchboard (ESB-SG-2) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.3 | SG2 | 262413 | 01440 | 0 | 0 | 262413-01440 | Procurement | Surfside Gardens South (SG-1, SG-2, SG-3 & SG-7) | Procurement.ElecEng.27.3 | Rev/Apprv. Product Submittals - SG2 Switchboard (ESB-SG-2) | 10 | 0 | 100% | 2021-02-24 | 2022-05-12 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.3 | SG3 | 262413 | 01415 | 0 | 0 | 262413-01415 | Procurement | Surfside Gardens South (SG-1, SG-2, SG-3 & SG-7) | Procurement.ElecEng.27.3 | Prep/Submit Product Submittals - SG3 Switchboard (MSSB-SG-3) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.3 | SG3 | 262413 | 01420 | 0 | 0 | 262413-01420 | Procurement | Surfside Gardens South (SG-1, SG-2, SG-3 & SG-7) | Procurement.ElecEng.27.3 | Rev/Apprv. Product Submittals - SG3 Switchboard (MSSB-SG-3) | 10 | 0 | 100% | 2021-02-24 | 2022-05-12 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.3 | SG3 | 262413 | 01405 | 0 | 0 | 262413-01405 | Procurement | Surfside Gardens South (SG-1, SG-2, SG-3 & SG-7) | Procurement.ElecEng.27.3 | Prep/Submit Product Submittals - SG3 Switchboard (ESB) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.3 | SG3 | 262413 | 01410 | 0 | 0 | 262413-01410 | Procurement | Surfside Gardens South (SG-1, SG-2, SG-3 & SG-7) | Procurement.ElecEng.27.3 | Rev/Apprv. Product Submittals - SG3 Switchboard (ESB) | 10 | 0 | 100% | 2021-02-24 | 2022-05-12 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.4 | SG4 | 262413 | 01015 | 0 | 0 | 262413-01015 | Procurement | Surfside Gardens North (SG-4, SG-5 & SG-6) | Procurement.ElecEng.27.4 | Prep/Submit Product Submittals - SG4 Switchboard (MSSB-SG-4) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.4 | SG4 | 262413 | 01020 | 0 | 0 | 262413-01020 | Procurement | Surfside Gardens North (SG-4, SG-5 & SG-6) | Procurement.ElecEng.27.4 | Rev/Apprv. Product Submittals - SG4 Switchboard (MSSB-SG-4) | 10 | 0 | 100% | 2021-02-24 | 2021-04-02 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.4 | SG4 | 262413 | 01005 | 0 | 0 | 262413-01005 | Procurement | Surfside Gardens North (SG-4, SG-5 & SG-6) | Procurement.ElecEng.27.4 | Prep/Submit Product Submittals - SG4 Switchboard (ESB) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.4 | SG4 | 262413 | 01010 | 0 | 0 | 262413-01010 | Procurement | Surfside Gardens North (SG-4, SG-5 & SG-6) | Procurement.ElecEng.27.4 | Rev/Apprv. Product Submittals - SG4 Switchboard (ESB) | 10 | 0 | 100% | 2021-02-24 | 2021-04-02 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.4 | SG5 | 262413 | 01035 | 0 | 0 | 262413-01035 | Procurement | Surfside Gardens North (SG-4, SG-5 & SG-6) | Procurement.ElecEng.27.4 | Prep/Submit Product Submittals - SG5 Switchboard (MSSB-SG-5) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.4 | SG5 | 262413 | 01040 | 0 | 0 | 262413-01040 | Procurement | Surfside Gardens North (SG-4, SG-5 & SG-6) | Procurement.ElecEng.27.4 | Rev/Apprv. Product Submittals - SG5 Switchboard (MSSB-SG-5) | 10 | 0 | 100% | 2021-02-24 | 2021-04-02 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.4 | SG5 | 262413 | 01025 | 0 | 0 | 262413-01025 | Procurement | Surfside Gardens North (SG-4, SG-5 & SG-6) | Procurement.ElecEng.27.4 | Prep/Submit Product Submittals - SG5 Switchboard (ESB) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.4 | SG5 | 262413 | 01030 | 0 | 0 | 262413-01030 | Procurement | Surfside Gardens North (SG-4, SG-5 & SG-6) | Procurement.ElecEng.27.4 | Rev/Apprv. Product Submittals - SG5 Switchboard (ESB) | 10 | 0 | 100% | 2021-02-24 | 2021-04-02 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.4 | SG6 | 262413 | 01045 | 0 | 0 | 262413-01045 | Procurement | Surfside Gardens North (SG-4, SG-5 & SG-6) | Procurement.ElecEng.27.4 | Prep/Submit Product Submittals - SG6 Switchboard (DB-SG-6) | 20 | 0 | 100% | 2020-11-02 | 2021-02-23 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.4 | SG6 | 262413 | 01050 | 0 | 0 | 262413-01050 | Procurement | Surfside Gardens North (SG-4, SG-5 & SG-6) | Procurement.ElecEng.27.4 | Rev/Apprv. Product Submittals - SG6 Switchboard (DB-SG-6) | 10 | 0 | 100% | 2021-02-24 | 2021-04-02 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.5 | S81 | 262413 | 01515 | 0 | 0 | 262413-01515 | Procurement | Site 8 (S8 & S8-1) | Procurement.ElecEng.27.5 | Prep/Submit Product Submittals - S8-1 Switchboard (MSSB) (Resubmittal) | 20 | 0 | 100% | 2020-11-02 | 2021-06-21 |  | 0 | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.5 | S81 | 262413 | 01520 | 0 | 0 | 262413-01520 | Procurement | Site 8 (S8 & S8-1) | Procurement.ElecEng.27.5 | Rev/Apprv. Product Submittals - S8-1 Switchboard (MSSB) | 10 | 0 | 100% | 2021-02-24 | 2021-07-13 |  | 0 | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.5 | S81 | 262413 | 01505 | 0 | 0 | 262413-01505 | Procurement | Site 8 (S8 & S8-1) | Procurement.ElecEng.27.5 | Prep/Submit Product Submittals - S8-1 Switchboard (ESB) (Resubmittal) | 20 | 0 | 100% | 2020-11-02 | 2021-06-21 |  | 0 | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Procurement.ElecEng.27.5 | S81 | 262413 | 01510 | 0 | 0 | 262413-01510 | Procurement | Site 8 (S8 & S8-1) | Procurement.ElecEng.27.5 | Rev/Apprv. Product Submittals - S8-1 Switchboard (ESB) | 10 | 0 | 100% | 2021-02-24 | 2021-07-13 |  | 0 | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.1 | SG4 | P | SG4 | 01010 | 0 | P-SG4-01010 | Procurement | Procurement | Procurement.ElecEng.1.2.8.1 | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 100% | 2021-04-06 | 2021-08-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.1 | SG4 | P | SG4 | 01015 | 0 | P-SG4-01015 | Procurement | Procurement | Procurement.ElecEng.1.2.8.1 | Deliver - Switchboards | 5 | 0 | 100% | 2021-08-26 08:00 | 2021-08-31 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.1 | SG4 | P | SG4 | 01005 | 0 | P-SG4-01005 | Procurement | Procurement | Procurement.ElecEng.1.2.8.1 | Release for Fabrication - Switchboards | 0 | 0 | 100% | 2021-04-05 |  |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.1 | SG4 | P | SG4 | 01090 | 0 | P-SG4-01090 | Procurement | Procurement | Procurement.ElecEng.1.2.8.1 | Fabricate - Panelboards | 30 | 0 | 100% | 2021-05-06 | 2021-07-12 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.1 | SG4 | P | SG4 | 01100 | 0 | P-SG4-01100 | Procurement | Procurement | Procurement.ElecEng.1.2.8.1 | Deliver - Panelboards | 5 | 0 | 100% | 2021-07-13 | 2021-07-16 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.1 | SG4 | P | SG4 | 01030 | 0 | P-SG4-01030 | Procurement | Procurement | Procurement.ElecEng.1.2.8.1 | Fabricate - ACTTS | 80 | 0 | 100% | 2021-04-06 | 2021-08-13 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.1 | SG4 | P | SG4 | 01070 | 0 | P-SG4-01070 | Procurement | Procurement | Procurement.ElecEng.1.2.8.1 | Deliver - ACTTS | 5 | 0 | 100% | 2021-08-16 | 2021-08-17 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.1 | SG4 | P | SG4 | 01020 | 0 | P-SG4-01020 | Procurement | Procurement | Procurement.ElecEng.1.2.8.1 | Release for Fabrication - ACTTS | 0 | 0 | 100% | 2021-04-05 |  |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.1 | SG4 | P | SG4 | 1105 | 0 | P-SG4-1105 | Procurement | Procurement | Procurement.ElecEng.1.2.8.1 | Fabricate & Deliver - Smoke Detection Equipment | 75 | 0 | 100% | 2021-07-06 | 2022-08-15 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.1 | SG4 | P | SG4 | 1120 | 0 | P-SG4-1120 | Procurement | Procurement | Procurement.ElecEng.1.2.8.1 | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 0 | 100% | 2022-03-25 08:00 | 2022-10-24 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.1 | SG4 | P | SG4 | 1130 | 0 | P-SG4-1130 | Procurement | Procurement | Procurement.ElecEng.1.2.8.1 | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 100% | 2021-10-28 | 2021-12-15 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.7 | SG4 | E | SG4 | 01070 | 0 | E-SG4-01070 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.8.7 | Prep/Submit Engineering Dwgs. - Cellar Lighting Controls | 60 | 0 | 100% | 2021-05-10 | 2021-12-07 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.7 | SG4 | E | SG4 | 01075 | 0 | E-SG4-01075 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.8.7 | Rev/Apprv. Engineering Dwgs. - Cellar Lighting Controls | 10 | 0 | 100% | 2021-12-08 | 2021-12-28 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.7 | SG4 | E | SG4 | 01080 | 0 | E-SG4-01080 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.8.7 | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 100% | 2021-05-10 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.7 | SG4 | E | SG4 | 01150 | 0 | E-SG4-01150 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.8.7 | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 100% | 2022-02-15 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.7 | SG4 | E | SG4 | 01160 | 0 | E-SG4-01160 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.8.7 | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 100% | 2021-02-01 | 2021-03-12 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.7 | SG4 | E | SG4 | 01170 | 0 | E-SG4-01170 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.8.7 | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 100% | 2021-03-15 | 2021-04-07 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.7 | SG4 | E | SG4 | 01020 | 0 | E-SG4-01020 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.8.7 | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 100% | 2020-11-02 | 2021-06-02 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.7 | SG4 | E | SG4 | 01025 | 0 | E-SG4-01025 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.8.7 | Rev/Apprv. Engineering Dwgs. - Electrical Service (NYCHA Approval Only) | 10 | 0 | 100% | 2021-06-03 | 2021-06-21 |  | 0 | 0 | 0 | 0 | 0-SG4
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.7 | SG4 | E | SG4 | 01000 | 0 | E-SG4-01000 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.8.7 | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 5 | 87% | 2021-05-10 | 2022-12-01 17:00 | 77 | FSE | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.7 | SG4 | E | SG4 | 01005 | 0 | E-SG4-01005 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.8.7 | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 0% | 2022-12-02 08:00 | 2022-12-15 17:00 | 77 | FSE | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.7 | SG4 | E | SG4 | 01010 | 0 | E-SG4-01010 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.8.7 | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 100% | 2020-08-03 | 2020-09-14 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.7 | SG4 | E | SG4 | 01015 | 0 | E-SG4-01015 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.8.7 | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 100% | 2020-08-15 | 2020-10-30 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.7 | SG4 | E | SG4 | 01050 | 0 | E-SG4-01050 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.8.7 | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 100% | 2020-12-10 | 2021-01-05 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.7 | SG4 | E | SG4 | 01055 | 0 | E-SG4-01055 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.8.7 | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 100% | 2021-01-06 | 2021-02-22 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.7 | SG4 | E | SG4 | 01030 | 0 | E-SG4-01030 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.8.7 | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 100% | 2021-05-21 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.7 | SG4 | E | SG4 | 01035 | 0 | E-SG4-01035 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.8.7 | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.7 | SG4 | E | SG4 | 01060 | 0 | E-SG4-01060 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.8.7 | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 100% | 2020-09-08 | 2020-10-27 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.8.7 | SG4 | E | SG4 | 01065 | 0 | E-SG4-01065 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.8.7 | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 100% | 2020-10-27 | 2020-11-03 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.1 | SG5 | P | SG5 | 01010 | 0 | P-SG5-01010 | Procurement | Procurement | Procurement.ElecEng.1.2.1.1 | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 100% | 2021-06-08 | 2021-10-08 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.1 | SG5 | P | SG5 | 01015 | 0 | P-SG5-01015 | Procurement | Procurement | Procurement.ElecEng.1.2.1.1 | Deliver - Switchboards | 5 | 0 | 100% | 2021-10-04 08:00 | 2021-10-15 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.1 | SG5 | P | SG5 | 01005 | 0 | P-SG5-01005 | Procurement | Procurement | Procurement.ElecEng.1.2.1.1 | Release for Fabrication - Switchboards | 0 | 0 | 100% | 2021-06-07 |  |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.1 | SG5 | P | SG5 | 01030 | 0 | P-SG5-01030 | Procurement | Procurement | Procurement.ElecEng.1.2.1.1 | Fabricate - ACTTS | 80 | 0 | 100% | 2021-07-06 | 2022-01-31 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.1 | SG5 | P | SG5 | 01035 | 0 | P-SG5-01035 | Procurement | Procurement | Procurement.ElecEng.1.2.1.1 | Deliver - ACTTS | 5 | 0 | 100% | 2022-02-01 | 2022-02-07 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.1 | SG5 | P | SG5 | 01025 | 0 | P-SG5-01025 | Procurement | Procurement | Procurement.ElecEng.1.2.1.1 | Release for Fabrication - ACTTS | 0 | 0 | 100% | 2021-07-05 |  |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.1 | SG5 | P | SG5 | 01060 | 0 | P-SG5-01060 | Procurement | Procurement | Procurement.ElecEng.1.2.1.1 | Fabricate - Panelboards | 30 | 0 | 100% | 2021-06-07 | 2021-08-20 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.1 | SG5 | P | SG5 | 01100 | 0 | P-SG5-01100 | Procurement | Procurement | Procurement.ElecEng.1.2.1.1 | Deliver - Panelboards | 5 | 0 | 100% | 2021-08-23 08:00 | 2021-08-24 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.1 | SG5 | P | SG5 | 01105 | 0 | P-SG5-01105 | Procurement | Procurement | Procurement.ElecEng.1.2.1.1 | Fabricate & Deliver - Smoke Detection Equipment | 75 | 0 | 100% | 2021-07-06 | 2022-10-24 |  | 0 | 0 | 0 | 0 | 0-SG5
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.1 | SG5 | P | SG5 | 01110 | 0 | P-SG5-01110 | Procurement | Procurement | Procurement.ElecEng.1.2.1.1 | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 46% | 2022-01-25 | 2022-12-06 17:00 | -33 | FSE | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.1 | SG5 | P | SG5 | 01120 | 0 | P-SG5-01120 | Procurement | Procurement | Procurement.ElecEng.1.2.1.1 | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 100% | 2021-10-28 | 2021-12-15 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.7 | SG5 | E | SG5 | 01070 | 0 | E-SG5-01070 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.1.7 | Prep/Submit Engineering Dwgs. - Cellar Lighting Controls | 60 | 0 | 100% | 2022-01-03 | 2022-02-15 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.7 | SG5 | E | SG5 | 01075 | 0 | E-SG5-01075 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.1.7 | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 100% | 2022-02-16 08:00 | 2022-03-24 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.7 | SG5 | E | SG5 | 01080 | 0 | E-SG5-01080 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.1.7 | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.7 | SG5 | E | SG5 | 01085 | 0 | E-SG5-01085 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.1.7 | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.7 | SG5 | E | SG5 | 01160 | 0 | E-SG5-01160 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.1.7 | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 60 | 0 | 100% | 2021-02-15 | 2021-03-01 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.7 | SG5 | E | SG5 | 01170 | 0 | E-SG5-01170 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.1.7 | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 100% | 2021-03-02 | 2021-03-19 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.7 | SG5 | E | SG5 | 01020 | 0 | E-SG5-01020 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.1.7 | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 100% | 2021-04-26 | 2021-06-02 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.7 | SG5 | E | SG5 | 01025 | 0 | E-SG5-01025 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.1.7 | Rev/Apprv. Engineering Dwgs. - Electrical Service (NYCHA Approval Only) | 10 | 0 | 100% | 2021-06-03 | 2021-06-21 |  | 0 | 0 | 0 | 0 | 0-SG5
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.7 | SG5 | E | SG5 | 01000 | 0 | E-SG5-01000 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.1.7 | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 15 | 62% | 2021-09-01 | 2022-12-15 17:00 | 67 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.7 | SG5 | E | SG5 | 01040 | 0 | E-SG5-01040 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.1.7 | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 0% | 2022-12-16 08:00 | 2022-12-30 17:00 | 67 | FSE | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.7 | SG5 | E | SG5 | 01010 | 0 | E-SG5-01010 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.1.7 | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 100% | 2020-08-03 | 2020-09-14 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.7 | SG5 | E | SG5 | 01015 | 0 | E-SG5-01015 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.1.7 | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 100% | 2020-09-15 | 2020-10-30 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.7 | SG5 | E | SG5 | 01050 | 0 | E-SG5-01050 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.1.7 | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 100% | 2020-12-01 | 2021-01-07 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.7 | SG5 | E | SG5 | 01055 | 0 | E-SG5-01055 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.1.7 | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 100% | 2021-01-08 | 2021-02-22 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.7 | SG5 | E | SG5 | 01060 | 0 | E-SG5-01060 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.1.7 | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 100% | 2020-09-08 | 2020-10-27 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.7 | SG5 | E | SG5 | 01065 | 0 | E-SG5-01065 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.1.7 | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 100% | 2020-10-27 | 2020-11-03 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.7 | SG5 | E | SG5 | 01030 | 0 | E-SG5-01030 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.1.7 | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 100% | 2022-02-25 08:00 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.1.7 | SG5 | E | SG5 | 01035 | 0 | E-SG5-01035 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.1.7 | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.1 | SG6 | P | SG6 | 01190 | 0 | P-SG6-01190 | Procurement | Procurement | Procurement.ElecEng.1.2.2.1 | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 0 | 100% | 2022-03-25 08:00 | 2022-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.1 | SG6 | P | SG6 | 01200 | 0 | P-SG6-01200 | Procurement | Procurement | Procurement.ElecEng.1.2.2.1 | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 100% | 2021-10-28 | 2021-12-15 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.1 | SG6 | P | SG6 | 01105 | 0 | P-SG6-01105 | Procurement | Procurement | Procurement.ElecEng.1.2.2.1 | Fabricate & Deliver - Smoke Detection Equipment | 75 | 0 | 100% | 2021-07-06 08:00 | 2022-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.1 | SG6 | P | SG6 | 01000 | 0 | P-SG6-01000 | Procurement | Procurement | Procurement.ElecEng.1.2.2.1 | Release for Fabrication - Generators (SG4 & SG5) | 0 | 0 | 100% | 2021-06-01 |  |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.1 | SG6 | P | SG6 | 01015 | 0 | P-SG6-01015 | Procurement | Procurement | Procurement.ElecEng.1.2.2.1 | Fabricate - Generator Enclosure (SG4 & SG5) | 40 | 0 | 100% | 2021-11-15 | 2022-04-06 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.1 | SG6 | P | SG6 | 01020 | 0 | P-SG6-01020 | Procurement | Procurement | Procurement.ElecEng.1.2.2.1 | FAT - Generator w/ Enclosure (SG4 & SG5) | 10 | 0 | 100% | 2022-04-07 08:00 | 2022-04-15 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.1 | SG6 | P | SG6 | 01025 | 0 | P-SG6-01025 | Procurement | Procurement | Procurement.ElecEng.1.2.2.1 | Deliver - Generator w/ Enclosure (SG4 & SG5) | 2 | 0 | 100% | 2022-04-18 08:00 | 2022-04-22 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.1 | SG6 | P | SG6 | 01010 | 0 | P-SG6-01010 | Procurement | Procurement | Procurement.ElecEng.1.2.2.1 | Fabricate - Generator (SG4 & SG5) | 120 | 0 | 100% | 2021-06-02 | 2021-11-08 13:48 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.1 | SG6 | P | SG6 | 01050 | 0 | P-SG6-01050 | Procurement | Procurement | Procurement.ElecEng.1.2.2.1 | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 100% | 2021-06-08 | 2021-10-11 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.1 | SG6 | P | SG6 | 01055 | 0 | P-SG6-01055 | Procurement | Procurement | Procurement.ElecEng.1.2.2.1 | Deliver - Switchboards | 5 | 0 | 100% | 2021-10-12 08:00 | 2021-10-18 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.1 | SG6 | P | SG6 | 01045 | 0 | P-SG6-01045 | Procurement | Procurement | Procurement.ElecEng.1.2.2.1 | Release for Fabrication - Switchboards | 0 | 0 | 100% | 2021-06-07 |  |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.1 | SG6 | P | SG6 | 01065 | 0 | P-SG6-01065 | Procurement | Procurement | Procurement.ElecEng.1.2.2.1 | Fabricate - ACTTS | 80 | 0 | 100% | 2021-10-11 | 2022-01-31 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.1 | SG6 | P | SG6 | 01070 | 0 | P-SG6-01070 | Procurement | Procurement | Procurement.ElecEng.1.2.2.1 | Deliver - ACTTS | 5 | 0 | 100% | 2022-02-15 08:00 | 2022-02-22 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.1 | SG6 | P | SG6 | 01110 | 0 | P-SG6-01110 | Procurement | Procurement | Procurement.ElecEng.1.2.2.1 | Fabricate - Panelboards & Generator Circuit Breaker (GCB) | 30 | 0 | 100% | 2021-06-07 | 2021-07-19 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.1 | SG6 | P | SG6 | 01115 | 0 | P-SG6-01115 | Procurement | Procurement | Procurement.ElecEng.1.2.2.1 | Deliver - Panelboards & Generator Circuit Breaker (GCB) | 5 | 0 | 100% | 2021-07-20 08:00 | 2021-07-27 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.1 | SG6 | P | SG6 | 01090 | 0 | P-SG6-01090 | Procurement | Procurement | Procurement.ElecEng.1.2.2.1 | Fabricate - Lightning Protection System | 60 | 0 | 100% | 2021-11-22 | 2022-04-11 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.1 | SG6 | P | SG6 | 01095 | 0 | P-SG6-01095 | Procurement | Procurement | Procurement.ElecEng.1.2.2.1 | Deliver - Lightning Protection System | 5 | 0 | 100% | 2021-12-13 | 2021-12-15 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.1 | SG6 | P | SG6 | 01060 | 0 | P-SG6-01060 | Procurement | Procurement | Procurement.ElecEng.1.2.2.1 | Release for Fabrication - ACTTS | 0 | 0 | 100% | 2021-10-08 |  |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.7 | SG6 | E | SG6 | 01005 | 0 | E-SG6-01005 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.2.7 | Prep/Submit Engineering Dwgs. - Enclosed Generators | 60 | 0 | 100% | 2020-07-13 | 2020-08-04 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.7 | SG6 | E | SG6 | 01010 | 0 | E-SG6-01010 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.2.7 | Rev/Apprv. Engineering Dwgs. - Enclosed Generators | 10 | 0 | 100% | 2020-08-05 | 2020-11-19 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.7 | SG6 | E | SG6 | 01055 | 0 | E-SG6-01055 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.2.7 | Prep/Submit Engineering Dwgs. - Lightning Protection | 60 | 0 | 100% | 2020-11-02 | 2020-12-08 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.7 | SG6 | E | SG6 | 01060 | 0 | E-SG6-01060 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.2.7 | Rev/Apprv. Engineering Dwgs. - Lightning Protection | 10 | 0 | 100% | 2020-12-09 | 2021-01-29 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.7 | SG6 | E | SG6 | 01035 | 0 | E-SG6-01035 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.2.7 | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 100% | 2021-05-26 | 2022-05-24 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.7 | SG6 | E | SG6 | 01040 | 0 | E-SG6-01040 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.2.7 | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 100% | 2022-04-01 | 2022-04-28 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.7 | SG6 | E | SG6 | 01045 | 0 | E-SG6-01045 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.2.7 | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 100% | 2021-06-09 08:00 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.7 | SG6 | E | SG6 | 01050 | 0 | E-SG6-01050 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.2.7 | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 100% | 2022-02-23 08:00 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.7 | SG6 | E | SG6 | 01070 | 0 | E-SG6-01070 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.2.7 | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 100% | 2021-02-25 | 2021-03-01 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.7 | SG6 | E | SG6 | 01075 | 0 | E-SG6-01075 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.2.7 | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 100% | 2021-03-02 | 2021-03-19 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.7 | SG6 | E | SG6 | 01015 | 0 | E-SG6-01015 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.2.7 | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 100% | 2020-12-01 | 2021-01-07 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.7 | SG6 | E | SG6 | 01020 | 0 | E-SG6-01020 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.2.7 | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 100% | 2021-01-08 | 2021-02-19 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.7 | SG6 | E | SG6 | 01025 | 0 | E-SG6-01025 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.2.7 | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 100% | 2020-09-08 | 2020-10-27 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.2.7 | SG6 | E | SG6 | 01030 | 0 | E-SG6-01030 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.2.2.7 | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 100% | 2020-10-27 | 2020-11-03 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.3 | SGN | E | SGN | 01010 | 0 | E-SGN-01010 | Procurement | Site Engineering | Procurement.ElecEng.1.2.3 | Prep/Submit Engineering Dwgs. - Site Lighting Installation - N/A | 30 | 0 | 100% | 2022-02-25 08:00 | 2022-02-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.3 | SGN | E | SGN | 01015 | 0 | E-SGN-01015 | Procurement | Site Engineering | Procurement.ElecEng.1.2.3 | Rev/Apprv. Engineering Dwgs. - Site Lighting Installation - N/A | 10 | 0 | 100% | 2022-02-25 08:00 | 2022-02-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.3 | SGN | E | SGN | 01020 | 0 | E-SGN-01020 | Procurement | Site Engineering | Procurement.ElecEng.1.2.3 | Prep/Submit Engineering Dwgs. - Underground Ducts Installation (Rev 1) | 30 | 0 | 100% | 2021-02-25 | 2021-06-02 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.3 | SGN | E | SGN | 01025 | 0 | E-SGN-01025 | Procurement | Site Engineering | Procurement.ElecEng.1.2.3 | Rev/Apprv. Engineering Dwgs. - Underground Ducts Installation | 10 | 0 | 100% | 2021-03-12 | 2021-06-21 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.3 | SGN | E | SGN | 01000 | 0 | E-SGN-01000 | Procurement | Site Engineering | Procurement.ElecEng.1.2.3 | Perform Engineering Coordination w/ all Trades (Incl. CON-ED) | 20 | 0 | 100% | 2021-01-25 | 2022-04-29 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.3 | SGN | E | SGN | 01030 | 0 | E-SGN-01030 | Procurement | Site Engineering | Procurement.ElecEng.1.2.3 | Prep/Submit Engineering Dwgs. - Electrical Removals & Relocations | 20 | 0 | 100% | 2021-04-06 | 2021-05-25 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.2.3 | SGN | E | SGN | 01035 | 0 | E-SGN-01035 | Procurement | Site Engineering | Procurement.ElecEng.1.2.3 | Rev/Apprv. Engineering Dwgs. - Electrical Removals & Relocations | 10 | 0 | 100% | 2021-05-25 | 2021-05-25 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.3 | OG2A | E | OG2A | 01010 | 0 | E-OG2A-01010 | Procurement | Site Engineering | Procurement.ElecEng.1.1.3 | Prep/Submit Engineering Dwgs. - Site Lighting Installation | 30 | 0 | 100% | 2022-07-25 08:00 | 2022-08-11 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.3 | OG2A | E | OG2A | 01015 | 0 | E-OG2A-01015 | Procurement | Site Engineering | Procurement.ElecEng.1.1.3 | Rev/Apprv. Engineering Dwgs. - Site Lighting Installation | 10 | 0 | 100% | 2022-08-12 08:00 | 2022-09-06 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.3 | OG2A | E | OG2A | 01020 | 0 | E-OG2A-01020 | Procurement | Site Engineering | Procurement.ElecEng.1.1.3 | Prep/Submit Engineering Dwgs. - Underground Ducts Installation | 30 | 0 | 100% | 2021-09-22 | 2021-09-24 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.3 | OG2A | E | OG2A | 01025 | 0 | E-OG2A-01025 | Procurement | Site Engineering | Procurement.ElecEng.1.1.3 | Rev/Apprv. Engineering Dwgs. - Underground Ducts Installation | 10 | 0 | 100% | 2021-09-27 08:00 | 2021-10-14 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.3 | OG2A | E | OG2A | 01000 | 0 | E-OG2A-01000 | Procurement | Site Engineering | Procurement.ElecEng.1.1.3 | Perform Engineering Coordination w/ all Trades (Incl. CON-ED) | 20 | 0 | 100% | 2021-02-15 | 2022-04-29 |  | 0 | 0 | 0 | 0 | 0-OG2A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.3 | OG2A | E | OG2A | 01030 | 0 | E-OG2A-01030 | Procurement | Site Engineering | Procurement.ElecEng.1.1.3 | Prep/Submit Engineering Dwgs. - Electrical Removals & Relocations - N/A | 20 | 0 | 100% | 2021-04-25 | 2021-04-25 |  | 0 | 0 | 0 | 0 | 0-OG2A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.3 | OG2A | E | OG2A | 01035 | 0 | E-OG2A-01035 | Procurement | Site Engineering | Procurement.ElecEng.1.1.3 | Rev/Apprv. Engineering Dwgs. - Electrical Removals & Relocations - N/A | 10 | 0 | 100% | 2021-04-25 | 2021-04-25 |  | 0 | 0 | 0 | 0 | 0-OG2A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.1 | OG8 | P | OG8 | 01030 | 0 | P-OG8-01030 | Procurement | Procurement | Procurement.ElecEng.1.1.2.1 | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 100% | 2021-07-14 | 2022-03-03 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.1 | OG8 | P | OG8 | 01120 | 0 | P-OG8-01120 | Procurement | Procurement | Procurement.ElecEng.1.1.2.1 | Deliver - Switchboards | 5 | 0 | 100% | 2022-03-04 | 2022-03-10 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.1 | OG8 | P | OG8 | 01020 | 0 | P-OG8-01020 | Procurement | Procurement | Procurement.ElecEng.1.1.2.1 | Release for Fabrication - Switchboards | 0 | 0 | 100% | 2021-07-09 08:00 |  |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.1 | OG8 | P | OG8 | 01050 | 0 | P-OG8-01050 | Procurement | Procurement | Procurement.ElecEng.1.1.2.1 | Release for Fabrication - ACTTS | 0 | 0 | 100% | 2021-10-08 |  |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.1 | OG8 | P | OG8 | 01060 | 0 | P-OG8-01060 | Procurement | Procurement | Procurement.ElecEng.1.1.2.1 | Fabricate - ACTTS | 80 | 0 | 100% | 2021-11-25 | 2022-03-17 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.1 | OG8 | P | OG8 | 01150 | 0 | P-OG8-01150 | Procurement | Procurement | Procurement.ElecEng.1.1.2.1 | Deliver - ACTTS | 5 | 0 | 100% | 2022-03-18 | 2022-03-24 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.1 | OG8 | P | OG8 | 01110 | 0 | P-OG8-01110 | Procurement | Procurement | Procurement.ElecEng.1.1.2.1 | Fabricate - Panelboards & Generator Circuit Breaker (GCB) | 30 | 0 | 100% | 2021-07-14 | 2022-01-07 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.1 | OG8 | P | OG8 | 01160 | 0 | P-OG8-01160 | Procurement | Procurement | Procurement.ElecEng.1.1.2.1 | Deliver - Panelboards & Generator Circuit Breaker (GCB) | 5 | 0 | 100% | 2022-01-10 | 2022-01-14 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.1 | OG8 | P | OG8 | 01000 | 0 | P-OG8-01000 | Procurement | Procurement | Procurement.ElecEng.1.1.2.1 | Release for Fabrication - Generators (OG4 & OG5) | 0 | 0 | 100% | 2021-06-01 |  |  | 0 | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.1 | OG8 | P | OG8 | 01040 | 0 | P-OG8-01040 | Procurement | Procurement | Procurement.ElecEng.1.1.2.1 | Fabricate - Generator Enclosure (OG4 & OG5) (Delayed) | 40 | 33 | 17% | 2022-01-31 | 2023-01-12 17:00 | -82 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.1 | OG8 | P | OG8 | 01140 | 0 | P-OG8-01140 | Procurement | Procurement | Procurement.ElecEng.1.1.2.1 | FAT - Generator w/ Enclosure (OG4 & OG5) | 10 | 10 | 0% | 2023-01-13 08:00 | 2023-01-27 17:00 | -82 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.1 | OG8 | P | OG8 | 01170 | 0 | P-OG8-01170 | Procurement | Procurement | Procurement.ElecEng.1.1.2.1 | Deliver - Generator w/ Enclosure (OG4 & OG5) | 2 | 2 | 0% | 2023-01-30 08:00 | 2023-01-31 17:00 | -82 | FSE | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.1 | OG8 | P | OG8 | 01010 | 0 | P-OG8-01010 | Procurement | Procurement | Procurement.ElecEng.1.1.2.1 | Fabricate - Generator (OG4 & OG5) | 120 | 0 | 100% | 2021-06-02 | 2022-01-28 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.1 | OG8 | P | OG8 | 01090 | 0 | P-OG8-01090 | Procurement | Procurement | Procurement.ElecEng.1.1.2.1 | Fabricate - Lightning Protection System | 60 | 0 | 100% | 2022-03-25 | 2022-05-19 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.1 | OG8 | P | OG8 | 01180 | 0 | P-OG8-01180 | Procurement | Procurement | Procurement.ElecEng.1.1.2.1 | Deliver - Lightning Protection System | 5 | 0 | 100% | 2022-05-20 | 2022-05-24 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.1 | OG8 | P | OG8 | 1105 | 0 | P-OG8-1105 | Procurement | Procurement | Procurement.ElecEng.1.1.2.1 | Fabricate & Deliver - Smoke Detection Equipment | 25 | 0 | 100% | 2022-10-11 08:00 | 2022-10-24 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.1 | OG8 | P | OG8 | 01210 | 0 | P-OG8-01210 | Procurement | Procurement | Procurement.ElecEng.1.1.2.1 | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 15 | 0% | 2022-01-25 | 2022-12-15 17:00 | -9 | FSE | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.1 | OG8 | P | OG8 | 01200 | 0 | P-OG8-01200 | Procurement | Procurement | Procurement.ElecEng.1.1.2.1 | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 100% | 2021-10-28 | 2021-12-15 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.7 | OG8 | E | OG8 | 01005 | 0 | E-OG8-01005 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.2.7 | Prep/Submit Engineering Dwgs. - Enclosed Generators | 60 | 0 | 100% | 2020-07-13 | 2020-08-04 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.7 | OG8 | E | OG8 | 01010 | 0 | E-OG8-01010 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.2.7 | Rev/Apprv. Engineering Dwgs. - Enclosed Generators | 10 | 0 | 100% | 2020-08-05 | 2020-11-19 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.7 | OG8 | E | OG8 | 01055 | 0 | E-OG8-01055 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.2.7 | Prep/Submit Engineering Dwgs. - Lightning Protection | 60 | 0 | 100% | 2020-08-03 | 2020-12-08 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.7 | OG8 | E | OG8 | 01060 | 0 | E-OG8-01060 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.2.7 | Rev/Apprv. Engineering Dwgs. - Lightning Protection | 10 | 0 | 100% | 2020-12-09 | 2021-01-29 |  | 0 | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.7 | OG8 | E | OG8 | 01035 | 0 | E-OG8-01035 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.2.7 | Prep/Submit Engineering Dwgs. - Lighting | 60 | 30 | 50% | 2022-03-25 | 2023-01-09 17:00 | -44 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.7 | OG8 | E | OG8 | 01040 | 0 | E-OG8-01040 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.2.7 | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 10 | 0% | 2023-01-10 08:00 | 2023-01-24 17:00 | -44 | FSE | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.7 | OG8 | E | OG8 | 01045 | 0 | E-OG8-01045 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.2.7 | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.7 | OG8 | E | OG8 | 01050 | 0 | E-OG8-01050 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.2.7 | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.7 | OG8 | E | OG8 | 01070 | 0 | E-OG8-01070 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.2.7 | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 100% | 2021-06-01 | 2021-07-01 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.7 | OG8 | E | OG8 | 01075 | 0 | E-OG8-01075 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.2.7 | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 100% | 2021-07-02 | 2021-07-14 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.7 | OG8 | E | OG8 | 01015 | 0 | E-OG8-01015 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.2.7 | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 100% | 2020-12-10 | 2021-01-05 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.7 | OG8 | E | OG8 | 01020 | 0 | E-OG8-01020 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.2.7 | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 100% | 2021-01-08 | 2021-02-22 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.7 | OG8 | E | OG8 | 01025 | 0 | E-OG8-01025 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.2.7 | Prep/Submit Engineering Dwgs. - Heat Tracing- N/A | 60 | 0 | 100% | 2020-09-08 | 2020-10-27 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.2.7 | OG8 | E | OG8 | 01030 | 0 | E-OG8-01030 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.2.7 | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 100% | 2020-10-27 | 2020-11-03 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.1 | OG4 | P | OG4 | 01010 | 0 | P-OG4-01010 | Procurement | Procurement | Procurement.ElecEng.1.1.8.1 | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 100% | 2021-07-14 | 2022-03-03 17:00 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.1 | OG4 | P | OG4 | 01050 | 0 | P-OG4-01050 | Procurement | Procurement | Procurement.ElecEng.1.1.8.1 | Deliver - Switchboards | 5 | 0 | 100% | 2022-03-04 08:00 | 2022-03-10 17:00 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.1 | OG4 | P | OG4 | 01000 | 0 | P-OG4-01000 | Procurement | Procurement | Procurement.ElecEng.1.1.8.1 | Release for Fabrication - Switchboards | 0 | 0 | 100% | 2021-07-09 08:00 |  |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.1 | OG4 | P | OG4 | 01020 | 0 | P-OG4-01020 | Procurement | Procurement | Procurement.ElecEng.1.1.8.1 | Release for Fabrication - ACTTS | 0 | 0 | 100% | 2021-10-08 |  |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.1 | OG4 | P | OG4 | 01030 | 0 | P-OG4-01030 | Procurement | Procurement | Procurement.ElecEng.1.1.8.1 | Fabricate - ACTTS | 80 | 0 | 100% | 2021-11-26 | 2022-03-17 17:00 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.1 | OG4 | P | OG4 | 01070 | 0 | P-OG4-01070 | Procurement | Procurement | Procurement.ElecEng.1.1.8.1 | Deliver - ACTTS | 5 | 0 | 100% | 2022-03-18 08:00 | 2022-03-24 17:00 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.1 | OG4 | P | OG4 | 01090 | 0 | P-OG4-01090 | Procurement | Procurement | Procurement.ElecEng.1.1.8.1 | Fabricate - Panelboards | 30 | 0 | 100% | 2021-07-14 | 2022-01-07 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.1 | OG4 | P | OG4 | 01100 | 0 | P-OG4-01100 | Procurement | Procurement | Procurement.ElecEng.1.1.8.1 | Deliver - Panelboards | 5 | 0 | 100% | 2022-01-10 | 2022-01-14 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.1 | OG4 | P | OG4 | 01105 | 0 | P-OG4-01105 | Procurement | Procurement | Procurement.ElecEng.1.1.8.1 | Fabricate & Deliver - Smoke Detection Equipment | 25 | 0 | 100% | 2022-10-11 | 2022-10-24 17:00 |  | 0 | 0 | 0 | 0 | 0-OG4
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.1 | OG4 | P | OG4 | 01110 | 0 | P-OG4-01110 | Procurement | Procurement | Procurement.ElecEng.1.1.8.1 | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 46% | 2022-01-25 | 2022-12-06 17:00 | -19 | FSE | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.1 | OG4 | P | OG4 | 01120 | 0 | P-OG4-01120 | Procurement | Procurement | Procurement.ElecEng.1.1.8.1 | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 100% | 2021-10-28 | 2021-12-15 |  | 0 | 0 | 0 | 0 | 0-OG4
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.7 | OG4 | E | OG4 | 01070 | 0 | E-OG4-01070 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.8.7 | Prep/Submit Engineering Dwgs. - Lighting | 60 | 15 | 75% | 2021-11-01 08:00 | 2022-12-15 17:00 | -61 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.7 | OG4 | E | OG4 | 01075 | 0 | E-OG4-01075 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.8.7 | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 10 | 0% | 2022-12-16 08:00 | 2022-12-30 17:00 | -61 | FSE | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.7 | OG4 | E | OG4 | 01080 | 0 | E-OG4-01080 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.8.7 | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.7 | OG4 | E | OG4 | 01085 | 0 | E-OG4-01085 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.8.7 | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.7 | OG4 | E | OG4 | 01160 | 0 | E-OG4-01160 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.8.7 | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 100% | 2021-06-01 | 2021-07-01 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.7 | OG4 | E | OG4 | 01170 | 0 | E-OG4-01170 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.8.7 | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 100% | 2021-07-02 | 2021-07-15 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.7 | OG4 | E | OG4 | 01020 | 0 | E-OG4-01020 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.8.7 | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 100% | 2021-11-01 08:00 | 2022-04-05 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.7 | OG4 | E | OG4 | 01025 | 0 | E-OG4-01025 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.8.7 | Rev/Apprv. Engineering Dwgs. - Electrical Service (NYCHA Approval Only) | 10 | 0 | 100% | 2022-04-06 | 2022-04-28 |  | 0 | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.7 | OG4 | E | OG4 | 01000 | 0 | E-OG4-01000 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.8.7 | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 40 | 0% | 2022-11-25 08:00 | 2023-01-24 17:00 | 42 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.7 | OG4 | E | OG4 | 01005 | 0 | E-OG4-01005 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.8.7 | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 0% | 2023-01-25 08:00 | 2023-02-07 17:00 | 42 | FSE | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.7 | OG4 | E | OG4 | 01010 | 0 | E-OG4-01010 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.8.7 | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 100% | 2021-05-10 | 2021-06-10 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.7 | OG4 | E | OG4 | 01015 | 0 | E-OG4-01015 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.8.7 | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 100% | 2021-06-11 | 2021-07-02 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.7 | OG4 | E | OG4 | 01050 | 0 | E-OG4-01050 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.8.7 | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 100% | 2020-12-01 | 2021-01-07 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.7 | OG4 | E | OG4 | 01055 | 0 | E-OG4-01055 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.8.7 | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 100% | 2021-01-08 | 2021-02-22 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.7 | OG4 | E | OG4 | 01030 | 0 | E-OG4-01030 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.8.7 | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.7 | OG4 | E | OG4 | 01035 | 0 | E-OG4-01035 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.8.7 | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.7 | OG4 | E | OG4 | 01060 | 0 | E-OG4-01060 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.8.7 | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 100% | 2020-09-08 | 2020-10-27 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.8.7 | OG4 | E | OG4 | 01065 | 0 | E-OG4-01065 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.8.7 | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 100% | 2020-10-27 | 2020-11-03 17:00 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.1 | OG5 | P | OG5 | 01010 | 0 | P-OG5-01010 | Procurement | Procurement | Procurement.ElecEng.1.1.1.1 | Fabricate, Assemble & Wire - Switchboards - N/A for Exist. Bldg | 120 | 0 | 100% | 2021-07-14 | 2022-03-03 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.1 | OG5 | P | OG5 | 01070 | 0 | P-OG5-01070 | Procurement | Procurement | Procurement.ElecEng.1.1.1.1 | Deliver - Switchboards | 5 | 0 | 100% | 2022-03-04 08:00 | 2022-03-10 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.1 | OG5 | P | OG5 | 01000 | 0 | P-OG5-01000 | Procurement | Procurement | Procurement.ElecEng.1.1.1.1 | Release for Fabrication - Switchboards | 0 | 0 | 100% | 2021-07-08 |  |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.1 | OG5 | P | OG5 | 01020 | 0 | P-OG5-01020 | Procurement | Procurement | Procurement.ElecEng.1.1.1.1 | Release for Fabrication - ACTTS - N/A for Exist. Bldg | 0 | 0 | 100% | 2021-10-08 |  |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.1 | OG5 | P | OG5 | 01030 | 0 | P-OG5-01030 | Procurement | Procurement | Procurement.ElecEng.1.1.1.1 | Fabricate - ACTTS - N/A for Exist. Bldg | 80 | 0 | 100% | 2021-11-26 | 2022-03-17 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.1 | OG5 | P | OG5 | 01090 | 0 | P-OG5-01090 | Procurement | Procurement | Procurement.ElecEng.1.1.1.1 | Deliver - ACTTS - N/A for Exist. Bldg | 5 | 0 | 100% | 2022-03-18 08:00 | 2022-03-24 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.1 | OG5 | P | OG5 | 01060 | 0 | P-OG5-01060 | Procurement | Procurement | Procurement.ElecEng.1.1.1.1 | Fabricate - Panelboards | 30 | 0 | 100% | 2021-07-14 | 2022-01-07 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.1 | OG5 | P | OG5 | 01100 | 0 | P-OG5-01100 | Procurement | Procurement | Procurement.ElecEng.1.1.1.1 | Deliver - Panelboards | 5 | 0 | 100% | 2022-02-25 08:00 | 2022-03-04 08:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.1 | OG5 | P | OG5 | 01105 | 0 | P-OG5-01105 | Procurement | Procurement | Procurement.ElecEng.1.1.1.1 | Fabricate & Deliver - Smoke Detection Equipment | 25 | 0 | 100% | 2022-10-11 | 2022-10-24 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.1 | OG5 | P | OG5 | 01110 | 0 | P-OG5-01110 | Procurement | Procurement | Procurement.ElecEng.1.1.1.1 | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 46% | 2022-01-25 | 2022-12-06 17:00 | -16 | FSE | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.1 | OG5 | P | OG5 | 01120 | 0 | P-OG5-01120 | Procurement | Procurement | Procurement.ElecEng.1.1.1.1 | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 100% | 2021-10-28 | 2021-12-15 |  | 0 | 0 | 0 | 0 | 0-OG5
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.7 | OG5 | E | OG5 | 01070 | 0 | E-OG5-01070 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.1.7 | Prep/Submit Engineering Dwgs. - Lighting | 60 | 15 | 75% | 2022-01-03 | 2022-12-15 17:00 | -53 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.7 | OG5 | E | OG5 | 01075 | 0 | E-OG5-01075 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.1.7 | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 10 | 0% | 2022-12-16 08:00 | 2022-12-30 17:00 | -53 | FSE | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.7 | OG5 | E | OG5 | 01080 | 0 | E-OG5-01080 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.1.7 | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.7 | OG5 | E | OG5 | 01085 | 0 | E-OG5-01085 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.1.7 | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.7 | OG5 | E | OG5 | 01160 | 0 | E-OG5-01160 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.1.7 | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 60 | 0 | 100% | 2021-06-01 | 2021-07-01 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.7 | OG5 | E | OG5 | 01170 | 0 | E-OG5-01170 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.1.7 | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 100% | 2021-07-02 | 2021-07-21 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.7 | OG5 | E | OG5 | 01020 | 0 | E-OG5-01020 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.1.7 | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 100% | 2021-12-27 08:00 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.7 | OG5 | E | OG5 | 01025 | 0 | E-OG5-01025 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.1.7 | Rev/Apprv. Engineering Dwgs. - Electrical Service (NYCHA Approval Only) | 10 | 0 | 100% | 2022-03-28 | 2022-04-11 |  | 0 | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.7 | OG5 | E | OG5 | 01000 | 0 | E-OG5-01000 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.1.7 | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 40 | 0% | 2022-11-25 08:00 | 2023-01-24 17:00 | 42 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.7 | OG5 | E | OG5 | 01005 | 0 | E-OG5-01005 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.1.7 | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 0% | 2023-01-25 08:00 | 2023-02-07 17:00 | 42 | FSE | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.7 | OG5 | E | OG5 | 01010 | 0 | E-OG5-01010 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.1.7 | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 100% | 2021-04-26 | 2021-05-20 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.7 | OG5 | E | OG5 | 01015 | 0 | E-OG5-01015 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.1.7 | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 100% | 2021-05-21 | 2021-06-04 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.7 | OG5 | E | OG5 | 01050 | 0 | E-OG5-01050 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.1.7 | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 100% | 2020-12-01 | 2021-01-07 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.7 | OG5 | E | OG5 | 01055 | 0 | E-OG5-01055 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.1.7 | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 100% | 2021-01-08 | 2021-02-22 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.7 | OG5 | E | OG5 | 01060 | 0 | E-OG5-01060 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.1.7 | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 100% | 2020-09-08 | 2020-10-27 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.7 | OG5 | E | OG5 | 01065 | 0 | E-OG5-01065 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.1.7 | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 100% | 2020-10-27 | 2020-11-03 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.7 | OG5 | E | OG5 | 01030 | 0 | E-OG5-01030 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.1.7 | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.1.1.7 | OG5 | E | OG5 | 01035 | 0 | E-OG5-01035 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.1.1.7 | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.3 | OGW | E | OGW | 01010 | 0 | E-OGW-01010 | Procurement | Site Engineering | Procurement.ElecEng.1.3.3 | Prep/Submit Engineering Dwgs. - Site Lighting Installation | 30 | 0 | 100% | 2022-08-08 08:00 | 2022-08-11 17:00 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.3 | OGW | E | OGW | 01015 | 0 | E-OGW-01015 | Procurement | Site Engineering | Procurement.ElecEng.1.3.3 | Rev/Apprv. Engineering Dwgs. - Site Lighting Installation | 10 | 0 | 100% | 2022-08-12 08:00 | 2022-09-21 17:00 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.3 | OGW | E | OGW | 01020 | 0 | E-OGW-01020 | Procurement | Site Engineering | Procurement.ElecEng.1.3.3 | Prep/Submit Engineering Dwgs. - Underground Ducts Installation | 30 | 0 | 100% | 2021-08-23 08:00 | 2021-09-24 17:00 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.3 | OGW | E | OGW | 01025 | 0 | E-OGW-01025 | Procurement | Site Engineering | Procurement.ElecEng.1.3.3 | Rev/Apprv. Engineering Dwgs. - Underground Ducts Installation | 10 | 0 | 100% | 2021-09-27 | 2021-10-15 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.3 | OGW | E | OGW | 01000 | 0 | E-OGW-01000 | Procurement | Site Engineering | Procurement.ElecEng.1.3.3 | Perform Engineering Coordination w/ all Trades (Incl. CON-ED) | 20 | 0 | 100% | 2021-02-24 | 2022-05-06 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.3 | OGW | E | OGW | 01030 | 0 | E-OGW-01030 | Procurement | Site Engineering | Procurement.ElecEng.1.3.3 | Prep/Submit Engineering Dwgs. - Electrical Removals & Relocations - N/A | 20 | 0 | 100% | 2021-04-25 | 2021-04-25 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.3 | OGW | E | OGW | 01035 | 0 | E-OGW-01035 | Procurement | Site Engineering | Procurement.ElecEng.1.3.3 | Rev/Apprv. Engineering Dwgs. - Electrical Removals & Relocations - N/A | 10 | 0 | 100% | 2021-04-25 | 2021-04-25 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.1 | OG9 | P | OG9 | 01030 | 0 | P-OG9-01030 | Procurement | Procurement | Procurement.ElecEng.1.3.2.1 | Fabricate, Assemble & Wire - Switchboards (Supply Chain Delay) | 120 | 0 | 100% | 2022-01-25 08:00 | 2022-08-22 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.1 | OG9 | P | OG9 | 01035 | 0 | P-OG9-01035 | Procurement | Procurement | Procurement.ElecEng.1.3.2.1 | Deliver - Switchboards | 5 | 0 | 100% | 2022-09-01 08:00 | 2022-09-07 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.1 | OG9 | P | OG9 | 01020 | 0 | P-OG9-01020 | Procurement | Procurement | Procurement.ElecEng.1.3.2.1 | Release for Fabrication - Switchboards | 0 | 0 | 100% | 2021-12-16 |  |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.1 | OG9 | P | OG9 | 01050 | 0 | P-OG9-01050 | Procurement | Procurement | Procurement.ElecEng.1.3.2.1 | Release for Fabrication - ACTTS | 0 | 0 | 100% | 2021-12-17 |  |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.1 | OG9 | P | OG9 | 01060 | 0 | P-OG9-01060 | Procurement | Procurement | Procurement.ElecEng.1.3.2.1 | Fabricate - ACTTS (Supply Chain Delay) | 120 | 0 | 100% | 2021-12-17 | 2022-06-08 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.1 | OG9 | P | OG9 | 01065 | 0 | P-OG9-01065 | Procurement | Procurement | Procurement.ElecEng.1.3.2.1 | Deliver - ACTTS | 5 | 0 | 100% | 2022-06-09 | 2022-06-15 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.1 | OG9 | P | OG9 | 01110 | 0 | P-OG9-01110 | Procurement | Procurement | Procurement.ElecEng.1.3.2.1 | Fabricate - Panelboards & Generator Circuit Breaker (GCB) | 30 | 0 | 100% | 2022-01-14 | 2022-06-02 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.1 | OG9 | P | OG9 | 01115 | 0 | P-OG9-01115 | Procurement | Procurement | Procurement.ElecEng.1.3.2.1 | Deliver - Panelboards & Generator Circuit Breaker (GCB) | 5 | 0 | 100% | 2022-06-03 08:00 | 2022-06-09 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.1 | OG9 | P | OG9 | 01000 | 0 | P-OG9-01000 | Procurement | Procurement | Procurement.ElecEng.1.3.2.1 | Release for Fabrication - Generators (OG2 & OG3) | 0 | 0 | 100% | 2021-06-01 |  |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.1 | OG9 | P | OG9 | 01040 | 0 | P-OG9-01040 | Procurement | Procurement | Procurement.ElecEng.1.3.2.1 | Fabricate - Generator Enclosure (OG2 & OG3) | 40 | 0 | 100% | 2022-02-23 | 2022-04-28 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.1 | OG9 | P | OG9 | 01045 | 0 | P-OG9-01045 | Procurement | Procurement | Procurement.ElecEng.1.3.2.1 | FAT - Generator w/ Enclosure (OG2 & OG3) | 10 | 0 | 100% | 2022-04-29 | 2022-05-12 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.1 | OG9 | P | OG9 | 01046 | 0 | P-OG9-01046 | Procurement | Procurement | Procurement.ElecEng.1.3.2.1 | Deliver - Generator w/ Enclosure (OG2 & OG3) | 2 | 0 | 100% | 2022-08-25 08:00 | 2022-08-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.1 | OG9 | P | OG9 | 01010 | 0 | P-OG9-01010 | Procurement | Procurement | Procurement.ElecEng.1.3.2.1 | Fabricate - Generator (OG2 & OG3) | 120 | 0 | 100% | 2021-06-01 | 2022-03-24 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.1 | OG9 | P | OG9 | 01090 | 0 | P-OG9-01090 | Procurement | Procurement | Procurement.ElecEng.1.3.2.1 | Fabricate - Lightning Protection System | 60 | 0 | 100% | 2022-03-25 | 2022-04-18 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.1 | OG9 | P | OG9 | 01095 | 0 | P-OG9-01095 | Procurement | Procurement | Procurement.ElecEng.1.3.2.1 | Deliver - Lightning Protection System | 5 | 0 | 100% | 2022-04-25 | 2022-04-29 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.1 | OG9 | P | OG9 | 01190 | 0 | P-OG9-01190 | Procurement | Procurement | Procurement.ElecEng.1.3.2.1 | Fabricate & Deliver - Smoke Detection Equipment | 25 | 0 | 100% | 2022-10-11 | 2022-10-24 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.1 | OG9 | P | OG9 | 01200 | 0 | P-OG9-01200 | Procurement | Procurement | Procurement.ElecEng.1.3.2.1 | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 46% | 2022-01-25 | 2022-12-06 17:00 | -27 | FSE | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.1 | OG9 | P | OG9 | 01210 | 0 | P-OG9-01210 | Procurement | Procurement | Procurement.ElecEng.1.3.2.1 | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 100% | 2021-10-28 | 2021-12-15 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.7 | OG9 | E | OG9 | 01000 | 0 | E-OG9-01000 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.2.7 | Prep/Submit Engineering Dwgs. - Enclosed Generators | 60 | 0 | 100% | 2020-07-13 | 2020-08-04 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.7 | OG9 | E | OG9 | 01005 | 0 | E-OG9-01005 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.2.7 | Rev/Apprv. Engineering Dwgs. - Enclosed Generators | 10 | 0 | 100% | 2020-08-05 | 2020-11-19 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.7 | OG9 | E | OG9 | 01050 | 0 | E-OG9-01050 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.2.7 | Prep/Submit Engineering Dwgs. - Lightning Protection | 60 | 0 | 100% | 2020-08-03 | 2020-12-08 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.7 | OG9 | E | OG9 | 01055 | 0 | E-OG9-01055 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.2.7 | Rev/Apprv. Engineering Dwgs. - Lightning Protection | 10 | 0 | 100% | 2020-12-09 | 2021-01-29 |  | 0 | 0 | 0 | 0 | 0-OG9
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.7 | OG9 | E | OG9 | 01030 | 0 | E-OG9-01030 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.2.7 | Prep/Submit Engineering Dwgs. - Lighting | 60 | 2 | 96% | 2022-10-03 08:00 | 2022-11-28 17:00 | -37 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.7 | OG9 | E | OG9 | 01035 | 0 | E-OG9-01035 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.2.7 | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 10 | 0% | 2022-11-29 08:00 | 2022-12-12 17:00 | -37 | FSE | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.7 | OG9 | E | OG9 | 01040 | 0 | E-OG9-01040 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.2.7 | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 100% | 2022-02-25 | 2022-03-01 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.7 | OG9 | E | OG9 | 01045 | 0 | E-OG9-01045 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.2.7 | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-03-01 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.7 | OG9 | E | OG9 | 01110 | 0 | E-OG9-01110 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.2.7 | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 100% | 2021-11-26 | 2022-01-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.7 | OG9 | E | OG9 | 01115 | 0 | E-OG9-01115 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.2.7 | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 100% | 2022-01-25 08:00 | 2022-02-09 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.7 | OG9 | E | OG9 | 01010 | 0 | E-OG9-01010 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.2.7 | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 100% | 2020-12-01 | 2021-01-07 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.7 | OG9 | E | OG9 | 01015 | 0 | E-OG9-01015 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.2.7 | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 100% | 2021-01-08 | 2021-02-22 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.7 | OG9 | E | OG9 | 01020 | 0 | E-OG9-01020 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.2.7 | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 100% | 2020-09-08 | 2020-10-27 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.2.7 | OG9 | E | OG9 | 01025 | 0 | E-OG9-01025 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.2.7 | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 100% | 2020-10-27 | 2020-11-03 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.1 | OG2 | P | OG2 | 01010 | 0 | P-OG2-01010 | Procurement | Procurement | Procurement.ElecEng.1.3.8.1 | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 100% | 2021-03-08 08:00 | 2022-06-15 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.1 | OG2 | P | OG2 | 01015 | 0 | P-OG2-01015 | Procurement | Procurement | Procurement.ElecEng.1.3.8.1 | Deliver - Switchboards | 5 | 0 | 100% | 2022-07-11 | 2022-07-15 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.1 | OG2 | P | OG2 | 01000 | 0 | P-OG2-01000 | Procurement | Procurement | Procurement.ElecEng.1.3.8.1 | Release for Fabrication - Switchboards | 0 | 0 | 100% | 2021-03-08 08:00 |  |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.1 | OG2 | P | OG2 | 01020 | 0 | P-OG2-01020 | Procurement | Procurement | Procurement.ElecEng.1.3.8.1 | Release for Fabrication - ACTTS | 0 | 0 | 100% | 2021-12-17 |  |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.1 | OG2 | P | OG2 | 01030 | 0 | P-OG2-01030 | Procurement | Procurement | Procurement.ElecEng.1.3.8.1 | Fabricate - ACTTS | 120 | 0 | 100% | 2021-12-17 | 2022-06-01 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.1 | OG2 | P | OG2 | 01070 | 0 | P-OG2-01070 | Procurement | Procurement | Procurement.ElecEng.1.3.8.1 | Deliver - ACTTS | 5 | 0 | 100% | 2022-07-11 | 2022-07-15 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.1 | OG2 | P | OG2 | 01090 | 0 | P-OG2-01090 | Procurement | Procurement | Procurement.ElecEng.1.3.8.1 | Fabricate - Panelboards | 30 | 0 | 100% | 2022-01-14 | 2022-05-27 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.1 | OG2 | P | OG2 | 01095 | 0 | P-OG2-01095 | Procurement | Procurement | Procurement.ElecEng.1.3.8.1 | Deliver - Panelboards | 5 | 0 | 100% | 2022-05-31 | 2022-06-06 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.1 | OG2 | P | OG2 | 01110 | 0 | P-OG2-01110 | Procurement | Procurement | Procurement.ElecEng.1.3.8.1 | Fabricate & Deliver - Smoke Detection Equipment | 25 | 0 | 100% | 2022-10-11 | 2022-10-24 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.1 | OG2 | P | OG2 | 01120 | 0 | P-OG2-01120 | Procurement | Procurement | Procurement.ElecEng.1.3.8.1 | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 46% | 2022-01-25 | 2022-12-06 17:00 | -34 | FSE | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.1 | OG2 | P | OG2 | 01130 | 0 | P-OG2-01130 | Procurement | Procurement | Procurement.ElecEng.1.3.8.1 | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 100% | 2021-10-28 | 2021-12-15 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.7 | OG2 | E | OG2 | 01070 | 0 | E-OG2-01070 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.8.7 | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 100% | 2022-01-03 | 2022-05-18 |  | 0 | 0 | 0 | 0 | 0-OG2
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.7 | OG2 | E | OG2 | 01075 | 0 | E-OG2-01075 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.8.7 | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 5 | 50% | 2022-05-19 | 2022-12-01 17:00 | -36 | FSE | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.7 | OG2 | E | OG2 | 01080 | 0 | E-OG2-01080 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.8.7 | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.7 | OG2 | E | OG2 | 01085 | 0 | E-OG2-01085 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.8.7 | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.7 | OG2 | E | OG2 | 01160 | 0 | E-OG2-01160 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.8.7 | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 100% | 2022-01-03 08:00 | 2022-02-01 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.7 | OG2 | E | OG2 | 01170 | 0 | E-OG2-01170 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.8.7 | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 100% | 2022-02-02 | 2022-04-28 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.7 | OG2 | E | OG2 | 01020 | 0 | E-OG2-01020 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.8.7 | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 100% | 2021-09-24 | 2022-03-02 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.7 | OG2 | E | OG2 | 01025 | 0 | E-OG2-01025 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.8.7 | Rev/Apprv. Engineering Dwgs. - Electrical Service (NYCHA Approval Only) | 10 | 0 | 100% | 2022-03-03 | 2022-03-18 |  | 0 | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.7 | OG2 | E | OG2 | 01000 | 0 | E-OG2-01000 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.8.7 | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 40 | 0% | 2022-11-25 08:00 | 2023-01-24 17:00 | 42 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.7 | OG2 | E | OG2 | 01005 | 0 | E-OG2-01005 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.8.7 | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 0% | 2023-01-25 08:00 | 2023-02-07 17:00 | 42 | FSE | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.7 | OG2 | E | OG2 | 01010 | 0 | E-OG2-01010 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.8.7 | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 100% | 2021-05-26 | 2021-06-28 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.7 | OG2 | E | OG2 | 01015 | 0 | E-OG2-01015 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.8.7 | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 100% | 2021-06-29 | 2021-08-12 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.7 | OG2 | E | OG2 | 01050 | 0 | E-OG2-01050 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.8.7 | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 100% | 2020-12-01 | 2021-01-07 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.7 | OG2 | E | OG2 | 01055 | 0 | E-OG2-01055 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.8.7 | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 100% | 2021-01-08 | 2021-02-22 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.7 | OG2 | E | OG2 | 01030 | 0 | E-OG2-01030 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.8.7 | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.7 | OG2 | E | OG2 | 01035 | 0 | E-OG2-01035 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.8.7 | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.7 | OG2 | E | OG2 | 01060 | 0 | E-OG2-01060 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.8.7 | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 100% | 2020-09-08 | 2020-10-27 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.8.7 | OG2 | E | OG2 | 01065 | 0 | E-OG2-01065 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.8.7 | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 100% | 2020-10-27 | 2020-11-03 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.1 | OG3 | P | OG3 | 01010 | 0 | P-OG3-01010 | Procurement | Procurement | Procurement.ElecEng.1.3.1.1 | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 100% | 2021-03-08 08:00 | 2022-08-09 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.1 | OG3 | P | OG3 | 01015 | 0 | P-OG3-01015 | Procurement | Procurement | Procurement.ElecEng.1.3.1.1 | Deliver - Switchboards | 5 | 0 | 100% | 2022-08-25 08:00 | 2022-09-21 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.1 | OG3 | P | OG3 | 01000 | 0 | P-OG3-01000 | Procurement | Procurement | Procurement.ElecEng.1.3.1.1 | Release for Fabrication - Switchboards | 0 | 0 | 100% | 2021-03-08 08:00 |  |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.1 | OG3 | P | OG3 | 01020 | 0 | P-OG3-01020 | Procurement | Procurement | Procurement.ElecEng.1.3.1.1 | Release for Fabrication - ACTTS | 0 | 0 | 100% | 2021-12-17 |  |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.1 | OG3 | P | OG3 | 01030 | 0 | P-OG3-01030 | Procurement | Procurement | Procurement.ElecEng.1.3.1.1 | Fabricate - ACTTS (Supply Chain Delay) | 120 | 0 | 100% | 2021-12-17 | 2022-06-08 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.1 | OG3 | P | OG3 | 01035 | 0 | P-OG3-01035 | Procurement | Procurement | Procurement.ElecEng.1.3.1.1 | Deliver - ACTTS | 5 | 0 | 100% | 2022-06-09 | 2022-06-15 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.1 | OG3 | P | OG3 | 01060 | 0 | P-OG3-01060 | Procurement | Procurement | Procurement.ElecEng.1.3.1.1 | Fabricate - Panelboards | 30 | 0 | 100% | 2021-12-14 | 2022-05-27 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.1 | OG3 | P | OG3 | 01065 | 0 | P-OG3-01065 | Procurement | Procurement | Procurement.ElecEng.1.3.1.1 | Deliver - Panelboards | 5 | 0 | 100% | 2022-05-31 08:00 | 2022-06-06 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.1 | OG3 | P | OG3 | 01110 | 0 | P-OG3-01110 | Procurement | Procurement | Procurement.ElecEng.1.3.1.1 | Fabricate & Deliver - Smoke Detection Equipment | 25 | 0 | 100% | 2022-10-11 | 2022-10-24 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.1 | OG3 | P | OG3 | 01120 | 0 | P-OG3-01120 | Procurement | Procurement | Procurement.ElecEng.1.3.1.1 | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 46% | 2022-01-25 | 2022-12-06 17:00 | 10 | FSE | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.1 | OG3 | P | OG3 | 01130 | 0 | P-OG3-01130 | Procurement | Procurement | Procurement.ElecEng.1.3.1.1 | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 100% | 2021-10-28 | 2021-12-15 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.7 | OG3 | E | OG3 | 01070 | 0 | E-OG3-01070 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.1.7 | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 100% | 2022-01-03 | 2022-05-18 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.7 | OG3 | E | OG3 | 01075 | 0 | E-OG3-01075 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.1.7 | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 100% | 2022-05-19 | 2022-07-15 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.7 | OG3 | E | OG3 | 01080 | 0 | E-OG3-01080 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.1.7 | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.7 | OG3 | E | OG3 | 01085 | 0 | E-OG3-01085 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.1.7 | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.7 | OG3 | E | OG3 | 01160 | 0 | E-OG3-01160 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.1.7 | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 60 | 0 | 100% | 2021-12-27 08:00 | 2022-01-18 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.7 | OG3 | E | OG3 | 01170 | 0 | E-OG3-01170 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.1.7 | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 100% | 2022-01-19 08:00 | 2022-02-09 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.7 | OG3 | E | OG3 | 01020 | 0 | E-OG3-01020 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.1.7 | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 100% | 2021-09-24 | 2022-01-18 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.7 | OG3 | E | OG3 | 01025 | 0 | E-OG3-01025 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.1.7 | Rev/Apprv. Engineering Dwgs. - Electrical Service (Con-Ed) | 10 | 0 | 100% | 2022-01-19 | 2022-02-09 |  | 0 | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.7 | OG3 | E | OG3 | 01000 | 0 | E-OG3-01000 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.1.7 | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 40 | 0% | 2022-11-25 08:00 | 2023-01-24 17:00 | 42 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.7 | OG3 | E | OG3 | 01005 | 0 | E-OG3-01005 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.1.7 | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 0% | 2023-01-25 08:00 | 2023-02-07 17:00 | 42 | FSE | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.7 | OG3 | E | OG3 | 01010 | 0 | E-OG3-01010 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.1.7 | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 100% | 2021-05-26 | 2021-07-01 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.7 | OG3 | E | OG3 | 01015 | 0 | E-OG3-01015 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.1.7 | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 100% | 2021-07-02 | 2021-08-12 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.7 | OG3 | E | OG3 | 01050 | 0 | E-OG3-01050 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.1.7 | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 100% | 2020-12-01 | 2021-01-07 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.7 | OG3 | E | OG3 | 01055 | 0 | E-OG3-01055 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.1.7 | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 100% | 2021-01-08 | 2021-02-22 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.7 | OG3 | E | OG3 | 01060 | 0 | E-OG3-01060 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.1.7 | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 100% | 2020-09-08 | 2020-10-27 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.7 | OG3 | E | OG3 | 01065 | 0 | E-OG3-01065 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.1.7 | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 100% | 2020-10-27 | 2020-11-03 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.7 | OG3 | E | OG3 | 01030 | 0 | E-OG3-01030 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.1.7 | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.3.1.7 | OG3 | E | OG3 | 01035 | 0 | E-OG3-01035 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.3.1.7 | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.3 | OGE | E | OGE | 01010 | 0 | E-OGE-01010 | Procurement | Site Engineering | Procurement.ElecEng.1.4.3 | Prep/Submit Engineering Dwgs. - Site Lighting Installation | 30 | 0 | 100% | 2022-07-25 08:00 | 2022-08-11 17:00 |  | 0 | 0 | 0 | 0 | 0-OGE
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.4.3 | OGE | E | OGE | 01015 | 0 | E-OGE-01015 | Procurement | Site Engineering | Procurement.ElecEng.1.4.3 | Rev/Apprv. Engineering Dwgs. - Site Lighting Installation | 10 | 10 | 0% | 2022-08-12 08:00 | 2022-12-08 17:00 | 108 | FSE | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.3 | OGE | E | OGE | 01020 | 0 | E-OGE-01020 | Procurement | Site Engineering | Procurement.ElecEng.1.4.3 | Prep/Submit Engineering Dwgs. - Underground Ducts Installation | 30 | 0 | 100% | 2021-09-01 | 2021-09-22 17:00 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.3 | OGE | E | OGE | 01025 | 0 | E-OGE-01025 | Procurement | Site Engineering | Procurement.ElecEng.1.4.3 | Rev/Apprv. Engineering Dwgs. - Underground Ducts Installation | 10 | 0 | 100% | 2021-09-23 08:00 | 2021-10-15 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.3 | OGE | E | OGE | 01000 | 0 | E-OGE-01000 | Procurement | Site Engineering | Procurement.ElecEng.1.4.3 | Perform Engineering Coordination w/ all Trades (Incl. CON-ED) | 20 | 0 | 100% | 2021-04-29 15:00 | 2022-05-24 17:00 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.3 | OGE | E | OGE | 01030 | 0 | E-OGE-01030 | Procurement | Site Engineering | Procurement.ElecEng.1.4.3 | Prep/Submit Engineering Dwgs. - Electrical Removals & Relocations - N/A | 20 | 0 | 100% | 2021-04-25 | 2021-04-25 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.3 | OGE | E | OGE | 01035 | 0 | E-OGE-01035 | Procurement | Site Engineering | Procurement.ElecEng.1.4.3 | Rev/Apprv. Engineering Dwgs. - Electrical Removals & Relocations - N/A | 10 | 0 | 100% | 2021-04-25 | 2021-04-25 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.1 | OG10 | P | OG10 | 01030 | 0 | P-OG10-01030 | Procurement | Procurement | Procurement.ElecEng.1.4.2.1 | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 100% | 2021-11-08 | 2022-03-18 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.1 | OG10 | P | OG10 | 01035 | 0 | P-OG10-01035 | Procurement | Procurement | Procurement.ElecEng.1.4.2.1 | Deliver - Switchboards | 5 | 0 | 100% | 2022-03-21 | 2022-03-24 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.1 | OG10 | P | OG10 | 01020 | 0 | P-OG10-01020 | Procurement | Procurement | Procurement.ElecEng.1.4.2.1 | Release for Fabrication - Switchboards | 0 | 0 | 100% | 2021-11-08 |  |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.1 | OG10 | P | OG10 | 01050 | 0 | P-OG10-01050 | Procurement | Procurement | Procurement.ElecEng.1.4.2.1 | Release for Fabrication - ACTTS | 0 | 0 | 100% | 2021-11-05 |  |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.1 | OG10 | P | OG10 | 01060 | 0 | P-OG10-01060 | Procurement | Procurement | Procurement.ElecEng.1.4.2.1 | Fabricate - ACTTS | 80 | 0 | 100% | 2022-02-25 | 2022-06-08 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.1 | OG10 | P | OG10 | 01065 | 0 | P-OG10-01065 | Procurement | Procurement | Procurement.ElecEng.1.4.2.1 | Deliver - ACTTS | 5 | 0 | 100% | 2022-06-09 | 2022-06-15 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.1 | OG10 | P | OG10 | 01110 | 0 | P-OG10-01110 | Procurement | Procurement | Procurement.ElecEng.1.4.2.1 | Fabricate - Panelboards & Generator Circuit Breaker (GCB) | 30 | 0 | 100% | 2021-11-12 | 2022-03-17 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.1 | OG10 | P | OG10 | 01115 | 0 | P-OG10-01115 | Procurement | Procurement | Procurement.ElecEng.1.4.2.1 | Deliver - Panelboards & Generator Circuit Breaker (GCB) | 5 | 0 | 100% | 2022-03-18 | 2022-03-24 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.1 | OG10 | P | OG10 | 01000 | 0 | P-OG10-01000 | Procurement | Procurement | Procurement.ElecEng.1.4.2.1 | Release for Fabrication - Generators (OG6 & OG1) | 0 | 0 | 100% | 2021-06-01 |  |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.1 | OG10 | P | OG10 | 01040 | 0 | P-OG10-01040 | Procurement | Procurement | Procurement.ElecEng.1.4.2.1 | Fabricate - Generator Enclosure (OG6 & OG1) | 40 | 0 | 100% | 2022-02-11 | 2022-05-06 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.1 | OG10 | P | OG10 | 01140 | 0 | P-OG10-01140 | Procurement | Procurement | Procurement.ElecEng.1.4.2.1 | FAT - Generator w/ Enclosure (OG6 & OG1) | 10 | 0 | 100% | 2022-05-09 | 2022-05-20 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.1 | OG10 | P | OG10 | 01145 | 0 | P-OG10-01145 | Procurement | Procurement | Procurement.ElecEng.1.4.2.1 | Deliver - Generator w/ Enclosure (OG6 & OG1) | 2 | 0 | 100% | 2022-08-25 08:00 | 2022-08-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.1 | OG10 | P | OG10 | 01010 | 0 | P-OG10-01010 | Procurement | Procurement | Procurement.ElecEng.1.4.2.1 | Fabricate - Generator (OG6 & OG1) | 120 | 0 | 100% | 2021-08-02 08:00 | 2022-02-10 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.1 | OG10 | P | OG10 | 01090 | 0 | P-OG10-01090 | Procurement | Procurement | Procurement.ElecEng.1.4.2.1 | Fabricate - Lightning Protection System | 60 | 0 | 100% | 2022-03-25 | 2022-05-10 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.1 | OG10 | P | OG10 | 01095 | 0 | P-OG10-01095 | Procurement | Procurement | Procurement.ElecEng.1.4.2.1 | Deliver - Lightning Protection System | 5 | 0 | 100% | 2022-05-11 | 2022-05-17 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.1 | OG10 | P | OG10 | 01190 | 0 | P-OG10-01190 | Procurement | Procurement | Procurement.ElecEng.1.4.2.1 | Fabricate & Deliver - Smoke Detection Equipment | 75 | 0 | 100% | 2022-01-25 | 2022-10-24 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.1 | OG10 | P | OG10 | 01200 | 0 | P-OG10-01200 | Procurement | Procurement | Procurement.ElecEng.1.4.2.1 | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 46% | 2022-01-25 | 2022-12-06 17:00 | 17 | FSE | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.1 | OG10 | P | OG10 | 01210 | 0 | P-OG10-01210 | Procurement | Procurement | Procurement.ElecEng.1.4.2.1 | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 100% | 2021-10-28 | 2021-12-15 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.7 | OG10 | E | OG10 | 01000 | 0 | E-OG10-01000 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.2.7 | Prep/Submit Engineering Dwgs. - Enclosed Generators | 60 | 0 | 100% | 2020-07-13 | 2020-08-04 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.7 | OG10 | E | OG10 | 01005 | 0 | E-OG10-01005 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.2.7 | Rev/Apprv. Engineering Dwgs. - Enclosed Generators | 10 | 0 | 100% | 2020-08-05 | 2020-11-19 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.7 | OG10 | E | OG10 | 01050 | 0 | E-OG10-01050 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.2.7 | Prep/Submit Engineering Dwgs. - Lightning Protection | 60 | 0 | 100% | 2020-08-03 | 2020-12-08 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.7 | OG10 | E | OG10 | 01055 | 0 | E-OG10-01055 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.2.7 | Rev/Apprv. Engineering Dwgs. - Lightning Protection | 10 | 0 | 100% | 2020-12-09 | 2021-01-29 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.7 | OG10 | E | OG10 | 01030 | 0 | E-OG10-01030 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.2.7 | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 100% | 2022-10-03 08:00 | 2022-10-26 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.7 | OG10 | E | OG10 | 01035 | 0 | E-OG10-01035 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.2.7 | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 100% | 2022-10-27 08:00 | 2022-11-16 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.7 | OG10 | E | OG10 | 01040 | 0 | E-OG10-01040 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.2.7 | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.7 | OG10 | E | OG10 | 01045 | 0 | E-OG10-01045 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.2.7 | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.7 | OG10 | E | OG10 | 01110 | 0 | E-OG10-01110 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.2.7 | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 100% | 2021-09-27 | 2021-10-27 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.7 | OG10 | E | OG10 | 01130 | 0 | E-OG10-01130 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.2.7 | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 100% | 2021-10-28 08:00 | 2021-11-12 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.7 | OG10 | E | OG10 | 01010 | 0 | E-OG10-01010 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.2.7 | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 100% | 2020-12-01 | 2021-01-07 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.7 | OG10 | E | OG10 | 01015 | 0 | E-OG10-01015 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.2.7 | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 100% | 2021-01-08 | 2021-02-22 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.7 | OG10 | E | OG10 | 01020 | 0 | E-OG10-01020 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.2.7 | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 100% | 2020-09-08 | 2020-10-27 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.2.7 | OG10 | E | OG10 | 01025 | 0 | E-OG10-01025 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.2.7 | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 100% | 2020-10-27 | 2020-11-03 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.1 | OG6 | P | OG6 | 01010 | 0 | P-OG6-01010 | Procurement | Procurement | Procurement.ElecEng.1.4.8.1 | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 100% | 2021-11-08 | 2022-03-17 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.1 | OG6 | P | OG6 | 01015 | 0 | P-OG6-01015 | Procurement | Procurement | Procurement.ElecEng.1.4.8.1 | Deliver - Switchboards | 5 | 0 | 100% | 2022-03-17 | 2022-03-24 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.1 | OG6 | P | OG6 | 01000 | 0 | P-OG6-01000 | Procurement | Procurement | Procurement.ElecEng.1.4.8.1 | Release for Fabrication - Switchboards | 0 | 0 | 100% | 2021-11-08 08:00 |  |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.1 | OG6 | P | OG6 | 01020 | 0 | P-OG6-01020 | Procurement | Procurement | Procurement.ElecEng.1.4.8.1 | Release for Fabrication - ACTTS | 0 | 0 | 100% | 2021-11-05 |  |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.1 | OG6 | P | OG6 | 01030 | 0 | P-OG6-01030 | Procurement | Procurement | Procurement.ElecEng.1.4.8.1 | Fabricate - ACTTS | 80 | 0 | 100% | 2022-02-25 08:00 | 2022-06-08 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.1 | OG6 | P | OG6 | 01035 | 0 | P-OG6-01035 | Procurement | Procurement | Procurement.ElecEng.1.4.8.1 | Deliver - ACTTS | 5 | 0 | 100% | 2022-06-09 | 2022-06-15 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.1 | OG6 | P | OG6 | 01090 | 0 | P-OG6-01090 | Procurement | Procurement | Procurement.ElecEng.1.4.8.1 | Fabricate - Panelboards | 30 | 0 | 100% | 2021-11-12 | 2022-03-17 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.1 | OG6 | P | OG6 | 01100 | 0 | P-OG6-01100 | Procurement | Procurement | Procurement.ElecEng.1.4.8.1 | Deliver - Panelboards | 5 | 0 | 100% | 2022-03-18 | 2022-03-24 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.1 | OG6 | P | OG6 | 01110 | 0 | P-OG6-01110 | Procurement | Procurement | Procurement.ElecEng.1.4.8.1 | Fabricate & Deliver - Smoke Detection Equipment | 25 | 0 | 100% | 2022-10-11 | 2022-10-24 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.1 | OG6 | P | OG6 | 01120 | 0 | P-OG6-01120 | Procurement | Procurement | Procurement.ElecEng.1.4.8.1 | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 46% | 2022-01-25 | 2022-12-06 17:00 | 14 | FSE | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.1 | OG6 | P | OG6 | 01130 | 0 | P-OG6-01130 | Procurement | Procurement | Procurement.ElecEng.1.4.8.1 | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 100% | 2021-10-28 | 2021-12-15 |  | 0 | 0 | 0 | 0 | 0-OG6
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.7 | OG6 | E | OG6 | 01070 | 0 | E-OG6-01070 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.8.7 | Prep/Submit Engineering Dwgs. - Lighting | 60 | 2 | 96% | 2021-11-01 08:00 | 2022-11-28 17:00 | -67 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.7 | OG6 | E | OG6 | 01075 | 0 | E-OG6-01075 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.8.7 | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 10 | 0% | 2022-11-29 08:00 | 2022-12-12 17:00 | -67 | FSE | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.7 | OG6 | E | OG6 | 01080 | 0 | E-OG6-01080 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.8.7 | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.7 | OG6 | E | OG6 | 01085 | 0 | E-OG6-01085 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.8.7 | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.7 | OG6 | E | OG6 | 01160 | 0 | E-OG6-01160 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.8.7 | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 100% | 2021-04-05 | 2021-05-19 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.7 | OG6 | E | OG6 | 01170 | 0 | E-OG6-01170 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.8.7 | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 100% | 2021-05-20 | 2021-06-10 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.7 | OG6 | E | OG6 | 01020 | 0 | E-OG6-01020 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.8.7 | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 100% | 2021-09-01 | 2021-09-22 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.7 | OG6 | E | OG6 | 01025 | 0 | E-OG6-01025 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.8.7 | Rev/Apprv. Engineering Dwgs. - Electrical Service (NYCHA Approval Only) | 10 | 0 | 100% | 2021-09-23 | 2021-10-15 |  | 0 | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.7 | OG6 | E | OG6 | 01000 | 0 | E-OG6-01000 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.8.7 | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 40 | 0% | 2022-11-25 08:00 | 2023-01-24 17:00 | 42 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.7 | OG6 | E | OG6 | 01040 | 0 | E-OG6-01040 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.8.7 | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 0% | 2023-01-25 08:00 | 2023-02-07 17:00 | 42 | FSE | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.7 | OG6 | E | OG6 | 01010 | 0 | E-OG6-01010 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.8.7 | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 100% | 2021-04-01 | 2021-04-23 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.7 | OG6 | E | OG6 | 01015 | 0 | E-OG6-01015 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.8.7 | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 100% | 2021-04-26 | 2021-05-20 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.7 | OG6 | E | OG6 | 01050 | 0 | E-OG6-01050 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.8.7 | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 100% | 2020-12-01 | 2021-01-07 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.7 | OG6 | E | OG6 | 01055 | 0 | E-OG6-01055 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.8.7 | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 100% | 2021-01-08 | 2021-02-22 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.7 | OG6 | E | OG6 | 01030 | 0 | E-OG6-01030 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.8.7 | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.7 | OG6 | E | OG6 | 01035 | 0 | E-OG6-01035 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.8.7 | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.7 | OG6 | E | OG6 | 01060 | 0 | E-OG6-01060 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.8.7 | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 100% | 2020-09-08 | 2020-10-27 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.8.7 | OG6 | E | OG6 | 01065 | 0 | E-OG6-01065 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.8.7 | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 100% | 2020-10-27 | 2020-11-03 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.1 | OG1 | P | OG1 | 01010 | 0 | P-OG1-01010 | Procurement | Procurement | Procurement.ElecEng.1.4.1.1 | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 100% | 2021-11-08 08:00 | 2022-03-17 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.1 | OG1 | P | OG1 | 01015 | 0 | P-OG1-01015 | Procurement | Procurement | Procurement.ElecEng.1.4.1.1 | Deliver - Switchboards | 5 | 0 | 100% | 2022-03-18 | 2022-03-24 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.1 | OG1 | P | OG1 | 01000 | 0 | P-OG1-01000 | Procurement | Procurement | Procurement.ElecEng.1.4.1.1 | Release for Fabrication - Switchboards | 0 | 0 | 100% | 2021-11-08 |  |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.1 | OG1 | P | OG1 | 01020 | 0 | P-OG1-01020 | Procurement | Procurement | Procurement.ElecEng.1.4.1.1 | Release for Fabrication - ACTTS | 0 | 0 | 100% | 2021-11-05 |  |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.1 | OG1 | P | OG1 | 01030 | 0 | P-OG1-01030 | Procurement | Procurement | Procurement.ElecEng.1.4.1.1 | Fabricate - ACTTS | 80 | 0 | 100% | 2022-01-25 08:00 | 2022-06-08 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.1 | OG1 | P | OG1 | 01035 | 0 | P-OG1-01035 | Procurement | Procurement | Procurement.ElecEng.1.4.1.1 | Deliver - ACTTS | 5 | 0 | 100% | 2022-06-09 | 2022-06-09 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.1 | OG1 | P | OG1 | 01060 | 0 | P-OG1-01060 | Procurement | Procurement | Procurement.ElecEng.1.4.1.1 | Fabricate - Panelboards | 30 | 0 | 100% | 2021-11-12 | 2022-03-17 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.1 | OG1 | P | OG1 | 01070 | 0 | P-OG1-01070 | Procurement | Procurement | Procurement.ElecEng.1.4.1.1 | Deliver - Panelboards | 5 | 0 | 100% | 2022-03-18 | 2022-03-24 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.1 | OG1 | P | OG1 | 01110 | 0 | P-OG1-01110 | Procurement | Procurement | Procurement.ElecEng.1.4.1.1 | Fabricate & Deliver - Smoke Detection Equipment | 25 | 0 | 100% | 2022-10-11 | 2022-10-24 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.1 | OG1 | P | OG1 | 01120 | 0 | P-OG1-01120 | Procurement | Procurement | Procurement.ElecEng.1.4.1.1 | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 46% | 2022-03-25 08:00 | 2022-12-06 17:00 | 73 | FSE | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.1 | OG1 | P | OG1 | 01130 | 0 | P-OG1-01130 | Procurement | Procurement | Procurement.ElecEng.1.4.1.1 | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 100% | 2021-10-28 | 2021-12-15 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.7 | OG1 | E | OG1 | 01070 | 0 | E-OG1-01070 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.1.7 | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 100% | 2022-04-04 | 2022-05-03 |  | 0 | 0 | 0 | 0 | 0-OG1
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.7 | OG1 | E | OG1 | 01075 | 0 | E-OG1-01075 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.1.7 | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 1 | 90% | 2022-05-04 | 2022-11-25 17:00 | 53 | FSE | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.7 | OG1 | E | OG1 | 01080 | 0 | E-OG1-01080 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.1.7 | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.7 | OG1 | E | OG1 | 01085 | 0 | E-OG1-01085 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.1.7 | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.7 | OG1 | E | OG1 | 01160 | 0 | E-OG1-01160 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.1.7 | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 60 | 0 | 100% | 2021-04-05 | 2021-05-19 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.7 | OG1 | E | OG1 | 01170 | 0 | E-OG1-01170 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.1.7 | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 100% | 2021-05-20 | 2021-06-10 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.7 | OG1 | E | OG1 | 01020 | 0 | E-OG1-01020 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.1.7 | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 100% | 2022-05-25 08:00 | 2022-08-01 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.7 | OG1 | E | OG1 | 01025 | 0 | E-OG1-01025 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.1.7 | Rev/Apprv. Engineering Dwgs. - Electrical Service (NYCHA Approval Only) | 10 | 0 | 100% | 2022-08-02 08:00 | 2022-08-15 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.7 | OG1 | E | OG1 | 01000 | 0 | E-OG1-01000 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.1.7 | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 40 | 0% | 2022-11-25 08:00 | 2023-01-24 17:00 | 42 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.7 | OG1 | E | OG1 | 01040 | 0 | E-OG1-01040 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.1.7 | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 0% | 2023-01-25 08:00 | 2023-02-07 17:00 | 42 | FSE | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.7 | OG1 | E | OG1 | 01010 | 0 | E-OG1-01010 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.1.7 | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 100% | 2021-04-05 | 2021-05-07 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.7 | OG1 | E | OG1 | 01015 | 0 | E-OG1-01015 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.1.7 | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 100% | 2021-05-10 | 2021-06-04 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.7 | OG1 | E | OG1 | 01050 | 0 | E-OG1-01050 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.1.7 | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 100% | 2020-12-01 | 2021-01-07 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.7 | OG1 | E | OG1 | 01055 | 0 | E-OG1-01055 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.1.7 | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 100% | 2021-01-08 | 2021-02-22 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.7 | OG1 | E | OG1 | 01060 | 0 | E-OG1-01060 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.1.7 | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 100% | 2020-09-08 | 2020-10-27 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.7 | OG1 | E | OG1 | 01065 | 0 | E-OG1-01065 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.1.7 | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 100% | 2020-10-27 | 2020-11-03 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.7 | OG1 | E | OG1 | 01030 | 0 | E-OG1-01030 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.1.7 | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.4.1.7 | OG1 | E | OG1 | 01035 | 0 | E-OG1-01035 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.4.1.7 | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.3 | SGS | E | SGS | 01010 | 0 | E-SGS-01010 | Procurement | Site Engineering | Procurement.ElecEng.1.5.3 | Prep/Submit Engineering Dwgs. - Site Lighting Installation | 30 | 0 | 100% | 2022-07-25 08:00 | 2022-08-11 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.3 | SGS | E | SGS | 01015 | 0 | E-SGS-01015 | Procurement | Site Engineering | Procurement.ElecEng.1.5.3 | Rev/Apprv. Engineering Dwgs. - Site Lighting Installation | 10 | 0 | 100% | 2022-08-12 08:00 | 2022-09-06 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.3 | SGS | E | SGS | 01020 | 0 | E-SGS-01020 | Procurement | Site Engineering | Procurement.ElecEng.1.5.3 | Prep/Submit Engineering Dwgs. - Underground Ducts Installation | 5 | 0 | 100% | 2022-04-15 | 2022-05-13 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.3 | SGS | E | SGS | 01025 | 0 | E-SGS-01025 | Procurement | Site Engineering | Procurement.ElecEng.1.5.3 | Rev/Apprv. Engineering Dwgs. - Underground Ducts Installation | 10 | 0 | 100% | 2022-05-02 | 2022-05-13 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.3 | SGS | E | SGS | 01000 | 0 | E-SGS-01000 | Procurement | Site Engineering | Procurement.ElecEng.1.5.3 | Perform Engineering Coordination w/ all Trades (Incl. CON-ED) | 20 | 0 | 100% | 2021-09-06 | 2022-05-13 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.3 | SGS | E | SGS | 01030 | 0 | E-SGS-01030 | Procurement | Site Engineering | Procurement.ElecEng.1.5.3 | Prep/Submit Engineering Dwgs. - Electrical Removals & Relocations - N/A | 20 | 0 | 100% | 2021-04-25 | 2021-04-25 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.3 | SGS | E | SGS | 01035 | 0 | E-SGS-01035 | Procurement | Site Engineering | Procurement.ElecEng.1.5.3 | Rev/Apprv. Engineering Dwgs. - Electrical Removals & Relocations - N/A | 10 | 0 | 100% | 2021-04-25 | 2021-04-25 |  | 0 | 0 | 0 | 0 | 0-SGS
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.1 | SG7 | P | SG7 | 01070 | 0 | P-SG7-01070 | Procurement | Procurement | Procurement.ElecEng.1.5.2.1 | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 5 | 66% | 2022-01-25 | 2022-12-01 17:00 | 38 | FSE | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.1 | SG7 | P | SG7 | 01045 | 0 | P-SG7-01045 | Procurement | Procurement | Procurement.ElecEng.1.5.2.1 | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 100% | 2021-10-28 | 2021-12-15 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.1 | SG7 | P | SG7 | 01050 | 0 | P-SG7-01050 | Procurement | Procurement | Procurement.ElecEng.1.5.2.1 | Fabricate & Deliver - Smoke Detection Equipment | 25 | 0 | 100% | 2022-10-11 | 2022-10-24 17:00 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.1 | SG7 | P | SG7 | 01020 | 0 | P-SG7-01020 | Procurement | Procurement | Procurement.ElecEng.1.5.2.1 | Release for Fabrication - Generators (SG1, SG2 & SG3) | 0 | 0 | 100% | 2021-06-01 |  |  | 0 | 0 | 0 | 0 | 0-SG7
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.1 | SG7 | P | SG7 | 01035 | 0 | P-SG7-01035 | Procurement | Procurement | Procurement.ElecEng.1.5.2.1 | Fabricate - Generator Enclosure (SG1, SG2 & SG3) | 40 | 55 | 0% | 2022-06-15 | 2023-02-14 17:00 | -45 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.1 | SG7 | P | SG7 | 01037 | 0 | P-SG7-01037 | Procurement | Procurement | Procurement.ElecEng.1.5.2.1 | FAT - Generator w/ Enclosure (SG1, SG2 & SG3) | 10 | 10 | 0% | 2023-02-15 08:00 | 2023-03-01 17:00 | -45 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.1 | SG7 | P | SG7 | 01040 | 0 | P-SG7-01040 | Procurement | Procurement | Procurement.ElecEng.1.5.2.1 | Deliver - Generator w/ Enclosure (SG1, SG2 & SG3) | 2 | 2 | 0% | 2023-03-02 08:00 | 2023-03-03 17:00 | -45 | FSE | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.1 | SG7 | P | SG7 | 01030 | 0 | P-SG7-01030 | Procurement | Procurement | Procurement.ElecEng.1.5.2.1 | Fabricate - Generator (SG1, SG2 & SG3) | 120 | 0 | 100% | 2021-10-04 | 2022-06-08 |  | 0 | 0 | 0 | 0 | 0-SG7
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.1 | SG7 | P | SG7 | 01060 | 0 | P-SG7-01060 | Procurement | Procurement | Procurement.ElecEng.1.5.2.1 | Fabricate, Assemble & Wire - Switchboards | 200 | 125 | 37% | 2022-05-03 08:00 | 2023-05-24 17:00 | -132 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.1 | SG7 | P | SG7 | 01065 | 0 | P-SG7-01065 | Procurement | Procurement | Procurement.ElecEng.1.5.2.1 | Deliver - Switchboards | 5 | 5 | 0% | 2023-05-25 08:00 | 2023-06-01 17:00 | -132 | FSE | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.1 | SG7 | P | SG7 | 01055 | 0 | P-SG7-01055 | Procurement | Procurement | Procurement.ElecEng.1.5.2.1 | Release for Fabrication - Switchboards | 0 | 0 | 100% | 2022-05-03 |  |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.1 | SG7 | P | SG7 | 01080 | 0 | P-SG7-01080 | Procurement | Procurement | Procurement.ElecEng.1.5.2.1 | Fabricate - ACTTS (Supply Chain Delay) | 120 | 0 | 100% | 2022-05-25 | 2022-10-07 17:00 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.1 | SG7 | P | SG7 | 01085 | 0 | P-SG7-01085 | Procurement | Procurement | Procurement.ElecEng.1.5.2.1 | Deliver - ACTTS | 5 | 0 | 100% | 2022-10-10 08:00 | 2022-10-14 17:00 |  | 0 | 0 | 0 | 0 | 0-SG7
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.1 | SG7 | P | SG7 | 01100 | 0 | P-SG7-01100 | Procurement | Procurement | Procurement.ElecEng.1.5.2.1 | Fabricate - Panelboards & Generator Circuit Breaker (GCB) | 30 | 40 | 0% | 2022-05-25 08:00 | 2023-01-24 17:00 | -32 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.1 | SG7 | P | SG7 | 01105 | 0 | P-SG7-01105 | Procurement | Procurement | Procurement.ElecEng.1.5.2.1 | Deliver - Panelboards & Generator Circuit Breaker (GCB) | 5 | 5 | 0% | 2023-01-25 08:00 | 2023-01-31 17:00 | -32 | FSE | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.1 | SG7 | P | SG7 | 01140 | 0 | P-SG7-01140 | Procurement | Procurement | Procurement.ElecEng.1.5.2.1 | Fabricate - Lightning Protection System | 60 | 0 | 100% | 2022-09-26 08:00 | 2022-10-24 17:00 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.1 | SG7 | P | SG7 | 01145 | 0 | P-SG7-01145 | Procurement | Procurement | Procurement.ElecEng.1.5.2.1 | Deliver - Lightning Protection System | 5 | 0 | 100% | 2022-10-24 08:00 | 2022-10-24 17:00 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.1 | SG7 | P | SG7 | 01075 | 0 | P-SG7-01075 | Procurement | Procurement | Procurement.ElecEng.1.5.2.1 | Release for Fabrication - ACTTS | 0 | 0 | 100% | 2022-05-25 |  |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.7 | SG7 | E | SG7 | 01000 | 0 | E-SG7-01000 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.2.7 | Prep/Submit Engineering Dwgs. - Enclosed Generators | 60 | 0 | 100% | 2020-07-13 | 2020-08-04 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.7 | SG7 | E | SG7 | 01005 | 0 | E-SG7-01005 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.2.7 | Rev/Apprv. Engineering Dwgs. - Enclosed Generators | 10 | 0 | 100% | 2020-08-05 | 2020-11-19 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.7 | SG7 | E | SG7 | 01050 | 0 | E-SG7-01050 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.2.7 | Prep/Submit Engineering Dwgs. - Lightning Protection | 60 | 0 | 100% | 2020-08-03 | 2020-12-08 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.7 | SG7 | E | SG7 | 01055 | 0 | E-SG7-01055 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.2.7 | Rev/Apprv. Engineering Dwgs. - Lightning Protection | 10 | 0 | 100% | 2020-12-09 | 2021-01-29 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.7 | SG7 | E | SG7 | 01030 | 0 | E-SG7-01030 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.2.7 | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 100% | 2022-08-25 08:00 | 2022-09-15 17:00 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.7 | SG7 | E | SG7 | 01035 | 0 | E-SG7-01035 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.2.7 | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 100% | 2022-09-16 08:00 | 2022-10-05 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.7 | SG7 | E | SG7 | 01040 | 0 | E-SG7-01040 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.2.7 | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.7 | SG7 | E | SG7 | 01045 | 0 | E-SG7-01045 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.2.7 | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.7 | SG7 | E | SG7 | 01110 | 0 | E-SG7-01110 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.2.7 | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 100% | 2022-07-05 08:00 | 2022-07-20 17:00 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.7 | SG7 | E | SG7 | 01115 | 0 | E-SG7-01115 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.2.7 | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 100% | 2022-07-21 08:00 | 2022-09-12 17:00 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.7 | SG7 | E | SG7 | 01010 | 0 | E-SG7-01010 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.2.7 | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 100% | 2020-12-01 | 2021-01-07 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.7 | SG7 | E | SG7 | 01015 | 0 | E-SG7-01015 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.2.7 | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 100% | 2021-01-08 | 2021-02-22 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.7 | SG7 | E | SG7 | 01020 | 0 | E-SG7-01020 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.2.7 | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 100% | 2020-09-08 | 2020-10-27 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.7 | SG7 | E | SG7 | 01025 | 0 | E-SG7-01025 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.2.7 | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 100% | 2020-10-27 | 2020-11-03 17:00 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.7 | SG7 | E | SG7 | 01140 | 0 | E-SG7-01140 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.2.7 | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) | 5 | 0 | 100% | 2022-07-23 | 2022-07-25 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.2.7 | SG7 | E | SG7 | 01150 | 0 | E-SG7-01150 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.2.7 | Rev/Apprv. Engineering Dwgs. - Electrical Service (Con-Ed) | 5 | 0 | 100% | 2022-07-26 08:00 | 2022-09-12 17:00 |  | 0 | 0 | 0 | 0 | 0-SG7
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.5.8.1 | SG1 | P | SG1 | 01090 | 0 | P-SG1-01090 | Procurement | Procurement | Procurement.ElecEng.1.5.8.1 | Fabricate - Panelboards | 30 | 25 | 16% | 2022-05-20 | 2022-12-30 17:00 | 5 | FSE | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.5.8.1 | SG1 | P | SG1 | 01100 | 0 | P-SG1-01100 | Procurement | Procurement | Procurement.ElecEng.1.5.8.1 | Deliver - Panelboards | 5 | 5 | 0% | 2023-01-03 08:00 | 2023-01-09 17:00 | 5 | FSE | 0 | 0 | 0 | 0-SG1
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.5.8.1 | SG1 | P | SG1 | 01050 | 0 | P-SG1-01050 | Procurement | Procurement | Procurement.ElecEng.1.5.8.1 | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 46% | 2022-01-25 | 2022-12-06 17:00 | 50 | FSE | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.8.7 | SG1 | E | SG1 | 01070 | 0 | E-SG1-01070 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.8.7 | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 100% | 2022-07-01 08:00 | 2022-07-11 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.8.7 | SG1 | E | SG1 | 01075 | 0 | E-SG1-01075 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.8.7 | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 100% | 2022-07-12 08:00 | 2022-09-12 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.8.7 | SG1 | E | SG1 | 01080 | 0 | E-SG1-01080 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.8.7 | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.8.7 | SG1 | E | SG1 | 01085 | 0 | E-SG1-01085 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.8.7 | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.8.7 | SG1 | E | SG1 | 01160 | 0 | E-SG1-01160 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.8.7 | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 100% | 2022-04-01 08:00 | 2022-04-01 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.8.7 | SG1 | E | SG1 | 01170 | 0 | E-SG1-01170 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.8.7 | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 100% | 2022-04-04 08:00 | 2022-04-27 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.8.7 | SG1 | E | SG1 | 01020 | 0 | E-SG1-01020 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.8.7 | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 100% | 2022-04-04 | 2022-04-27 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.8.7 | SG1 | E | SG1 | 01025 | 0 | E-SG1-01025 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.8.7 | Rev/Apprv. Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) (NYCHA Approval Only) | 10 | 0 | 100% | 2022-04-28 | 2022-05-11 |  | 0 | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.5.8.7 | SG1 | E | SG1 | 01000 | 0 | E-SG1-01000 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.8.7 | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 40 | 0% | 2022-11-25 08:00 | 2023-01-24 17:00 | 42 | FSE | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.5.8.7 | SG1 | E | SG1 | 01005 | 0 | E-SG1-01005 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.8.7 | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 0% | 2023-01-25 08:00 | 2023-02-07 17:00 | 42 | FSE | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.8.7 | SG1 | E | SG1 | 01010 | 0 | E-SG1-01010 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.8.7 | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 100% | 2021-05-26 | 2021-08-16 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.8.7 | SG1 | E | SG1 | 01015 | 0 | E-SG1-01015 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.8.7 | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 100% | 2021-08-17 08:00 | 2021-10-15 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.8.7 | SG1 | E | SG1 | 01030 | 0 | E-SG1-01030 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.8.7 | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.8.7 | SG1 | E | SG1 | 01035 | 0 | E-SG1-01035 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.8.7 | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.8.7 | SG1 | E | SG1 | 01060 | 0 | E-SG1-01060 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.8.7 | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 100% | 2020-09-08 | 2020-10-27 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.8.7 | SG1 | E | SG1 | 01065 | 0 | E-SG1-01065 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.8.7 | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 100% | 2020-10-27 | 2020-11-03 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.5.1.1 | SG2 | P | SG2 | 01070 | 0 | P-SG2-01070 | Procurement | Procurement | Procurement.ElecEng.1.5.1.1 | Fabricate - Panelboards | 30 | 40 | 0% | 2022-05-20 | 2023-01-24 17:00 | -11 | FSE | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.5.1.1 | SG2 | P | SG2 | 01100 | 0 | P-SG2-01100 | Procurement | Procurement | Procurement.ElecEng.1.5.1.1 | Deliver - Panelboards | 5 | 5 | 0% | 2023-01-25 08:00 | 2023-01-31 17:00 | -11 | FSE | 0 | 0 | 0 | 0-SG2
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.5.1.1 | SG2 | P | SG2 | 01040 | 0 | P-SG2-01040 | Procurement | Procurement | Procurement.ElecEng.1.5.1.1 | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 46% | 2022-01-25 | 2022-12-06 17:00 | 56 | FSE | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.1.7 | SG2 | E | SG2 | 01070 | 0 | E-SG2-01070 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.1.7 | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 100% | 2021-07-12 08:00 | 2022-08-05 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.1.7 | SG2 | E | SG2 | 01075 | 0 | E-SG2-01075 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.1.7 | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 100% | 2022-08-08 08:00 | 2022-09-12 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.1.7 | SG2 | E | SG2 | 01080 | 0 | E-SG2-01080 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.1.7 | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.1.7 | SG2 | E | SG2 | 01085 | 0 | E-SG2-01085 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.1.7 | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.1.7 | SG2 | E | SG2 | 01160 | 0 | E-SG2-01160 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.1.7 | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 60 | 0 | 100% | 2022-04-01 08:00 | 2022-04-01 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.1.7 | SG2 | E | SG2 | 01170 | 0 | E-SG2-01170 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.1.7 | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 100% | 2022-04-04 08:00 | 2022-04-27 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.1.7 | SG2 | E | SG2 | 01020 | 0 | E-SG2-01020 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.1.7 | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 100% | 2022-04-01 | 2022-04-27 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.1.7 | SG2 | E | SG2 | 01025 | 0 | E-SG2-01025 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.1.7 | Rev/Apprv. Engineering Dwgs. - Electrical Service (NYCHA Approval Only) | 10 | 0 | 100% | 2022-04-28 | 2022-05-11 |  | 0 | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.5.1.7 | SG2 | E | SG2 | 01000 | 0 | E-SG2-01000 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.1.7 | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 40 | 0% | 2022-11-25 08:00 | 2023-01-24 17:00 | 42 | FSE | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.5.1.7 | SG2 | E | SG2 | 01005 | 0 | E-SG2-01005 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.1.7 | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 0% | 2023-01-25 08:00 | 2023-02-07 17:00 | 42 | FSE | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.1.7 | SG2 | E | SG2 | 01010 | 0 | E-SG2-01010 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.1.7 | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 100% | 2021-05-26 | 2021-08-16 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.1.7 | SG2 | E | SG2 | 01015 | 0 | E-SG2-01015 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.1.7 | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 100% | 2021-08-17 08:00 | 2021-10-15 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.1.7 | SG2 | E | SG2 | 01060 | 0 | E-SG2-01060 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.1.7 | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 100% | 2020-09-08 | 2020-10-27 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.1.7 | SG2 | E | SG2 | 01065 | 0 | E-SG2-01065 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.1.7 | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 100% | 2020-10-27 | 2020-11-03 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.1.7 | SG2 | E | SG2 | 01030 | 0 | E-SG2-01030 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.1.7 | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.1.7 | SG2 | E | SG2 | 01035 | 0 | E-SG2-01035 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.1.7 | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-SG2
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.1 | SG3 | P | SG3 | 01050 | 0 | P-SG3-01050 | Procurement | Procurement | Procurement.ElecEng.1.5.4.1 | Fabricate, Assemble & Wire - Switchboards | 200 | 130 | 35% | 2022-05-04 | 2023-06-01 17:00 | -136 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.1 | SG3 | P | SG3 | 01055 | 0 | P-SG3-01055 | Procurement | Procurement | Procurement.ElecEng.1.5.4.1 | Deliver - Switchboards | 5 | 5 | 0% | 2023-06-02 08:00 | 2023-06-08 17:00 | -136 | FSE | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.1 | SG3 | P | SG3 | 01045 | 0 | P-SG3-01045 | Procurement | Procurement | Procurement.ElecEng.1.5.4.1 | Release for Fabrication - Switchboards | 0 | 0 | 100% | 2022-05-03 |  |  | 0 | 0 | 0 | 0 | 0-SG3
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.1 | SG3 | P | SG3 | 01060 | 0 | P-SG3-01060 | Procurement | Procurement | Procurement.ElecEng.1.5.4.1 | Fabricate - ACTTS | 120 | 20 | 83% | 2022-05-25 | 2022-12-22 17:00 | -16 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.1 | SG3 | P | SG3 | 01065 | 0 | P-SG3-01065 | Procurement | Procurement | Procurement.ElecEng.1.5.4.1 | Deliver - ACTTS | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | -16 | FSE | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.1 | SG3 | P | SG3 | 01059 | 0 | P-SG3-01059 | Procurement | Procurement | Procurement.ElecEng.1.5.4.1 | Release for Fabrication - ACTTS | 0 | 0 | 100% | 2022-05-25 |  |  | 0 | 0 | 0 | 0 | 0-SG3
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.1 | SG3 | P | SG3 | 01070 | 0 | P-SG3-01070 | Procurement | Procurement | Procurement.ElecEng.1.5.4.1 | Fabricate - Panelboards | 30 | 40 | 0% | 2022-08-01 08:00 | 2023-01-24 17:00 | -27 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.1 | SG3 | P | SG3 | 01075 | 0 | P-SG3-01075 | Procurement | Procurement | Procurement.ElecEng.1.5.4.1 | Deliver - Panelboards | 5 | 5 | 0% | 2023-01-25 08:00 | 2023-01-31 17:00 | -27 | FSE | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.1 | SG3 | P | SG3 | 01020 | 0 | P-SG3-01020 | Procurement | Procurement | Procurement.ElecEng.1.5.4.1 | Fabricate & Deliver - Smoke Detection Equipment | 25 | 0 | 100% | 2022-10-11 | 2022-10-24 17:00 |  | 0 | 0 | 0 | 0 | 0-SG3
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.1 | SG3 | P | SG3 | 01040 | 0 | P-SG3-01040 | Procurement | Procurement | Procurement.ElecEng.1.5.4.1 | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 46% | 2022-01-25 | 2022-12-06 17:00 | 86 | FSE | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.1 | SG3 | P | SG3 | 01030 | 0 | P-SG3-01030 | Procurement | Procurement | Procurement.ElecEng.1.5.4.1 | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 100% | 2021-10-28 | 2021-12-15 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.7 | SG3 | E | SG3 | 01070 | 0 | E-SG3-01070 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.4.7 | Prep/Submit Engineering Dwgs. - Lighting | 60 | 0 | 100% | 2022-07-25 08:00 | 2022-08-17 17:00 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.7 | SG3 | E | SG3 | 01075 | 0 | E-SG3-01075 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.4.7 | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 0 | 100% | 2022-08-18 08:00 | 2022-10-05 17:00 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.7 | SG3 | E | SG3 | 01080 | 0 | E-SG3-01080 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.4.7 | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.7 | SG3 | E | SG3 | 01085 | 0 | E-SG3-01085 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.4.7 | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.7 | SG3 | E | SG3 | 01090 | 0 | E-SG3-01090 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.4.7 | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 60 | 0 | 100% | 2022-04-01 | 2022-05-18 17:00 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.7 | SG3 | E | SG3 | 01095 | 0 | E-SG3-01095 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.4.7 | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 100% | 2022-05-19 08:00 | 2022-09-12 17:00 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.7 | SG3 | E | SG3 | 01020 | 0 | E-SG3-01020 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.4.7 | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 0 | 100% | 2022-04-01 | 2022-04-27 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.7 | SG3 | E | SG3 | 01025 | 0 | E-SG3-01025 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.4.7 | Rev/Apprv. Engineering Dwgs. - Electrical Service (NYCHA Approval Only) | 10 | 0 | 100% | 2022-04-28 | 2022-05-11 |  | 0 | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.7 | SG3 | E | SG3 | 01000 | 0 | E-SG3-01000 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.4.7 | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 40 | 0% | 2022-11-25 08:00 | 2023-01-24 17:00 | 42 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.7 | SG3 | E | SG3 | 01005 | 0 | E-SG3-01005 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.4.7 | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 0% | 2023-01-25 08:00 | 2023-02-07 17:00 | 42 | FSE | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.7 | SG3 | E | SG3 | 01010 | 0 | E-SG3-01010 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.4.7 | Prep/Submit Engineering Dwgs. - Existing Conditions | 60 | 0 | 100% | 2021-05-26 | 2021-09-17 17:00 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.7 | SG3 | E | SG3 | 01015 | 0 | E-SG3-01015 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.4.7 | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 100% | 2021-09-20 08:00 | 2021-10-15 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.7 | SG3 | E | SG3 | 01050 | 0 | E-SG3-01050 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.4.7 | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 100% | 2020-12-01 | 2021-01-07 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.7 | SG3 | E | SG3 | 01055 | 0 | E-SG3-01055 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.4.7 | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 100% | 2021-01-08 | 2021-02-22 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.7 | SG3 | E | SG3 | 01060 | 0 | E-SG3-01060 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.4.7 | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 100% | 2020-09-08 | 2020-10-27 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.7 | SG3 | E | SG3 | 01065 | 0 | E-SG3-01065 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.4.7 | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 100% | 2020-10-27 | 2020-11-03 17:00 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.7 | SG3 | E | SG3 | 01030 | 0 | E-SG3-01030 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.4.7 | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.5.4.7 | SG3 | E | SG3 | 01035 | 0 | E-SG3-01035 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.5.4.7 | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.3 | S8 | E | S8 | 01010 | 0 | E-S8-01010 | Procurement | Site Engineering | Procurement.ElecEng.1.6.3 | Prep/Submit Engineering Dwgs. - Site Lighting Installation | 30 | 0 | 100% | 2022-07-25 08:00 | 2022-08-11 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.6.3 | S8 | E | S8 | 01015 | 0 | E-S8-01015 | Procurement | Site Engineering | Procurement.ElecEng.1.6.3 | Rev/Apprv. Engineering Dwgs. - Site Lighting Installation | 10 | 10 | 0% | 2022-08-12 08:00 | 2022-12-08 17:00 | 99 | FSE | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.3 | S8 | E | S8 | 01020 | 0 | E-S8-01020 | Procurement | Site Engineering | Procurement.ElecEng.1.6.3 | Prep/Submit Engineering Dwgs. - Underground Ducts Installation | 30 | 0 | 100% | 2022-05-13 08:00 | 2022-06-01 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.3 | S8 | E | S8 | 01025 | 0 | E-S8-01025 | Procurement | Site Engineering | Procurement.ElecEng.1.6.3 | Rev/Apprv. Engineering Dwgs. - Underground Ducts Installation | 10 | 0 | 100% | 2022-06-02 08:00 | 2022-10-10 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.3 | S8 | E | S8 | 01000 | 0 | E-S8-01000 | Procurement | Site Engineering | Procurement.ElecEng.1.6.3 | Perform Engineering Coordination w/ all Trades (Incl. CON-ED) | 20 | 0 | 100% | 2022-03-07 | 2022-05-06 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.3 | S8 | E | S8 | 01030 | 0 | E-S8-01030 | Procurement | Site Engineering | Procurement.ElecEng.1.6.3 | Prep/Submit Engineering Dwgs. - Electrical Removals & Relocations - N/A | 20 | 0 | 100% | 2021-04-25 | 2021-04-25 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.3 | S8 | E | S8 | 01035 | 0 | E-S8-01035 | Procurement | Site Engineering | Procurement.ElecEng.1.6.3 | Rev/Apprv. Engineering Dwgs. - Electrical Removals & Relocations - N/A | 10 | 0 | 100% | 2021-04-25 | 2021-04-25 |  | 0 | 0 | 0 | 0 | 0-S8
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.1 | S82 | P | S8A | 01070 | 0 | P-S8A-01070 | Procurement | Procurement | Procurement.ElecEng.1.6.2.1 | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 46% | 2022-01-25 | 2022-12-06 17:00 | 29 | FSE | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.1 | S8A | P | S8A | 01040 | 0 | P-S8A-01040 | Procurement | Procurement | Procurement.ElecEng.1.6.2.1 | Fabricate & Deliver - Lighting Fixtures | 85 | 0 | 100% | 2021-10-28 | 2021-12-15 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.1 | S8A | P | S8A | 01050 | 0 | P-S8A-01050 | Procurement | Procurement | Procurement.ElecEng.1.6.2.1 | Fabricate & Deliver - Smoke Detection Equipment | 75 | 0 | 100% | 2022-10-11 | 2022-10-24 17:00 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.1 | S8A | P | S8A | 01020 | 0 | P-S8A-01020 | Procurement | Procurement | Procurement.ElecEng.1.6.2.1 | Release for Fabrication - Generators (S8E) | 0 | 0 | 100% | 2021-06-01 |  |  | 0 | 0 | 0 | 0 | 0-S8A
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.1 | S82 | P | S8A | 01090 | 0 | P-S8A-01090 | Procurement | Procurement | Procurement.ElecEng.1.6.2.1 | Fabricate - Generator Enclosures (S8E) | 40 | 95 | 0% | 2022-09-12 08:00 | 2023-04-12 17:00 | -84 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.1 | S82 | P | S8A | 01095 | 0 | P-S8A-01095 | Procurement | Procurement | Procurement.ElecEng.1.6.2.1 | FAT - Generators w/ Enclosures (S8E) | 10 | 10 | 0% | 2023-04-13 08:00 | 2023-04-26 17:00 | -84 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.1 | S82 | P | S8A | 01100 | 0 | P-S8A-01100 | Procurement | Procurement | Procurement.ElecEng.1.6.2.1 | Deliver - Generators w/ Enclosures (S8E) | 5 | 5 | 0% | 2023-04-27 08:00 | 2023-05-03 17:00 | -84 | FSE | 0 | 0 | 0 | 0-S82
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.1 | S82 | P | S8A | 01030 | 0 | P-S8A-01030 | Procurement | Procurement | Procurement.ElecEng.1.6.2.1 | Fabricate - Generator (S8E) | 120 | 95 | 20% | 2022-01-25 | 2023-04-12 17:00 | -84 | FSE | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.1 | S8A | P | S8A | 01060 | 0 | P-S8A-01060 | Procurement | Procurement | Procurement.ElecEng.1.6.2.1 | Fabricate, Assemble & Wire - Switchboards | 120 | 0 | 100% | 2021-08-02 08:00 | 2021-11-26 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.1 | S8A | P | S8A | 01065 | 0 | P-S8A-01065 | Procurement | Procurement | Procurement.ElecEng.1.6.2.1 | Deliver - Switchboards | 5 | 0 | 100% | 2021-11-29 | 2021-12-01 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.1 | S8A | P | S8A | 01055 | 0 | P-S8A-01055 | Procurement | Procurement | Procurement.ElecEng.1.6.2.1 | Release for Fabrication - Switchboards | 0 | 0 | 100% | 2021-06-29 08:00 |  |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.1 | S8A | P | S8A | 01080 | 0 | P-S8A-01080 | Procurement | Procurement | Procurement.ElecEng.1.6.2.1 | Fabricate - ACTTS (Supply Chain Delay) | 120 | 0 | 100% | 2022-05-17 | 2022-10-11 17:00 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.1 | S8A | P | S8A | 01085 | 0 | P-S8A-01085 | Procurement | Procurement | Procurement.ElecEng.1.6.2.1 | Deliver - ACTTS | 5 | 0 | 100% | 2022-10-12 08:00 | 2022-10-14 17:00 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.1 | S8A | P | S8A | 01120 | 0 | P-S8A-01120 | Procurement | Procurement | Procurement.ElecEng.1.6.2.1 | Fabricate - Panelboards & Generator Circuit Breaker (GCB) | 30 | 0 | 100% | 2021-06-29 08:00 | 2022-04-14 17:00 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.1 | S8A | P | S8A | 01130 | 0 | P-S8A-01130 | Procurement | Procurement | Procurement.ElecEng.1.6.2.1 | Deliver - Panelboards & Generator Circuit Breaker (GCB) | 5 | 0 | 100% | 2022-04-15 08:00 | 2022-04-21 17:00 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.1 | S8A | P | S8A | 01015 | 0 | P-S8A-01015 | Procurement | Procurement | Procurement.ElecEng.1.6.2.1 | Fabricate - Lightning Protection System | 60 | 0 | 100% | 2022-08-12 08:00 | 2022-10-17 17:00 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.1 | S8A | P | S8A | 01017 | 0 | P-S8A-01017 | Procurement | Procurement | Procurement.ElecEng.1.6.2.1 | Deliver - Lightning Protection System | 5 | 0 | 100% | 2022-10-18 08:00 | 2022-10-21 17:00 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.1 | S8A | P | S8A | 01075 | 0 | P-S8A-01075 | Procurement | Procurement | Procurement.ElecEng.1.6.2.1 | Release for Fabrication - ACTTS | 0 | 0 | 100% | 2022-05-16 |  |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.7 | S8A | E | S8A | 01000 | 0 | E-S8A-01000 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.2.7 | Prep/Submit Engineering Dwgs. - Enclosed Generators | 60 | 0 | 100% | 2020-07-13 | 2020-08-04 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.7 | S8A | E | S8A | 01005 | 0 | E-S8A-01005 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.2.7 | Rev/Apprv. Engineering Dwgs. - Enclosed Generators | 10 | 0 | 100% | 2020-08-05 | 2020-11-19 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.7 | S8A | E | S8A | 01050 | 0 | E-S8A-01050 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.2.7 | Prep/Submit Engineering Dwgs. - Lightning Protection | 60 | 0 | 100% | 2020-08-03 | 2020-12-08 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.7 | S8A | E | S8A | 01055 | 0 | E-S8A-01055 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.2.7 | Rev/Apprv. Engineering Dwgs. - Lightning Protection | 10 | 0 | 100% | 2020-12-09 | 2021-01-29 |  | 0 | 0 | 0 | 0 | 0-S8A
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.7 | S82 | E | S8A | 01030 | 0 | E-S8A-01030 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.2.7 | Prep/Submit Engineering Dwgs. - Lighting | 60 | 60 | 0% | 2022-11-25 08:00 | 2023-02-22 17:00 | -63 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.7 | S82 | E | S8A | 01035 | 0 | E-S8A-01035 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.2.7 | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 10 | 0% | 2023-02-23 08:00 | 2023-03-08 17:00 | -63 | FSE | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.7 | S8A | E | S8A | 01040 | 0 | E-S8A-01040 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.2.7 | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.7 | S8A | E | S8A | 01045 | 0 | E-S8A-01045 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.2.7 | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.7 | S8A | E | S8A | 01110 | 0 | E-S8A-01110 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.2.7 | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 100% | 2022-06-10 08:00 | 2022-06-17 17:00 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.7 | S8A | E | S8A | 01115 | 0 | E-S8A-01115 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.2.7 | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 100% | 2022-06-20 08:00 | 2022-07-13 17:00 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.7 | S8A | E | S8A | 01010 | 0 | E-S8A-01010 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.2.7 | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 100% | 2020-12-01 | 2021-01-07 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.7 | S8A | E | S8A | 01015 | 0 | E-S8A-01015 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.2.7 | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 100% | 2021-01-08 | 2021-02-22 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.7 | S8A | E | S8A | 01020 | 0 | E-S8A-01020 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.2.7 | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 100% | 2020-09-08 | 2020-10-27 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.2.7 | S8A | E | S8A | 01025 | 0 | E-S8A-01025 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.2.7 | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 100% | 2020-10-27 | 2020-11-03 17:00 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.8.1 | S8E | P | S8E | 01090 | 0 | P-S8E-01090 | Procurement | Procurement | Procurement.ElecEng.1.6.8.1 | Fabricate - Panelboards | 30 | 0 | 100% | 2021-06-29 08:00 | 2021-11-26 |  | 0 | 0 | 0 | 0 | 0-S8E
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.8.1 | S8E | P | S8E | 01100 | 0 | P-S8E-01100 | Procurement | Procurement | Procurement.ElecEng.1.6.8.1 | Deliver - Panelboards | 5 | 0 | 100% | 2021-11-29 | 2021-12-01 |  | 0 | 0 | 0 | 0 | 0-S8E
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.6.8.1 | S81 | P | S8E | 01050 | 0 | P-S8E-01050 | Procurement | Procurement | Procurement.ElecEng.1.6.8.1 | Fabricate & Deliver - Exterior Lighting Controls & Fixtures | 15 | 8 | 46% | 2022-03-25 08:00 | 2022-12-06 17:00 | 71 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.6.8.7 | S81 | E | S8E | 01070 | 0 | E-S8E-01070 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.8.7 | Prep/Submit Engineering Dwgs. - Lighting | 60 | 60 | 0% | 2022-11-25 08:00 | 2023-02-22 17:00 | -12 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.6.8.7 | S81 | E | S8E | 01075 | 0 | E-S8E-01075 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.8.7 | Rev/Apprv. Engineering Dwgs. - Lighting | 10 | 10 | 0% | 2023-02-23 08:00 | 2023-03-08 17:00 | -12 | FSE | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.8.7 | S8E | E | S8E | 01080 | 0 | E-S8E-01080 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.8.7 | Prep/Submit Engineering Dwgs. - Exterior Lighting - N/A | 60 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-S8E
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.8.7 | S8E | E | S8E | 01085 | 0 | E-S8E-01085 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.8.7 | Rev/Apprv. Engineering Dwgs. - Exterior Lighting - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-S8E
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.8.7 | S8E | E | S8E | 01160 | 0 | E-S8E-01160 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.8.7 | Prep/Submit Engineering Dwgs. - Electrical Distribution & Equipment | 40 | 0 | 100% | 2022-06-01 08:00 | 2022-06-17 17:00 |  | 0 | 0 | 0 | 0 | 0-S8E
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.8.7 | S8E | E | S8E | 01170 | 0 | E-S8E-01170 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.8.7 | Rev/Apprv. Engineering Dwgs. - Electrical Distribution & Equipment | 10 | 0 | 100% | 2022-06-20 08:00 | 2022-07-13 17:00 |  | 0 | 0 | 0 | 0 | 0-S8E
In Progress | CI NYCHA Update #22.Procurement.ElecEng.1.6.8.7 | S81 | E | S8E | 01020 | 0 | E-S8E-01020 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.8.7 | Prep/Submit Engineering Dwgs. - Electrical Service (Con-Ed) (RFI #184) | 60 | 15 | 75% | 2022-05-25 08:00 | 2022-12-15 17:00 | -20 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.6.8.7 | S81 | E | S8E | 01025 | 0 | E-S8E-01025 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.8.7 | Rev/Apprv. Engineering Dwgs. - Electrical Service (NYCHA Approval Only) | 10 | 10 | 0% | 2022-12-16 08:00 | 2022-12-30 17:00 | -20 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.6.8.7 | S81 | E | S8E | 01000 | 0 | E-S8E-01000 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.8.7 | Prep/Submit Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 40 | 40 | 0% | 2022-11-25 08:00 | 2023-01-24 17:00 | 42 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Procurement.ElecEng.1.6.8.7 | S81 | E | S8E | 01005 | 0 | E-S8E-01005 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.8.7 | Rev/Apprv. Engineering Dwgs. - Electrical Removals, Relocations & Bypass Connections | 10 | 10 | 0% | 2023-01-25 08:00 | 2023-02-07 17:00 | 42 | FSE | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.8.7 | S8E | E | S8E | 01010 | 0 | E-S8E-01010 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.8.7 | Prep/Submit Engineering Dwgs. - Exisiting Conditions | 60 | 0 | 100% | 2021-12-01 | 2022-03-11 17:00 |  | 0 | 0 | 0 | 0 | 0-S8E
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.8.7 | S8E | E | S8E | 01015 | 0 | E-S8E-01015 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.8.7 | Rev/Apprv. Engineering Dwgs. - Exisiting Conditions | 10 | 0 | 100% | 2022-03-14 | 2022-04-11 17:00 |  | 0 | 0 | 0 | 0 | 0-S8E
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.8.7 | S8E | E | S8E | 01050 | 0 | E-S8E-01050 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.8.7 | Prep/Submit Engineering Dwgs. - Smoke Detection System | 60 | 0 | 100% | 2020-12-01 | 2021-01-07 |  | 0 | 0 | 0 | 0 | 0-S8E
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.8.7 | S8E | E | S8E | 01055 | 0 | E-S8E-01055 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.8.7 | Rev/Apprv. Engineering Dwgs. - Smoke Detection System | 10 | 0 | 100% | 2021-01-08 | 2021-02-22 |  | 0 | 0 | 0 | 0 | 0-S8E
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.8.7 | S8E | E | S8E | 01030 | 0 | E-S8E-01030 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.8.7 | Prep/Submit Engineering Dwgs. - Grounding - N/A | 60 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-S8E
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.8.7 | S8E | E | S8E | 01035 | 0 | E-S8E-01035 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.8.7 | Rev/Apprv. Engineering Dwgs. - Grounding - N/A | 10 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-S8E
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.8.7 | S8E | E | S8E | 01060 | 0 | E-S8E-01060 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.8.7 | Prep/Submit Engineering Dwgs. - Heat Tracing - N/A | 60 | 0 | 100% | 2020-09-08 | 2020-10-27 |  | 0 | 0 | 0 | 0 | 0-S8E
Completed | CI NYCHA Update #22.Procurement.ElecEng.1.6.8.7 | S8E | E | S8E | 01065 | 0 | E-S8E-01065 | Procurement | Engineering Shop Drawings | Procurement.ElecEng.1.6.8.7 | Rev/Apprv. Engineering Dwgs. - Heat Tracing - N/A | 10 | 0 | 100% | 2020-10-27 | 2020-11-03 17:00 |  | 0 | 0 | 0 | 0 | 0-S8E
Completed | CI NYCHA Update #22.Procurement.ElecEng | 0 | PROC | E | 01010 | 0 | PROC-E-01010 | Procurement | Div. 26 - Electrical Submittals & General Procurement | Procurement.ElecEng | Prep/Submit Detailed Coordinated Phasing Plan (Pending RFI #535) | 30 | 0 | 100% | 2020-06-03 | 2022-07-05 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng | 0 | PROC | E | 01015 | 0 | PROC-E-01015 | Procurement | Div. 26 - Electrical Submittals & General Procurement | Procurement.ElecEng | Rev/Appr. Detailed Coordinated Phasing Plan | 10 | 0 | 100% | 2022-07-05 | 2022-07-07 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng | 0 | PROC | E | 01020 | 0 | PROC-E-01020 | Procurement | Div. 26 - Electrical Submittals & General Procurement | Procurement.ElecEng | Prep/Submit Electrical Vendor/Manufacturer List | 20 | 0 | 100% | 2020-07-13 | 2020-10-05 |  | FSE | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.ElecEng | 0 | PROC | E | 01025 | 0 | PROC-E-01025 | Procurement | Div. 26 - Electrical Submittals & General Procurement | Procurement.ElecEng | Rev/Appr. Electrical Vendor/Manufacturer List | 10 | 0 | 100% | 2020-10-06 | 2020-11-06 |  | FSE | 0 | 0 | 0 | 0-0
Not Started | CI NYCHA Update #22.Construction.7.6 | SG4 | R | 01000 | 0 | 0 | R-01000 | Construction | Demolition & Removals | Construction.7.6 | Remove & Dispose (E) Switchgear Equipment - SG4 | 5 | 5 | 0% | 2023-05-08 08:00 | 2023-05-12 17:00 | 10 | FSE | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.7.6 | SG5 | R | 01010 | 0 | 0 | R-01010 | Construction | Demolition & Removals | Construction.7.6 | Remove & Dispose (E) Switchgear Equipment - SG5 | 5 | 5 | 0% | 2023-05-26 08:00 | 2023-06-02 17:00 | -4 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.7.6 | OG4 | R | 01020 | 0 | 0 | R-01020 | Construction | Demolition & Removals | Construction.7.6 | Remove & Dispose (E) Switchgear Equipment - OG4 | 5 | 5 | 0% | 2023-05-03 08:00 | 2023-05-09 17:00 | 13 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.7.6 | OG5 | R | 01030 | 0 | 0 | R-01030 | Construction | Demolition & Removals | Construction.7.6 | Remove & Dispose (E) Switchgear Equipment - OG5 | 5 | 5 | 0% | 2023-05-09 08:00 | 2023-05-15 17:00 | 9 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.7.6 | OG6 | R | 01040 | 0 | 0 | R-01040 | Construction | Demolition & Removals | Construction.7.6 | Remove & Dispose (E) Switchgear Equipment - OG6 | 5 | 5 | 0% | 2023-06-05 08:00 | 2023-06-09 17:00 | -9 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.7.6 | OG1 | R | 01050 | 0 | 0 | R-01050 | Construction | Demolition & Removals | Construction.7.6 | Remove & Dispose (E) Switchgear Equipment - OG1 | 5 | 5 | 0% | 2023-06-09 08:00 | 2023-06-15 17:00 | -13 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.7.6 | SG1 | R | 01060 | 0 | 0 | R-01060 | Construction | Demolition & Removals | Construction.7.6 | Remove & Dispose (E) Switchgear Equipment - SG1 | 5 | 5 | 0% | 2023-09-22 08:00 | 2023-09-28 17:00 | -86 | FSE | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.7.6 | SG2 | R | 01070 | 0 | 0 | R-01070 | Construction | Demolition & Removals | Construction.7.6 | Remove & Dispose (E) Switchgear Equipment - SG2 | 5 | 5 | 0% | 2023-09-26 08:00 | 2023-10-02 17:00 | -88 | FSE | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.7.6 | SG3 | R | 01080 | 0 | 0 | R-01080 | Construction | Demolition & Removals | Construction.7.6 | Remove & Dispose (E) Switchgear Equipment - SG3 | 5 | 5 | 0% | 2023-09-26 08:00 | 2023-10-02 17:00 | -88 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.7.6 | S81 | R | 01090 | 0 | 0 | R-01090 | Construction | Demolition & Removals | Construction.7.6 | Remove & Dispose (E) Switchgear Equipment - S8E | 5 | 5 | 0% | 2023-07-19 08:00 | 2023-07-25 17:00 | -40 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.7.6 | OG3 | R | 01100 | 0 | 0 | R-01100 | Construction | Demolition & Removals | Construction.7.6 | Remove & Dispose (E) Switchgear Equipment - OG3 | 5 | 5 | 0% | 2023-05-03 08:00 | 2023-05-09 17:00 | 13 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.7.6 | OG2 | R | 01110 | 0 | 0 | R-01110 | Construction | Demolition & Removals | Construction.7.6 | Remove & Dispose (E) Switchgear Equipment - OG2 | 5 | 5 | 0% | 2023-05-05 08:00 | 2023-05-11 17:00 | 11 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 02005 | 0 | 0 | SGN-02005 | Construction | Site Utilities | Construction.2.5.1 | Remove, Relocate or Abandon Exisiting Feeder Conduit & Cable | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 27 | FSE | 0 | 0 | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.2 | SGN | SGN | 02105 | 0 | 0 | SGN-02105 | Construction | Cable Pulls | Construction.2.5.2 | Pull CON-ED Feeder Cable - 32nd St. to SG-5 Cellar (On Hold pending SG5 Tenant Delays) | 10 | 10 | 0% | 2022-12-01 08:00 | 2022-12-14 17:00 | -36 | FSE | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.2 | SGN | SGN | 02120 | 0 | 0 | SGN-02120 | Construction | Cable Pulls | Construction.2.5.2 | Pull CON-ED Feeder Cable - 33rd St. to SG-4 Cellar | 10 | 0 | 100% | 2022-07-18 | 2022-07-22 |  | FSE | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.2 | SGN | SGN | 02125 | 0 | 0 | SGN-02125 | Construction | Cable Pulls | Construction.2.5.2 | Pull Feeder Cable - SG-4 Switchgear to SG-6 Foundation | 10 | 0 | 100% | 2022-07-11 | 2022-07-15 |  | FSE | 0 | 0 | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.2 | SGN | SGN | 02110 | 0 | 0 | SGN-02110 | Construction | Cable Pulls | Construction.2.5.2 | Pull Generator Feeder Cable from SG-6 to SG-5 Switchgear (On Hold pending SG5 Tenant Delays) | 5 | 5 | 0% | 2022-11-29 08:00 | 2022-12-05 17:00 | -19 | FSE | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.2 | SGN | SGN | 02115 | 0 | 0 | SGN-02115 | Construction | Cable Pulls | Construction.2.5.2 | Pull Generator Feeder Cable from SG-6 to SG-4 Switchgear | 5 | 0 | 100% | 2022-07-11 | 2022-07-15 |  | FSE | 0 | 0 | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.3 | SGN | SGN | 02205 | 0 | 0 | SGN-02205 | Construction | Site Lighting | Construction.2.5.3 | Remove Existing Lighting Conduit, Cable & Fixtures | 5 | 5 | 0% | 2023-05-26 08:00 | 2023-06-02 17:00 | -27 | FSE | 0 | 0 | 0 | 0-SGN
In Progress | CI NYCHA Update #22.Construction.2.5.3 | SGN | SGN | 02210 | 0 | 0 | SGN-02210 | Construction | Site Lighting | Construction.2.5.3 | Furnish & Install Site Lighting Conduit | 10 | 1 | 90% | 2022-08-23 13:00 | 2023-06-07 17:00 | -27 | FSE | 0 | 0 | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.3 | SGN | SGN | 02215 | 0 | 0 | SGN-02215 | Construction | Site Lighting | Construction.2.5.3 | Pull Site Lighting Wire | 5 | 5 | 0% | 2023-06-08 08:00 | 2023-06-14 17:00 | -27 | FSE | 0 | 0 | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.3 | SGN | SGN | 02220 | 0 | 0 | SGN-02220 | Construction | Site Lighting | Construction.2.5.3 | Install Site Lighting Fixtures & Terminate | 10 | 10 | 0% | 2023-06-15 08:00 | 2023-06-28 17:00 | -27 | FSE | 0 | 0 | 0 | 0-SGN
In Progress | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 02205 | 0 | 0 | SG4-02205 | Construction | Cellar | Construction.2.2.6.1 | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 4 | 3 | 25% | 2022-02-22 08:00 | 2022-11-29 17:00 | -28 | FSE | 0 | 0 | 0 | 0-SG4
In Progress | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 02225 | 0 | 0 | SG4-02225 | Construction | Cellar | Construction.2.2.6.1 | Install Bypass Connections - Cellar | 6 | 1 | 85% | 2021-10-15 | 2022-11-29 17:00 | -28 | MEP | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 02210 | 0 | 0 | SG4-02210 | Construction | Cellar | Construction.2.2.6.1 | Relocate (E) & Install Temporary Lighting - Cellar | 5 | 0 | 100% | 2021-10-15 | 2021-12-01 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 02215 | 0 | 0 | SG4-02215 | Construction | Cellar | Construction.2.2.6.1 | Core Drill & Install Incoming Feeder Conduits & Racks - Cellar | 20 | 0 | 100% | 2021-08-30 | 2021-10-20 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 02230 | 0 | 0 | SG4-02230 | Construction | Cellar | Construction.2.2.6.1 | Install Branch Conduit - Cellar | 20 | 0 | 100% | 2021-12-06 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-SG4
In Progress | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 02220 | 0 | 0 | SG4-02220 | Construction | Cellar | Construction.2.2.6.1 | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 20 | 1 | 95% | 2022-04-11 | 2022-11-25 17:00 | -16 | FSE | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 02255 | 0 | 0 | SG4-02255 | Construction | Cellar | Construction.2.2.6.1 | Link & Seal Conduit Sleeves - Cellar | 12 | 0 | 100% | 2021-10-22 | 2021-10-22 |  | 0 | 0 | 0 | 0 | 0-SG4
In Progress | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 02240 | 0 | 0 | SG4-02240 | Construction | Cellar | Construction.2.2.6.1 | Pull Lighting Wiring - Cellar | 6 | 0 | 95% | 2022-06-13 | 2022-11-25 17:00 | -16 | FSE | 0 | 0 | 0 | 0-SG4
In Progress | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 02250 | 0 | 0 | SG4-02250 | Construction | Cellar | Construction.2.2.6.1 | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 6 | 0 | 95% | 2022-10-06 08:00 | 2022-11-25 17:00 | -16 | FSE | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 02245 | 0 | 0 | SG4-02245 | Construction | Cellar | Construction.2.2.6.1 | Pull Branch Wiring - Cellar | 8 | 0 | 100% | 2022-06-13 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-SG4
In Progress | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 02260 | 0 | 0 | SG4-02260 | Construction | Cellar | Construction.2.2.6.1 | Install Heat Trace for Plumbing Lines - Cellar | 5 | 1 | 90% | 2022-08-01 08:00 | 2022-11-25 12:00 | -16 | FSE | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 02265 | 0 | 0 | SG4-02265 | Construction | Cellar | Construction.2.2.6.1 | Core Drill & Install Feeder Conduits Risers & Racks to 1st Floor - Cellar | 20 | 0 | 100% | 2021-12-02 | 2022-02-07 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 02235 | 0 | 0 | SG4-02235 | Construction | Cellar | Construction.2.2.6.1 | Install Panelboards (Misc.) - Cellar | 2 | 0 | 100% | 2022-02-07 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 02270 | 0 | 0 | SG4-02270 | Construction | Cellar | Construction.2.2.6.1 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Cellar | 5 | 0 | 100% | 2022-07-01 08:00 | 2022-09-28 17:00 |  | FSE | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.2 | SG4 | SG4 | 02305 | 0 | 0 | SG4-02305 | Construction | 1st Floor | Construction.2.2.6.2 | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 15 | 0 | 100% | 2022-01-03 | 2022-03-07 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.2 | SG4 | SG4 | 02310 | 0 | 0 | SG4-02310 | Construction | 1st Floor | Construction.2.2.6.2 | Install Pull/Splice Boxes - 1st Floor | 3 | 0 | 100% | 2022-02-01 | 2022-02-03 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.2 | SG4 | SG4 | 02315 | 0 | 0 | SG4-02315 | Construction | 1st Floor | Construction.2.2.6.2 | Install Branch Conduit - 1st Floor | 15 | 0 | 100% | 2022-02-07 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.2 | SG4 | SG4 | 02320 | 0 | 0 | SG4-02320 | Construction | 1st Floor | Construction.2.2.6.2 | Pull Branch Wiring - 1st Floor | 6 | 0 | 100% | 2022-06-06 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.2 | SG4 | SG4 | 02325 | 0 | 0 | SG4-02325 | Construction | 1st Floor | Construction.2.2.6.2 | Install Fire Alarm Control Panel & Equipment - 1st Floor | 2 | 0 | 100% | 2022-06-08 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.2 | SG4 | SG4 | 02330 | 0 | 0 | SG4-02330 | Construction | 1st Floor | Construction.2.2.6.2 | Pull Fire Alarm Wiring - 1st Floor | 2 | 0 | 100% | 2022-09-26 13:00 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-SG4
In Progress | CI NYCHA Update #22.Construction.2.2.6.2 | SG4 | SG4 | 02335 | 0 | 0 | SG4-02335 | Construction | 1st Floor | Construction.2.2.6.2 | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 6 | 2 | 75% | 2022-06-13 | 2022-11-28 12:00 | -17 | FSE | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.2 | SG4 | SG4 | 02340 | 0 | 0 | SG4-02340 | Construction | 1st Floor | Construction.2.2.6.2 | Supply Power to Exterior Building Signage | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | -17 | FSE | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.2 | SG4 | SG4 | 02345 | 0 | 0 | SG4-02345 | Construction | 1st Floor | Construction.2.2.6.2 | Install Firestopping - 1st Floor | 5 | 0 | 100% | 2022-03-07 | 2022-11-15 |  | MLJ | FIRESTOPPING | 0 | 0 | 0-SG4
In Progress | CI NYCHA Update #22.Construction.2.2.6.2 | SG4 | SG4 | 02350 | 0 | 0 | SG4-02350 | Construction | 1st Floor | Construction.2.2.6.2 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 1st Floor | 5 | 0 | 95% | 2022-06-20 | 2022-12-16 15:00 | -31 | FSE | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 02405 | 0 | 0 | SG4-02405 | Construction | 2nd Floor | Construction.2.2.6.3 | Install Switchboards - 2nd Floor | 12 | 0 | 100% | 2022-02-14 | 2022-04-08 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 02430 | 0 | 0 | SG4-02430 | Construction | 2nd Floor | Construction.2.2.6.3 | Install ACTTS - 2nd Floor | 6 | 0 | 100% | 2022-02-15 | 2022-04-11 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 02435 | 0 | 0 | SG4-02435 | Construction | 2nd Floor | Construction.2.2.6.3 | Install Feeder Conduits & Racks to Switchgear Equipment - 2nd Floor | 20 | 0 | 100% | 2022-01-03 | 2022-03-22 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 02410 | 0 | 0 | SG4-02410 | Construction | 2nd Floor | Construction.2.2.6.3 | Install Panelboards - 2nd Floor | 5 | 0 | 100% | 2022-02-14 | 2022-05-16 |  | FSE | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 02420 | 0 | 0 | SG4-02420 | Construction | 2nd Floor | Construction.2.2.6.3 | Install Branch Conduit - 2nd Floor | 20 | 0 | 100% | 2022-06-13 | 2022-07-01 |  | FSE | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 02440 | 0 | 0 | SG4-02440 | Construction | 2nd Floor | Construction.2.2.6.3 | Pull Branch Wiring - 2nd Floor | 6 | 0 | 100% | 2022-06-13 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 02470 | 0 | 0 | SG4-02470 | Construction | 2nd Floor | Construction.2.2.6.3 | Install Light Fixtures & Controls - 2nd Floor | 5 | 0 | 100% | 2022-09-23 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 02415 | 0 | 0 | SG4-02415 | Construction | 2nd Floor | Construction.2.2.6.3 | Install Fire Alarm Equipment - 2nd Floor | 6 | 0 | 100% | 2022-06-10 | 2022-07-01 |  | FSE | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 02425 | 0 | 0 | SG4-02425 | Construction | 2nd Floor | Construction.2.2.6.3 | Install Receptacles - 2nd Floor | 5 | 0 | 100% | 2022-06-13 | 2022-11-15 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 02445 | 0 | 0 | SG4-02445 | Construction | 2nd Floor | Construction.2.2.6.3 | Install Fire Stopping - 2nd Floor | 5 | 0 | 100% | 2022-03-23 | 2022-11-15 |  | 0 | FIRESTOPPING | 0 | 0 | 0-SG4
In Progress | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 02450 | 0 | 0 | SG4-02450 | Construction | 2nd Floor | Construction.2.2.6.3 | Tag & Terminate Panelboards | 2 | 0 | 95% | 2022-08-01 15:00 | 2022-11-25 10:00 | -15 | FSE | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 02455 | 0 | 0 | SG4-02455 | Construction | 2nd Floor | Construction.2.2.6.3 | Tag & Terminate Switchgear Equipment | 5 | 0 | 100% | 2022-07-15 | 2022-09-26 15:00 |  | FSE | 0 | 0 | 0 | 0-SG4
In Progress | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 02475 | 0 | 0 | SG4-02475 | Construction | 2nd Floor | Construction.2.2.6.3 | Ground Equipment | 5 | 0 | 95% | 2022-08-22 15:00 | 2022-11-25 10:00 | -15 | FSE | GROUNDING EQUIP | 0 | 0 | 0-SG4
In Progress | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 02480 | 0 | 0 | SG4-02480 | Construction | 2nd Floor | Construction.2.2.6.3 | Tag & Terminate Fire Alarm System | 5 | 0 | 95% | 2022-09-23 | 2022-11-25 10:00 | 112 | FSE | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 02465 | 0 | 0 | SG4-02465 | Construction | 2nd Floor | Construction.2.2.6.3 | Pull CON-ED Feeder Cable - Cellar to Switchgear Equipment - 2nd Floor | 20 | 0 | 100% | 2022-07-01 | 2022-07-22 |  | FSE | 0 | 0 | 0 | 0-SG4
In Progress | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 02460 | 0 | 0 | SG4-02460 | Construction | 2nd Floor | Construction.2.2.6.3 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 5 | 0 | 95% | 2022-07-01 | 2023-01-25 15:00 | -56 | FSE | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.4 | SG4 | SG4 | 02505 | 0 | 0 | SG4-02505 | Construction | Testing & Start-Up | Construction.2.2.6.4 | Fire Alarm Operational & FDNY Acceptance Testing - SG4 | 5 | 5 | 0% | 2023-05-08 08:00 | 2023-05-12 17:00 | 0 | FSE | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.4 | SG4 | SG4 | 02515 | 0 | 0 | SG4-02515 | Construction | Testing & Start-Up | Construction.2.2.6.4 | Energize Switchgear - SG4 | 5 | 0 | 100% | 2022-10-03 08:00 | 2022-10-07 17:00 |  | FSE | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.4 | SG4 | SG4 | 02535 | 0 | 0 | SG4-02535 | Construction | Testing & Start-Up | Construction.2.2.6.4 | Start-Up Generator/Switchgear - SG4 | 4 | 4 | 0% | 2023-05-02 08:00 | 2023-05-05 17:00 | -114 | FSE | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.4 | SG4 | SG4 | 02510 | 0 | 0 | SG4-02510 | Construction | Testing & Start-Up | Construction.2.2.6.4 | Perform Electrical Inspections - SG4 | 5 | 5 | 0% | 2023-03-14 08:00 | 2023-03-20 17:00 | -88 | FSE | 0 | 0 | 0 | 0-SG4
In Progress | CI NYCHA Update #22.Construction.2.2.6.4 | SG4 | SG4 | 02520 | 0 | 0 | SG4-02520 | Construction | Testing & Start-Up | Construction.2.2.6.4 | Perform 3rd Party Test - SG4 | 2 | 1 | 75% | 2022-07-01 08:00 | 2023-04-26 17:00 | -114 | UNSURE | STARTUP | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.4 | SG4 | SG4 | 02525 | 0 | 0 | SG4-02525 | Construction | Testing & Start-Up | Construction.2.2.6.4 | Notify NYCHA of Fire Alarm Acceptance Testing - SG4 | 14 | 14 | 0% | 2023-04-18 08:00 | 2023-05-05 17:00 | 0 | FSE | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.4 | SG4 | SG4 | 02530 | 0 | 0 | SG4-02530 | Construction | Testing & Start-Up | Construction.2.2.6.4 | Perform Tie-in's to Exisiting | 3 | 3 | 0% | 2023-04-27 08:00 | 2023-05-01 17:00 | -114 | UNSURE | STARTUP | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 02205 | 0 | 0 | SG5-02205 | Construction | Cellar | Construction.2.3.6.1 | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 4 | 4 | 0% | 2022-11-25 08:00 | 2022-11-30 17:00 | -36 | FSE | 0 | 0 | 0 | 0-SG5
In Progress | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 02210 | 0 | 0 | SG5-02210 | Construction | Cellar | Construction.2.3.6.1 | Install Bypass Connections - Cellar | 6 | 3 | 50% | 2021-12-01 | 2022-11-30 17:00 | 8 | MEP | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 02220 | 0 | 0 | SG5-02220 | Construction | Cellar | Construction.2.3.6.1 | Relocate (E) & Install Temporary Lighting - Cellar | 4 | 0 | 100% | 2021-11-29 | 2022-10-03 17:00 |  | FSE | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 02225 | 0 | 0 | SG5-02225 | Construction | Cellar | Construction.2.3.6.1 | Core Drill & Install Incoming Feeder Conduits & Racks - Cellar | 20 | 0 | 100% | 2021-08-23 | 2021-09-22 |  | 0 | 0 | 0 | 0 | 0-SG5
In Progress | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 02215 | 0 | 0 | SG5-02215 | Construction | Cellar | Construction.2.3.6.1 | Install Branch Conduit - Cellar | 20 | 5 | 75% | 2021-12-15 | 2022-12-21 17:00 | -36 | FSE | 0 | 0 | 0 | 0-SG5
In Progress | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 02230 | 0 | 0 | SG5-02230 | Construction | Cellar | Construction.2.3.6.1 | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 20 | 10 | 50% | 2022-09-30 08:00 | 2022-12-08 17:00 | -40 | FSE | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 02260 | 0 | 0 | SG5-02260 | Construction | Cellar | Construction.2.3.6.1 | Link & Seal Conduit Sleeves - Cellar | 10 | 0 | 100% | 2021-10-22 | 2021-10-22 |  | 0 | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 02255 | 0 | 0 | SG5-02255 | Construction | Cellar | Construction.2.3.6.1 | Pull Lighting Wiring - Cellar | 5 | 5 | 0% | 2022-12-09 08:00 | 2022-12-15 17:00 | -40 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 02265 | 0 | 0 | SG5-02265 | Construction | Cellar | Construction.2.3.6.1 | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -40 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 02235 | 0 | 0 | SG5-02235 | Construction | Cellar | Construction.2.3.6.1 | Pull Branch Wiring - Cellar | 7 | 7 | 0% | 2022-12-22 08:00 | 2023-01-03 17:00 | -35 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 02240 | 0 | 0 | SG5-02240 | Construction | Cellar | Construction.2.3.6.1 | Install Heat Trace for Plumbing Lines - Cellar | 2 | 2 | 0% | 2023-01-04 08:00 | 2023-01-05 17:00 | -35 | FSE | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 02250 | 0 | 0 | SG5-02250 | Construction | Cellar | Construction.2.3.6.1 | Core Drill & Install Feeder Conduits Risers & Racks to 1st Floor - Cellar | 15 | 0 | 100% | 2022-01-03 08:00 | 2022-01-04 17:00 |  | FSE | CORE DRILL | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 02270 | 0 | 0 | SG5-02270 | Construction | Cellar | Construction.2.3.6.1 | Install Panelboards (Misc.) - Cellar | 5 | 5 | 0% | 2022-12-01 08:00 | 2022-12-07 17:00 | -36 | FSE | 0 | 0 | 0 | 0-SG5
In Progress | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 02245 | 0 | 0 | SG5-02245 | Construction | Cellar | Construction.2.3.6.1 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Cellar | 5 | 3 | 50% | 2022-06-21 | 2022-11-29 12:00 | -10 | FSE | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.6.2 | SG5 | SG5 | 02325 | 0 | 0 | SG5-02325 | Construction | 1st Floor | Construction.2.3.6.2 | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 12 | 0 | 100% | 2021-12-01 08:00 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.6.2 | SG5 | SG5 | 02335 | 0 | 0 | SG5-02335 | Construction | 1st Floor | Construction.2.3.6.2 | Install Pull/Splice Boxes - 1st Floor | 4 | 0 | 100% | 2022-09-26 08:00 | 2022-11-15 |  | 0 | 0 | 0 | 0 | 0-SG5
In Progress | CI NYCHA Update #22.Construction.2.3.6.2 | SG5 | SG5 | 02305 | 0 | 0 | SG5-02305 | Construction | 1st Floor | Construction.2.3.6.2 | Install Branch Conduit - 1st Floor | 12 | 3 | 75% | 2022-10-03 08:00 | 2022-11-29 17:00 | -29 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.2 | SG5 | SG5 | 02310 | 0 | 0 | SG5-02310 | Construction | 1st Floor | Construction.2.3.6.2 | Pull Branch Wiring - 1st Floor | 6 | 6 | 0% | 2022-11-30 08:00 | 2022-12-07 17:00 | -29 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.2 | SG5 | SG5 | 02315 | 0 | 0 | SG5-02315 | Construction | 1st Floor | Construction.2.3.6.2 | Install Fire Alarm Control Panel (FACP) & Smoke Detectors - 1st Floor | 2 | 2 | 0% | 2022-12-08 08:00 | 2022-12-09 17:00 | -28 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.2 | SG5 | SG5 | 02320 | 0 | 0 | SG5-02320 | Construction | 1st Floor | Construction.2.3.6.2 | Pull Fire Alarm Wiring - 1st Floor | 2 | 2 | 0% | 2022-12-12 08:00 | 2022-12-13 17:00 | 80 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.2 | SG5 | SG5 | 02330 | 0 | 0 | SG5-02330 | Construction | 1st Floor | Construction.2.3.6.2 | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | -40 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.2 | SG5 | SG5 | 02340 | 0 | 0 | SG5-02340 | Construction | 1st Floor | Construction.2.3.6.2 | Supply Power to Exterior Building Signage | 2 | 2 | 0% | 2022-12-08 08:00 | 2022-12-09 17:00 | -23 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.2 | SG5 | SG5 | 02345 | 0 | 0 | SG5-02345 | Construction | 1st Floor | Construction.2.3.6.2 | Install Firestopping - 1st Floor | 5 | 5 | 0% | 2022-12-12 08:00 | 2022-12-16 17:00 | -23 | MLJ | FIRESTOPPING | EXISTING BUILDING | 07-1200 | 07-1200-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.2 | SG5 | SG5 | 02350 | 0 | 0 | SG5-02350 | Construction | 1st Floor | Construction.2.3.6.2 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 1st Floor | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -27 | FSE | 0 | 0 | 0 | 0-SG5
In Progress | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 02415 | 0 | 0 | SG5-02415 | Construction | 2nd Floor | Construction.2.3.6.3 | Install Switchboards - 2nd Floor | 10 | 2 | 80% | 2022-10-15 08:00 | 2022-11-28 17:00 | -27 | FSE | 0 | 0 | 0 | 0-SG5
In Progress | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 02420 | 0 | 0 | SG5-02420 | Construction | 2nd Floor | Construction.2.3.6.3 | Install ACTTS - 2nd Floor | 4 | 1 | 80% | 2022-10-10 08:00 | 2022-11-28 17:00 | -27 | FSE | ACTTS | 0 | 0 | 0-SG5
In Progress | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 02425 | 0 | 0 | SG5-02425 | Construction | 2nd Floor | Construction.2.3.6.3 | Install Feeder Conduits & Racks to Switchgear Equipment - 2nd Floor | 20 | 2 | 90% | 2022-10-10 08:00 | 2022-11-28 17:00 | -24 | FSE | 0 | 0 | 0 | 0-SG5
In Progress | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 02430 | 0 | 0 | SG5-02430 | Construction | 2nd Floor | Construction.2.3.6.3 | Install Panelboards - 2nd Floor | 4 | 1 | 80% | 2022-10-10 08:00 | 2022-11-28 17:00 | -27 | FSE | 0 | 0 | 0 | 0-SG5
In Progress | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 02440 | 0 | 0 | SG5-02440 | Construction | 2nd Floor | Construction.2.3.6.3 | Install Branch Conduit - 2nd Floor | 15 | 8 | 50% | 2022-11-02 08:00 | 2022-12-06 12:00 | -28 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 02445 | 0 | 0 | SG5-02445 | Construction | 2nd Floor | Construction.2.3.6.3 | Pull Branch Wiring - 2nd Floor | 5 | 5 | 0% | 2022-12-06 13:00 | 2022-12-13 12:00 | -28 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 02450 | 0 | 0 | SG5-02450 | Construction | 2nd Floor | Construction.2.3.6.3 | Install Light Fixtures & Controls - 2nd Floor | 4 | 4 | 0% | 2023-01-03 08:00 | 2023-01-06 17:00 | -40 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 02455 | 0 | 0 | SG5-02455 | Construction | 2nd Floor | Construction.2.3.6.3 | Install Smoke Detection Equipment - 2nd Floor | 5 | 5 | 0% | 2022-12-14 08:00 | 2022-12-20 17:00 | 80 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 02460 | 0 | 0 | SG5-02460 | Construction | 2nd Floor | Construction.2.3.6.3 | Install Receptacles - 2nd Floor | 4 | 4 | 0% | 2022-12-13 13:00 | 2022-12-19 12:00 | -24 | FSE | RECEPTACLES | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 02465 | 0 | 0 | SG5-02465 | Construction | 2nd Floor | Construction.2.3.6.3 | Install Fire Stopping - 2nd Floor | 4 | 4 | 0% | 2023-01-09 08:00 | 2023-01-12 17:00 | -40 | MLJ | FIRESTOPPING | EXISTING BUILDING | 07-1200 | 07-1200-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 02405 | 0 | 0 | SG5-02405 | Construction | 2nd Floor | Construction.2.3.6.3 | Tag & Terminate Switchgear Equipment | 5 | 5 | 0% | 2022-12-30 08:00 | 2023-01-06 17:00 | -36 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 02410 | 0 | 0 | SG5-02410 | Construction | 2nd Floor | Construction.2.3.6.3 | Tag & Terminate Panelboards - 2nd Floor | 2 | 2 | 0% | 2022-12-30 08:00 | 2023-01-03 17:00 | -33 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 02470 | 0 | 0 | SG5-02470 | Construction | 2nd Floor | Construction.2.3.6.3 | Ground Equipment | 5 | 5 | 0% | 2022-12-12 08:00 | 2022-12-16 17:00 | -28 | FSE | GROUNDING EQUIP | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 02480 | 0 | 0 | SG5-02480 | Construction | 2nd Floor | Construction.2.3.6.3 | Tag & Terminate Fire Alarm System - 2nd Floor | 2 | 2 | 0% | 2022-12-21 08:00 | 2022-12-22 17:00 | 92 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 02475 | 0 | 0 | SG5-02475 | Construction | 2nd Floor | Construction.2.3.6.3 | Pull CON-ED Feeder Cable - Cellar to SG-5 Switchgear - 2nd Floor | 10 | 10 | 0% | 2022-12-15 08:00 | 2022-12-29 17:00 | -36 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 02435 | 0 | 0 | SG5-02435 | Construction | 2nd Floor | Construction.2.3.6.3 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -27 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.4 | SG5 | SG5 | 02535 | 0 | 0 | SG5-02535 | Construction | Testing & Start-Up | Construction.2.3.6.4 | Start-Up Generator/Switchgear - SG-5 | 4 | 4 | 0% | 2023-05-22 08:00 | 2023-05-25 17:00 | -114 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.4 | SG5 | SG5 | 02505 | 0 | 0 | SG5-02505 | Construction | Testing & Start-Up | Construction.2.3.6.4 | Fire Alarm Operational & FDNY Acceptance Testing - SG5 | 5 | 5 | 0% | 2023-05-26 08:00 | 2023-06-02 17:00 | -14 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.4 | SG5 | SG5 | 02515 | 0 | 0 | SG5-02515 | Construction | Testing & Start-Up | Construction.2.3.6.4 | Energize Switchgear (By CON-ED) - SG5 | 5 | 5 | 0% | 2023-05-10 08:00 | 2023-05-16 17:00 | -114 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.4 | SG5 | SG5 | 02510 | 0 | 0 | SG5-02510 | Construction | Testing & Start-Up | Construction.2.3.6.4 | Perform Electrical Inspections - SG5 | 5 | 5 | 0% | 2023-03-14 08:00 | 2023-03-20 17:00 | -80 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.4 | SG5 | SG5 | 02525 | 0 | 0 | SG5-02525 | Construction | Testing & Start-Up | Construction.2.3.6.4 | Perform Tie-Ins to Existing | 3 | 3 | 0% | 2023-05-17 08:00 | 2023-05-19 17:00 | -114 | UNSURE | STARTUP | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.4 | SG5 | SG5 | 02530 | 0 | 0 | SG5-02530 | Construction | Testing & Start-Up | Construction.2.3.6.4 | Perform 3rd Party Test | 2 | 2 | 0% | 2023-05-08 08:00 | 2023-05-09 17:00 | -114 | UNSURE | STARTUP | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.4 | SG5 | SG5 | 02520 | 0 | 0 | SG5-02520 | Construction | Testing & Start-Up | Construction.2.3.6.4 | Notify NYCHA of Fire Alarm Acceptance Testing | 14 | 14 | 0% | 2023-05-08 08:00 | 2023-05-25 17:00 | -14 | FSE | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 02125 | 0 | 0 | SG6-02125 | Construction | 1st Floor | Construction.2.4.7.1 | Install Smoke Detection/Fire Alarm Equipment - 1st Floor | 5 | 0 | 100% | 2022-06-01 | 2022-09-26 17:00 |  | FSE | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 02130 | 0 | 0 | SG6-02130 | Construction | 1st Floor | Construction.2.4.7.1 | Install Light/Emergency Fixtures - 1st Floor | 5 | 0 | 100% | 2022-06-03 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 02115 | 0 | 0 | SG6-02115 | Construction | 1st Floor | Construction.2.4.7.1 | Pull Fire Alarm Wiring - 1st Floor | 5 | 0 | 100% | 2022-03-30 15:00 | 2022-09-26 12:00 |  | FSE | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 02135 | 0 | 0 | SG6-02135 | Construction | 1st Floor | Construction.2.4.7.1 | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - 1st Floor | 5 | 0 | 95% | 2022-09-23 | 2022-11-25 10:00 | 8 | FSE | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 02150 | 0 | 0 | SG6-02150 | Construction | 1st Floor | Construction.2.4.7.1 | Install Receptacles - 1st Floor | 2 | 0 | 100% | 2022-06-06 | 2022-11-15 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 02145 | 0 | 0 | SG6-02145 | Construction | 1st Floor | Construction.2.4.7.1 | Install Remote Annunciator Panel (RAP). - 1st Floor | 2 | 0 | 100% | 2022-06-06 | 2022-09-23 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 02105 | 0 | 0 | SG6-02105 | Construction | 1st Floor | Construction.2.4.7.1 | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 20 | 0 | 100% | 2021-11-30 | 2022-02-28 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 02110 | 0 | 0 | SG6-02110 | Construction | 1st Floor | Construction.2.4.7.1 | Install Branch Conduits - 1st Floor | 15 | 0 | 100% | 2021-07-01 | 2022-03-30 15:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 02120 | 0 | 0 | SG6-02120 | Construction | 1st Floor | Construction.2.4.7.1 | Pull Branch Wiring - 1st Floor | 5 | 0 | 100% | 2022-04-11 08:00 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 02140 | 0 | 0 | SG6-02140 | Construction | 1st Floor | Construction.2.4.7.1 | Install Heat Trace for Plumbing Lines -1st Floor | 3 | 0 | 100% | 2022-09-21 | 2022-09-23 |  | FSE | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 02155 | 0 | 0 | SG6-02155 | Construction | 1st Floor | Construction.2.4.7.1 | Install In-slab Conduits - drop from roof of 1st floor=2nd floor slab | 5 | 0 | 100% | 2021-08-02 08:00 | 2021-08-09 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 02160 | 0 | 0 | SG6-02160 | Construction | 1st Floor | Construction.2.4.7.1 | Install Exterior Lighting & Controls - 1st Floor | 2 | 0 | 100% | 2022-06-06 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.2 | SG6 | SG6 | 02210 | 0 | 0 | SG6-02210 | Construction | 2nd Floor | Construction.2.4.7.2 | Install Feeder Conduit Risers & Racks to Roof - 2nd Floor | 20 | 0 | 100% | 2021-12-14 | 2022-04-11 |  | FSE | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.2 | SG6 | SG6 | 02220 | 0 | 0 | SG6-02220 | Construction | 2nd Floor | Construction.2.4.7.2 | Install Controls & Pull Wire for Mechanical & Plumbing Equipment - 2nd Floor | 10 | 1 | 95% | 2022-06-13 | 2022-11-25 12:00 | -23 | FSE | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.2 | SG6 | SG6 | 02215 | 0 | 0 | SG6-02215 | Construction | 2nd Floor | Construction.2.4.7.2 | Install Branch Conduits - 2nd Floor | 15 | 0 | 100% | 2022-01-10 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.2 | SG6 | SG6 | 02225 | 0 | 0 | SG6-02225 | Construction | 2nd Floor | Construction.2.4.7.2 | Pull Branch Wiring - 2nd Floor | 5 | 0 | 100% | 2022-04-11 10:48 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.2 | SG6 | SG6 | 02230 | 0 | 0 | SG6-02230 | Construction | 2nd Floor | Construction.2.4.7.2 | Pull Fire Alarm Wiring - 2nd Floor | 5 | 0 | 100% | 2022-08-15 13:00 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.2 | SG6 | SG6 | 02235 | 0 | 0 | SG6-02235 | Construction | 2nd Floor | Construction.2.4.7.2 | Install Smoke Detection/Fire Alarm Equipment - 2nd Floor | 5 | 0 | 100% | 2022-06-13 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.2 | SG6 | SG6 | 02240 | 0 | 0 | SG6-02240 | Construction | 2nd Floor | Construction.2.4.7.2 | Install Light/Emergency Fixtures - 2nd Floor | 5 | 1 | 75% | 2022-06-13 | 2022-11-28 10:00 | -25 | FSE | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.2 | SG6 | SG6 | 02205 | 0 | 0 | SG6-02205 | Construction | 2nd Floor | Construction.2.4.7.2 | Install In-slab Conduits - drop from roof of 2nd floor=roof slab | 10 | 0 | 100% | 2021-11-26 08:00 | 2021-12-09 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.2 | SG6 | SG6 | 02245 | 0 | 0 | SG6-02245 | Construction | 2nd Floor | Construction.2.4.7.2 | Install Receptacles - 2nd Floor | 2 | 0 | 100% | 2022-06-13 | 2022-11-15 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02325 | 0 | 0 | SG6-02325 | Construction | Roof | Construction.2.4.7.3 | Install Feeder Conduit & Racks - Roof | 15 | 0 | 100% | 2022-01-10 | 2022-07-22 |  | FSE | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02375 | 0 | 0 | SG6-02375 | Construction | Roof | Construction.2.4.7.3 | Rig Generator SG-5 - Roof | 1 | 0 | 100% | 2022-04-22 08:00 | 2022-04-22 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02385 | 0 | 0 | SG6-02385 | Construction | Roof | Construction.2.4.7.3 | Install Generator Circuit Breakers & Wire Generator SG-4 - Roof | 10 | 1 | 95% | 2022-05-25 08:00 | 2022-11-25 12:00 | -18 | FSE | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02320 | 0 | 0 | SG6-02320 | Construction | Roof | Construction.2.4.7.3 | Install Branch Conduit - Roof | 5 | 0 | 95% | 2022-02-14 | 2022-11-25 10:00 | -24 | FSE | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02330 | 0 | 0 | SG6-02330 | Construction | Roof | Construction.2.4.7.3 | Pull Branch Wiring - Roof | 5 | 0 | 95% | 2022-06-15 | 2022-11-25 10:00 | -24 | FSE | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02380 | 0 | 0 | SG6-02380 | Construction | Roof | Construction.2.4.7.3 | Rig Generator SG-4 - Roof | 1 | 0 | 100% | 2022-04-22 08:00 | 2022-04-22 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02390 | 0 | 0 | SG6-02390 | Construction | Roof | Construction.2.4.7.3 | Install Generator Circuit Breakers & Wire Generator SG-5 - Roof | 10 | 1 | 95% | 2022-05-25 | 2022-11-25 12:00 | -18 | FSE | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02350 | 0 | 0 | SG6-02350 | Construction | Roof | Construction.2.4.7.3 | Terminate all Mech. & Plumbing Equipment at Panel (PP-SG6) - Roof | 5 | 1 | 90% | 2022-07-18 13:00 | 2022-11-30 15:00 | -23 | FSE | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02340 | 0 | 0 | SG6-02340 | Construction | Roof | Construction.2.4.7.3 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Roof | 5 | 0 | 95% | 2022-06-15 | 2022-11-25 10:00 | -22 | FSE | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02305 | 0 | 0 | SG6-02305 | Construction | Roof | Construction.2.4.7.3 | Install Switchboards - Roof | 4 | 0 | 100% | 2022-04-22 08:00 | 2022-05-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02310 | 0 | 0 | SG6-02310 | Construction | Roof | Construction.2.4.7.3 | Install ACTTS - Roof | 5 | 0 | 100% | 2022-05-26 08:00 | 2022-06-02 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02315 | 0 | 0 | SG6-02315 | Construction | Roof | Construction.2.4.7.3 | Install Panelboards - Roof | 10 | 0 | 100% | 2022-06-03 08:00 | 2022-07-22 |  | FSE | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02335 | 0 | 0 | SG6-02335 | Construction | Roof | Construction.2.4.7.3 | Install Smoke Detection/Fire Alarm Equipment - Roof | 5 | 0 | 95% | 2022-06-15 | 2022-11-25 10:00 | 86 | FSE | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02360 | 0 | 0 | SG6-02360 | Construction | Roof | Construction.2.4.7.3 | Install Receptacles - Roof | 3 | 1 | 75% | 2022-06-20 | 2022-11-25 15:00 | -25 | FSE | RECEPTACLES | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02355 | 0 | 0 | SG6-02355 | Construction | Roof | Construction.2.4.7.3 | Install Light/Emergency Fixtures - Roof | 5 | 1 | 75% | 2022-06-20 | 2022-11-28 10:00 | -25 | FSE | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02395 | 0 | 0 | SG6-02395 | Construction | Roof | Construction.2.4.7.3 | Install Lightning protection Air terminals - Roof | 5 | 1 | 90% | 2022-06-01 | 2022-11-25 12:00 | 80 | FSE | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02400 | 0 | 0 | SG6-02400 | Construction | Roof | Construction.2.4.7.3 | Install Grounding & Ground Equipment | 5 | 0 | 95% | 2022-04-15 | 2022-11-25 10:00 | -24 | FSE | GROUNDING EQUIP | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02365 | 0 | 0 | SG6-02365 | Construction | Roof | Construction.2.4.7.3 | Install Fire Alarm Control Panel (Incl. Telephone Lines) - Roof | 2 | 0 | 90% | 2022-06-17 | 2022-11-25 10:00 | 72 | FSE | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02345 | 0 | 0 | SG6-02345 | Construction | Roof | Construction.2.4.7.3 | Pull Fire Alarm Wiring - Roof | 5 | 0 | 95% | 2022-07-18 13:00 | 2022-11-25 10:00 | -24 | FSE | 0 | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02370 | 0 | 0 | SG6-02370 | Construction | Roof | Construction.2.4.7.3 | Terminate Light Fixtures - Roof | 5 | 5 | 0% | 2022-11-28 10:00 | 2022-12-05 10:00 | -25 | FSE | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02425 | 0 | 0 | SG6-02425 | Construction | Roof | Construction.2.4.7.3 | Install Firestopping | 4 | 0 | 95% | 2022-03-07 | 2022-11-25 10:00 | -19 | MLJ | FIRESTOPPING | NEW BUILDING | 07-1300 | 07-1300-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02405 | 0 | 0 | SG6-02405 | Construction | Roof | Construction.2.4.7.3 | Tag & Terminate Switchgear Equipment - Roof | 5 | 0 | 95% | 2022-08-08 15:00 | 2022-11-25 15:00 | -25 | FSE | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02415 | 0 | 0 | SG6-02415 | Construction | Roof | Construction.2.4.7.3 | Tag & Terminate Panelboards - Roof | 2 | 0 | 95% | 2022-08-08 15:00 | 2022-11-25 15:00 | -25 | FSE | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02420 | 0 | 0 | SG6-02420 | Construction | Roof | Construction.2.4.7.3 | Tag & Terminate Fire Alarm Equipment | 2 | 0 | 95% | 2022-08-08 15:00 | 2022-11-25 15:00 | 85 | FSE | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 02410 | 0 | 0 | SG6-02410 | Construction | Roof | Construction.2.4.7.3 | Pull Feeder Cable from Foundation to Roof - Roof | 10 | 0 | 100% | 2022-08-08 15:00 | 2022-09-26 17:00 |  | FSE | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.5 | SG6 | SG6 | 02010 | 0 | 0 | SG6-02010 | Construction | Foundation/Plumbing Shaft | Construction.2.4.7.5 | Install Branch Conduit in Plumbing Shaft - Foundation | 2 | 0 | 100% | 2022-06-09 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.5 | SG6 | SG6 | 02025 | 0 | 0 | SG6-02025 | Construction | Foundation/Plumbing Shaft | Construction.2.4.7.5 | Install Temporary Lighting & Temporary Power for SG-6 | 5 | 0 | 100% | 2021-06-01 | 2021-09-20 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.5 | SG6 | SG6 | 02005 | 0 | 0 | SG6-02005 | Construction | Foundation/Plumbing Shaft | Construction.2.4.7.5 | Install Conduit Risers to 1st Floor for Incoming Feeders - Foundation | 8 | 0 | 100% | 2021-07-01 | 2021-11-29 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.5 | SG6 | SG6 | 02015 | 0 | 0 | SG6-02015 | Construction | Foundation/Plumbing Shaft | Construction.2.4.7.5 | Pull Wire to Light Fixtures & Mechanical Equipment in Plumbing Shaft - Foundation | 2 | 0 | 100% | 2022-04-11 08:00 | 2022-09-26 17:00 |  | FSE | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.5 | SG6 | SG6 | 02020 | 0 | 0 | SG6-02020 | Construction | Foundation/Plumbing Shaft | Construction.2.4.7.5 | Install Pull Box - Foundation | 2 | 0 | 100% | 2021-10-24 | 2021-10-24 |  | 0 | 0 | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.2.4.7.6 | SG6 | SG6 | 02505 | 0 | 0 | SG6-02505 | Construction | Testing & Start-Up | Construction.2.4.7.6 | Fire Alarm Operational & FDNY Acceptance Testing - SG6 | 5 | 5 | 0% | 2023-04-26 08:00 | 2023-05-02 17:00 | -18 | FSE | 0 | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.2.4.7.6 | SG6 | SG6 | 02510 | 0 | 0 | SG6-02510 | Construction | Testing & Start-Up | Construction.2.4.7.6 | Provide Load Bank & Perform Acceptance Testing for Generator SG4 - SG6 | 2 | 2 | 0% | 2023-04-20 08:00 | 2023-04-21 17:00 | -114 | UNSURE | STARTUP | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.2.4.7.6 | SG6 | SG6 | 02520 | 0 | 0 | SG6-02520 | Construction | Testing & Start-Up | Construction.2.4.7.6 | Perform Electrical Inspections for SG6 | 5 | 5 | 0% | 2023-04-13 08:00 | 2023-04-19 17:00 | -114 | FSE | 0 | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.2.4.7.6 | SG6 | SG6 | 02525 | 0 | 0 | SG6-02525 | Construction | Testing & Start-Up | Construction.2.4.7.6 | Energize Switchgear Equipment - SG6 | 3 | 3 | 0% | 2022-11-25 08:00 | 2022-11-29 17:00 | -17 | FSE | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.6 | SG6 | SG6 | 02530 | 0 | 0 | SG6-02530 | Construction | Testing & Start-Up | Construction.2.4.7.6 | Perform 3rd Party Testing - SG6 | 2 | 0 | 100% | 2022-08-23 08:00 | 2022-10-07 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.2.4.7.6 | SG6 | SG6 | 02535 | 0 | 0 | SG6-02535 | Construction | Testing & Start-Up | Construction.2.4.7.6 | Notify NYCHA of Fire Alarm Testing - SG6 | 14 | 14 | 0% | 2023-04-06 08:00 | 2023-04-25 17:00 | -18 | FSE | 0 | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.2.4.7.6 | SG6 | SG6 | 02515 | 0 | 0 | SG6-02515 | Construction | Testing & Start-Up | Construction.2.4.7.6 | Provide Load Bank & Perform Acceptance Testing for Generator SG5 - SG6 | 2 | 2 | 0% | 2023-04-24 08:00 | 2023-04-25 17:00 | -114 | UNSURE | STARTUP | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.2.4.7.6 | SG6 | SG6 | 02540 | 0 | 0 | SG6-02540 | Construction | Testing & Start-Up | Construction.2.4.7.6 | Notify NYCHA of Generator Acceptance Testing - SG6 | 5 | 5 | 0% | 2023-04-13 08:00 | 2023-04-19 17:00 | -114 | UNSURE | STARTUP | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 02005 | 0 | 0 | OGW-02005 | Construction | Site Utilities | Construction.5.6.6 | Remove, Relocate or Abandon Exisiting Feeder Conduit & Cable | 5 | 3 | 50% | 2021-11-26 | 2022-11-29 12:00 | -28 | FSE | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 02010 | 0 | 0 | OGW-02010 | Construction | Site Utilities | Construction.5.6.6 | Install Manholes & Grounding | 8 | 0 | 100% | 2021-11-24 | 2021-11-24 |  | 0 | 0 | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.4 | OGW | OGW | 02105 | 0 | 0 | OGW-02105 | Construction | Cable Pulls | Construction.5.6.4 | Pull CON-ED Feeder Cable - 35th St. to OG3 Cellar | 10 | 10 | 0% | 2022-11-29 08:00 | 2022-12-12 17:00 | -14 | FSE | 0 | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.4 | OGW | OGW | 02110 | 0 | 0 | OGW-02110 | Construction | Cable Pulls | Construction.5.6.4 | Pull CON-ED Feeder Cable - 33rd St. to OG2 Cellar | 9 | 9 | 0% | 2022-11-25 08:00 | 2022-12-07 17:00 | -48 | FSE | 0 | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.4 | OGW | OGW | 02115 | 0 | 0 | OGW-02115 | Construction | Cable Pulls | Construction.5.6.4 | Pull Feeder Cable - OG2 Switchgear to OG9 Foundation | 10 | 10 | 0% | 2022-12-14 08:00 | 2022-12-28 17:00 | -38 | FSE | 0 | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.4 | OGW | OGW | 02125 | 0 | 0 | OGW-02125 | Construction | Cable Pulls | Construction.5.6.4 | Pull Generator Feeder Cable from OG9 to OG3 | 5 | 5 | 0% | 2022-12-09 08:00 | 2022-12-15 17:00 | 23 | FSE | 0 | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.4 | OGW | OGW | 02120 | 0 | 0 | OGW-02120 | Construction | Cable Pulls | Construction.5.6.4 | Pull Generator Feeder Cable from OG9 to OG2 | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | -17 | FSE | 0 | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.2 | OGW | OGW | 02205 | 0 | 0 | OGW-02205 | Construction | Site Lighting | Construction.5.6.2 | Remove Existing Lighting Conduit, Cable & Fixtures | 5 | 5 | 0% | 2023-05-05 08:00 | 2023-05-11 17:00 | -6 | FSE | 0 | 0 | 0 | 0-OGW
In Progress | CI NYCHA Update #22.Construction.5.6.2 | OGW | OGW | 02210 | 0 | 0 | OGW-02210 | Construction | Site Lighting | Construction.5.6.2 | Furnish & Install Site Lighting Conduit | 5 | 1 | 75% | 2022-09-21 | 2023-05-17 17:00 | -6 | FSE | 0 | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.2 | OGW | OGW | 02215 | 0 | 0 | OGW-02215 | Construction | Site Lighting | Construction.5.6.2 | Pull Site Lighting Wire | 3 | 3 | 0% | 2023-05-18 08:00 | 2023-05-22 17:00 | -6 | FSE | 0 | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.2 | OGW | OGW | 02220 | 0 | 0 | OGW-02220 | Construction | Site Lighting | Construction.5.6.2 | Install Site Lighting Fixtures & Terminate | 5 | 5 | 0% | 2023-05-23 08:00 | 2023-05-30 17:00 | -6 | FSE | 0 | 0 | 0 | 0-OGW
In Progress | CI NYCHA Update #22.Construction.5.4.5.4 | OG9 | OG9 | 02015 | 0 | 0 | OG9-02015 | Construction | Foundation | Construction.5.4.5.4 | Install Branch Conduit in Plumbing Shaft - Foundation | 2 | 1 | 50% | 2022-05-25 08:00 | 2022-11-25 17:00 | -26 | FSE | 0 | 0 | 0 | 0-OG9
In Progress | CI NYCHA Update #22.Construction.5.4.5.4 | OG9 | OG9 | 02005 | 0 | 0 | OG9-02005 | Construction | Foundation | Construction.5.4.5.4 | Install Temporary Lighting & Temporary Power for OG-9 | 5 | 1 | 85% | 2021-10-15 | 2022-11-25 15:00 | -11 | FSE | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.4 | OG9 | OG9 | 02010 | 0 | 0 | OG9-02010 | Construction | Foundation | Construction.5.4.5.4 | Install Conduit Risers to 1st Floor for Incoming Feeders - Foundation | 10 | 0 | 100% | 2021-10-06 | 2022-02-16 |  | 0 | 0 | 0 | 0 | 0-OG9
In Progress | CI NYCHA Update #22.Construction.5.4.5.4 | OG9 | OG9 | 02025 | 0 | 0 | OG9-02025 | Construction | Foundation | Construction.5.4.5.4 | Pull Wire to Light Fixture & Mechanical Equipment in Plumbing Shaft - Foundation | 2 | 1 | 50% | 2022-05-25 | 2022-12-12 17:00 | -37 | FSE | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.4 | OG9 | OG9 | 02020 | 0 | 0 | OG9-02020 | Construction | Foundation | Construction.5.4.5.4 | Install Pull Box - Foundation | 2 | 0 | 100% | 2022-01-27 | 2022-01-31 |  | 0 | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 02135 | 0 | 0 | OG9-02135 | Construction | 1st Floor | Construction.5.4.5.1 | Install Smoke Detection/Fire Alarm Equipment - 1st Floor | 3 | 3 | 0% | 2022-12-16 08:00 | 2022-12-20 17:00 | -37 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 02140 | 0 | 0 | OG9-02140 | Construction | 1st Floor | Construction.5.4.5.1 | Install Light/Emergency Fixtures - 1st Floor | 3 | 3 | 0% | 2022-12-16 08:00 | 2022-12-20 17:00 | -35 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 02120 | 0 | 0 | OG9-02120 | Construction | 1st Floor | Construction.5.4.5.1 | Pull Fire Alarm Wiring - 1st Floor | 3 | 3 | 0% | 2022-11-29 08:00 | 2022-12-01 17:00 | -27 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 02145 | 0 | 0 | OG9-02145 | Construction | 1st Floor | Construction.5.4.5.1 | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - 1st Floor | 3 | 3 | 0% | 2022-12-16 08:00 | 2022-12-20 17:00 | -35 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 02155 | 0 | 0 | OG9-02155 | Construction | 1st Floor | Construction.5.4.5.1 | Install Receptacles - 1st Floor | 2 | 2 | 0% | 2022-12-23 08:00 | 2022-12-27 17:00 | -37 | FSE | RECEPTACLES | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 02150 | 0 | 0 | OG9-02150 | Construction | 1st Floor | Construction.5.4.5.1 | Install Remote Annunciator Panel (RAP). - 1st Floor | 2 | 2 | 0% | 2022-12-21 08:00 | 2022-12-22 17:00 | -37 | MEP | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 02110 | 0 | 0 | OG9-02110 | Construction | 1st Floor | Construction.5.4.5.1 | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 10 | 0 | 100% | 2022-02-21 | 2022-07-01 |  | FSE | 0 | 0 | 0 | 0-OG9
In Progress | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 02115 | 0 | 0 | OG9-02115 | Construction | 1st Floor | Construction.5.4.5.1 | Install Branch Conduits - 1st Floor | 10 | 2 | 80% | 2022-02-21 | 2022-11-28 17:00 | -27 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 02125 | 0 | 0 | OG9-02125 | Construction | 1st Floor | Construction.5.4.5.1 | Pull Branch Wiring - 1st Floor | 3 | 3 | 0% | 2022-12-13 08:00 | 2022-12-15 17:00 | -37 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 02130 | 0 | 0 | OG9-02130 | Construction | 1st Floor | Construction.5.4.5.1 | Install Heat Trace for Plumbing Lines -1st Floor | 3 | 3 | 0% | 2022-12-16 08:00 | 2022-12-20 17:00 | -19 | FSE | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 02105 | 0 | 0 | OG9-02105 | Construction | 1st Floor | Construction.5.4.5.1 | Install In-slab Conduits - 1st floor slab | 3 | 0 | 100% | 2021-12-17 08:00 | 2021-12-21 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 02160 | 0 | 0 | OG9-02160 | Construction | 1st Floor | Construction.5.4.5.1 | Install Exterior Lighting & Controls - 1st Floor | 2 | 2 | 0% | 2022-12-16 08:00 | 2022-12-19 17:00 | -34 | FSE | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 02215 | 0 | 0 | OG9-02215 | Construction | 2nd Floor | Construction.5.4.5.2 | Install Feeder Conduit Risers & Racks to Roof - 2nd Floor | 20 | 0 | 100% | 2022-02-01 08:00 | 2022-07-01 17:00 |  | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 02240 | 0 | 0 | OG9-02240 | Construction | 2nd Floor | Construction.5.4.5.2 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | -14 | FSE | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 02220 | 0 | 0 | OG9-02220 | Construction | 2nd Floor | Construction.5.4.5.2 | Install Branch Conduits - 2nd Floor | 10 | 0 | 100% | 2021-12-20 | 2022-02-16 |  | 0 | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 02225 | 0 | 0 | OG9-02225 | Construction | 2nd Floor | Construction.5.4.5.2 | Pull Branch Wiring - 2nd Floor | 3 | 3 | 0% | 2022-11-25 08:00 | 2022-11-29 17:00 | -18 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 02230 | 0 | 0 | OG9-02230 | Construction | 2nd Floor | Construction.5.4.5.2 | Pull Fire Alarm Wiring - 2nd Floor | 3 | 3 | 0% | 2022-12-02 08:00 | 2022-12-06 17:00 | -26 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 02210 | 0 | 0 | OG9-02210 | Construction | 2nd Floor | Construction.5.4.5.2 | Install Smoke Detection/Fire Alarm Equipment - 2nd Floor | 3 | 3 | 0% | 2022-12-21 08:00 | 2022-12-23 17:00 | 86 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 02245 | 0 | 0 | OG9-02245 | Construction | 2nd Floor | Construction.5.4.5.2 | Install Light/Emergency Fixtures - 2nd Floor | 3 | 3 | 0% | 2022-11-30 08:00 | 2022-12-02 17:00 | -15 | FSE | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 02205 | 0 | 0 | OG9-02205 | Construction | 2nd Floor | Construction.5.4.5.2 | Install In-slab Conduits - 2nd floor slab - 2nd Floor | 10 | 0 | 100% | 2021-12-21 | 2022-02-15 |  | 0 | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 02235 | 0 | 0 | OG9-02235 | Construction | 2nd Floor | Construction.5.4.5.2 | Install Receptacles - 2nd Floor | 2 | 2 | 0% | 2022-12-28 08:00 | 2022-12-29 17:00 | -37 | FSE | RECEPTACLES | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 02270 | 0 | 0 | OG9-02270 | Construction | 2nd Floor | Construction.5.4.5.2 | Install Switchboards - 2nd Floor | 3 | 0 | 100% | 2022-09-07 | 2022-09-14 |  | FSE | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 02275 | 0 | 0 | OG9-02275 | Construction | 2nd Floor | Construction.5.4.5.2 | Install ACTTS - 2nd Floor | 3 | 0 | 100% | 2022-09-07 | 2022-09-14 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 02280 | 0 | 0 | OG9-02280 | Construction | 2nd Floor | Construction.5.4.5.2 | Install Panelboards - 2nd Floor | 6 | 0 | 100% | 2022-09-07 | 2022-09-14 |  | FSE | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 02250 | 0 | 0 | OG9-02250 | Construction | 2nd Floor | Construction.5.4.5.2 | Install Feeder Conduits & Racks - 2nd Floor | 15 | 0 | 100% | 2022-02-17 | 2022-07-01 10:00 |  | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 02255 | 0 | 0 | OG9-02255 | Construction | 2nd Floor | Construction.5.4.5.2 | Pull Feeder Cable from Foundation Level - 2nd Floor | 5 | 5 | 0% | 2022-12-29 08:00 | 2023-01-05 17:00 | -36 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 02260 | 0 | 0 | OG9-02260 | Construction | 2nd Floor | Construction.5.4.5.2 | Tag & Terminate Switchgear - 2nd Floor | 5 | 5 | 0% | 2023-01-06 08:00 | 2023-01-12 17:00 | -34 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 02265 | 0 | 0 | OG9-02265 | Construction | 2nd Floor | Construction.5.4.5.2 | Tag & Terminate Panelboards - 2nd Floor | 5 | 5 | 0% | 2023-01-06 08:00 | 2023-01-12 17:00 | -34 | FSE | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02325 | 0 | 0 | OG9-02325 | Construction | Roof | Construction.5.4.5.3 | Install Feeder Conduit & Racks - Roof | 5 | 0 | 100% | 2022-06-20 | 2022-07-01 12:00 |  | FSE | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02310 | 0 | 0 | OG9-02310 | Construction | Roof | Construction.5.4.5.3 | Rig Generator OG2 - Roof | 1 | 0 | 100% | 2022-08-24 08:00 | 2022-08-24 17:00 |  | WELKIN | GENERATOR | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02335 | 0 | 0 | OG9-02335 | Construction | Roof | Construction.5.4.5.3 | Install Generator Circuit Breakers & Wire Generator OG3- Roof | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | -38 | FSE | 0 | 0 | 0 | 0-OG9
In Progress | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02330 | 0 | 0 | OG9-02330 | Construction | Roof | Construction.5.4.5.3 | Install Branch Conduit - Roof | 4 | 1 | 80% | 2022-01-17 | 2022-11-25 15:24 | -22 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02340 | 0 | 0 | OG9-02340 | Construction | Roof | Construction.5.4.5.3 | Pull Branch Wiring - Roof | 3 | 3 | 0% | 2022-11-25 15:24 | 2022-11-30 15:24 | -22 | FSE | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02315 | 0 | 0 | OG9-02315 | Construction | Roof | Construction.5.4.5.3 | Rig Generator OG3 - Roof | 1 | 0 | 100% | 2022-08-24 08:00 | 2022-08-24 17:00 |  | WELKIN | GENERATOR | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02360 | 0 | 0 | OG9-02360 | Construction | Roof | Construction.5.4.5.3 | Install Generator Circuit Breakers & Wire Generator OG2 - Roof | 10 | 10 | 0% | 2022-12-09 08:00 | 2022-12-22 17:00 | -38 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02415 | 0 | 0 | OG9-02415 | Construction | Roof | Construction.5.4.5.3 | Terminate all Mech. & Plumbing Equipment at Panel (PP-OG9) - Roof | 3 | 3 | 0% | 2023-01-12 08:00 | 2023-01-17 17:00 | -36 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02345 | 0 | 0 | OG9-02345 | Construction | Roof | Construction.5.4.5.3 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Roof | 5 | 5 | 0% | 2022-11-30 08:00 | 2022-12-06 17:00 | -12 | FSE | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02320 | 0 | 0 | OG9-02320 | Construction | Roof | Construction.5.4.5.3 | Install Panelboards - Roof | 1 | 0 | 100% | 2022-08-24 08:00 | 2022-08-24 17:00 |  | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02375 | 0 | 0 | OG9-02375 | Construction | Roof | Construction.5.4.5.3 | Install Smoke Detection/Fire Alarm Equipment - Roof | 3 | 3 | 0% | 2022-12-27 08:00 | 2022-12-29 17:00 | 86 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02370 | 0 | 0 | OG9-02370 | Construction | Roof | Construction.5.4.5.3 | Install Receptacles - Roof | 3 | 3 | 0% | 2022-12-30 08:00 | 2023-01-04 17:00 | -37 | FSE | RECEPTACLES | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02350 | 0 | 0 | OG9-02350 | Construction | Roof | Construction.5.4.5.3 | Install Light/Emergency Fixtures - Roof | 3 | 3 | 0% | 2022-12-05 08:00 | 2022-12-07 17:00 | -15 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02380 | 0 | 0 | OG9-02380 | Construction | Roof | Construction.5.4.5.3 | Install Lightning protection Air terminals - Roof | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | -38 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02385 | 0 | 0 | OG9-02385 | Construction | Roof | Construction.5.4.5.3 | Install Grounding & Ground Equipment | 3 | 3 | 0% | 2023-01-03 08:00 | 2023-01-05 17:00 | -38 | FSE | GROUNDING EQUIP | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02365 | 0 | 0 | OG9-02365 | Construction | Roof | Construction.5.4.5.3 | Install Fire Alarm Control Panel (Incl. Telephone Lines) - Roof | 2 | 2 | 0% | 2022-12-23 08:00 | 2022-12-27 17:00 | -35 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02355 | 0 | 0 | OG9-02355 | Construction | Roof | Construction.5.4.5.3 | Pull Fire Alarm Wiring - Roof | 3 | 3 | 0% | 2022-12-07 08:00 | 2022-12-09 17:00 | -26 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02420 | 0 | 0 | OG9-02420 | Construction | Roof | Construction.5.4.5.3 | Terminate Light Fixtures - Roof | 5 | 5 | 0% | 2023-01-12 08:00 | 2023-01-19 17:00 | -38 | FSE | 0 | 0 | 0 | 0-OG9
In Progress | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02400 | 0 | 0 | OG9-02400 | Construction | Roof | Construction.5.4.5.3 | Install Firestopping | 4 | 2 | 50% | 2022-06-21 | 2022-11-28 17:00 | -3 | MLJ | FIRESTOPPING | NEW BUILDING | 07-1300 | 07-1300-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02395 | 0 | 0 | OG9-02395 | Construction | Roof | Construction.5.4.5.3 | Tag & Terminate Switchgear Equipment - Roof | 2 | 2 | 0% | 2023-01-06 08:00 | 2023-01-09 17:00 | -38 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02405 | 0 | 0 | OG9-02405 | Construction | Roof | Construction.5.4.5.3 | Tag & Terminate Panelboards - Roof | 2 | 2 | 0% | 2023-01-10 08:00 | 2023-01-11 17:00 | -38 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02410 | 0 | 0 | OG9-02410 | Construction | Roof | Construction.5.4.5.3 | Tag & Terminate Fire Alarm Equipment | 2 | 2 | 0% | 2023-01-12 08:00 | 2023-01-13 17:00 | 78 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 02390 | 0 | 0 | OG9-02390 | Construction | Roof | Construction.5.4.5.3 | Pull CON-ED Feeder Cable from Foundation Level - Roof | 5 | 5 | 0% | 2022-12-29 08:00 | 2023-01-05 17:00 | -38 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.6 | OG9 | OG9 | 02535 | 0 | 0 | OG9-02535 | Construction | Testing & Start-Up | Construction.5.4.6 | Fire Alarm Operational & FDNY Acceptance Testing - OG9 | 5 | 5 | 0% | 2023-04-20 08:00 | 2023-04-26 17:00 | 12 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.6 | OG9 | OG9 | 02520 | 0 | 0 | OG9-02520 | Construction | Testing & Start-Up | Construction.5.4.6 | Provide Load Bank & Perform Acceptance Testing for Generator OG3 - OG9 | 2 | 2 | 0% | 2023-04-03 08:00 | 2023-04-04 17:00 | -83 | UNSURE | STARTUP | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.6 | OG9 | OG9 | 02505 | 0 | 0 | OG9-02505 | Construction | Testing & Start-Up | Construction.5.4.6 | Perform Electrical Inspections for OG9 | 5 | 5 | 0% | 2023-03-14 08:00 | 2023-03-20 17:00 | -74 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.6 | OG9 | OG9 | 02515 | 0 | 0 | OG9-02515 | Construction | Testing & Start-Up | Construction.5.4.6 | Energize Switchgear Equipment - OG9 | 3 | 3 | 0% | 2023-04-17 08:00 | 2023-04-19 17:00 | 12 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.6 | OG9 | OG9 | 02510 | 0 | 0 | OG9-02510 | Construction | Testing & Start-Up | Construction.5.4.6 | Perform 3rd Party Testing - OG9 | 2 | 2 | 0% | 2023-04-13 08:00 | 2023-04-14 17:00 | 12 | UNSURE | STARTUP | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.6 | OG9 | OG9 | 02525 | 0 | 0 | OG9-02525 | Construction | Testing & Start-Up | Construction.5.4.6 | Notify NYCHA of Fire Alarm Testing - OG9 | 14 | 14 | 0% | 2023-03-31 08:00 | 2023-04-19 17:00 | 12 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.6 | OG9 | OG9 | 02530 | 0 | 0 | OG9-02530 | Construction | Testing & Start-Up | Construction.5.4.6 | Provide Load Bank & Perform Acceptance Testing for Generator OG2 - OG9 | 2 | 2 | 0% | 2023-04-05 08:00 | 2023-04-06 17:00 | -83 | UNSURE | STARTUP | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.6 | OG9 | OG9 | 02540 | 0 | 0 | OG9-02540 | Construction | Testing & Start-Up | Construction.5.4.6 | Notify NYCHA of Generator Acceptance Testing- OG9 | 15 | 15 | 0% | 2023-03-13 08:00 | 2023-03-31 17:00 | -83 | UNSURE | STARTUP | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 02005 | 0 | 0 | OG2-02005 | Construction | Cellar | Construction.5.2.8.1 | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | -29 | FSE | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 02010 | 0 | 0 | OG2-02010 | Construction | Cellar | Construction.5.2.8.1 | Install Bypass Connections - Cellar | 6 | 0 | 100% | 2022-05-17 | 2022-05-20 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 02015 | 0 | 0 | OG2-02015 | Construction | Cellar | Construction.5.2.8.1 | Relocate (E) & Install Temporary Lighting Cellar | 5 | 0 | 100% | 2021-12-20 | 2022-09-09 17:00 |  | FSE | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 02030 | 0 | 0 | OG2-02030 | Construction | Cellar | Construction.5.2.8.1 | Core Drill & Install Incoming Feeder Conduits & Racks - Cellar | 18 | 0 | 100% | 2022-02-18 | 2022-05-16 |  | 0 | 0 | 0 | 0 | 0-OG2
In Progress | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 02020 | 0 | 0 | OG2-02020 | Construction | Cellar | Construction.5.2.8.1 | Install Branch Conduit - Cellar | 20 | 5 | 75% | 2022-06-16 | 2022-12-05 17:00 | -29 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 02040 | 0 | 0 | OG2-02040 | Construction | Cellar | Construction.5.2.8.1 | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 20 | 20 | 0% | 2022-11-25 08:00 | 2022-12-22 17:00 | -51 | FSE | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 02045 | 0 | 0 | OG2-02045 | Construction | Cellar | Construction.5.2.8.1 | Link & Seal Conduit Sleeves - Cellar | 10 | 0 | 100% | 2021-10-22 | 2021-10-22 |  | 0 | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 02050 | 0 | 0 | OG2-02050 | Construction | Cellar | Construction.5.2.8.1 | Pull Lighting Wiring - Cellar | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | -51 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 02055 | 0 | 0 | OG2-02055 | Construction | Cellar | Construction.5.2.8.1 | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 5 | 5 | 0% | 2023-01-03 08:00 | 2023-01-09 17:00 | -51 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 02025 | 0 | 0 | OG2-02025 | Construction | Cellar | Construction.5.2.8.1 | Pull Branch Wiring - Cellar | 8 | 8 | 0% | 2022-12-06 08:00 | 2022-12-15 17:00 | -29 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 02035 | 0 | 0 | OG2-02035 | Construction | Cellar | Construction.5.2.8.1 | Install Heat Trace for Plumbing Lines - Cellar | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -29 | FSE | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 02060 | 0 | 0 | OG2-02060 | Construction | Cellar | Construction.5.2.8.1 | Cored Drill & Install Feeder Conduits Risers & Racks to 1st Floor - Cellar | 18 | 0 | 100% | 2022-05-12 | 2022-07-01 |  | FSE | CORE DRILL | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 02065 | 0 | 0 | OG2-02065 | Construction | Cellar | Construction.5.2.8.1 | Install Panelboards (Misc.) | 2 | 2 | 0% | 2022-12-02 08:00 | 2022-12-05 17:00 | -29 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 02070 | 0 | 0 | OG2-02070 | Construction | Cellar | Construction.5.2.8.1 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Cellar | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -29 | FSE | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.8.2 | OG2 | OG2 | 02130 | 0 | 0 | OG2-02130 | Construction | 1st Floor | Construction.5.2.8.2 | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 10 | 0 | 100% | 2022-06-01 | 2022-07-15 |  | FSE | 0 | 0 | 0 | 0-OG2
In Progress | CI NYCHA Update #22.Construction.5.2.8.2 | OG2 | OG2 | 02135 | 0 | 0 | OG2-02135 | Construction | 1st Floor | Construction.5.2.8.2 | Install Pull Boxes - 1st Floor | 6 | 1 | 90% | 2022-06-13 | 2022-11-25 13:48 | -40 | FSE | PULL BOXES | 0 | 0 | 0-OG2
In Progress | CI NYCHA Update #22.Construction.5.2.8.2 | OG2 | OG2 | 02105 | 0 | 0 | OG2-02105 | Construction | 1st Floor | Construction.5.2.8.2 | Install Branch Conduit - 1st Floor | 15 | 4 | 75% | 2022-06-10 | 2022-11-30 15:00 | -30 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.2 | OG2 | OG2 | 02110 | 0 | 0 | OG2-02110 | Construction | 1st Floor | Construction.5.2.8.2 | Pull Branch Wiring - 1st Floor | 5 | 5 | 0% | 2022-11-30 15:00 | 2022-12-07 15:00 | -30 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.2 | OG2 | OG2 | 02115 | 0 | 0 | OG2-02115 | Construction | 1st Floor | Construction.5.2.8.2 | Install Fire Alarm Control Panel & Equipment - 1st Floor | 2 | 2 | 0% | 2022-12-07 15:00 | 2022-12-09 15:00 | -30 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.2 | OG2 | OG2 | 02120 | 0 | 0 | OG2-02120 | Construction | 1st Floor | Construction.5.2.8.2 | Pull Fire Alarm Wiring - 1st Floor | 2 | 2 | 0% | 2022-12-09 15:00 | 2022-12-13 15:00 | 80 | FSE | 0 | 0 | 0 | 0-OG2
In Progress | CI NYCHA Update #22.Construction.5.2.8.2 | OG2 | OG2 | 02125 | 0 | 0 | OG2-02125 | Construction | 1st Floor | Construction.5.2.8.2 | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 5 | 4 | 25% | 2022-06-13 | 2022-11-30 15:00 | -22 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.2 | OG2 | OG2 | 02140 | 0 | 0 | OG2-02140 | Construction | 1st Floor | Construction.5.2.8.2 | Supply Power to Exterior Building Signage | 2 | 2 | 0% | 2023-01-10 08:00 | 2023-01-11 17:00 | -51 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.2 | OG2 | OG2 | 02145 | 0 | 0 | OG2-02145 | Construction | 1st Floor | Construction.5.2.8.2 | Install Firestopping - 1st Floor | 5 | 5 | 0% | 2023-01-12 08:00 | 2023-01-19 17:00 | -51 | MLJ | FIRESTOPPING | EXISTING BUILDING | 07-1200 | 07-1200-OG2
In Progress | CI NYCHA Update #22.Construction.5.2.8.2 | OG2 | OG2 | 02150 | 0 | 0 | OG2-02150 | Construction | 1st Floor | Construction.5.2.8.2 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 1st Floor | 5 | 4 | 15% | 2022-06-14 | 2022-12-01 10:00 | -13 | FSE | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 02205 | 0 | 0 | OG2-02205 | Construction | 2nd Floor | Construction.5.2.8.3 | Install Switchboards - 2nd Floor | 12 | 0 | 100% | 2022-07-01 | 2022-09-30 17:00 |  | FSE | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 02210 | 0 | 0 | OG2-02210 | Construction | 2nd Floor | Construction.5.2.8.3 | Install ACTTS - 2nd Floor | 5 | 0 | 100% | 2022-07-01 | 2022-09-30 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 02215 | 0 | 0 | OG2-02215 | Construction | 2nd Floor | Construction.5.2.8.3 | Install Feeder Conduits & Racks to Switchgear Equipment - 2nd Floor | 18 | 0 | 100% | 2022-06-15 | 2022-10-06 17:00 |  | FSE | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 02220 | 0 | 0 | OG2-02220 | Construction | 2nd Floor | Construction.5.2.8.3 | Install Panelboards - 2nd Floor | 5 | 0 | 100% | 2022-10-07 08:00 | 2022-10-13 17:00 |  | FSE | 0 | 0 | 0 | 0-OG2
In Progress | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 02230 | 0 | 0 | OG2-02230 | Construction | 2nd Floor | Construction.5.2.8.3 | Install Branch Conduit - 2nd Floor | 18 | 3 | 85% | 2022-06-15 | 2022-11-29 14:36 | -27 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 02235 | 0 | 0 | OG2-02235 | Construction | 2nd Floor | Construction.5.2.8.3 | Pull Branch Wiring - 2nd Floor | 6 | 6 | 0% | 2022-11-29 14:36 | 2022-12-07 14:36 | -27 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 02240 | 0 | 0 | OG2-02240 | Construction | 2nd Floor | Construction.5.2.8.3 | Install Lighting Fixtures & Controls - 2nd Floor | 4 | 4 | 0% | 2022-12-07 14:36 | 2022-12-13 14:36 | -27 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 02270 | 0 | 0 | OG2-02270 | Construction | 2nd Floor | Construction.5.2.8.3 | Install Fire Alarm Equipment - 2nd Floor | 5 | 5 | 0% | 2023-01-12 08:00 | 2023-01-19 17:00 | 61 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 02245 | 0 | 0 | OG2-02245 | Construction | 2nd Floor | Construction.5.2.8.3 | Install Receptacles - 2nd Floor | 4 | 4 | 0% | 2022-12-07 14:36 | 2022-12-13 14:36 | -22 | FSE | RECEPTACLES | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 02275 | 0 | 0 | OG2-02275 | Construction | 2nd Floor | Construction.5.2.8.3 | Install Fire Stopping - 2nd Floor | 5 | 5 | 0% | 2023-01-20 08:00 | 2023-01-26 17:00 | -51 | MLJ | FIRESTOPPING | EXISTING BUILDING | 07-1200 | 07-1200-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 02255 | 0 | 0 | OG2-02255 | Construction | 2nd Floor | Construction.5.2.8.3 | Tag & Terminate Panelboards | 2 | 2 | 0% | 2023-01-05 08:00 | 2023-01-06 17:00 | -38 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 02260 | 0 | 0 | OG2-02260 | Construction | 2nd Floor | Construction.5.2.8.3 | Tag & Terminate Switchgear Equipment | 5 | 5 | 0% | 2023-01-05 08:00 | 2023-01-11 17:00 | -41 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 02225 | 0 | 0 | OG2-02225 | Construction | 2nd Floor | Construction.5.2.8.3 | Ground Equipment | 5 | 5 | 0% | 2022-12-09 15:00 | 2022-12-16 15:00 | -30 | FSE | GROUNDING EQUIP | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 02280 | 0 | 0 | OG2-02280 | Construction | 2nd Floor | Construction.5.2.8.3 | Terminate Fire Alarm System | 5 | 5 | 0% | 2023-01-20 08:00 | 2023-01-26 17:00 | 70 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 02250 | 0 | 0 | OG2-02250 | Construction | 2nd Floor | Construction.5.2.8.3 | Pull CON-ED Feeder Cable - Cellar to Switchgear - 2nd Floor | 18 | 18 | 0% | 2022-12-08 08:00 | 2023-01-04 17:00 | -48 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 02265 | 0 | 0 | OG2-02265 | Construction | 2nd Floor | Construction.5.2.8.3 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -29 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.4 | OG2 | OG2 | 02535 | 0 | 0 | OG2-02535 | Construction | Testing & Start-Up | Construction.5.2.8.4 | Fire Alarm Operational & FDNY Acceptance Testing - OG2 | 5 | 5 | 0% | 2023-05-05 08:00 | 2023-05-11 17:00 | 1 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.4 | OG2 | OG2 | 02515 | 0 | 0 | OG2-02515 | Construction | Testing & Start-Up | Construction.5.2.8.4 | Energize Switchgear - OG2 | 5 | 5 | 0% | 2023-04-17 08:00 | 2023-04-21 17:00 | -99 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.4 | OG2 | OG2 | 02525 | 0 | 0 | OG2-02525 | Construction | Testing & Start-Up | Construction.5.2.8.4 | Start-Up Generator/Switchgear - OG2 | 4 | 4 | 0% | 2023-05-01 08:00 | 2023-05-04 17:00 | -99 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.4 | OG2 | OG2 | 02505 | 0 | 0 | OG2-02505 | Construction | Testing & Start-Up | Construction.5.2.8.4 | Perform Electrical Inspections - OG2 | 5 | 5 | 0% | 2023-03-14 08:00 | 2023-03-20 17:00 | -82 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.4 | OG2 | OG2 | 02510 | 0 | 0 | OG2-02510 | Construction | Testing & Start-Up | Construction.5.2.8.4 | Perform 3rd Party Test - OG2 | 2 | 2 | 0% | 2023-04-13 08:00 | 2023-04-14 17:00 | -99 | UNSURE | STARTUP | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.4 | OG2 | OG2 | 02530 | 0 | 0 | OG2-02530 | Construction | Testing & Start-Up | Construction.5.2.8.4 | Notify NYCHA of Fire Alarm Acceptance Testing - OG2 | 14 | 14 | 0% | 2023-04-17 08:00 | 2023-05-04 17:00 | 1 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.4 | OG2 | OG2 | 02520 | 0 | 0 | OG2-02520 | Construction | Testing & Start-Up | Construction.5.2.8.4 | Perform Tie-in's to Exisiting - OG2 | 5 | 5 | 0% | 2023-04-24 08:00 | 2023-04-28 17:00 | -99 | UNSURE | STARTUP | 0 | 0 | 0-OG2
In Progress | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 02005 | 0 | 0 | OG3-02005 | Construction | Cellar | Construction.5.3.8.1 | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 4 | 3 | 15% | 2022-06-06 | 2022-11-30 11:12 | -15 | FSE | 0 | 0 | 0 | 0-OG3
In Progress | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 02010 | 0 | 0 | OG3-02010 | Construction | Cellar | Construction.5.3.8.1 | Install Bypass Connections - Cellar | 6 | 5 | 15% | 2022-02-15 | 2022-12-07 11:12 | -15 | MEP | 0 | 0 | 0 | 0-OG3
In Progress | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 02015 | 0 | 0 | OG3-02015 | Construction | Cellar | Construction.5.3.8.1 | Relocate (E) & Install Temporary Lighting Cellar | 4 | 1 | 75% | 2022-02-16 | 2022-12-09 11:12 | -15 | FSE | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 02035 | 0 | 0 | OG3-02035 | Construction | Cellar | Construction.5.3.8.1 | Core Drill & Install Incoming Feeder Conduits & Racks - Cellar | 18 | 0 | 100% | 2021-12-20 | 2022-06-01 |  | FSE | CORE DRILL | 0 | 0 | 0-OG3
In Progress | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 02020 | 0 | 0 | OG3-02020 | Construction | Cellar | Construction.5.3.8.1 | Install Branch Conduit - Cellar | 20 | 10 | 50% | 2022-02-16 | 2022-12-23 11:12 | -9 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 02040 | 0 | 0 | OG3-02040 | Construction | Cellar | Construction.5.3.8.1 | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 18 | 18 | 0% | 2022-12-09 11:12 | 2023-01-06 11:12 | -15 | FSE | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 02050 | 0 | 0 | OG3-02050 | Construction | Cellar | Construction.5.3.8.1 | Link & Seal Conduit Sleeves - Cellar | 10 | 0 | 100% | 2021-10-22 | 2021-10-22 |  | 0 | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 02045 | 0 | 0 | OG3-02045 | Construction | Cellar | Construction.5.3.8.1 | Pull Lighting Wiring - Cellar | 5 | 5 | 0% | 2023-01-06 11:12 | 2023-01-13 11:12 | -15 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 02055 | 0 | 0 | OG3-02055 | Construction | Cellar | Construction.5.3.8.1 | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 5 | 5 | 0% | 2023-01-13 11:12 | 2023-01-23 11:12 | -15 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 02025 | 0 | 0 | OG3-02025 | Construction | Cellar | Construction.5.3.8.1 | Pull Branch Wiring - Cellar | 7 | 7 | 0% | 2022-12-23 11:12 | 2023-01-05 11:12 | -9 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 02030 | 0 | 0 | OG3-02030 | Construction | Cellar | Construction.5.3.8.1 | Install Heat Trace for Plumbing Lines - Cellar | 2 | 2 | 0% | 2023-01-05 11:12 | 2023-01-09 11:12 | -6 | FSE | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 02060 | 0 | 0 | OG3-02060 | Construction | Cellar | Construction.5.3.8.1 | Core Drill & Install Conduits Risers & Racks to 1st Floor - Cellar | 18 | 0 | 100% | 2022-05-10 | 2022-07-01 |  | FSE | CORE DRILL | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 02065 | 0 | 0 | OG3-02065 | Construction | Cellar | Construction.5.3.8.1 | Install Panelboards (Misc.) | 2 | 2 | 0% | 2022-11-30 11:12 | 2022-12-02 11:12 | -9 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 02070 | 0 | 0 | OG3-02070 | Construction | Cellar | Construction.5.3.8.1 | Install Controls & Pull Wire to Mechanical & Plumbing Equipmen - Cellar | 5 | 5 | 0% | 2023-01-05 11:12 | 2023-01-12 11:12 | -9 | FSE | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.8.2 | OG3 | OG3 | 02130 | 0 | 0 | OG3-02130 | Construction | 1st Floor | Construction.5.3.8.2 | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 12 | 0 | 100% | 2022-05-23 | 2022-07-01 |  | FSE | 0 | 0 | 0 | 0-OG3
In Progress | CI NYCHA Update #22.Construction.5.3.8.2 | OG3 | OG3 | 02135 | 0 | 0 | OG3-02135 | Construction | 1st Floor | Construction.5.3.8.2 | Install Pull Boxes - 1st Floor | 4 | 2 | 50% | 2022-06-24 | 2022-11-28 17:00 | -14 | FSE | PULL BOXES | 0 | 0 | 0-OG3
In Progress | CI NYCHA Update #22.Construction.5.3.8.2 | OG3 | OG3 | 02105 | 0 | 0 | OG3-02105 | Construction | 1st Floor | Construction.5.3.8.2 | Install Branch Conduit - 1st Floor | 11 | 6 | 50% | 2022-06-13 | 2022-12-02 12:00 | -3 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.2 | OG3 | OG3 | 02110 | 0 | 0 | OG3-02110 | Construction | 1st Floor | Construction.5.3.8.2 | Pull Branch Wiring - 1st Floor | 6 | 6 | 0% | 2022-12-02 13:00 | 2022-12-12 12:00 | -3 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.2 | OG3 | OG3 | 02115 | 0 | 0 | OG3-02115 | Construction | 1st Floor | Construction.5.3.8.2 | Install Fire Alarm Control Panel (FACP) & Smoke Detectors - 1st Floor | 2 | 2 | 0% | 2022-12-12 13:00 | 2022-12-14 12:00 | -3 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.2 | OG3 | OG3 | 02120 | 0 | 0 | OG3-02120 | Construction | 1st Floor | Construction.5.3.8.2 | Pull Fire Alarm Wiring - 1st Floor | 2 | 2 | 0% | 2022-12-14 13:00 | 2022-12-16 12:00 | 78 | FSE | 0 | 0 | 0 | 0-OG3
In Progress | CI NYCHA Update #22.Construction.5.3.8.2 | OG3 | OG3 | 02125 | 0 | 0 | OG3-02125 | Construction | 1st Floor | Construction.5.3.8.2 | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 5 | 4 | 25% | 2022-06-14 | 2022-11-30 15:00 | 15 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.2 | OG3 | OG3 | 02140 | 0 | 0 | OG3-02140 | Construction | 1st Floor | Construction.5.3.8.2 | Supply Power to Exterior Building Signage | 2 | 2 | 0% | 2023-01-10 08:00 | 2023-01-11 17:00 | -9 | FSE | 0 | 0 | 0 | 0-OG3
In Progress | CI NYCHA Update #22.Construction.5.3.8.2 | OG3 | OG3 | 02150 | 0 | 0 | OG3-02150 | Construction | 1st Floor | Construction.5.3.8.2 | Install Firestopping - 1st Floor | 5 | 4 | 25% | 2022-06-17 | 2022-12-12 12:00 | 12 | MLJ | FIRESTOPPING | EXISTING BUILDING | 07-1200 | 07-1200-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.2 | OG3 | OG3 | 02145 | 0 | 0 | OG3-02145 | Construction | 1st Floor | Construction.5.3.8.2 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 1st Floor | 5 | 5 | 0% | 2023-01-03 08:00 | 2023-01-09 17:00 | -7 | FSE | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 02205 | 0 | 0 | OG3-02205 | Construction | 2nd Floor | Construction.5.3.8.3 | Install Switchboards - 2nd Floor | 12 | 0 | 100% | 2022-09-23 | 2022-10-14 17:00 |  | FSE | 0 | 0 | 0 | 0-OG3
In Progress | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 02210 | 0 | 0 | OG3-02210 | Construction | 2nd Floor | Construction.5.3.8.3 | Install ACTTS - 2nd Floor | 4 | 0 | 95% | 2022-10-03 08:00 | 2022-11-25 09:36 | -2 | FSE | ACTTS | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 02215 | 0 | 0 | OG3-02215 | Construction | 2nd Floor | Construction.5.3.8.3 | Install Feeder Conduits & Racks to Switchgear Equipment - 2nd Floor | 18 | 0 | 100% | 2022-06-15 | 2022-07-01 |  | FSE | 0 | 0 | 0 | 0-OG3
In Progress | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 02220 | 0 | 0 | OG3-02220 | Construction | 2nd Floor | Construction.5.3.8.3 | Install Panelboards - 2nd Floor | 4 | 0 | 95% | 2022-10-03 08:00 | 2022-11-25 09:36 | 9 | FSE | 0 | 0 | 0 | 0-OG3
In Progress | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 02230 | 0 | 0 | OG3-02230 | Construction | 2nd Floor | Construction.5.3.8.3 | Install Branch Conduit - 2nd Floor | 18 | 5 | 75% | 2022-11-01 | 2022-12-02 09:36 | 9 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 02235 | 0 | 0 | OG3-02235 | Construction | 2nd Floor | Construction.5.3.8.3 | Pull Branch Wiring - 2nd Floor | 5 | 5 | 0% | 2022-12-02 09:36 | 2022-12-09 09:36 | 9 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 02240 | 0 | 0 | OG3-02240 | Construction | 2nd Floor | Construction.5.3.8.3 | Install Lighting Fixtures & Controls - 2nd Floor | 4 | 4 | 0% | 2022-12-12 08:00 | 2022-12-15 17:00 | 8 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 02250 | 0 | 0 | OG3-02250 | Construction | 2nd Floor | Construction.5.3.8.3 | Install Smoke Detection Equipment - 2nd Floor | 5 | 5 | 0% | 2022-12-16 13:00 | 2022-12-23 12:00 | 78 | FSE | 0 | 0 | 0 | 0-OG3
In Progress | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 02245 | 0 | 0 | OG3-02245 | Construction | 2nd Floor | Construction.5.3.8.3 | Install Receptacles - 2nd Floor | 4 | 3 | 25% | 2022-06-17 | 2022-11-29 17:00 | 13 | FSE | RECEPTACLES | 0 | 0 | 0-OG3
In Progress | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 02255 | 0 | 0 | OG3-02255 | Construction | 2nd Floor | Construction.5.3.8.3 | Install Fire Stopping - 2nd Floor | 4 | 3 | 15% | 2022-06-17 | 2022-12-02 09:36 | 13 | MLJ | FIRESTOPPING | EXISTING BUILDING | 07-1200 | 07-1200-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 02265 | 0 | 0 | OG3-02265 | Construction | 2nd Floor | Construction.5.3.8.3 | Tag & Terminate Switchgear Equipment | 5 | 5 | 0% | 2023-01-10 08:00 | 2023-01-17 17:00 | -14 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 02270 | 0 | 0 | OG3-02270 | Construction | 2nd Floor | Construction.5.3.8.3 | Tag & Terminate Panelboards | 2 | 2 | 0% | 2023-01-18 08:00 | 2023-01-19 17:00 | -14 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 02225 | 0 | 0 | OG3-02225 | Construction | 2nd Floor | Construction.5.3.8.3 | Ground Equipment | 5 | 5 | 0% | 2022-12-14 13:00 | 2022-12-21 12:00 | -3 | FSE | GROUNDING EQUIP | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 02275 | 0 | 0 | OG3-02275 | Construction | 2nd Floor | Construction.5.3.8.3 | Terminate Fire Alarm System | 2 | 2 | 0% | 2023-01-18 08:00 | 2023-01-19 17:00 | 75 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 02260 | 0 | 0 | OG3-02260 | Construction | 2nd Floor | Construction.5.3.8.3 | Pull CON-ED Feeder Cable - Cellar to OG-3 Switchgear - 2nd Floor | 18 | 18 | 0% | 2022-12-13 08:00 | 2023-01-09 17:00 | -14 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 02280 | 0 | 0 | OG3-02280 | Construction | 2nd Floor | Construction.5.3.8.3 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 5 | 5 | 0% | 2023-01-18 08:00 | 2023-01-24 17:00 | -17 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.4 | OG3 | OG3 | 02525 | 0 | 0 | OG3-02525 | Construction | Testing & Start-Up | Construction.5.3.8.4 | Start-Up Generator/Switchgear - OG3 | 4 | 4 | 0% | 2023-04-27 08:00 | 2023-05-02 17:00 | -67 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.4 | OG3 | OG3 | 02535 | 0 | 0 | OG3-02535 | Construction | Testing & Start-Up | Construction.5.3.8.4 | Fire Alarm Operational & FDNY Acceptance Testing - OG3 | 5 | 5 | 0% | 2023-05-03 08:00 | 2023-05-09 17:00 | 3 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.4 | OG3 | OG3 | 02515 | 0 | 0 | OG3-02515 | Construction | Testing & Start-Up | Construction.5.3.8.4 | Energize Switchgear - OG3 | 5 | 5 | 0% | 2023-04-17 08:00 | 2023-04-21 17:00 | -67 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.4 | OG3 | OG3 | 02505 | 0 | 0 | OG3-02505 | Construction | Testing & Start-Up | Construction.5.3.8.4 | Perform Electrical Inspections - OG3 | 5 | 5 | 0% | 2023-03-14 08:00 | 2023-03-20 17:00 | -50 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.4 | OG3 | OG3 | 02520 | 0 | 0 | OG3-02520 | Construction | Testing & Start-Up | Construction.5.3.8.4 | Perform Tie-Ins to Existing | 3 | 3 | 0% | 2023-04-24 08:00 | 2023-04-26 17:00 | -67 | UNSURE | STARTUP | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.4 | OG3 | OG3 | 02510 | 0 | 0 | OG3-02510 | Construction | Testing & Start-Up | Construction.5.3.8.4 | Perform 3rd Party Test | 2 | 2 | 0% | 2023-04-13 08:00 | 2023-04-14 17:00 | -67 | UNSURE | STARTUP | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.4 | OG3 | OG3 | 02530 | 0 | 0 | OG3-02530 | Construction | Testing & Start-Up | Construction.5.3.8.4 | Notify NYCHA of Fire Alarm Acceptance Testing | 14 | 14 | 0% | 2023-04-13 08:00 | 2023-05-02 17:00 | 3 | FSE | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 02005 | 0 | 0 | S8-02005 | Construction | Site Utilities | Construction.8.3.6 | Remove, Relocate or Abandon Exisiting Feeder Conduit & Cable | 5 | 0 | 100% | 2022-09-06 08:00 | 2022-09-30 17:00 |  | FSE | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 02010 | 0 | 0 | S8-02010 | Construction | Site Utilities | Construction.8.3.6 | Install Manholes & Grounding | 3 | 0 | 100% | 2022-08-05 | 2022-10-10 |  | 0 | 0 | 0 | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.2 | S8 | S8 | 02105 | 0 | 0 | S8-02105 | Construction | Cable Pulls | Construction.8.3.2 | Pull CON-ED Feeder Cable - Surf Ave to S8-ADD Cellar | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | 26 | FSE | 0 | 0 | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.2 | S8 | S8 | 02110 | 0 | 0 | S8-02110 | Construction | Cable Pulls | Construction.8.3.2 | Pull Generator Cable - S8-ADD to S8(E) | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 64 | FSE | 0 | 0 | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.3 | S8 | S8 | 02205 | 0 | 0 | S8-02205 | Construction | Site Lighting | Construction.8.3.3 | Remove Existing Lighting Conduit, Cable & Fixtures - S8 | 5 | 5 | 0% | 2023-07-19 08:00 | 2023-07-25 17:00 | -53 | FSE | 0 | 0 | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.3 | S8 | S8 | 02210 | 0 | 0 | S8-02210 | Construction | Site Lighting | Construction.8.3.3 | Install Site Lighting Conduit - S8 | 5 | 5 | 0% | 2023-07-26 08:00 | 2023-08-01 17:00 | -53 | FSE | 0 | 0 | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.3 | S8 | S8 | 02215 | 0 | 0 | S8-02215 | Construction | Site Lighting | Construction.8.3.3 | Pull Site Lighting Wire - S8 | 3 | 3 | 0% | 2023-08-02 08:00 | 2023-08-04 17:00 | -53 | FSE | 0 | 0 | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.3 | S8 | S8 | 02220 | 0 | 0 | S8-02220 | Construction | Site Lighting | Construction.8.3.3 | Install Site Lighting Fixtures & Terminate - S8 | 5 | 5 | 0% | 2023-08-07 08:00 | 2023-08-11 17:00 | -53 | FSE | 0 | 0 | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 02005 | 0 | 0 | S8E-02005 | Construction | Cellar | Construction.8.1.8.1 | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 5 | 5 | 0% | 2022-11-30 08:00 | 2022-12-06 17:00 | -9 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 02010 | 0 | 0 | S8E-02010 | Construction | Cellar | Construction.8.1.8.1 | Install Bypass Connections - Cellar | 6 | 6 | 0% | 2022-12-07 08:00 | 2022-12-14 17:00 | -9 | MEP | 0 | 0 | 0 | 0-S81
In Progress | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 02020 | 0 | 0 | S8E-02020 | Construction | Cellar | Construction.8.1.8.1 | Relocate (E) & Install Temporary Lighting - Cellar | 5 | 4 | 25% | 2022-06-07 | 2022-12-14 17:00 | -9 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 02045 | 0 | 0 | S8E-02045 | Construction | Cellar | Construction.8.1.8.1 | Install Controls & Pull Wire to Mechanical/Plumbing Equipment & Terminate - Cellar | 5 | 5 | 0% | 2023-02-15 08:00 | 2023-02-22 17:00 | 2 | FSE | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Construction.8.1.8.1 | S8E | S8E | 02035 | 0 | 0 | S8E-02035 | Construction | Cellar | Construction.8.1.8.1 | Link & Seal Conduit Sleeves - Cellar | 15 | 0 | 100% | 2021-10-22 | 2021-10-22 |  | 0 | 0 | 0 | 0 | 0-S8E
Not Started | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 02050 | 0 | 0 | S8E-02050 | Construction | Cellar | Construction.8.1.8.1 | Pull Lighting Wiring - Cellar | 6 | 6 | 0% | 2023-03-30 08:00 | 2023-04-06 17:00 | -12 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 02060 | 0 | 0 | S8E-02060 | Construction | Cellar | Construction.8.1.8.1 | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 3 | 3 | 0% | 2023-04-07 08:00 | 2023-04-11 17:00 | -12 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 02055 | 0 | 0 | S8E-02055 | Construction | Cellar | Construction.8.1.8.1 | Install Heat Trace for Plumbing Lines - Cellar | 5 | 5 | 0% | 2023-02-23 08:00 | 2023-03-01 17:00 | 2 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 02025 | 0 | 0 | S8E-02025 | Construction | Cellar | Construction.8.1.8.1 | Core Drill & Install Feeder Conduits Risers & Racks to 1st Floor - Cellar | 20 | 20 | 0% | 2023-01-03 08:00 | 2023-01-31 17:00 | -20 | FSE | CORE DRILL | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 02015 | 0 | 0 | S8E-02015 | Construction | Cellar | Construction.8.1.8.1 | Install Panelboards (Misc.) - Cellar | 2 | 2 | 0% | 2022-12-07 08:00 | 2022-12-08 17:00 | 27 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 02030 | 0 | 0 | S8E-02030 | Construction | Cellar | Construction.8.1.8.1 | Install Branch Conduit | 15 | 15 | 0% | 2022-12-15 08:00 | 2023-01-06 17:00 | 23 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 02040 | 0 | 0 | S8E-02040 | Construction | Cellar | Construction.8.1.8.1 | Pull Branch Wiring | 5 | 5 | 0% | 2023-01-09 08:00 | 2023-01-13 17:00 | 23 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 02065 | 0 | 0 | S8E-02065 | Construction | Cellar | Construction.8.1.8.1 | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 15 | 15 | 0% | 2023-03-09 08:00 | 2023-03-29 17:00 | -12 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.2 | S81 | S8E | 02105 | 0 | 0 | S8E-02105 | Construction | 1st Floor | Construction.8.1.8.2 | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 20 | 20 | 0% | 2023-02-01 08:00 | 2023-03-01 17:00 | -20 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.2 | S81 | S8E | 02110 | 0 | 0 | S8E-02110 | Construction | 1st Floor | Construction.8.1.8.2 | Install Pull/Splice Boxes - 1st Floor | 5 | 5 | 0% | 2023-03-02 08:00 | 2023-03-08 17:00 | -20 | MEP | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.2 | S81 | S8E | 02125 | 0 | 0 | S8E-02125 | Construction | 1st Floor | Construction.8.1.8.2 | Supply Power to Exterior Building Signage | 2 | 2 | 0% | 2023-03-23 08:00 | 2023-03-24 17:00 | -20 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.2 | S81 | S8E | 02130 | 0 | 0 | S8E-02130 | Construction | 1st Floor | Construction.8.1.8.2 | Install Firestopping - 1st Floor | 5 | 5 | 0% | 2023-03-27 08:00 | 2023-03-31 17:00 | -20 | MLJ | FIRESTOPPING | EXISTING BUILDING | 07-1200 | 07-1200-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.2 | S81 | S8E | 02120 | 0 | 0 | S8E-02120 | Construction | 1st Floor | Construction.8.1.8.2 | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 3 | 3 | 0% | 2023-04-12 08:00 | 2023-04-14 17:00 | -12 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.2 | S81 | S8E | 02115 | 0 | 0 | S8E-02115 | Construction | 1st Floor | Construction.8.1.8.2 | Pull Feeder Cable from Cellar to 1st Floor - 1st Floor | 10 | 10 | 0% | 2023-03-09 08:00 | 2023-03-22 17:00 | -20 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.3 | S81 | S8E | 02505 | 0 | 0 | S8E-02505 | Construction | Testing & Start-Up | Construction.8.1.8.3 | Perform Tie-In's to Exisiting Equipment - S8E | 5 | 5 | 0% | 2023-07-06 08:00 | 2023-07-12 17:00 | -84 | UNSURE | STARTUP | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.3 | S81 | S8E | 02510 | 0 | 0 | S8E-02510 | Construction | Testing & Start-Up | Construction.8.1.8.3 | Perform Electrical Inspections - S8E | 2 | 2 | 0% | 2023-04-03 08:00 | 2023-04-04 17:00 | -20 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.2.5.4 | S82 | S8A | 02005 | 0 | 0 | S8A-02005 | Construction | Foundation | Construction.8.2.5.4 | Install Branch Conduit in Plumbing Shaft - Foundation | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | 5 | FSE | 0 | 0 | 0 | 0-S82
In Progress | CI NYCHA Update #22.Construction.8.2.5.4 | S82 | S8A | 02010 | 0 | 0 | S8A-02010 | Construction | Foundation | Construction.8.2.5.4 | Install Temporary Lighting & Temporary Power for S8A | 5 | 3 | 40% | 2021-07-01 | 2022-11-29 17:00 | 1 | FSE | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Construction.8.2.5.4 | S8A | S8A | 02015 | 0 | 0 | S8A-02015 | Construction | Foundation | Construction.8.2.5.4 | Install Conduit Risers to 1st Floor for Incoming Feeders - Foundation | 10 | 0 | 100% | 2022-06-17 | 2022-11-15 |  | 0 | 0 | 0 | 0 | 0-S8A
Not Started | CI NYCHA Update #22.Construction.8.2.5.4 | S82 | S8A | 02020 | 0 | 0 | S8A-02020 | Construction | Foundation | Construction.8.2.5.4 | Pull Wire to Light Fixture & Mechanical Equipment in Plumbing Shaft - Foundation | 2 | 2 | 0% | 2023-03-09 08:00 | 2023-03-10 17:00 | -63 | FSE | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Construction.8.2.5.4 | S8A | S8A | 02025 | 0 | 0 | S8A-02025 | Construction | Foundation | Construction.8.2.5.4 | Install Pull Box - Foundation | 2 | 0 | 100% | 2022-06-17 | 2022-11-07 12:00 |  | 0 | 0 | 0 | 0 | 0-S8A
Not Started | CI NYCHA Update #22.Construction.8.2.5.1 | S82 | S8A | 02105 | 0 | 0 | S8A-02105 | Construction | 1st Floor | Construction.8.2.5.1 | Install Smoke Detection/Fire Alarm Equipment - 1st Floor | 5 | 5 | 0% | 2023-03-20 08:00 | 2023-03-24 17:00 | -45 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.1 | S82 | S8A | 02110 | 0 | 0 | S8A-02110 | Construction | 1st Floor | Construction.8.2.5.1 | Install Light/Emergency Fixtures - 1st Floor | 5 | 5 | 0% | 2023-03-20 08:00 | 2023-03-24 17:00 | -43 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.1 | S82 | S8A | 02115 | 0 | 0 | S8A-02115 | Construction | 1st Floor | Construction.8.2.5.1 | Pull Fire Alarm Wiring - 1st Floor | 5 | 5 | 0% | 2022-12-06 13:00 | 2022-12-13 12:00 | 17 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.1 | S82 | S8A | 02120 | 0 | 0 | S8A-02120 | Construction | 1st Floor | Construction.8.2.5.1 | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - 1st Floor | 5 | 5 | 0% | 2023-03-20 08:00 | 2023-03-24 17:00 | -43 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.1 | S82 | S8A | 02125 | 0 | 0 | S8A-02125 | Construction | 1st Floor | Construction.8.2.5.1 | Install Receptacles - 1st Floor | 2 | 2 | 0% | 2023-03-29 08:00 | 2023-03-30 17:00 | -45 | FSE | RECEPTACLES | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.1 | S82 | S8A | 02130 | 0 | 0 | S8A-02130 | Construction | 1st Floor | Construction.8.2.5.1 | Install Remote Annunciator Panel (RAP). - 1st Floor | 2 | 2 | 0% | 2023-03-27 08:00 | 2023-03-28 17:00 | -45 | MEP | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Construction.8.2.5.1 | S8A | S8A | 02135 | 0 | 0 | S8A-02135 | Construction | 1st Floor | Construction.8.2.5.1 | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 20 | 0 | 100% | 2022-11-01 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-S8A
In Progress | CI NYCHA Update #22.Construction.8.2.5.1 | S82 | S8A | 02140 | 0 | 0 | S8A-02140 | Construction | 1st Floor | Construction.8.2.5.1 | Install Branch Conduits - 1st Floor | 15 | 8 | 50% | 2022-09-23 | 2022-12-06 12:00 | 2 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.1 | S82 | S8A | 02145 | 0 | 0 | S8A-02145 | Construction | 1st Floor | Construction.8.2.5.1 | Pull Branch Wiring - 1st Floor | 5 | 5 | 0% | 2023-03-13 08:00 | 2023-03-17 17:00 | -63 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.1 | S82 | S8A | 02150 | 0 | 0 | S8A-02150 | Construction | 1st Floor | Construction.8.2.5.1 | Install Heat Trace for Plumbing Lines -1st Floor | 3 | 3 | 0% | 2023-03-20 08:00 | 2023-03-22 17:00 | -22 | FSE | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Construction.8.2.5.1 | S8A | S8A | 02155 | 0 | 0 | S8A-02155 | Construction | 1st Floor | Construction.8.2.5.1 | Install In-slab Conduits - 1st floor slab | 5 | 0 | 100% | 2022-07-11 08:00 | 2022-07-14 17:00 |  | 0 | 0 | 0 | 0 | 0-S8A
Not Started | CI NYCHA Update #22.Construction.8.2.5.1 | S82 | S8A | 02160 | 0 | 0 | S8A-02160 | Construction | 1st Floor | Construction.8.2.5.1 | Install Exterior Lighting & Controls - 1st Floor | 2 | 2 | 0% | 2023-03-20 08:00 | 2023-03-21 17:00 | -40 | FSE | 0 | 0 | 0 | 0-S82
In Progress | CI NYCHA Update #22.Construction.8.2.5.2 | S82 | S8A | 02205 | 0 | 0 | S8A-02205 | Construction | 2nd Floor | Construction.8.2.5.2 | Install Feeder Conduit Risers & Racks to Roof - 2nd Floor | 20 | 5 | 75% | 2022-11-10 | 2022-12-01 17:00 | 26 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.2 | S82 | S8A | 02210 | 0 | 0 | S8A-02210 | Construction | 2nd Floor | Construction.8.2.5.2 | Install Controls & Pull Wire for Mechanical & Plumbing Equipment - 2nd Floor | 10 | 10 | 0% | 2023-04-10 08:00 | 2023-04-21 17:00 | -49 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.2 | S82 | S8A | 02215 | 0 | 0 | S8A-02215 | Construction | 2nd Floor | Construction.8.2.5.2 | Install Branch Conduits - 2nd Floor | 15 | 15 | 0% | 2023-03-20 08:00 | 2023-04-07 17:00 | -63 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.2 | S82 | S8A | 02220 | 0 | 0 | S8A-02220 | Construction | 2nd Floor | Construction.8.2.5.2 | Pull Branch Wiring - 2nd Floor | 5 | 5 | 0% | 2023-04-10 08:00 | 2023-04-14 17:00 | -56 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.2 | S82 | S8A | 02225 | 0 | 0 | S8A-02225 | Construction | 2nd Floor | Construction.8.2.5.2 | Pull Fire Alarm Wiring - 2nd Floor | 5 | 5 | 0% | 2023-04-10 08:00 | 2023-04-14 17:00 | -63 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.2 | S82 | S8A | 02230 | 0 | 0 | S8A-02230 | Construction | 2nd Floor | Construction.8.2.5.2 | Install Smoke Detection/Fire Alarm Equipment - 2nd Floor | 5 | 5 | 0% | 2023-04-17 08:00 | 2023-04-21 17:00 | 2 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.2 | S82 | S8A | 02235 | 0 | 0 | S8A-02235 | Construction | 2nd Floor | Construction.8.2.5.2 | Install Light/Emergency Fixtures - 2nd Floor | 5 | 5 | 0% | 2023-04-17 08:00 | 2023-04-21 17:00 | -54 | FSE | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Construction.8.2.5.2 | S8A | S8A | 02240 | 0 | 0 | S8A-02240 | Construction | 2nd Floor | Construction.8.2.5.2 | Install In-slab Conduits - 2nd floor slab | 10 | 0 | 100% | 2022-09-13 | 2022-09-23 |  | 0 | 0 | 0 | 0 | 0-S8A
Not Started | CI NYCHA Update #22.Construction.8.2.5.2 | S82 | S8A | 02245 | 0 | 0 | S8A-02245 | Construction | 2nd Floor | Construction.8.2.5.2 | Install Receptacles - 2nd Floor | 2 | 2 | 0% | 2023-04-17 08:00 | 2023-04-18 17:00 | -56 | FSE | RECEPTACLES | 0 | 0 | 0-S82
In Progress | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02305 | 0 | 0 | S8A-02305 | Construction | Roof | Construction.8.2.5.3 | Install Feeder Conduit & Racks - Roof | 15 | 8 | 50% | 2022-11-15 | 2022-12-08 17:00 | 26 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02310 | 0 | 0 | S8A-02310 | Construction | Roof | Construction.8.2.5.3 | Install Generator Circuit Breakers & Wire Generators - Roof | 10 | 10 | 0% | 2023-05-05 08:00 | 2023-05-18 17:00 | -84 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02315 | 0 | 0 | S8A-02315 | Construction | Roof | Construction.8.2.5.3 | Install Branch Conduit - Roof | 5 | 5 | 0% | 2023-01-18 08:00 | 2023-01-24 17:00 | -11 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02320 | 0 | 0 | S8A-02320 | Construction | Roof | Construction.8.2.5.3 | Pull Branch Wiring - Roof | 5 | 5 | 0% | 2023-01-25 08:00 | 2023-01-31 17:00 | -11 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02325 | 0 | 0 | S8A-02325 | Construction | Roof | Construction.8.2.5.3 | Rig Generator S8 (2 No's) - Roof | 1 | 1 | 0% | 2023-05-04 08:00 | 2023-05-04 17:00 | -84 | WELKIN | GENERATOR | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02330 | 0 | 0 | S8A-02330 | Construction | Roof | Construction.8.2.5.3 | Terminate all Mech. & Plumbing Equipment at Panel - Roof | 5 | 5 | 0% | 2023-06-13 08:00 | 2023-06-19 17:00 | -84 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02335 | 0 | 0 | S8A-02335 | Construction | Roof | Construction.8.2.5.3 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Roof | 5 | 5 | 0% | 2023-04-17 08:00 | 2023-04-21 17:00 | -49 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02340 | 0 | 0 | S8A-02340 | Construction | Roof | Construction.8.2.5.3 | Install Switchboards - Roof | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -11 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02345 | 0 | 0 | S8A-02345 | Construction | Roof | Construction.8.2.5.3 | Install ACTTS - Roof | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | -11 | FSE | ACTTS | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02350 | 0 | 0 | S8A-02350 | Construction | Roof | Construction.8.2.5.3 | Install Panelboards - Roof | 10 | 10 | 0% | 2023-01-03 08:00 | 2023-01-17 17:00 | -11 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02355 | 0 | 0 | S8A-02355 | Construction | Roof | Construction.8.2.5.3 | Install Smoke Detection/Fire Alarm Equipment - Roof | 5 | 5 | 0% | 2023-04-24 08:00 | 2023-04-28 17:00 | 2 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02360 | 0 | 0 | S8A-02360 | Construction | Roof | Construction.8.2.5.3 | Install Receptacles - Roof | 3 | 3 | 0% | 2023-04-24 08:00 | 2023-04-26 17:00 | -59 | FSE | RECEPTACLES | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02365 | 0 | 0 | S8A-02365 | Construction | Roof | Construction.8.2.5.3 | Install Light/Emergency Fixtures - Roof | 5 | 5 | 0% | 2023-04-24 08:00 | 2023-04-28 17:00 | -54 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02370 | 0 | 0 | S8A-02370 | Construction | Roof | Construction.8.2.5.3 | Install Lightning protection Air terminals - Roof | 4 | 4 | 0% | 2023-05-19 08:00 | 2023-05-24 17:00 | -84 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02375 | 0 | 0 | S8A-02375 | Construction | Roof | Construction.8.2.5.3 | Install Grounding & Ground Equipment | 5 | 5 | 0% | 2023-05-25 08:00 | 2023-06-01 17:00 | -84 | FSE | GROUNDING EQUIP | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02380 | 0 | 0 | S8A-02380 | Construction | Roof | Construction.8.2.5.3 | Install Fire Alarm Control Panel (Incl. Telephone Lines) - Roof | 2 | 2 | 0% | 2023-04-24 08:00 | 2023-04-25 17:00 | -63 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02385 | 0 | 0 | S8A-02385 | Construction | Roof | Construction.8.2.5.3 | Pull Fire Alarm Wiring - Roof | 5 | 5 | 0% | 2023-04-17 08:00 | 2023-04-21 17:00 | -63 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02390 | 0 | 0 | S8A-02390 | Construction | Roof | Construction.8.2.5.3 | Terminate Light Fixtures - Roof | 5 | 5 | 0% | 2023-06-13 08:00 | 2023-06-19 17:00 | -84 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02395 | 0 | 0 | S8A-02395 | Construction | Roof | Construction.8.2.5.3 | Install Firestopping - Roof | 4 | 4 | 0% | 2023-01-25 08:00 | 2023-01-30 17:00 | 14 | MLJ | FIRESTOPPING | NEW BUILDING | 07-1300 | 07-1300-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02400 | 0 | 0 | S8A-02400 | Construction | Roof | Construction.8.2.5.3 | Tag & Terminate Switchgear Equipment - Roof | 5 | 5 | 0% | 2023-06-02 08:00 | 2023-06-08 17:00 | -84 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02405 | 0 | 0 | S8A-02405 | Construction | Roof | Construction.8.2.5.3 | Tag & Terminate Panelboards - Roof | 2 | 2 | 0% | 2023-06-09 08:00 | 2023-06-12 17:00 | -84 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02410 | 0 | 0 | S8A-02410 | Construction | Roof | Construction.8.2.5.3 | Tag & Terminate Fire Alarm Equipment | 2 | 2 | 0% | 2023-06-13 08:00 | 2023-06-14 17:00 | -28 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 02415 | 0 | 0 | S8A-02415 | Construction | Roof | Construction.8.2.5.3 | Pull Feeder Cable from Foundation to Roof - Roof | 10 | 10 | 0% | 2022-12-09 08:00 | 2022-12-22 17:00 | 26 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.6 | S82 | S8A | 02505 | 0 | 0 | S8A-02505 | Construction | Testing & Start-Up | Construction.8.2.5.6 | Fire Alarm Operational & FDNY Acceptance Testing - S8A | 5 | 5 | 0% | 2023-07-19 08:00 | 2023-07-25 17:00 | -51 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.6 | S82 | S8A | 02510 | 0 | 0 | S8A-02510 | Construction | Testing & Start-Up | Construction.8.2.5.6 | Provide Load Bank & Perform Acceptance Testing for Generator SG4 - S8A | 2 | 2 | 0% | 2023-07-06 08:00 | 2023-07-07 17:00 | -44 | UNSURE | STARTUP | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.6 | S82 | S8A | 02515 | 0 | 0 | S8A-02515 | Construction | Testing & Start-Up | Construction.8.2.5.6 | Perform Electrical Inspections for S8A | 5 | 5 | 0% | 2023-06-20 08:00 | 2023-06-26 17:00 | -84 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.6 | S82 | S8A | 02520 | 0 | 0 | S8A-02520 | Construction | Testing & Start-Up | Construction.8.2.5.6 | Energize Switchgear Equipment - S8A | 4 | 4 | 0% | 2023-06-29 08:00 | 2023-07-05 17:00 | -84 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.6 | S82 | S8A | 02525 | 0 | 0 | S8A-02525 | Construction | Testing & Start-Up | Construction.8.2.5.6 | Perform 3rd Party Testing - S8A | 2 | 2 | 0% | 2023-06-27 08:00 | 2023-06-28 17:00 | -84 | UNSURE | STARTUP | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.6 | S82 | S8A | 02530 | 0 | 0 | S8A-02530 | Construction | Testing & Start-Up | Construction.8.2.5.6 | Notify NYCHA of Fire Alarm Testing - S8A | 14 | 14 | 0% | 2023-06-28 08:00 | 2023-07-18 17:00 | -51 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.6 | S82 | S8A | 02535 | 0 | 0 | S8A-02535 | Construction | Testing & Start-Up | Construction.8.2.5.6 | Notify NYCHA of Generator Acceptance Testing - S8A | 5 | 5 | 0% | 2023-06-28 08:00 | 2023-07-05 17:00 | -44 | UNSURE | STARTUP | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.6 | S82 | S8A | 02540 | 0 | 0 | S8A-02540 | Construction | Testing & Start-Up | Construction.8.2.5.6 | Start-Up Switchgear/Generator S8E - S8A | 4 | 4 | 0% | 2023-07-13 08:00 | 2023-07-18 17:00 | -61 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.3.5.2 | OGP1 | OGP1 | 02025 | 0 | 0 | OGP1-02025 | Construction | Cable Pulls | Construction.3.5.2 | Pull CON-ED Feeder Cable - 33rd St. to OG-5 Cellar | 10 | 10 | 0% | 2022-11-30 13:48 | 2022-12-14 13:48 | 1 | FSE | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.2 | OGP1 | OGP1 | 02005 | 0 | 0 | OGP1-02005 | Construction | Cable Pulls | Construction.3.5.2 | Pull CON-ED Feeder Cable - 33rd St. to OG-4 Cellar | 10 | 0 | 100% | 2022-10-28 15:00 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.2 | OGP1 | OGP1 | 02010 | 0 | 0 | OGP1-02010 | Construction | Cable Pulls | Construction.3.5.2 | Pull Feeder Cable - OG-4 Switchgear to OG-8 Foundation | 10 | 10 | 0% | 2022-12-01 08:00 | 2022-12-14 17:00 | -26 | FSE | 0 | 0 | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.2 | OGP1 | OGP1 | 02020 | 0 | 0 | OGP1-02020 | Construction | Cable Pulls | Construction.3.5.2 | Pull Generator Feeder Cable from OG-8 to OG-5 | 5 | 5 | 0% | 2023-03-21 08:00 | 2023-03-27 17:00 | -60 | FSE | 0 | 0 | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.2 | OGP1 | OGP1 | 02015 | 0 | 0 | OGP1-02015 | Construction | Cable Pulls | Construction.3.5.2 | Pull Generator Feeder Cable from OG-8 to OG-4 | 5 | 5 | 0% | 2023-03-07 08:00 | 2023-03-13 17:00 | -54 | FSE | 0 | 0 | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.3 | OGP1 | OGP1 | 02105 | 0 | 0 | OGP1-02105 | Construction | Site Lighting | Construction.3.5.3 | Remove Existing Lighting Conduit, Cable & Fixtures | 5 | 5 | 0% | 2023-05-09 08:00 | 2023-05-15 17:00 | 4 | FSE | 0 | 0 | 0 | 0-OGP1
In Progress | CI NYCHA Update #22.Construction.3.5.3 | OGP1 | OGP1 | 02110 | 0 | 0 | OGP1-02110 | Construction | Site Lighting | Construction.3.5.3 | Furnish & Install Site Lighting Conduit | 5 | 3 | 50% | 2022-11-01 | 2022-11-29 12:00 | 112 | FSE | 0 | 0 | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.3 | OGP1 | OGP1 | 02115 | 0 | 0 | OGP1-02115 | Construction | Site Lighting | Construction.3.5.3 | Pull Site Lighting Wire | 3 | 3 | 0% | 2022-11-29 13:00 | 2022-12-02 12:00 | 112 | FSE | 0 | 0 | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.3 | OGP1 | OGP1 | 02120 | 0 | 0 | OGP1-02120 | Construction | Site Lighting | Construction.3.5.3 | Install Site Lighting Fixtures & Terminate | 5 | 5 | 0% | 2023-05-09 08:00 | 2023-05-15 17:00 | 4 | FSE | 0 | 0 | 0 | 0-OGP1
In Progress | CI NYCHA Update #22.Construction.3.1.8.4 | OG8 | OG8 | 02015 | 0 | 0 | OG8-02015 | Construction | Foundation | Construction.3.1.8.4 | Install Branch Conduit in Plumbing Shaft - Foundation | 2 | 1 | 75% | 2022-05-25 08:00 | 2022-11-25 12:00 | -18 | FSE | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.4 | OG8 | OG8 | 02005 | 0 | 0 | OG8-02005 | Construction | Foundation | Construction.3.1.8.4 | Install Temporary Lighting & Temporary Power for OG8 | 5 | 1 | 75% | 2022-02-07 08:00 | 2022-11-28 10:00 | -15 | FSE | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.8.4 | OG8 | OG8 | 02010 | 0 | 0 | OG8-02010 | Construction | Foundation | Construction.3.1.8.4 | Install Conduit Risers to 1st Floor for Incoming Feeders - Foundation | 10 | 0 | 100% | 2021-10-27 | 2021-11-30 |  | 0 | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.4 | OG8 | OG8 | 02025 | 0 | 0 | OG8-02025 | Construction | Foundation | Construction.3.1.8.4 | Pull Wire to Light Fixture & Mechanical Equipment in Plumbing Shaft - Foundation | 2 | 1 | 50% | 2022-05-26 | 2023-01-24 17:00 | -33 | FSE | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.8.4 | OG8 | OG8 | 02020 | 0 | 0 | OG8-02020 | Construction | Foundation | Construction.3.1.8.4 | Install Pull Box - Foundation | 2 | 0 | 100% | 2022-02-07 | 2022-04-25 |  | 0 | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 02135 | 0 | 0 | OG8-02135 | Construction | 1st Floor | Construction.3.1.8.1 | Install Smoke Detection/Fire Alarm Equipment - 1st Floor | 3 | 3 | 0% | 2022-11-30 08:00 | 2022-12-02 17:00 | -9 | FSE | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 02140 | 0 | 0 | OG8-02140 | Construction | 1st Floor | Construction.3.1.8.1 | Install Light/Emergency Fixtures - 1st Floor | 3 | 1 | 75% | 2022-10-03 08:00 | 2023-01-24 17:00 | -33 | FSE | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 02125 | 0 | 0 | OG8-02125 | Construction | 1st Floor | Construction.3.1.8.1 | Pull Fire Alarm Wiring - 1st Floor | 3 | 2 | 50% | 2022-11-01 | 2022-11-28 12:00 | -12 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 02145 | 0 | 0 | OG8-02145 | Construction | 1st Floor | Construction.3.1.8.1 | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - 1st Floor | 3 | 3 | 0% | 2022-11-30 08:00 | 2022-12-02 17:00 | -2 | FSE | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 02160 | 0 | 0 | OG8-02160 | Construction | 1st Floor | Construction.3.1.8.1 | Install Receptacles - 1st Floor | 2 | 2 | 25% | 2022-06-13 | 2022-11-28 12:00 | 6 | FSE | RECEPTACLES | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 02155 | 0 | 0 | OG8-02155 | Construction | 1st Floor | Construction.3.1.8.1 | Install Remote Annunciator Panel (RAP). - 1st Floor | 2 | 2 | 0% | 2022-12-05 08:00 | 2022-12-06 17:00 | -9 | MEP | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 02110 | 0 | 0 | OG8-02110 | Construction | 1st Floor | Construction.3.1.8.1 | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 20 | 0 | 100% | 2022-03-14 | 2022-07-01 |  | FSE | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 02115 | 0 | 0 | OG8-02115 | Construction | 1st Floor | Construction.3.1.8.1 | Install Branch Conduits - 1st Floor | 10 | 1 | 90% | 2022-02-21 | 2022-11-25 17:00 | -9 | FSE | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 02130 | 0 | 0 | OG8-02130 | Construction | 1st Floor | Construction.3.1.8.1 | Pull Branch Wiring - 1st Floor | 3 | 2 | 50% | 2022-06-13 | 2022-11-29 17:00 | -9 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 02150 | 0 | 0 | OG8-02150 | Construction | 1st Floor | Construction.3.1.8.1 | Install Heat Trace for Plumbing Lines -1st Floor | 3 | 3 | 0% | 2022-11-30 08:00 | 2022-12-02 17:00 | 1 | FSE | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 02105 | 0 | 0 | OG8-02105 | Construction | 1st Floor | Construction.3.1.8.1 | Install In-slab Conduits - 1st floor slab - 1st Floor | 3 | 0 | 100% | 2022-02-21 | 2022-03-18 |  | 0 | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 02120 | 0 | 0 | OG8-02120 | Construction | 1st Floor | Construction.3.1.8.1 | Install Exterior Lighting & Controls - 1st Floor | 2 | 1 | 50% | 2022-11-01 | 2022-12-16 17:00 | -9 | FSE | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 02220 | 0 | 0 | OG8-02220 | Construction | 2nd Floor | Construction.3.1.8.2 | Install Feeder Conduit Risers & Racks to 3rd Floor - 2nd Floor | 15 | 0 | 100% | 2022-03-14 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 02225 | 0 | 0 | OG8-02225 | Construction | 2nd Floor | Construction.3.1.8.2 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 10 | 10 | 0% | 2022-11-29 08:00 | 2022-12-12 17:00 | -8 | FSE | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 02210 | 0 | 0 | OG8-02210 | Construction | 2nd Floor | Construction.3.1.8.2 | Install Branch Conduits - 2nd Floor | 15 | 2 | 90% | 2022-06-15 | 2022-11-28 12:00 | -19 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 02230 | 0 | 0 | OG8-02230 | Construction | 2nd Floor | Construction.3.1.8.2 | Pull Branch Wiring - 2nd Floor | 3 | 3 | 0% | 2022-11-28 13:00 | 2022-12-01 12:00 | -9 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 02235 | 0 | 0 | OG8-02235 | Construction | 2nd Floor | Construction.3.1.8.2 | Pull Fire Alarm Wiring - 2nd Floor | 3 | 3 | 0% | 2022-11-28 13:00 | 2022-12-01 12:00 | -12 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 02215 | 0 | 0 | OG8-02215 | Construction | 2nd Floor | Construction.3.1.8.2 | Install Smoke Detection/Fire Alarm Equipment - 2nd Floor | 3 | 3 | 0% | 2022-12-01 13:00 | 2022-12-06 12:00 | 105 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 02240 | 0 | 0 | OG8-02240 | Construction | 2nd Floor | Construction.3.1.8.2 | Install Light/Emergency Fixtures - 2nd Floor | 3 | 3 | 0% | 2023-01-25 08:00 | 2023-01-27 17:00 | -44 | FSE | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 02205 | 0 | 0 | OG8-02205 | Construction | 2nd Floor | Construction.3.1.8.2 | Install In-slab Conduits - 2nd floor slab - 2nd Floor | 10 | 0 | 100% | 2022-03-14 | 2022-04-04 |  | 0 | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 02245 | 0 | 0 | OG8-02245 | Construction | 2nd Floor | Construction.3.1.8.2 | Install Receptacles - 2nd Floor | 2 | 2 | 0% | 2022-12-01 13:00 | 2022-12-05 12:00 | 1 | FSE | RECEPTACLES | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 02250 | 0 | 0 | OG8-02250 | Construction | 2nd Floor | Construction.3.1.8.2 | Install Switchboards - 2nd Floor | 3 | 0 | 100% | 2022-03-14 | 2022-09-26 10:24 |  | FSE | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 02255 | 0 | 0 | OG8-02255 | Construction | 2nd Floor | Construction.3.1.8.2 | Install ACTTS - 2nd Floor | 3 | 0 | 95% | 2022-05-03 | 2022-11-25 09:12 | -11 | FSE | ACTTS | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 02260 | 0 | 0 | OG8-02260 | Construction | 2nd Floor | Construction.3.1.8.2 | Install Panelboards - 2nd Floor | 3 | 0 | 95% | 2022-07-28 08:00 | 2022-11-25 09:12 | -7 | FSE | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 02265 | 0 | 0 | OG8-02265 | Construction | 2nd Floor | Construction.3.1.8.2 | Install Feeder Conduit & Racks - 2nd Floor | 15 | 1 | 95% | 2022-07-28 08:00 | 2022-11-29 09:12 | -11 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 02275 | 0 | 0 | OG8-02275 | Construction | 2nd Floor | Construction.3.1.8.2 | Tag & Terminate Switchgear Equipment - 2nd Floor | 3 | 3 | 0% | 2022-12-30 08:00 | 2023-01-04 17:00 | -20 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 02280 | 0 | 0 | OG8-02280 | Construction | 2nd Floor | Construction.3.1.8.2 | Tag & Terminate Panelboards - 2nd Floor | 3 | 3 | 0% | 2022-12-30 08:00 | 2023-01-04 17:00 | -23 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 02270 | 0 | 0 | OG8-02270 | Construction | 2nd Floor | Construction.3.1.8.2 | Pull CON-ED Feeder Cable from Foundation to Switchgear Equipment - 2nd Floor | 10 | 10 | 0% | 2022-12-15 08:00 | 2022-12-29 17:00 | -23 | FSE | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02455 | 0 | 0 | OG8-02455 | Construction | Roof | Construction.3.1.3 | Install Feeder Conduit & Racks - Roof | 10 | 2 | 80% | 2022-06-21 | 2023-02-02 17:00 | -59 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02405 | 0 | 0 | OG8-02405 | Construction | Roof | Construction.3.1.3 | Rig Generator OG-5 - Roof (DELAYED) | 1 | 1 | 0% | 2023-02-01 08:00 | 2023-02-01 17:00 | -82 | WELKIN | GENERATOR | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02415 | 0 | 0 | OG8-02415 | Construction | Roof | Construction.3.1.3 | Install Generator Circuit Breakers & Wire Generators OG-4 (2 No's) - Roof | 20 | 20 | 0% | 2023-02-06 08:00 | 2023-03-06 17:00 | -82 | FSE | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02440 | 0 | 0 | OG8-02440 | Construction | Roof | Construction.3.1.3 | Install Branch Conduit - Roof | 15 | 8 | 50% | 2022-08-22 08:00 | 2022-12-06 12:00 | -14 | FSE | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02445 | 0 | 0 | OG8-02445 | Construction | Roof | Construction.3.1.3 | Pull Branch Wiring - Roof | 3 | 2 | 25% | 2022-06-21 | 2022-12-08 12:00 | -14 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02410 | 0 | 0 | OG8-02410 | Construction | Roof | Construction.3.1.3 | Rig Generator OG-4 (2 No's) - Roof (DELAYED) | 2 | 2 | 0% | 2023-02-02 08:00 | 2023-02-03 17:00 | -82 | WELKIN | GENERATOR | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02420 | 0 | 0 | OG8-02420 | Construction | Roof | Construction.3.1.3 | Install Generator Circuit Breakers & Wire Generator OG-5 - Roof | 10 | 10 | 0% | 2023-03-07 08:00 | 2023-03-20 17:00 | -82 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02510 | 0 | 0 | OG8-02510 | Construction | Roof | Construction.3.1.3 | Terminate all Mech. & Plumbing Equipment at Panel (MEP-LR) - Roof | 3 | 3 | 0% | 2023-03-31 08:00 | 2023-04-04 17:00 | -82 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02450 | 0 | 0 | OG8-02450 | Construction | Roof | Construction.3.1.3 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Roof | 5 | 5 | 0% | 2022-12-14 13:00 | 2022-12-21 12:00 | -15 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02430 | 0 | 0 | OG8-02430 | Construction | Roof | Construction.3.1.3 | Install Switchboards - Roof | 2 | 2 | 0% | 2023-02-01 08:00 | 2023-02-02 17:00 | -59 | FSE | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02435 | 0 | 0 | OG8-02435 | Construction | Roof | Construction.3.1.3 | Install ACTTS - Roof | 2 | 0 | 100% | 2022-09-01 08:00 | 2022-09-01 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02470 | 0 | 0 | OG8-02470 | Construction | Roof | Construction.3.1.3 | Install Smoke Detection/Fire Alarm Equipment - Roof | 3 | 3 | 0% | 2022-12-20 13:00 | 2022-12-23 12:00 | 92 | FSE | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02475 | 0 | 0 | OG8-02475 | Construction | Roof | Construction.3.1.3 | Install Receptacles - Roof | 3 | 2 | 25% | 2022-06-21 | 2022-12-20 12:00 | -14 | FSE | RECEPTACLES | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02460 | 0 | 0 | OG8-02460 | Construction | Roof | Construction.3.1.3 | Install Light/Emergency Fixtures - Roof | 3 | 3 | 0% | 2023-02-01 08:00 | 2023-02-03 17:00 | -44 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02425 | 0 | 0 | OG8-02425 | Construction | Roof | Construction.3.1.3 | Install Lightning protection Air terminals - Roof | 5 | 5 | 0% | 2023-03-21 08:00 | 2023-03-27 17:00 | -82 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02485 | 0 | 0 | OG8-02485 | Construction | Roof | Construction.3.1.3 | Install Grounding & Ground Equipment | 3 | 3 | 0% | 2023-03-28 08:00 | 2023-03-30 17:00 | -82 | FSE | GROUNDING EQUIP | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02480 | 0 | 0 | OG8-02480 | Construction | Roof | Construction.3.1.3 | Install Fire Alarm Control Panel (Incl. Telephone Lines) - Roof | 2 | 2 | 0% | 2022-12-20 13:00 | 2022-12-22 12:00 | -19 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02465 | 0 | 0 | OG8-02465 | Construction | Roof | Construction.3.1.3 | Pull Fire Alarm Wiring - Roof | 3 | 3 | 0% | 2022-12-15 13:00 | 2022-12-20 12:00 | -19 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02495 | 0 | 0 | OG8-02495 | Construction | Roof | Construction.3.1.3 | Install Firestopping | 4 | 4 | 0% | 2023-02-27 08:00 | 2023-03-02 17:00 | -59 | MLJ | FIRESTOPPING | NEW BUILDING | 07-1300 | 07-1300-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02500 | 0 | 0 | OG8-02500 | Construction | Roof | Construction.3.1.3 | Tag & Terminate Switchgear Equipment - Roof | 3 | 3 | 0% | 2023-03-31 08:00 | 2023-04-04 17:00 | -82 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02515 | 0 | 0 | OG8-02515 | Construction | Roof | Construction.3.1.3 | Tag & Terminate all Fire Alarm Equipment - Roof | 3 | 3 | 0% | 2023-03-31 08:00 | 2023-04-04 17:00 | 26 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02490 | 0 | 0 | OG8-02490 | Construction | Roof | Construction.3.1.3 | Pull Feeder Cable from Foundation to Switchgear Equipment - Roof | 15 | 15 | 0% | 2023-02-03 08:00 | 2023-02-24 17:00 | -59 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02520 | 0 | 0 | OG8-02520 | Construction | Roof | Construction.3.1.3 | Terminate Light Fixtures - Roof | 3 | 3 | 0% | 2023-03-31 08:00 | 2023-04-04 17:00 | -82 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02505 | 0 | 0 | OG8-02505 | Construction | Roof | Construction.3.1.3 | Install Panelboards- Roof | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | -8 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 02507 | 0 | 0 | OG8-02507 | Construction | Roof | Construction.3.1.3 | Tag & Terminate Panelboards - Roof | 3 | 3 | 0% | 2022-11-29 08:00 | 2022-12-01 17:00 | 2 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.6 | OG8 | OG8 | 02740 | 0 | 0 | OG8-02740 | Construction | Testing & Start-Up | Construction.3.1.6 | Fire Alarm Operational & FDNY Acceptance Testing - OG8 | 2 | 2 | 0% | 2023-04-26 08:00 | 2023-04-27 17:00 | 11 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.6 | OG8 | OG8 | 02730 | 0 | 0 | OG8-02730 | Construction | Testing & Start-Up | Construction.3.1.6 | Provide Load Bank & Perform Acceptance Testing for Generator OG4(2 No's) - OG8 | 2 | 2 | 0% | 2023-04-20 08:00 | 2023-04-21 17:00 | -83 | UNSURE | STARTUP | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.6 | OG8 | OG8 | 02705 | 0 | 0 | OG8-02705 | Construction | Testing & Start-Up | Construction.3.1.6 | Perform Electrical Inspections for OG8 | 5 | 5 | 0% | 2023-04-05 08:00 | 2023-04-11 17:00 | -82 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.6 | OG8 | OG8 | 02725 | 0 | 0 | OG8-02725 | Construction | Testing & Start-Up | Construction.3.1.6 | Energize Switchgear Equipment - OG8 | 3 | 3 | 0% | 2023-04-17 08:00 | 2023-04-19 17:00 | -83 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.6 | OG8 | OG8 | 02720 | 0 | 0 | OG8-02720 | Construction | Testing & Start-Up | Construction.3.1.6 | Perform 3rd Party Testing - OG8 | 2 | 2 | 0% | 2023-04-13 08:00 | 2023-04-14 17:00 | -83 | UNSURE | STARTUP | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.6 | OG8 | OG8 | 02710 | 0 | 0 | OG8-02710 | Construction | Testing & Start-Up | Construction.3.1.6 | Notify NYCHA of Fire Alarm Testing - OG8 | 14 | 14 | 0% | 2023-04-06 08:00 | 2023-04-25 17:00 | 11 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.6 | OG8 | OG8 | 02735 | 0 | 0 | OG8-02735 | Construction | Testing & Start-Up | Construction.3.1.6 | Provide Load Bank & Perform Acceptance Testing for Generator OG5 - OG8 | 2 | 2 | 0% | 2023-04-24 08:00 | 2023-04-25 17:00 | -81 | UNSURE | STARTUP | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.6 | OG8 | OG8 | 02715 | 0 | 0 | OG8-02715 | Construction | Testing & Start-Up | Construction.3.1.6 | Notify NYCHA of Generator Acceptance Testing- OG8 | 15 | 15 | 0% | 2023-03-30 08:00 | 2023-04-19 17:00 | -83 | UNSURE | STARTUP | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.5 | OG8 | OG8 | 02305 | 0 | 0 | OG8-02305 | Construction | Upper Second Floor | Construction.3.1.8.5 | Install Feeder Conduit Risers & Racks to Roof - Upper Second Floor | 20 | 1 | 95% | 2022-05-04 | 2022-11-25 17:00 | -13 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.5 | OG8 | OG8 | 02310 | 0 | 0 | OG8-02310 | Construction | Upper Second Floor | Construction.3.1.8.5 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Upper Second Floor | 10 | 10 | 0% | 2022-12-12 13:00 | 2022-12-27 12:00 | -18 | FSE | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.5 | OG8 | OG8 | 02315 | 0 | 0 | OG8-02315 | Construction | Upper Second Floor | Construction.3.1.8.5 | Install Branch Conduits - Upper Second Floor | 20 | 6 | 70% | 2022-06-20 | 2022-12-12 12:00 | -19 | FSE | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.5 | OG8 | OG8 | 02320 | 0 | 0 | OG8-02320 | Construction | Upper Second Floor | Construction.3.1.8.5 | Pull Branch Wiring - Upper Second Floor | 3 | 2 | 25% | 2022-06-20 | 2022-12-14 12:00 | -15 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.5 | OG8 | OG8 | 02325 | 0 | 0 | OG8-02325 | Construction | Upper Second Floor | Construction.3.1.8.5 | Pull Fire Alarm Wiring - Upper Second Floor | 3 | 3 | 0% | 2022-12-12 13:00 | 2022-12-15 12:00 | -19 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.5 | OG8 | OG8 | 02330 | 0 | 0 | OG8-02330 | Construction | Upper Second Floor | Construction.3.1.8.5 | Install Smoke Detection/Fire Alarm Equipment - Upper Second Floor | 3 | 3 | 0% | 2022-12-15 13:00 | 2022-12-20 12:00 | 95 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.5 | OG8 | OG8 | 02335 | 0 | 0 | OG8-02335 | Construction | Upper Second Floor | Construction.3.1.8.5 | Install Light/Emergency Fixtures - Upper Second Floor | 2 | 2 | 0% | 2023-01-30 08:00 | 2023-01-31 17:00 | -44 | FSE | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.8.5 | OG8 | OG8 | 02340 | 0 | 0 | OG8-02340 | Construction | Upper Second Floor | Construction.3.1.8.5 | Install In-slab Conduits - 2nd Floor slab - Upper Second Floor | 10 | 0 | 100% | 2022-03-18 | 2022-05-05 |  | 0 | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.5 | OG8 | OG8 | 02345 | 0 | 0 | OG8-02345 | Construction | Upper Second Floor | Construction.3.1.8.5 | Install Receptacles - Upper Second Floor | 2 | 2 | 25% | 2022-06-20 | 2022-12-14 12:00 | -10 | FSE | RECEPTACLES | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 02005 | 0 | 0 | OG4-02005 | Construction | Cellar | Construction.3.6.8.1 | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 5 | 4 | 25% | 2022-06-10 | 2022-11-30 15:00 | -40 | FSE | 0 | 0 | 0 | 0-OG4
In Progress | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 02015 | 0 | 0 | OG4-02015 | Construction | Cellar | Construction.3.6.8.1 | Install Bypass Connections - Cellar | 6 | 5 | 25% | 2022-06-13 | 2022-12-01 12:00 | -41 | MEP | 0 | 0 | 0 | 0-OG4
In Progress | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 02025 | 0 | 0 | OG4-02025 | Construction | Cellar | Construction.3.6.8.1 | Relocate (E) & Install Temporary Lighting - Cellar | 5 | 3 | 50% | 2022-06-20 | 2022-12-30 17:00 | -61 | FSE | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 02030 | 0 | 0 | OG4-02030 | Construction | Cellar | Construction.3.6.8.1 | Core Drill & Install Incoming Feeder Conduits & Racks - Cellar | 20 | 0 | 100% | 2022-04-24 | 2022-04-24 |  | 0 | 0 | 0 | 0 | 0-OG4
In Progress | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 02020 | 0 | 0 | OG4-02020 | Construction | Cellar | Construction.3.6.8.1 | Install Branch Conduit - Cellar | 20 | 10 | 50% | 2022-06-15 | 2022-12-08 17:00 | -19 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 02035 | 0 | 0 | OG4-02035 | Construction | Cellar | Construction.3.6.8.1 | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 20 | 20 | 0% | 2023-01-03 08:00 | 2023-01-31 17:00 | -61 | FSE | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 02055 | 0 | 0 | OG4-02055 | Construction | Cellar | Construction.3.6.8.1 | Link & Seal Conduit Sleeves - Cellar | 10 | 0 | 100% | 2021-10-22 | 2021-10-22 |  | 0 | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 02060 | 0 | 0 | OG4-02060 | Construction | Cellar | Construction.3.6.8.1 | Pull Lighting Wiring - Cellar | 5 | 5 | 0% | 2023-02-01 08:00 | 2023-02-07 17:00 | -61 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 02070 | 0 | 0 | OG4-02070 | Construction | Cellar | Construction.3.6.8.1 | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 5 | 5 | 0% | 2023-02-08 08:00 | 2023-02-14 17:00 | -61 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 02040 | 0 | 0 | OG4-02040 | Construction | Cellar | Construction.3.6.8.1 | Pull Branch Wiring - Cellar | 8 | 8 | 0% | 2022-12-09 08:00 | 2022-12-20 17:00 | -19 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 02045 | 0 | 0 | OG4-02045 | Construction | Cellar | Construction.3.6.8.1 | Install Heat Trace for Plumbing Lines - Cellar | 5 | 5 | 0% | 2023-02-08 08:00 | 2023-02-14 17:00 | -51 | FSE | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 02065 | 0 | 0 | OG4-02065 | Construction | Cellar | Construction.3.6.8.1 | Core Drill & Install Feeder Conduits Risers & Racks Directly to 1st Floor - Cellar | 20 | 0 | 100% | 2022-06-20 | 2022-09-23 17:00 |  | FSE | CORE DRILL | 0 | 0 | 0-OG4
In Progress | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 02010 | 0 | 0 | OG4-02010 | Construction | Cellar | Construction.3.6.8.1 | Install Panelboards (Misc.) - Cellar | 2 | 1 | 50% | 2022-09-29 15:00 | 2022-11-25 17:00 | -10 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 02050 | 0 | 0 | OG4-02050 | Construction | Cellar | Construction.3.6.8.1 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Cellar | 5 | 5 | 0% | 2022-12-21 08:00 | 2022-12-28 17:00 | -19 | FSE | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.8.2 | OG4 | OG4 | 02130 | 0 | 0 | OG4-02130 | Construction | 1st Floor | Construction.3.6.8.2 | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 15 | 0 | 100% | 2022-06-22 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.8.2 | OG4 | OG4 | 02135 | 0 | 0 | OG4-02135 | Construction | 1st Floor | Construction.3.6.8.2 | Install Pull/Splice Boxes - 1st Floor | 5 | 0 | 100% | 2022-07-01 13:00 | 2022-11-15 |  | 0 | 0 | 0 | 0 | 0-OG4
In Progress | CI NYCHA Update #22.Construction.3.6.8.2 | OG4 | OG4 | 02105 | 0 | 0 | OG4-02105 | Construction | 1st Floor | Construction.3.6.8.2 | Install Branch Conduit - 1st Floor | 15 | 2 | 90% | 2022-07-01 15:00 | 2022-11-28 12:00 | -18 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.2 | OG4 | OG4 | 02110 | 0 | 0 | OG4-02110 | Construction | 1st Floor | Construction.3.6.8.2 | Pull Branch Wiring - 1st Floor | 5 | 5 | 0% | 2022-11-28 13:00 | 2022-12-05 12:00 | -18 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.2 | OG4 | OG4 | 02115 | 0 | 0 | OG4-02115 | Construction | 1st Floor | Construction.3.6.8.2 | Install Fire Alarm Control Panel & Equipment - 1st Floor | 5 | 5 | 0% | 2022-12-05 13:00 | 2022-12-12 12:00 | -18 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.2 | OG4 | OG4 | 02125 | 0 | 0 | OG4-02125 | Construction | 1st Floor | Construction.3.6.8.2 | Pull Fire Alarm Wiring - 1st Floor | 2 | 2 | 0% | 2022-12-12 13:00 | 2022-12-14 12:00 | 80 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.2 | OG4 | OG4 | 02120 | 0 | 0 | OG4-02120 | Construction | 1st Floor | Construction.3.6.8.2 | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 5 | 5 | 0% | 2023-02-15 08:00 | 2023-02-22 17:00 | -61 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.2 | OG4 | OG4 | 02140 | 0 | 0 | OG4-02140 | Construction | 1st Floor | Construction.3.6.8.2 | Supply Power to Exterior Building Signage | 2 | 2 | 0% | 2022-12-05 13:00 | 2022-12-07 12:00 | -10 | FSE | 0 | 0 | 0 | 0-OG4
In Progress | CI NYCHA Update #22.Construction.3.6.8.2 | OG4 | OG4 | 02145 | 0 | 0 | OG4-02145 | Construction | 1st Floor | Construction.3.6.8.2 | Install Firestopping - 1st Floor | 5 | 3 | 50% | 2022-11-01 | 2022-12-07 12:00 | -10 | MLJ | FIRESTOPPING | EXISTING BUILDING | 07-1200 | 07-1200-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.2 | OG4 | OG4 | 02150 | 0 | 0 | OG4-02150 | Construction | 1st Floor | Construction.3.6.8.2 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 1st Floor | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -16 | FSE | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 02205 | 0 | 0 | OG4-02205 | Construction | 2nd Floor | Construction.3.6.8.3 | Install Switchboards - 2nd Floor | 15 | 0 | 100% | 2022-04-22 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-OG4
In Progress | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 02210 | 0 | 0 | OG4-02210 | Construction | 2nd Floor | Construction.3.6.8.3 | Install ACTTS - 2nd Floor | 5 | 0 | 95% | 2022-06-16 | 2022-11-25 10:00 | -6 | FSE | ACTTS | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 02215 | 0 | 0 | OG4-02215 | Construction | 2nd Floor | Construction.3.6.8.3 | Install Feeder Conduits & Racks to Switchgear Equipment - 2nd Floor | 20 | 0 | 100% | 2022-07-01 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-OG4
In Progress | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 02220 | 0 | 0 | OG4-02220 | Construction | 2nd Floor | Construction.3.6.8.3 | Install Panelboards - 2nd Floor | 5 | 0 | 95% | 2022-10-24 | 2022-11-25 10:00 | -10 | FSE | 0 | 0 | 0 | 0-OG4
In Progress | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 02225 | 0 | 0 | OG4-02225 | Construction | 2nd Floor | Construction.3.6.8.3 | Install Branch Conduit - 2nd Floor | 15 | 4 | 75% | 2022-10-15 | 2022-12-01 10:00 | -10 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 02235 | 0 | 0 | OG4-02235 | Construction | 2nd Floor | Construction.3.6.8.3 | Pull Branch Wiring - 2nd Floor | 5 | 5 | 0% | 2022-12-01 10:00 | 2022-12-08 10:00 | -10 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 02240 | 0 | 0 | OG4-02240 | Construction | 2nd Floor | Construction.3.6.8.3 | Install Lighting Fixtures & Controls - 2nd Floor | 5 | 5 | 0% | 2023-02-23 08:00 | 2023-03-01 17:00 | -61 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 02265 | 0 | 0 | OG4-02265 | Construction | 2nd Floor | Construction.3.6.8.3 | Install Fire Alarm Equipment - 2nd Floor | 5 | 5 | 0% | 2022-12-27 13:00 | 2023-01-04 12:00 | 72 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 02245 | 0 | 0 | OG4-02245 | Construction | 2nd Floor | Construction.3.6.8.3 | Install Receptacles - 2nd Floor | 5 | 5 | 0% | 2022-12-08 10:00 | 2022-12-15 10:00 | -10 | FSE | RECEPTACLES | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 02270 | 0 | 0 | OG4-02270 | Construction | 2nd Floor | Construction.3.6.8.3 | Install Fire Stopping - 2nd Floor | 5 | 5 | 0% | 2022-12-07 13:00 | 2022-12-14 12:00 | -10 | MLJ | FIRESTOPPING | EXISTING BUILDING | 07-1200 | 07-1200-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 02255 | 0 | 0 | OG4-02255 | Construction | 2nd Floor | Construction.3.6.8.3 | Tag & Terminate Panelboards | 2 | 2 | 0% | 2022-12-19 13:00 | 2022-12-21 12:00 | -15 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 02260 | 0 | 0 | OG4-02260 | Construction | 2nd Floor | Construction.3.6.8.3 | Tag & Terminate Switchgear Equipment | 5 | 5 | 0% | 2022-12-19 13:00 | 2022-12-27 12:00 | -18 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 02230 | 0 | 0 | OG4-02230 | Construction | 2nd Floor | Construction.3.6.8.3 | Ground Equipment | 5 | 5 | 0% | 2022-12-12 13:00 | 2022-12-19 12:00 | -18 | FSE | GROUNDING EQUIP | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 02275 | 0 | 0 | OG4-02275 | Construction | 2nd Floor | Construction.3.6.8.3 | Terminate Fire Alarm System | 5 | 5 | 0% | 2023-01-04 13:00 | 2023-01-11 12:00 | 81 | FSE | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 02250 | 0 | 0 | OG4-02250 | Construction | 2nd Floor | Construction.3.6.8.3 | Pull CON-ED Feeder Cable from Cellar to Switchgear - 2nd Floor | 20 | 0 | 100% | 2022-11-01 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 02280 | 0 | 0 | OG4-02280 | Construction | 2nd Floor | Construction.3.6.8.3 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -16 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.4 | OG4 | OG4 | 02535 | 0 | 0 | OG4-02535 | Construction | Testing & Start-Up | Construction.3.6.8.4 | Fire Alarm Operational & FDNY Acceptance Testing - OG4 | 5 | 5 | 0% | 2023-05-03 08:00 | 2023-05-09 17:00 | 3 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.4 | OG4 | OG4 | 02515 | 0 | 0 | OG4-02515 | Construction | Testing & Start-Up | Construction.3.6.8.4 | Energize Switchgear - OG4 | 5 | 5 | 0% | 2023-04-17 08:00 | 2023-04-21 17:00 | -86 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.4 | OG4 | OG4 | 02530 | 0 | 0 | OG4-02530 | Construction | Testing & Start-Up | Construction.3.6.8.4 | Start-Up Generator/Switchgear - OG4 | 4 | 4 | 0% | 2023-04-27 08:00 | 2023-05-02 17:00 | -86 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.4 | OG4 | OG4 | 02505 | 0 | 0 | OG4-02505 | Construction | Testing & Start-Up | Construction.3.6.8.4 | Perform Electrical Inspections - OG4 | 5 | 5 | 0% | 2023-03-14 08:00 | 2023-03-20 17:00 | -69 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.4 | OG4 | OG4 | 02510 | 0 | 0 | OG4-02510 | Construction | Testing & Start-Up | Construction.3.6.8.4 | Perform 3rd Party Test - OG4 | 2 | 2 | 0% | 2023-04-13 08:00 | 2023-04-14 17:00 | -86 | UNSURE | STARTUP | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.4 | OG4 | OG4 | 02525 | 0 | 0 | OG4-02525 | Construction | Testing & Start-Up | Construction.3.6.8.4 | Notify NYCHA of Fire Alarm Acceptance Testing - OG4 | 14 | 14 | 0% | 2023-04-13 08:00 | 2023-05-02 17:00 | 3 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.4 | OG4 | OG4 | 02520 | 0 | 0 | OG4-02520 | Construction | Testing & Start-Up | Construction.3.6.8.4 | Perform Tie-in's to Exisiting | 3 | 3 | 0% | 2023-04-24 08:00 | 2023-04-26 17:00 | -86 | UNSURE | STARTUP | 0 | 0 | 0-OG4
In Progress | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 02005 | 0 | 0 | OG5-02005 | Construction | Cellar | Construction.3.3.8.1 | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 4 | 4 | 10% | 2022-06-10 | 2022-11-30 13:48 | -35 | FSE | 0 | 0 | 0 | 0-OG5
In Progress | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 02010 | 0 | 0 | OG5-02010 | Construction | Cellar | Construction.3.3.8.1 | Install Bypass Connections - Cellar | 7 | 5 | 25% | 2022-06-13 | 2022-12-05 13:48 | -35 | MEP | 0 | 0 | 0 | 0-OG5
In Progress | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 02025 | 0 | 0 | OG5-02025 | Construction | Cellar | Construction.3.3.8.1 | Relocate (E) & Install Temporary Lighting Cellar | 3 | 2 | 25% | 2022-06-15 | 2022-12-05 13:48 | -35 | FSE | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 02030 | 0 | 0 | OG5-02030 | Construction | Cellar | Construction.3.3.8.1 | Core Drill & Install Incoming Feeder Conduits & Racks - Cellar | 18 | 0 | 100% | 2022-06-15 | 2022-07-01 |  | FSE | CORE DRILL | 0 | 0 | 0-OG5
In Progress | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 02015 | 0 | 0 | OG5-02015 | Construction | Cellar | Construction.3.3.8.1 | Install Branch Conduit - Cellar | 19 | 10 | 50% | 2022-07-01 | 2022-12-08 12:00 | -12 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 02035 | 0 | 0 | OG5-02035 | Construction | Cellar | Construction.3.3.8.1 | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 15 | 15 | 0% | 2023-01-03 08:00 | 2023-01-24 17:00 | -53 | FSE | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 02055 | 0 | 0 | OG5-02055 | Construction | Cellar | Construction.3.3.8.1 | Link & Seal Conduit Sleeves - Cellar | 10 | 0 | 100% | 2021-10-22 | 2021-10-22 |  | 0 | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 02060 | 0 | 0 | OG5-02060 | Construction | Cellar | Construction.3.3.8.1 | Pull Lighting Wiring - Cellar | 5 | 5 | 0% | 2023-01-25 08:00 | 2023-01-31 17:00 | -53 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 02070 | 0 | 0 | OG5-02070 | Construction | Cellar | Construction.3.3.8.1 | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 5 | 5 | 0% | 2023-02-01 08:00 | 2023-02-07 17:00 | -53 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 02040 | 0 | 0 | OG5-02040 | Construction | Cellar | Construction.3.3.8.1 | Pull Branch Wiring - Cellar | 7 | 7 | 0% | 2022-12-08 13:00 | 2022-12-19 12:00 | -12 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 02045 | 0 | 0 | OG5-02045 | Construction | Cellar | Construction.3.3.8.1 | Install Heat Trace for Plumbing Lines - Cellar | 2 | 2 | 0% | 2022-12-19 13:00 | 2022-12-21 12:00 | -9 | FSE | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 02065 | 0 | 0 | OG5-02065 | Construction | Cellar | Construction.3.3.8.1 | Core Drill & Install Conduits Risers & Racks to 1st Floor - Cellar | 20 | 0 | 100% | 2022-06-20 | 2022-09-27 17:00 |  | FSE | CORE DRILL | 0 | 0 | 0-OG5
In Progress | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 02020 | 0 | 0 | OG5-02020 | Construction | Cellar | Construction.3.3.8.1 | Install Panelboards (Misc.) - Cellar | 2 | 1 | 50% | 2022-09-29 13:48 | 2022-11-25 17:00 | -3 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 02050 | 0 | 0 | OG5-02050 | Construction | Cellar | Construction.3.3.8.1 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Cellar | 5 | 5 | 0% | 2023-01-10 08:00 | 2023-01-17 17:00 | -25 | FSE | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.8.2 | OG5 | OG5 | 02125 | 0 | 0 | OG5-02125 | Construction | 1st Floor | Construction.3.3.8.2 | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 12 | 0 | 100% | 2022-06-20 | 2022-09-27 17:00 |  | FSE | 0 | 0 | 0 | 0-OG5
In Progress | CI NYCHA Update #22.Construction.3.3.8.2 | OG5 | OG5 | 02135 | 0 | 0 | OG5-02135 | Construction | 1st Floor | Construction.3.3.8.2 | Install Pull/Splice Boxes - 1st Floor | 4 | 0 | 90% | 2022-06-20 10:00 | 2022-11-25 11:12 | 5 | MEP | 0 | 0 | 0 | 0-OG5
In Progress | CI NYCHA Update #22.Construction.3.3.8.2 | OG5 | OG5 | 02105 | 0 | 0 | OG5-02105 | Construction | 1st Floor | Construction.3.3.8.2 | Install Branch Conduit - 1st Floor | 11 | 1 | 90% | 2022-07-15 15:48 | 2022-11-28 08:48 | -14 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.2 | OG5 | OG5 | 02110 | 0 | 0 | OG5-02110 | Construction | 1st Floor | Construction.3.3.8.2 | Pull Branch Wiring - 1st Floor | 6 | 6 | 0% | 2022-11-28 08:48 | 2022-12-06 08:48 | -14 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.2 | OG5 | OG5 | 02115 | 0 | 0 | OG5-02115 | Construction | 1st Floor | Construction.3.3.8.2 | Install Fire Alarm Control Panel (FACP) & Smoke Detectors - 1st Floor | 5 | 5 | 0% | 2022-12-06 08:48 | 2022-12-13 08:48 | -14 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.2 | OG5 | OG5 | 02130 | 0 | 0 | OG5-02130 | Construction | 1st Floor | Construction.3.3.8.2 | Pull Fire Alarm Wiring - 1st Floor | 2 | 2 | 0% | 2022-12-13 08:48 | 2022-12-15 08:48 | 79 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.2 | OG5 | OG5 | 02120 | 0 | 0 | OG5-02120 | Construction | 1st Floor | Construction.3.3.8.2 | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 5 | 5 | 0% | 2023-02-08 08:00 | 2023-02-14 17:00 | -53 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.2 | OG5 | OG5 | 02140 | 0 | 0 | OG5-02140 | Construction | 1st Floor | Construction.3.3.8.2 | Supply Power to Exterior Building Signage | 2 | 2 | 0% | 2022-12-06 08:48 | 2022-12-08 08:48 | -4 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.2 | OG5 | OG5 | 02145 | 0 | 0 | OG5-02145 | Construction | 1st Floor | Construction.3.3.8.2 | Install Firestopping - 1st Floor | 5 | 5 | 0% | 2022-12-08 08:48 | 2022-12-15 08:48 | -4 | MLJ | FIRESTOPPING | EXISTING BUILDING | 07-1200 | 07-1200-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.2 | OG5 | OG5 | 02150 | 0 | 0 | OG5-02150 | Construction | 1st Floor | Construction.3.3.8.2 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 1st Floor | 5 | 5 | 0% | 2023-01-18 08:00 | 2023-01-24 17:00 | -30 | FSE | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 02205 | 0 | 0 | OG5-02205 | Construction | 2nd Floor | Construction.3.3.8.3 | Install Switchboards - 2nd Floor | 12 | 0 | 100% | 2022-05-16 | 2022-10-21 17:00 |  | FSE | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 02210 | 0 | 0 | OG5-02210 | Construction | 2nd Floor | Construction.3.3.8.3 | Install ACTTS - 2nd Floor | 4 | 0 | 100% | 2022-05-16 | 2022-10-21 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 02215 | 0 | 0 | OG5-02215 | Construction | 2nd Floor | Construction.3.3.8.3 | Install Feeder Conduits & Racks to Switchgear Equipment - 2nd Floor | 15 | 0 | 100% | 2022-07-01 | 2022-10-21 17:00 |  | FSE | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 02220 | 0 | 0 | OG5-02220 | Construction | 2nd Floor | Construction.3.3.8.3 | Install Panelboards - 2nd Floor | 4 | 0 | 100% | 2022-09-23 | 2022-10-21 17:00 |  | FSE | 0 | 0 | 0 | 0-OG5
In Progress | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 02225 | 0 | 0 | OG5-02225 | Construction | 2nd Floor | Construction.3.3.8.3 | Install Branch Conduit - 2nd Floor | 15 | 2 | 90% | 2022-09-23 | 2022-11-28 12:00 | -8 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 02235 | 0 | 0 | OG5-02235 | Construction | 2nd Floor | Construction.3.3.8.3 | Pull Branch Wiring - 2nd Floor | 5 | 5 | 0% | 2022-11-28 13:00 | 2022-12-05 12:00 | -8 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 02240 | 0 | 0 | OG5-02240 | Construction | 2nd Floor | Construction.3.3.8.3 | Install Lighting Fixtures & Controls - 2nd Floor | 4 | 4 | 0% | 2023-02-15 08:00 | 2023-02-21 17:00 | -53 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 02245 | 0 | 0 | OG5-02245 | Construction | 2nd Floor | Construction.3.3.8.3 | Install Smoke Detection Equipment - 2nd Floor | 5 | 5 | 0% | 2022-12-15 08:48 | 2022-12-22 08:48 | 79 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 02250 | 0 | 0 | OG5-02250 | Construction | 2nd Floor | Construction.3.3.8.3 | Install Receptacles - 2nd Floor | 4 | 4 | 0% | 2022-12-05 13:00 | 2022-12-09 12:00 | -8 | FSE | RECEPTACLES | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 02255 | 0 | 0 | OG5-02255 | Construction | 2nd Floor | Construction.3.3.8.3 | Install Fire Stopping - 2nd Floor | 4 | 4 | 0% | 2023-02-22 08:00 | 2023-02-27 17:00 | -53 | MLJ | FIRESTOPPING | EXISTING BUILDING | 07-1200 | 07-1200-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 02265 | 0 | 0 | OG5-02265 | Construction | 2nd Floor | Construction.3.3.8.3 | Tag & Terminate Switchgear Equipment | 5 | 5 | 0% | 2022-12-20 08:48 | 2022-12-28 08:48 | -14 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 02275 | 0 | 0 | OG5-02275 | Construction | 2nd Floor | Construction.3.3.8.3 | Tag & Terminate Panelboards | 2 | 2 | 0% | 2022-12-28 08:48 | 2022-12-30 08:48 | -14 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 02230 | 0 | 0 | OG5-02230 | Construction | 2nd Floor | Construction.3.3.8.3 | Ground Equipment | 5 | 5 | 0% | 2022-12-13 08:48 | 2022-12-20 08:48 | -14 | FSE | GROUNDING EQUIP | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 02280 | 0 | 0 | OG5-02280 | Construction | 2nd Floor | Construction.3.3.8.3 | Terminate Fire Alarm System | 2 | 2 | 0% | 2022-12-28 08:48 | 2022-12-30 08:48 | 88 | FSE | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 02260 | 0 | 0 | OG5-02260 | Construction | 2nd Floor | Construction.3.3.8.3 | Pull CON-ED Feeder Cable - Cellar to OG5 Switchgear - 2nd Floor | 20 | 0 | 100% | 2022-11-01 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 02270 | 0 | 0 | OG5-02270 | Construction | 2nd Floor | Construction.3.3.8.3 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 5 | 5 | 0% | 2023-02-01 08:00 | 2023-02-07 17:00 | -40 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.4 | OG5 | OG5 | 02530 | 0 | 0 | OG5-02530 | Construction | Testing & Start-Up | Construction.3.3.8.4 | Start-Up Generator/Switchgear - OG5 | 4 | 4 | 0% | 2023-05-03 08:00 | 2023-05-08 17:00 | -86 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.4 | OG5 | OG5 | 02535 | 0 | 0 | OG5-02535 | Construction | Testing & Start-Up | Construction.3.3.8.4 | Fire Alarm Operational & FDNY Acceptance Testing - OG5 | 5 | 5 | 0% | 2023-05-09 08:00 | 2023-05-15 17:00 | -1 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.4 | OG5 | OG5 | 02515 | 0 | 0 | OG5-02515 | Construction | Testing & Start-Up | Construction.3.3.8.4 | Energize Switchgear - OG5 | 5 | 5 | 0% | 2023-03-21 08:00 | 2023-03-27 17:00 | -63 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.4 | OG5 | OG5 | 02505 | 0 | 0 | OG5-02505 | Construction | Testing & Start-Up | Construction.3.3.8.4 | Perform Electrical Inspections - OG5 | 5 | 5 | 0% | 2023-03-14 08:00 | 2023-03-20 17:00 | -63 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.4 | OG5 | OG5 | 02520 | 0 | 0 | OG5-02520 | Construction | Testing & Start-Up | Construction.3.3.8.4 | Perform Tie-Ins to Existing | 3 | 3 | 0% | 2023-03-28 08:00 | 2023-03-30 17:00 | -63 | UNSURE | STARTUP | 0 | 0 | 0-OG5
In Progress | CI NYCHA Update #22.Construction.3.3.8.4 | OG5 | OG5 | 02510 | 0 | 0 | OG5-02510 | Construction | Testing & Start-Up | Construction.3.3.8.4 | Perform 3rd Party Test | 2 | 1 | 50% | 2022-09-15 | 2023-03-20 17:00 | -63 | UNSURE | STARTUP | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.4 | OG5 | OG5 | 02525 | 0 | 0 | OG5-02525 | Construction | Testing & Start-Up | Construction.3.3.8.4 | Notify NYCHA of Fire Alarm Acceptance Testing | 14 | 14 | 0% | 2023-04-19 08:00 | 2023-05-08 17:00 | -1 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.1.5.2 | OGE | OGE | 02105 | 0 | 0 | OGE-02105 | Construction | Cable Pulls | Construction.1.5.2 | Pull CON-ED Feeder Cable - 33rd st. to OG1 Cellar | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | 17 | FSE | 0 | 0 | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.2 | OGE | OGE | 02110 | 0 | 0 | OGE-02110 | Construction | Cable Pulls | Construction.1.5.2 | Pull CON-ED Feeder Cable - 33rd St. to OG6 Cellar | 10 | 10 | 0% | 2023-02-09 08:00 | 2023-02-23 17:00 | -67 | FSE | 0 | 0 | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.2 | OGE | OGE | 02115 | 0 | 0 | OGE-02115 | Construction | Cable Pulls | Construction.1.5.2 | Pull Feeder Cable - OG6 Switchgear to OG10 Foundation | 10 | 10 | 0% | 2023-03-07 08:00 | 2023-03-20 17:00 | -49 | FSE | 0 | 0 | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.2 | OGE | OGE | 02125 | 0 | 0 | OGE-02125 | Construction | Cable Pulls | Construction.1.5.2 | Pull Generator Feeder Cable from OG10 to OG1 | 5 | 5 | 0% | 2022-12-28 08:00 | 2023-01-04 17:00 | 2 | FSE | 0 | 0 | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.2 | OGE | OGE | 02120 | 0 | 0 | OGE-02120 | Construction | Cable Pulls | Construction.1.5.2 | Pull Generator Feeder Cable from OG10 to OG6 | 5 | 5 | 0% | 2023-03-07 08:00 | 2023-03-13 17:00 | -44 | FSE | 0 | 0 | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.3 | OGE | OGE | 02205 | 0 | 0 | OGE-02205 | Construction | Site Lighting | Construction.1.5.3 | Remove Existing Lighting Conduit, Cable & Fixtures | 5 | 5 | 0% | 2023-06-09 08:00 | 2023-06-15 17:00 | -22 | FSE | 0 | 0 | 0 | 0-OGE
In Progress | CI NYCHA Update #22.Construction.1.5.3 | OGE | OGE | 02210 | 0 | 0 | OGE-02210 | Construction | Site Lighting | Construction.1.5.3 | Furnish & Install Site Lighting Conduit | 5 | 3 | 50% | 2022-10-10 08:00 | 2023-06-15 17:00 | -22 | FSE | 0 | 0 | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.3 | OGE | OGE | 02215 | 0 | 0 | OGE-02215 | Construction | Site Lighting | Construction.1.5.3 | Pull Site Lighting Wire | 4 | 4 | 0% | 2023-06-16 08:00 | 2023-06-21 17:00 | -22 | FSE | 0 | 0 | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.3 | OGE | OGE | 02220 | 0 | 0 | OGE-02220 | Construction | Site Lighting | Construction.1.5.3 | Install Site Lighting Fixtures & Terminate | 5 | 5 | 0% | 2023-06-22 08:00 | 2023-06-28 17:00 | -22 | FSE | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.4.5.4 | OG10 | OG10 | 02015 | 0 | 0 | OG10-02015 | Construction | Foundation | Construction.1.4.5.4 | Install Branch Conduit in Plumbing Shaft - Foundation | 2 | 0 | 100% | 2022-05-25 08:00 | 2022-09-01 17:00 |  | FSE | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.4 | OG10 | OG10 | 02005 | 0 | 0 | OG10-02005 | Construction | Foundation | Construction.1.4.5.4 | Install Temporary Lighting & Temporary Power for OG10 | 5 | 0 | 100% | 2022-07-01 | 2022-09-24 |  | FSE | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.4 | OG10 | OG10 | 02010 | 0 | 0 | OG10-02010 | Construction | Foundation | Construction.1.4.5.4 | Install Conduit Risers to 1st Floor for Incoming Feeders - Foundation | 10 | 0 | 100% | 2021-09-21 | 2022-02-10 |  | 0 | 0 | 0 | 0 | 0-OG10
In Progress | CI NYCHA Update #22.Construction.1.4.5.4 | OG10 | OG10 | 02025 | 0 | 0 | OG10-02025 | Construction | Foundation | Construction.1.4.5.4 | Pull Wire to Light Fixture & Mechanical Equipment in Plumbing Shaft - Foundation | 2 | 1 | 50% | 2022-05-27 08:00 | 2022-11-25 17:00 | 21 | FSE | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.4 | OG10 | OG10 | 02020 | 0 | 0 | OG10-02020 | Construction | Foundation | Construction.1.4.5.4 | Install Pull Box - Foundation | 2 | 0 | 100% | 2022-02-10 | 2022-02-14 |  | 0 | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 02130 | 0 | 0 | OG10-02130 | Construction | 1st Floor | Construction.1.4.5.1 | Install Smoke Detection/Fire Alarm Equipment - 1st Floor | 3 | 3 | 0% | 2022-11-30 08:00 | 2022-12-02 17:00 | 19 | FSE | 0 | 0 | 0 | 0-OG10
In Progress | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 02135 | 0 | 0 | OG10-02135 | Construction | 1st Floor | Construction.1.4.5.1 | Install Light/Emergency Fixtures - 1st Floor | 3 | 2 | 50% | 2022-11-01 | 2022-11-29 12:00 | 25 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 02120 | 0 | 0 | OG10-02120 | Construction | 1st Floor | Construction.1.4.5.1 | Pull Fire Alarm Wiring - 1st Floor | 3 | 3 | 0% | 2022-11-25 08:00 | 2022-11-29 17:00 | 19 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 02140 | 0 | 0 | OG10-02140 | Construction | 1st Floor | Construction.1.4.5.1 | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - 1st Floor | 3 | 3 | 0% | 2022-11-28 13:00 | 2022-12-01 12:00 | 23 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 02155 | 0 | 0 | OG10-02155 | Construction | 1st Floor | Construction.1.4.5.1 | Install Receptacles - 1st Floor | 2 | 2 | 0% | 2022-12-09 08:00 | 2022-12-12 17:00 | 17 | FSE | RECEPTACLES | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 02150 | 0 | 0 | OG10-02150 | Construction | 1st Floor | Construction.1.4.5.1 | Install Remote Annunciator Panel (RAP). - 1st Floor | 2 | 2 | 0% | 2022-12-05 08:00 | 2022-12-06 17:00 | 19 | MEP | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 02110 | 0 | 0 | OG10-02110 | Construction | 1st Floor | Construction.1.4.5.1 | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 10 | 0 | 100% | 2022-02-01 | 2022-02-16 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 02115 | 0 | 0 | OG10-02115 | Construction | 1st Floor | Construction.1.4.5.1 | Install Branch Conduits - 1st Floor | 15 | 0 | 100% | 2022-01-17 | 2022-09-09 12:00 |  | FSE | 0 | 0 | 0 | 0-OG10
In Progress | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 02125 | 0 | 0 | OG10-02125 | Construction | 1st Floor | Construction.1.4.5.1 | Pull Branch Wiring - 1st Floor | 3 | 2 | 50% | 2022-06-10 | 2022-11-28 12:00 | 21 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 02145 | 0 | 0 | OG10-02145 | Construction | 1st Floor | Construction.1.4.5.1 | Install Heat Trace for Plumbing Lines -1st Floor | 3 | 3 | 0% | 2022-11-28 13:00 | 2022-12-01 12:00 | 42 | FSE | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 02105 | 0 | 0 | OG10-02105 | Construction | 1st Floor | Construction.1.4.5.1 | Install In-slab Conduits - 1st floor slab | 3 | 0 | 100% | 2022-01-17 | 2022-02-22 |  | 0 | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 02160 | 0 | 0 | OG10-02160 | Construction | 1st Floor | Construction.1.4.5.1 | Install Exterior Lighting & Controls - 1st Floor | 2 | 2 | 0% | 2022-12-07 08:00 | 2022-12-08 17:00 | 17 | FSE | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.2 | OG10 | OG10 | 02220 | 0 | 0 | OG10-02220 | Construction | 2nd Floor | Construction.1.4.5.2 | Install Feeder Conduit Risers & Racks to Roof - 2nd Floor | 20 | 0 | 100% | 2022-02-14 | 2022-07-01 |  | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.2 | OG10 | OG10 | 02225 | 0 | 0 | OG10-02225 | Construction | 2nd Floor | Construction.1.4.5.2 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 10 | 10 | 0% | 2022-12-23 08:00 | 2023-01-09 17:00 | 13 | FSE | 0 | 0 | 0 | 0-OG10
In Progress | CI NYCHA Update #22.Construction.1.4.5.2 | OG10 | OG10 | 02210 | 0 | 0 | OG10-02210 | Construction | 2nd Floor | Construction.1.4.5.2 | Install Branch Conduits - 2nd Floor | 15 | 3 | 80% | 2022-02-10 | 2022-11-29 17:00 | 20 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.2 | OG10 | OG10 | 02230 | 0 | 0 | OG10-02230 | Construction | 2nd Floor | Construction.1.4.5.2 | Pull Branch Wiring - 2nd Floor | 3 | 3 | 0% | 2022-11-30 08:00 | 2022-12-02 17:00 | 23 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.2 | OG10 | OG10 | 02235 | 0 | 0 | OG10-02235 | Construction | 2nd Floor | Construction.1.4.5.2 | Pull Fire Alarm Wiring - 2nd Floor | 3 | 3 | 0% | 2022-11-30 08:00 | 2022-12-02 17:00 | 20 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.2 | OG10 | OG10 | 02215 | 0 | 0 | OG10-02215 | Construction | 2nd Floor | Construction.1.4.5.2 | Install Smoke Detection/Fire Alarm Equipment - 2nd Floor | 3 | 3 | 0% | 2022-12-05 08:00 | 2022-12-07 17:00 | 99 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.2 | OG10 | OG10 | 02240 | 0 | 0 | OG10-02240 | Construction | 2nd Floor | Construction.1.4.5.2 | Install Light/Emergency Fixtures - 2nd Floor | 3 | 3 | 0% | 2022-12-05 08:00 | 2022-12-07 17:00 | 29 | FSE | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.2 | OG10 | OG10 | 02205 | 0 | 0 | OG10-02205 | Construction | 2nd Floor | Construction.1.4.5.2 | Install In-slab Conduits - 2nd floor slab | 10 | 0 | 100% | 2022-01-21 | 2022-02-02 |  | 0 | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.2 | OG10 | OG10 | 02245 | 0 | 0 | OG10-02245 | Construction | 2nd Floor | Construction.1.4.5.2 | Install Receptacles - 2nd Floor | 2 | 2 | 0% | 2022-12-13 08:00 | 2022-12-14 17:00 | 17 | FSE | RECEPTACLES | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02360 | 0 | 0 | OG10-02360 | Construction | Roof | Construction.1.4.5.3 | Install Feeder Conduit & Racks - Roof | 5 | 0 | 100% | 2022-06-13 | 2022-07-01 |  | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02305 | 0 | 0 | OG10-02305 | Construction | Roof | Construction.1.4.5.3 | Rig Generator OG1 - Roof | 1 | 1 | 0% | 2022-11-25 08:00 | 2022-11-25 17:00 | 2 | WELKIN | GENERATOR | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02315 | 0 | 0 | OG10-02315 | Construction | Roof | Construction.1.4.5.3 | Install Generator Circuit Breakers & Wire Generator OG6 - Roof | 10 | 10 | 0% | 2022-11-29 08:00 | 2022-12-12 17:00 | 2 | FSE | 0 | 0 | 0 | 0-OG10
In Progress | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02345 | 0 | 0 | OG10-02345 | Construction | Roof | Construction.1.4.5.3 | Install Branch Conduit - Roof | 4 | 0 | 90% | 2022-06-08 | 2022-11-25 11:12 | 23 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02350 | 0 | 0 | OG10-02350 | Construction | Roof | Construction.1.4.5.3 | Pull Branch Wiring - Roof | 3 | 3 | 0% | 2022-11-25 11:12 | 2022-11-30 11:12 | 23 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02310 | 0 | 0 | OG10-02310 | Construction | Roof | Construction.1.4.5.3 | Rig Generator OG6 - Roof | 1 | 1 | 0% | 2022-11-28 08:00 | 2022-11-28 17:00 | 2 | WELKIN | GENERATOR | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02320 | 0 | 0 | OG10-02320 | Construction | Roof | Construction.1.4.5.3 | Install Generator Circuit Breakers & Wire Generator OG1 - Roof | 10 | 10 | 0% | 2022-12-13 08:00 | 2022-12-27 17:00 | 2 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02415 | 0 | 0 | OG10-02415 | Construction | Roof | Construction.1.4.5.3 | Terminate all Mech. & Plumbing Equipment at Panel (PP-OG10) - Roof | 3 | 3 | 0% | 2023-04-06 08:00 | 2023-04-10 17:00 | -47 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02355 | 0 | 0 | OG10-02355 | Construction | Roof | Construction.1.4.5.3 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Roof | 5 | 5 | 0% | 2022-12-05 08:00 | 2022-12-09 17:00 | 32 | FSE | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.2 | OG10 | OG10 | 02330 | 0 | 0 | OG10-02330 | Construction | 2nd Floor | Construction.1.4.5.2 | Install Switchboards - 2nd Floor | 3 | 0 | 100% | 2022-07-22 | 2022-09-15 |  | FSE | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.2 | OG10 | OG10 | 02335 | 0 | 0 | OG10-02335 | Construction | 2nd Floor | Construction.1.4.5.2 | Install ACTTS - 2nd Floor | 3 | 0 | 100% | 2022-07-22 | 2022-09-15 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.2 | OG10 | OG10 | 02340 | 0 | 0 | OG10-02340 | Construction | 2nd Floor | Construction.1.4.5.2 | Install Panelboards - 2nd Floor | 8 | 0 | 100% | 2022-07-22 | 2022-09-15 |  | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02375 | 0 | 0 | OG10-02375 | Construction | Roof | Construction.1.4.5.3 | Install Smoke Detection/Fire Alarm Equipment - Roof | 3 | 3 | 0% | 2022-12-08 08:00 | 2022-12-12 17:00 | 99 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02380 | 0 | 0 | OG10-02380 | Construction | Roof | Construction.1.4.5.3 | Install Receptacles - Roof | 3 | 3 | 0% | 2022-12-15 08:00 | 2022-12-19 17:00 | 17 | FSE | RECEPTACLES | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02365 | 0 | 0 | OG10-02365 | Construction | Roof | Construction.1.4.5.3 | Install Light/Emergency Fixtures - Roof | 3 | 3 | 0% | 2022-12-08 08:00 | 2022-12-12 17:00 | 29 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02325 | 0 | 0 | OG10-02325 | Construction | Roof | Construction.1.4.5.3 | Install Lightning protection Air terminals - Roof | 5 | 5 | 0% | 2022-12-28 08:00 | 2023-01-04 17:00 | 4 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02390 | 0 | 0 | OG10-02390 | Construction | Roof | Construction.1.4.5.3 | Install Grounding & Ground Equipment | 3 | 3 | 0% | 2023-01-05 08:00 | 2023-01-09 17:00 | 4 | FSE | GROUNDING EQUIP | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02385 | 0 | 0 | OG10-02385 | Construction | Roof | Construction.1.4.5.3 | Install Fire Alarm Control Panel (Incl. Telephone Lines) - Roof | 2 | 2 | 0% | 2022-12-08 08:00 | 2022-12-09 17:00 | 20 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02370 | 0 | 0 | OG10-02370 | Construction | Roof | Construction.1.4.5.3 | Pull Fire Alarm Wiring - Roof | 3 | 3 | 0% | 2022-12-05 08:00 | 2022-12-07 17:00 | 20 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02420 | 0 | 0 | OG10-02420 | Construction | Roof | Construction.1.4.5.3 | Terminate Light Fixtures - Roof | 5 | 5 | 0% | 2023-04-06 08:00 | 2023-04-12 17:00 | -49 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02400 | 0 | 0 | OG10-02400 | Construction | Roof | Construction.1.4.5.3 | Install Firestopping | 4 | 4 | 0% | 2023-03-28 08:00 | 2023-03-31 17:00 | -41 | MLJ | FIRESTOPPING | NEW BUILDING | 07-1300 | 07-1300-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02405 | 0 | 0 | OG10-02405 | Construction | Roof | Construction.1.4.5.3 | Tag & Terminate Switchgear Equipment - Roof | 5 | 5 | 0% | 2023-03-28 08:00 | 2023-04-03 17:00 | -49 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02410 | 0 | 0 | OG10-02410 | Construction | Roof | Construction.1.4.5.3 | Tag & Terminate Panelboards - Roof | 2 | 2 | 0% | 2023-04-04 08:00 | 2023-04-05 17:00 | -49 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02425 | 0 | 0 | OG10-02425 | Construction | Roof | Construction.1.4.5.3 | Tag & Terminate Fire Alarm Equipment | 2 | 2 | 0% | 2023-04-06 08:00 | 2023-04-07 17:00 | 21 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 02395 | 0 | 0 | OG10-02395 | Construction | Roof | Construction.1.4.5.3 | Pull Feeder Cable - Foundation to Roof - Roof | 5 | 5 | 0% | 2023-03-21 08:00 | 2023-03-27 17:00 | -49 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.6 | OG10 | OG10 | 02540 | 0 | 0 | OG10-02540 | Construction | Testing & Start-Up | Construction.1.4.6 | Fire Alarm Operational & FDNY Acceptance Testing - OG10 | 4 | 4 | 0% | 2023-04-27 08:00 | 2023-05-02 17:00 | 8 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.6 | OG10 | OG10 | 02530 | 0 | 0 | OG10-02530 | Construction | Testing & Start-Up | Construction.1.4.6 | Provide Load Bank & Perform Acceptance Testing for Generator OG6 - OG10 | 2 | 2 | 0% | 2023-04-20 08:00 | 2023-04-21 17:00 | -49 | UNSURE | STARTUP | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.6 | OG10 | OG10 | 02505 | 0 | 0 | OG10-02505 | Construction | Testing & Start-Up | Construction.1.4.6 | Perform Electrical Inspections for OG10 | 5 | 5 | 0% | 2023-04-13 08:00 | 2023-04-19 17:00 | -49 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.6 | OG10 | OG10 | 02525 | 0 | 0 | OG10-02525 | Construction | Testing & Start-Up | Construction.1.4.6 | Energize Switchgear Equipment - OG10 | 3 | 3 | 0% | 2023-04-24 08:00 | 2023-04-26 17:00 | 8 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.6 | OG10 | OG10 | 02520 | 0 | 0 | OG10-02520 | Construction | Testing & Start-Up | Construction.1.4.6 | Perform 3rd Party Testing - OG10 | 2 | 2 | 0% | 2023-04-20 08:00 | 2023-04-21 17:00 | 8 | UNSURE | STARTUP | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.6 | OG10 | OG10 | 02510 | 0 | 0 | OG10-02510 | Construction | Testing & Start-Up | Construction.1.4.6 | Notify NYCHA of Fire Alarm Testing - OG10 | 14 | 14 | 0% | 2023-04-07 08:00 | 2023-04-26 17:00 | 8 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.6 | OG10 | OG10 | 02535 | 0 | 0 | OG10-02535 | Construction | Testing & Start-Up | Construction.1.4.6 | Provide Load Bank & Perform Acceptance Testing for Generator OG1 - OG10 | 2 | 2 | 0% | 2023-04-24 08:00 | 2023-04-25 17:00 | -35 | UNSURE | STARTUP | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.6 | OG10 | OG10 | 02515 | 0 | 0 | OG10-02515 | Construction | Testing & Start-Up | Construction.1.4.6 | Notify NYCHA of Generator Acceptance Testing- OG10 | 15 | 15 | 0% | 2023-03-30 08:00 | 2023-04-19 17:00 | -49 | UNSURE | STARTUP | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 02005 | 0 | 0 | OG6-02005 | Construction | Cellar | Construction.1.2.5.1 | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 5 | 5 | 0% | 2022-12-13 08:00 | 2022-12-19 17:00 | -67 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 02015 | 0 | 0 | OG6-02015 | Construction | Cellar | Construction.1.2.5.1 | Install Bypass Connections - Cellar | 5 | 5 | 0% | 2022-12-20 08:00 | 2022-12-27 17:00 | -67 | MEP | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 02025 | 0 | 0 | OG6-02025 | Construction | Cellar | Construction.1.2.5.1 | Relocate (E) & Install Temporary Lighting Cellar | 4 | 4 | 0% | 2022-12-28 08:00 | 2023-01-03 17:00 | -67 | FSE | 0 | 0 | 0 | 0-OG6
In Progress | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 02030 | 0 | 0 | OG6-02030 | Construction | Cellar | Construction.1.2.5.1 | Core Drill & Install Incoming Feeder Conduits & Racks - Cellar | 20 | 10 | 50% | 2022-06-13 | 2023-01-18 17:00 | -67 | FSE | CORE DRILL | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 02020 | 0 | 0 | OG6-02020 | Construction | Cellar | Construction.1.2.5.1 | Install Branch Conduit - Cellar | 20 | 20 | 0% | 2022-12-22 08:00 | 2023-01-23 17:00 | -53 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 02035 | 0 | 0 | OG6-02035 | Construction | Cellar | Construction.1.2.5.1 | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 20 | 20 | 0% | 2023-01-04 08:00 | 2023-02-01 17:00 | -29 | FSE | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 02055 | 0 | 0 | OG6-02055 | Construction | Cellar | Construction.1.2.5.1 | Link & Seal Conduit Sleeves - Cellar | 10 | 0 | 100% | 2021-10-22 | 2021-10-22 |  | 0 | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 02065 | 0 | 0 | OG6-02065 | Construction | Cellar | Construction.1.2.5.1 | Pull Lighting Wiring - Cellar | 5 | 5 | 0% | 2023-02-02 08:00 | 2023-02-08 17:00 | -29 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 02070 | 0 | 0 | OG6-02070 | Construction | Cellar | Construction.1.2.5.1 | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 5 | 5 | 0% | 2023-02-09 08:00 | 2023-02-15 17:00 | -29 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 02040 | 0 | 0 | OG6-02040 | Construction | Cellar | Construction.1.2.5.1 | Pull Branch Wiring - Cellar | 8 | 8 | 0% | 2023-01-24 08:00 | 2023-02-02 17:00 | -53 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 02045 | 0 | 0 | OG6-02045 | Construction | Cellar | Construction.1.2.5.1 | Install Heat Trace for Plumbing Lines - Cellar | 5 | 5 | 0% | 2023-02-03 08:00 | 2023-02-09 17:00 | -15 | FSE | 0 | 0 | 0 | 0-OG6
In Progress | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 02060 | 0 | 0 | OG6-02060 | Construction | Cellar | Construction.1.2.5.1 | Core Drill & Install Feeder Conduits Risers & Racks to 1st Floor - Cellar | 20 | 10 | 50% | 2022-06-15 | 2023-02-01 17:00 | -67 | FSE | CORE DRILL | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 02010 | 0 | 0 | OG6-02010 | Construction | Cellar | Construction.1.2.5.1 | Install Panelboards (Misc.) | 2 | 2 | 0% | 2022-12-20 08:00 | 2022-12-21 17:00 | -53 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 02050 | 0 | 0 | OG6-02050 | Construction | Cellar | Construction.1.2.5.1 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Cellar | 5 | 5 | 0% | 2023-02-03 08:00 | 2023-02-09 17:00 | -15 | FSE | 0 | 0 | 0 | 0-OG6
In Progress | CI NYCHA Update #22.Construction.1.2.5.2 | OG6 | OG6 | 02115 | 0 | 0 | OG6-02115 | Construction | 1st Floor | Construction.1.2.5.2 | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 20 | 15 | 25% | 2022-06-20 | 2023-02-01 17:00 | -67 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.2 | OG6 | OG6 | 02135 | 0 | 0 | OG6-02135 | Construction | 1st Floor | Construction.1.2.5.2 | Install Pull Boxes - 1st Floor | 5 | 5 | 0% | 2023-02-02 08:00 | 2023-02-08 17:00 | -67 | FSE | PULL BOXES | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.2 | OG6 | OG6 | 02105 | 0 | 0 | OG6-02105 | Construction | 1st Floor | Construction.1.2.5.2 | Install Branch Conduit - 1st Floor | 15 | 15 | 0% | 2023-02-03 08:00 | 2023-02-24 17:00 | -53 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.2 | OG6 | OG6 | 02110 | 0 | 0 | OG6-02110 | Construction | 1st Floor | Construction.1.2.5.2 | Pull Branch Wiring - 1st Floor | 5 | 5 | 0% | 2023-02-27 08:00 | 2023-03-03 17:00 | -53 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.2 | OG6 | OG6 | 02120 | 0 | 0 | OG6-02120 | Construction | 1st Floor | Construction.1.2.5.2 | Install Fire Alarm Control Panel & Equipment - 1st Floor | 2 | 2 | 0% | 2023-03-06 08:00 | 2023-03-07 17:00 | -42 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.2 | OG6 | OG6 | 02130 | 0 | 0 | OG6-02130 | Construction | 1st Floor | Construction.1.2.5.2 | Pull Fire Alarm Wiring - 1st Floor | 2 | 2 | 0% | 2023-03-08 08:00 | 2023-03-09 17:00 | 22 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.2 | OG6 | OG6 | 02125 | 0 | 0 | OG6-02125 | Construction | 1st Floor | Construction.1.2.5.2 | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 5 | 5 | 0% | 2023-03-06 08:00 | 2023-03-10 17:00 | -40 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.2 | OG6 | OG6 | 02140 | 0 | 0 | OG6-02140 | Construction | 1st Floor | Construction.1.2.5.2 | Supply Power to Exterior Building Signage | 2 | 2 | 0% | 2023-04-04 08:00 | 2023-04-05 17:00 | -74 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.2 | OG6 | OG6 | 02145 | 0 | 0 | OG6-02145 | Construction | 1st Floor | Construction.1.2.5.2 | Install Firestopping - 1st Floor | 5 | 5 | 0% | 2023-04-06 08:00 | 2023-04-12 17:00 | -74 | MLJ | FIRESTOPPING | EXISTING BUILDING | 07-1200 | 07-1200-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.2 | OG6 | OG6 | 02150 | 0 | 0 | OG6-02150 | Construction | 1st Floor | Construction.1.2.5.2 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 1st Floor | 5 | 5 | 0% | 2023-03-06 08:00 | 2023-03-10 17:00 | -35 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 02205 | 0 | 0 | OG6-02205 | Construction | 2nd Floor | Construction.1.2.5.3 | Install Switchboards - 2nd Floor | 15 | 15 | 0% | 2023-01-06 08:00 | 2023-01-27 17:00 | -74 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 02210 | 0 | 0 | OG6-02210 | Construction | 2nd Floor | Construction.1.2.5.3 | Install ACTTS - 2nd Floor | 5 | 5 | 0% | 2023-01-30 08:00 | 2023-02-03 17:00 | -74 | FSE | ACTTS | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 02215 | 0 | 0 | OG6-02215 | Construction | 2nd Floor | Construction.1.2.5.3 | Install Feeder Conduits & Racks to Switchgear Equipment - 2nd Floor | 20 | 20 | 0% | 2023-02-06 08:00 | 2023-03-06 17:00 | -74 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 02220 | 0 | 0 | OG6-02220 | Construction | 2nd Floor | Construction.1.2.5.3 | Install Panelboards - 2nd Floor | 5 | 5 | 0% | 2023-03-07 08:00 | 2023-03-13 17:00 | -72 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 02225 | 0 | 0 | OG6-02225 | Construction | 2nd Floor | Construction.1.2.5.3 | Install Branch Conduit - 2nd Floor | 20 | 20 | 0% | 2023-03-14 08:00 | 2023-04-10 17:00 | -72 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 02235 | 0 | 0 | OG6-02235 | Construction | 2nd Floor | Construction.1.2.5.3 | Pull Branch Wiring - 2nd Floor | 5 | 5 | 0% | 2023-04-11 08:00 | 2023-04-17 17:00 | -66 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 02240 | 0 | 0 | OG6-02240 | Construction | 2nd Floor | Construction.1.2.5.3 | Install Lighting Fixtures & Controls - 2nd Floor | 5 | 5 | 0% | 2023-04-28 08:00 | 2023-05-04 17:00 | -74 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 02270 | 0 | 0 | OG6-02270 | Construction | 2nd Floor | Construction.1.2.5.3 | Install Fire Alarm Equipment - 2nd Floor | 5 | 5 | 0% | 2023-04-18 08:00 | 2023-04-24 17:00 | -5 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 02245 | 0 | 0 | OG6-02245 | Construction | 2nd Floor | Construction.1.2.5.3 | Install Receptacles - 2nd Floor | 5 | 5 | 0% | 2023-04-18 08:00 | 2023-04-24 17:00 | -66 | FSE | RECEPTACLES | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 02275 | 0 | 0 | OG6-02275 | Construction | 2nd Floor | Construction.1.2.5.3 | Install Fire Stopping - 2nd Floor | 6 | 6 | 0% | 2023-04-13 08:00 | 2023-04-20 17:00 | -74 | MLJ | FIRESTOPPING | EXISTING BUILDING | 07-1200 | 07-1200-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 02255 | 0 | 0 | OG6-02255 | Construction | 2nd Floor | Construction.1.2.5.3 | Tag & Terminate Panelboards | 2 | 2 | 0% | 2023-04-04 08:00 | 2023-04-05 17:00 | -53 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 02260 | 0 | 0 | OG6-02260 | Construction | 2nd Floor | Construction.1.2.5.3 | Tag & Terminate Switchgear Equipment | 5 | 5 | 0% | 2023-04-04 08:00 | 2023-04-10 17:00 | -56 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 02230 | 0 | 0 | OG6-02230 | Construction | 2nd Floor | Construction.1.2.5.3 | Ground Equipment | 5 | 5 | 0% | 2023-03-14 08:00 | 2023-03-20 17:00 | -46 | FSE | GROUNDING EQUIP | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 02280 | 0 | 0 | OG6-02280 | Construction | 2nd Floor | Construction.1.2.5.3 | Terminate Fire Alarm System | 5 | 5 | 0% | 2023-04-25 08:00 | 2023-05-01 17:00 | 4 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 02250 | 0 | 0 | OG6-02250 | Construction | 2nd Floor | Construction.1.2.5.3 | Pull CON-ED Feeder Cable - Cellar to Switchgear - 2nd Floor | 20 | 20 | 0% | 2023-03-07 08:00 | 2023-04-03 17:00 | -74 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 02265 | 0 | 0 | OG6-02265 | Construction | 2nd Floor | Construction.1.2.5.3 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 5 | 5 | 0% | 2023-04-04 08:00 | 2023-04-10 17:00 | -56 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.4 | OG6 | OG6 | 02535 | 0 | 0 | OG6-02535 | Construction | Testing & Start-Up | Construction.1.2.5.4 | Fire Alarm Operational & FDNY Acceptance Testing - OG6 | 5 | 5 | 0% | 2023-06-05 08:00 | 2023-06-09 17:00 | -19 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.4 | OG6 | OG6 | 02515 | 0 | 0 | OG6-02515 | Construction | Testing & Start-Up | Construction.1.2.5.4 | Energize Switchgear - OG6 | 5 | 5 | 0% | 2023-05-17 08:00 | 2023-05-23 17:00 | -74 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.4 | OG6 | OG6 | 02530 | 0 | 0 | OG6-02530 | Construction | Testing & Start-Up | Construction.1.2.5.4 | Start-Up Generator/Switchgear - OG6 | 4 | 4 | 0% | 2023-05-30 08:00 | 2023-06-02 17:00 | -74 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.4 | OG6 | OG6 | 02505 | 0 | 0 | OG6-02505 | Construction | Testing & Start-Up | Construction.1.2.5.4 | Perform Electrical Inspections - OG6 | 5 | 5 | 0% | 2023-05-05 08:00 | 2023-05-11 17:00 | -74 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.4 | OG6 | OG6 | 02510 | 0 | 0 | OG6-02510 | Construction | Testing & Start-Up | Construction.1.2.5.4 | Perform 3rd Party Test - OG6 | 3 | 3 | 0% | 2023-05-12 08:00 | 2023-05-16 17:00 | -74 | UNSURE | STARTUP | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.4 | OG6 | OG6 | 02525 | 0 | 0 | OG6-02525 | Construction | Testing & Start-Up | Construction.1.2.5.4 | Notify NYCHA of Fire Alarm Acceptance Testing - OG6 | 14 | 14 | 0% | 2023-05-15 08:00 | 2023-06-02 17:00 | -19 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.4 | OG6 | OG6 | 02520 | 0 | 0 | OG6-02520 | Construction | Testing & Start-Up | Construction.1.2.5.4 | Perform Tie-in's to Exisiting | 3 | 3 | 0% | 2023-05-24 08:00 | 2023-05-26 17:00 | -74 | UNSURE | STARTUP | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 02005 | 0 | 0 | OG1-02005 | Construction | Cellar | Construction.1.3.5.1 | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 4 | 4 | 0% | 2022-11-25 08:00 | 2022-11-30 17:00 | 36 | FSE | 0 | 0 | 0 | 0-OG1
In Progress | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 02010 | 0 | 0 | OG1-02010 | Construction | Cellar | Construction.1.3.5.1 | Install Bypass Connections - Cellar | 5 | 4 | 25% | 2022-08-01 08:00 | 2022-11-30 17:00 | 50 | MEP | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 02020 | 0 | 0 | OG1-02020 | Construction | Cellar | Construction.1.3.5.1 | Relocate (E) & Install Temporary Lighting Cellar | 4 | 4 | 0% | 2022-12-01 08:00 | 2022-12-06 17:00 | 50 | FSE | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 02025 | 0 | 0 | OG1-02025 | Construction | Cellar | Construction.1.3.5.1 | Core Drill & Install Incoming Feeder Conduits & Racks - Cellar | 20 | 0 | 100% | 2021-11-22 | 2021-12-09 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
In Progress | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 02015 | 0 | 0 | OG1-02015 | Construction | Cellar | Construction.1.3.5.1 | Install Branch Conduit - Cellar | 20 | 8 | 60% | 2022-08-01 08:00 | 2022-12-06 17:00 | 34 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 02030 | 0 | 0 | OG1-02030 | Construction | Cellar | Construction.1.3.5.1 | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 18 | 18 | 0% | 2022-12-07 08:00 | 2023-01-03 17:00 | 50 | FSE | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 02050 | 0 | 0 | OG1-02050 | Construction | Cellar | Construction.1.3.5.1 | Link & Seal Conduit Sleeves - Cellar | 10 | 0 | 100% | 2021-10-22 | 2021-10-22 |  | 0 | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 02055 | 0 | 0 | OG1-02055 | Construction | Cellar | Construction.1.3.5.1 | Pull Lighting Wiring - Cellar | 5 | 5 | 0% | 2023-01-04 08:00 | 2023-01-10 17:00 | 50 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 02065 | 0 | 0 | OG1-02065 | Construction | Cellar | Construction.1.3.5.1 | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 5 | 5 | 0% | 2023-01-11 08:00 | 2023-01-18 17:00 | 50 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 02035 | 0 | 0 | OG1-02035 | Construction | Cellar | Construction.1.3.5.1 | Pull Branch Wiring - Cellar | 7 | 7 | 0% | 2022-12-07 08:00 | 2022-12-15 17:00 | 34 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 02040 | 0 | 0 | OG1-02040 | Construction | Cellar | Construction.1.3.5.1 | Install Heat Trace for Plumbing Lines - Cellar | 2 | 2 | 0% | 2022-12-16 08:00 | 2022-12-19 17:00 | 37 | FSE | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 02060 | 0 | 0 | OG1-02060 | Construction | Cellar | Construction.1.3.5.1 | Core Drill & Install Conduits Risers & Racks to 1st Floor - Cellar | 15 | 0 | 100% | 2022-07-22 | 2022-11-15 |  | FSE | CORE DRILL | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 02045 | 0 | 0 | OG1-02045 | Construction | Cellar | Construction.1.3.5.1 | Install Panelboards (Misc.) - Cellar | 2 | 2 | 0% | 2022-12-01 08:00 | 2022-12-02 17:00 | 36 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 02070 | 0 | 0 | OG1-02070 | Construction | Cellar | Construction.1.3.5.1 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Cellar | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | 34 | FSE | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.5.2 | OG1 | OG1 | 02125 | 0 | 0 | OG1-02125 | Construction | 1st Floor | Construction.1.3.5.2 | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 10 | 0 | 100% | 2022-08-01 | 2022-10-31 12:00 |  | FSE | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.5.2 | OG1 | OG1 | 02135 | 0 | 0 | OG1-02135 | Construction | 1st Floor | Construction.1.3.5.2 | Install Pull Boxes - 1st Floor | 4 | 0 | 100% | 2022-11-01 | 2022-11-15 |  | 0 | 0 | 0 | 0 | 0-OG1
In Progress | CI NYCHA Update #22.Construction.1.3.5.2 | OG1 | OG1 | 02105 | 0 | 0 | OG1-02105 | Construction | 1st Floor | Construction.1.3.5.2 | Install Branch Conduit - 1st Floor | 11 | 2 | 80% | 2022-08-01 08:00 | 2022-11-29 09:36 | 32 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.2 | OG1 | OG1 | 02110 | 0 | 0 | OG1-02110 | Construction | 1st Floor | Construction.1.3.5.2 | Pull Branch Wiring - 1st Floor | 6 | 6 | 0% | 2022-11-29 09:36 | 2022-12-07 09:36 | 32 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.2 | OG1 | OG1 | 02115 | 0 | 0 | OG1-02115 | Construction | 1st Floor | Construction.1.3.5.2 | Install Fire Alarm Control Panel (FACP) & Smoke Detectors - 1st Floor | 2 | 2 | 0% | 2022-12-07 09:36 | 2022-12-09 09:36 | 32 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.2 | OG1 | OG1 | 02130 | 0 | 0 | OG1-02130 | Construction | 1st Floor | Construction.1.3.5.2 | Pull Fire Alarm Wiring - 1st Floor | 2 | 2 | 0% | 2022-12-09 09:36 | 2022-12-13 09:36 | 81 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.2 | OG1 | OG1 | 02120 | 0 | 0 | OG1-02120 | Construction | 1st Floor | Construction.1.3.5.2 | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 5 | 5 | 0% | 2023-01-19 08:00 | 2023-01-25 17:00 | 50 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.2 | OG1 | OG1 | 02140 | 0 | 0 | OG1-02140 | Construction | 1st Floor | Construction.1.3.5.2 | Supply Power to Exterior Building Signage | 2 | 2 | 0% | 2023-01-10 08:00 | 2023-01-11 17:00 | 17 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.2 | OG1 | OG1 | 02145 | 0 | 0 | OG1-02145 | Construction | 1st Floor | Construction.1.3.5.2 | Install Firestopping - 1st Floor | 5 | 5 | 0% | 2023-01-12 08:00 | 2023-01-19 17:00 | 17 | MLJ | FIRESTOPPING | EXISTING BUILDING | 07-1200 | 07-1200-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.2 | OG1 | OG1 | 02150 | 0 | 0 | OG1-02150 | Construction | 1st Floor | Construction.1.3.5.2 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 1st Floor | 5 | 5 | 0% | 2022-12-19 08:00 | 2022-12-23 17:00 | 33 | FSE | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 02205 | 0 | 0 | OG1-02205 | Construction | 2nd Floor | Construction.1.3.5.3 | Install Switchboards - 2nd Floor | 12 | 0 | 100% | 2022-06-10 | 2022-11-02 17:00 |  | FSE | 0 | 0 | 0 | 0-OG1
In Progress | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 02210 | 0 | 0 | OG1-02210 | Construction | 2nd Floor | Construction.1.3.5.3 | Install ACTTS - 2nd Floor | 4 | 0 | 90% | 2022-06-10 | 2022-11-25 11:12 | 24 | FSE | ACTTS | 0 | 0 | 0-OG1
In Progress | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 02215 | 0 | 0 | OG1-02215 | Construction | 2nd Floor | Construction.1.3.5.3 | Install Feeder Conduits & Racks to Switchgear Equipment - 2nd Floor | 18 | 2 | 90% | 2022-08-01 08:00 | 2022-11-28 15:24 | 22 | FSE | 0 | 0 | 0 | 0-OG1
In Progress | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 02220 | 0 | 0 | OG1-02220 | Construction | 2nd Floor | Construction.1.3.5.3 | Install Panelboards - 2nd Floor | 4 | 1 | 75% | 2022-11-01 | 2022-11-28 15:24 | 30 | FSE | 0 | 0 | 0 | 0-OG1
In Progress | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 02225 | 0 | 0 | OG1-02225 | Construction | 2nd Floor | Construction.1.3.5.3 | Install Branch Conduit - 2nd Floor | 18 | 5 | 75% | 2022-11-01 | 2022-12-05 15:24 | 30 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 02235 | 0 | 0 | OG1-02235 | Construction | 2nd Floor | Construction.1.3.5.3 | Pull Branch Wiring - 2nd Floor | 6 | 6 | 0% | 2022-12-05 15:24 | 2022-12-13 15:24 | 30 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 02240 | 0 | 0 | OG1-02240 | Construction | 2nd Floor | Construction.1.3.5.3 | Install Lighting Fixtures & Controls - 2nd Floor | 4 | 4 | 0% | 2023-01-26 08:00 | 2023-01-31 17:00 | 50 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 02245 | 0 | 0 | OG1-02245 | Construction | 2nd Floor | Construction.1.3.5.3 | Install Smoke Detection Equipment - 2nd Floor | 5 | 5 | 0% | 2022-12-13 15:24 | 2022-12-20 15:24 | 80 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 02250 | 0 | 0 | OG1-02250 | Construction | 2nd Floor | Construction.1.3.5.3 | Install Receptacles - 2nd Floor | 4 | 4 | 0% | 2022-12-13 15:24 | 2022-12-19 15:24 | 30 | FSE | RECEPTACLES | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 02255 | 0 | 0 | OG1-02255 | Construction | 2nd Floor | Construction.1.3.5.3 | Install Fire Stopping - 2nd Floor | 4 | 4 | 0% | 2022-12-05 15:24 | 2022-12-09 15:24 | 43 | MLJ | FIRESTOPPING | EXISTING BUILDING | 07-1200 | 07-1200-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 02265 | 0 | 0 | OG1-02265 | Construction | 2nd Floor | Construction.1.3.5.3 | Tag & Terminate Switchgear Equipment | 5 | 5 | 0% | 2023-01-10 08:00 | 2023-01-17 17:00 | 17 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 02275 | 0 | 0 | OG1-02275 | Construction | 2nd Floor | Construction.1.3.5.3 | Tag & Terminate Panelboards | 2 | 2 | 0% | 2023-01-18 08:00 | 2023-01-19 17:00 | 17 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 02230 | 0 | 0 | OG1-02230 | Construction | 2nd Floor | Construction.1.3.5.3 | Ground Equipment | 5 | 5 | 0% | 2022-12-09 09:36 | 2022-12-16 09:36 | 32 | FSE | GROUNDING EQUIP | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 02280 | 0 | 0 | OG1-02280 | Construction | 2nd Floor | Construction.1.3.5.3 | Terminate Fire Alarm System | 2 | 2 | 0% | 2023-01-18 08:00 | 2023-01-19 17:00 | 75 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 02260 | 0 | 0 | OG1-02260 | Construction | 2nd Floor | Construction.1.3.5.3 | Pull CON-ED Feeder Cable - Cellar to OG1 Switchgear - 2nd Floor | 20 | 20 | 0% | 2022-12-09 08:00 | 2023-01-09 17:00 | 17 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 02270 | 0 | 0 | OG1-02270 | Construction | 2nd Floor | Construction.1.3.5.3 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 5 | 5 | 0% | 2023-01-10 08:00 | 2023-01-17 17:00 | 19 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.4 | OG1 | OG1 | 02530 | 0 | 0 | OG1-02530 | Construction | Testing & Start-Up | Construction.1.3.5.4 | Start-Up Generator/Switchgear - OG1 | 4 | 4 | 0% | 2023-06-05 08:00 | 2023-06-08 17:00 | -62 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.4 | OG1 | OG1 | 02535 | 0 | 0 | OG1-02535 | Construction | Testing & Start-Up | Construction.1.3.5.4 | Fire Alarm Operational & FDNY Acceptance Testing - OG1 | 5 | 5 | 0% | 2023-06-09 08:00 | 2023-06-15 17:00 | -23 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.4 | OG1 | OG1 | 02515 | 0 | 0 | OG1-02515 | Construction | Testing & Start-Up | Construction.1.3.5.4 | Energize Switchgear - OG1 | 5 | 5 | 0% | 2023-04-17 08:00 | 2023-04-21 17:00 | -36 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.4 | OG1 | OG1 | 02505 | 0 | 0 | OG1-02505 | Construction | Testing & Start-Up | Construction.1.3.5.4 | Perform Electrical Inspections - OG1 | 5 | 5 | 0% | 2023-03-14 08:00 | 2023-03-20 17:00 | -19 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.4 | OG1 | OG1 | 02520 | 0 | 0 | OG1-02520 | Construction | Testing & Start-Up | Construction.1.3.5.4 | Perform Tie-Ins to Existing | 3 | 3 | 0% | 2023-04-24 08:00 | 2023-04-26 17:00 | -36 | UNSURE | STARTUP | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.4 | OG1 | OG1 | 02510 | 0 | 0 | OG1-02510 | Construction | Testing & Start-Up | Construction.1.3.5.4 | Perform 3rd Party Test | 2 | 2 | 0% | 2023-04-13 08:00 | 2023-04-14 17:00 | -36 | UNSURE | STARTUP | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.4 | OG1 | OG1 | 02525 | 0 | 0 | OG1-02525 | Construction | Testing & Start-Up | Construction.1.3.5.4 | Notify NYCHA of Fire Alarm Acceptance Testing | 14 | 14 | 0% | 2023-05-19 08:00 | 2023-06-08 17:00 | -23 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.4.5.2 | SGS | SGS | 02115 | 0 | 0 | SGS-02115 | Construction | Cable Pulls | Construction.4.5.2 | Pull CON-ED Feeder Cable - 31st St. to SG3 Cellar | 10 | 10 | 0% | 2023-07-07 08:00 | 2023-07-20 17:00 | -128 | FSE | 0 | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.2 | SGS | SGS | 02105 | 0 | 0 | SGS-02105 | Construction | Cable Pulls | Construction.4.5.2 | Pull Feeder Cable - SG3 Switchgear to SG7 Foundation | 10 | 10 | 0% | 2023-07-07 08:00 | 2023-07-20 17:00 | -101 | FSE | 0 | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.2 | SGS | SGS | 02120 | 0 | 0 | SGS-02120 | Construction | Cable Pulls | Construction.4.5.2 | Pull CON-ED Feeder Cable - 31st St. to SG7 Foundation (for SG2) | 5 | 5 | 0% | 2023-07-17 08:00 | 2023-07-21 17:00 | -121 | FSE | 0 | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.2 | SGS | SGS | 02130 | 0 | 0 | SGS-02130 | Construction | Cable Pulls | Construction.4.5.2 | Pull Generator Feeder Cable from SG7 to SG3 Switchgear | 10 | 10 | 0% | 2023-07-07 08:00 | 2023-07-20 17:00 | -94 | FSE | 0 | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.2 | SGS | SGS | 02125 | 0 | 0 | SGS-02125 | Construction | Cable Pulls | Construction.4.5.2 | Pull Feeder Cable from SG7 to SG2 | 10 | 10 | 0% | 2023-04-05 08:00 | 2023-04-18 17:00 | -45 | FSE | 0 | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.2 | SGS | SGS | 02135 | 0 | 0 | SGS-02135 | Construction | Cable Pulls | Construction.4.5.2 | Pull Feeder Cable from SG7 to SG1 | 5 | 5 | 0% | 2023-03-22 08:00 | 2023-03-28 17:00 | -35 | FSE | 0 | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.2 | SGS | SGS | 02110 | 0 | 0 | SGS-02110 | Construction | Cable Pulls | Construction.4.5.2 | Pull CON-ED Feeder Cable - 31st St. to SG7 Foundation (for SG1) | 5 | 5 | 0% | 2023-07-10 08:00 | 2023-07-14 17:00 | -121 | FSE | 0 | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.3 | SGS | SGS | 02205 | 0 | 0 | SGS-02205 | Construction | Site Lighting | Construction.4.5.3 | Remove Existing Lighting Conduit, Cable & Fixtures | 5 | 5 | 0% | 2023-09-26 08:00 | 2023-10-02 17:00 | -118 | FSE | 0 | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.3 | SGS | SGS | 02210 | 0 | 0 | SGS-02210 | Construction | Site Lighting | Construction.4.5.3 | Furnish & Install Site Lighting Conduit | 10 | 10 | 0% | 2023-10-03 08:00 | 2023-10-17 17:00 | -118 | FSE | 0 | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.3 | SGS | SGS | 02215 | 0 | 0 | SGS-02215 | Construction | Site Lighting | Construction.4.5.3 | Pull Site Lighting Wire | 5 | 5 | 0% | 2023-10-18 08:00 | 2023-10-24 17:00 | -118 | FSE | 0 | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.3 | SGS | SGS | 02220 | 0 | 0 | SGS-02220 | Construction | Site Lighting | Construction.4.5.3 | Install Site Lighting Fixtures & Terminate | 10 | 10 | 0% | 2023-10-25 08:00 | 2023-11-08 17:00 | -118 | FSE | 0 | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.4.5.4 | SG7 | SG7 | 02015 | 0 | 0 | SG7-02015 | Construction | Foundation | Construction.4.4.5.4 | Install Branch Conduit in Plumbing Shaft - Foundation | 2 | 2 | 0% | 2022-11-29 08:00 | 2022-11-30 17:00 | 12 | FSE | 0 | 0 | 0 | 0-SG7
In Progress | CI NYCHA Update #22.Construction.4.4.5.4 | SG7 | SG7 | 02005 | 0 | 0 | SG7-02005 | Construction | Foundation | Construction.4.4.5.4 | Install Temporary Lighting & Temporary Power for SG7 | 5 | 3 | 50% | 2021-11-26 | 2022-11-29 12:00 | -5 | FSE | 0 | 0 | 0 | 0-SG7
In Progress | CI NYCHA Update #22.Construction.4.4.5.4 | SG7 | SG7 | 02010 | 0 | 0 | SG7-02010 | Construction | Foundation | Construction.4.4.5.4 | Install Conduit Risers to 1st Floor for Incoming Feeders - Foundation | 20 | 2 | 90% | 2022-05-08 | 2022-11-28 17:00 | -5 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.4 | SG7 | SG7 | 02025 | 0 | 0 | SG7-02025 | Construction | Foundation | Construction.4.4.5.4 | Pull Wire to Light Fixture & Mechanical Equipment in Plumbing Shaft - Foundation | 2 | 2 | 0% | 2022-12-01 08:00 | 2022-12-02 17:00 | 12 | FSE | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.5.4 | SG7 | SG7 | 02020 | 0 | 0 | SG7-02020 | Construction | Foundation | Construction.4.4.5.4 | Install Pull Box - Foundation | 2 | 0 | 100% | 2022-11-01 | 2022-11-01 |  | 0 | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 02130 | 0 | 0 | SG7-02130 | Construction | 1st Floor | Construction.4.4.5.1 | Install Smoke Detection/Fire Alarm Equipment - 1st Floor | 5 | 5 | 0% | 2022-12-22 08:00 | 2022-12-29 17:00 | 15 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 02135 | 0 | 0 | SG7-02135 | Construction | 1st Floor | Construction.4.4.5.1 | Install Light/Emergency Fixtures - 1st Floor | 5 | 5 | 0% | 2022-12-22 08:00 | 2022-12-29 17:00 | 21 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 02120 | 0 | 0 | SG7-02120 | Construction | 1st Floor | Construction.4.4.5.1 | Pull Fire Alarm Wiring - 1st Floor | 5 | 5 | 0% | 2022-12-15 08:00 | 2022-12-21 17:00 | 15 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 02140 | 0 | 0 | SG7-02140 | Construction | 1st Floor | Construction.4.4.5.1 | Install Controls & Pull Wire to Mechanical/Plumbing Equipment (Motorized Dampers/FO Pump/EUH) - 1st Floor | 5 | 5 | 0% | 2023-02-01 08:00 | 2023-02-07 17:00 | -5 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 02160 | 0 | 0 | SG7-02160 | Construction | 1st Floor | Construction.4.4.5.1 | Install Receptacles - 1st Floor | 2 | 2 | 0% | 2023-02-08 08:00 | 2023-02-09 17:00 | -5 | FSE | RECEPTACLES | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 02155 | 0 | 0 | SG7-02155 | Construction | 1st Floor | Construction.4.4.5.1 | Install Remote Annunciator Panel (RAP). - 1st Floor | 2 | 2 | 0% | 2022-12-30 08:00 | 2023-01-03 17:00 | 15 | MEP | 0 | 0 | 0 | 0-SG7
In Progress | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 02110 | 0 | 0 | SG7-02110 | Construction | 1st Floor | Construction.4.4.5.1 | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 20 | 2 | 90% | 2022-10-03 08:00 | 2022-11-30 17:00 | 4 | FSE | 0 | 0 | 0 | 0-SG7
In Progress | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 02115 | 0 | 0 | SG7-02115 | Construction | 1st Floor | Construction.4.4.5.1 | Install Branch Conduits - 1st Floor | 15 | 12 | 20% | 2022-08-23 08:00 | 2022-12-14 17:00 | 4 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 02125 | 0 | 0 | SG7-02125 | Construction | 1st Floor | Construction.4.4.5.1 | Pull Branch Wiring - 1st Floor | 5 | 5 | 0% | 2022-12-15 08:00 | 2022-12-21 17:00 | 4 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 02145 | 0 | 0 | SG7-02145 | Construction | 1st Floor | Construction.4.4.5.1 | Install Heat Trace for Plumbing Lines -1st Floor | 3 | 3 | 0% | 2023-02-15 08:00 | 2023-02-17 17:00 | -10 | FSE | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 02105 | 0 | 0 | SG7-02105 | Construction | 1st Floor | Construction.4.4.5.1 | Install In-slab Conduits - 1st floor slab | 5 | 0 | 100% | 2022-05-10 | 2022-06-24 |  | 0 | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 02165 | 0 | 0 | SG7-02165 | Construction | 1st Floor | Construction.4.4.5.1 | Tag & Terminate FIre Alarm Equipment - 2nd Floor | 5 | 5 | 0% | 2022-12-30 08:00 | 2023-01-06 17:00 | 29 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 02150 | 0 | 0 | SG7-02150 | Construction | 1st Floor | Construction.4.4.5.1 | Install Exterior Lighting & Controls - 1st Floor | 2 | 2 | 0% | 2022-12-22 08:00 | 2022-12-23 17:00 | 24 | FSE | 0 | 0 | 0 | 0-SG7
In Progress | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 02210 | 0 | 0 | SG7-02210 | Construction | 2nd Floor | Construction.4.4.5.2 | Install Feeder Conduit Risers & Racks to Roof - 2nd Floor | 10 | 3 | 75% | 2022-10-03 08:00 | 2022-12-05 17:00 | 35 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 02225 | 0 | 0 | SG7-02225 | Construction | 2nd Floor | Construction.4.4.5.2 | Install Controls & Pull Wire for Mechanical & Plumbing Equipment - 2nd Floor | 10 | 10 | 0% | 2023-07-31 08:00 | 2023-08-11 17:00 | -127 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 02215 | 0 | 0 | SG7-02215 | Construction | 2nd Floor | Construction.4.4.5.2 | Install Branch Conduits - 2nd Floor | 15 | 15 | 0% | 2023-07-10 08:00 | 2023-07-28 17:00 | -132 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 02230 | 0 | 0 | SG7-02230 | Construction | 2nd Floor | Construction.4.4.5.2 | Pull Branch Wiring - 2nd Floor | 5 | 5 | 0% | 2023-07-31 08:00 | 2023-08-04 17:00 | -132 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 02235 | 0 | 0 | SG7-02235 | Construction | 2nd Floor | Construction.4.4.5.2 | Pull Fire Alarm Wiring - 2nd Floor | 5 | 5 | 0% | 2023-07-31 08:00 | 2023-08-04 17:00 | -127 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 02220 | 0 | 0 | SG7-02220 | Construction | 2nd Floor | Construction.4.4.5.2 | Install Smoke Detection/Fire Alarm Equipment - 2nd Floor | 5 | 5 | 0% | 2023-08-07 08:00 | 2023-08-11 17:00 | -127 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 02240 | 0 | 0 | SG7-02240 | Construction | 2nd Floor | Construction.4.4.5.2 | Install Light/Emergency Fixtures - 2nd Floor | 5 | 5 | 0% | 2023-08-07 08:00 | 2023-08-11 17:00 | -132 | FSE | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 02205 | 0 | 0 | SG7-02205 | Construction | 2nd Floor | Construction.4.4.5.2 | Install In-slab Conduits - 2nd floor roof slab | 2 | 0 | 100% | 2022-08-23 08:00 | 2022-09-23 |  | 0 | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 02245 | 0 | 0 | SG7-02245 | Construction | 2nd Floor | Construction.4.4.5.2 | Install Receptacles - 2nd Floor | 2 | 2 | 0% | 2023-08-07 08:00 | 2023-08-08 17:00 | -128 | FSE | RECEPTACLES | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 02255 | 0 | 0 | SG7-02255 | Construction | 2nd Floor | Construction.4.4.5.2 | Terminate all Mech. & Plumbing Equipment at Panel - 2nd Floor | 5 | 5 | 0% | 2023-08-15 08:00 | 2023-08-21 17:00 | -128 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 02250 | 0 | 0 | SG7-02250 | Construction | 2nd Floor | Construction.4.4.5.2 | Install Fire Alarm Control Panel (Incl. Telephone Lines) - 2nd Floor | 2 | 2 | 0% | 2023-01-04 08:00 | 2023-01-05 17:00 | 15 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 02260 | 0 | 0 | SG7-02260 | Construction | 2nd Floor | Construction.4.4.5.2 | Instal ACTTS (ATS Room) - 2nd Floor | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | 29 | FSE | ACTTS | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 02265 | 0 | 0 | SG7-02265 | Construction | 2nd Floor | Construction.4.4.5.2 | Tag & Terminate Fire Alarm Equipment - 2nd Floor | 5 | 5 | 0% | 2023-08-14 08:00 | 2023-08-18 17:00 | -127 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 02270 | 0 | 0 | SG7-02270 | Construction | 2nd Floor | Construction.4.4.5.2 | Install Grounding & Ground Equipment | 3 | 3 | 0% | 2023-06-23 08:00 | 2023-06-27 17:00 | -99 | FSE | GROUNDING EQUIP | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 02275 | 0 | 0 | SG7-02275 | Construction | 2nd Floor | Construction.4.4.5.2 | Pull SG3 Feeder Cable from Foundation & Terminate ACTTS/GCB - 2nd Floor | 5 | 5 | 0% | 2023-07-21 08:00 | 2023-07-27 17:00 | -101 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 02280 | 0 | 0 | SG7-02280 | Construction | 2nd Floor | Construction.4.4.5.2 | Install ACTTS & Generator Circuit Breaker (GCB) for SG3 - 2nd Floor | 2 | 2 | 0% | 2023-02-01 08:00 | 2023-02-02 17:00 | 16 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2.1 | SG7 | SG7 | 02320 | 0 | 0 | SG7-02320 | Construction | SG1 Equipment | Construction.4.4.5.2.1 | Install SG1 Feeder Conduit & Racks - 2nd Floor | 15 | 15 | 0% | 2023-06-16 08:00 | 2023-07-07 17:00 | -121 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2.1 | SG7 | SG7 | 02305 | 0 | 0 | SG7-02305 | Construction | SG1 Equipment | Construction.4.4.5.2.1 | Install SG1 Switchboards - 2nd Floor | 5 | 5 | 0% | 2023-06-02 08:00 | 2023-06-08 17:00 | -132 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2.1 | SG7 | SG7 | 02310 | 0 | 0 | SG7-02310 | Construction | SG1 Equipment | Construction.4.4.5.2.1 | Install SG1 ACTTS - 2nd Floor | 5 | 5 | 0% | 2023-06-09 08:00 | 2023-06-15 17:00 | -127 | FSE | ACTTS | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2.1 | SG7 | SG7 | 02315 | 0 | 0 | SG7-02315 | Construction | SG1 Equipment | Construction.4.4.5.2.1 | Install SG1 Panelboards - 2nd Floor | 10 | 10 | 0% | 2023-06-16 08:00 | 2023-06-29 17:00 | -127 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2.1 | SG7 | SG7 | 02330 | 0 | 0 | SG7-02330 | Construction | SG1 Equipment | Construction.4.4.5.2.1 | Tag & Terminate SG1 Switchgear Equipment - 2nd Floor | 2 | 2 | 0% | 2023-08-09 08:00 | 2023-08-10 17:00 | -128 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2.1 | SG7 | SG7 | 02335 | 0 | 0 | SG7-02335 | Construction | SG1 Equipment | Construction.4.4.5.2.1 | Tag & Terminate SG1 Panelboards - 2nd Floor | 2 | 2 | 0% | 2023-08-11 08:00 | 2023-08-14 17:00 | -128 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2.1 | SG7 | SG7 | 02325 | 0 | 0 | SG7-02325 | Construction | SG1 Equipment | Construction.4.4.5.2.1 | Pull CON-ED Feeder Cable to SG1 Equipment - Foundation to 2nd Floor - 2nd Floor | 10 | 10 | 0% | 2023-07-17 08:00 | 2023-07-28 17:00 | -121 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2.2 | SG7 | SG7 | 02365 | 0 | 0 | SG7-02365 | Construction | SG2 Equipment | Construction.4.4.5.2.2 | Install SG2 Feeder Conduit & Racks - 2nd Floor | 15 | 15 | 0% | 2023-06-23 08:00 | 2023-07-14 17:00 | -121 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2.2 | SG7 | SG7 | 02350 | 0 | 0 | SG7-02350 | Construction | SG2 Equipment | Construction.4.4.5.2.2 | Install SG2 Switchboards - 2nd Floor | 5 | 5 | 0% | 2023-06-09 08:00 | 2023-06-15 17:00 | -132 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2.2 | SG7 | SG7 | 02355 | 0 | 0 | SG7-02355 | Construction | SG2 Equipment | Construction.4.4.5.2.2 | Install SG2 ACTTS - 2nd Floor | 5 | 5 | 0% | 2023-06-16 08:00 | 2023-06-22 17:00 | -132 | FSE | ACTTS | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2.2 | SG7 | SG7 | 02360 | 0 | 0 | SG7-02360 | Construction | SG2 Equipment | Construction.4.4.5.2.2 | Install SG2 Panelboards - 2nd Floor | 10 | 10 | 0% | 2023-06-23 08:00 | 2023-07-07 17:00 | -132 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2.2 | SG7 | SG7 | 02375 | 0 | 0 | SG7-02375 | Construction | SG2 Equipment | Construction.4.4.5.2.2 | Tag & Terminate SG2 Switchgear Equipment - 2nd Floor | 2 | 2 | 0% | 2023-08-11 08:00 | 2023-08-14 17:00 | -125 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2.2 | SG7 | SG7 | 02380 | 0 | 0 | SG7-02380 | Construction | SG2 Equipment | Construction.4.4.5.2.2 | Tag & Terminate SG2 Panelboards - 2nd Floor | 2 | 2 | 0% | 2023-08-15 08:00 | 2023-08-16 17:00 | -125 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2.2 | SG7 | SG7 | 02370 | 0 | 0 | SG7-02370 | Construction | SG2 Equipment | Construction.4.4.5.2.2 | Pull CON-ED Feeder Cable to SG2 Equipment - Foundation to 2nd Floor - 2nd Floor | 10 | 10 | 0% | 2023-07-24 08:00 | 2023-08-04 17:00 | -121 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 02405 | 0 | 0 | SG7-02405 | Construction | Roof | Construction.4.4.5.3 | Rig Generator SG2 - Roof | 1 | 1 | 0% | 2023-03-06 08:00 | 2023-03-06 17:00 | -45 | WELKIN | GENERATOR | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 02415 | 0 | 0 | SG7-02415 | Construction | Roof | Construction.4.4.5.3 | Install & Wire Generator SG1 - Roof | 10 | 10 | 0% | 2023-03-08 08:00 | 2023-03-21 17:00 | -45 | FSE | GENERATOR | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 02435 | 0 | 0 | SG7-02435 | Construction | Roof | Construction.4.4.5.3 | Install Branch Conduit - Roof | 5 | 5 | 0% | 2023-06-30 08:00 | 2023-07-07 17:00 | -112 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 02440 | 0 | 0 | SG7-02440 | Construction | Roof | Construction.4.4.5.3 | Pull Branch Wiring - Roof | 5 | 5 | 0% | 2023-07-10 08:00 | 2023-07-14 17:00 | -112 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 02410 | 0 | 0 | SG7-02410 | Construction | Roof | Construction.4.4.5.3 | Rig Generator SG1 - Roof | 1 | 1 | 0% | 2023-03-07 08:00 | 2023-03-07 17:00 | -45 | WELKIN | GENERATOR | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 02420 | 0 | 0 | SG7-02420 | Construction | Roof | Construction.4.4.5.3 | Install & Wire Generator SG2 - Roof | 10 | 10 | 0% | 2023-03-22 08:00 | 2023-04-04 17:00 | -45 | FSE | GENERATOR | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 02445 | 0 | 0 | SG7-02445 | Construction | Roof | Construction.4.4.5.3 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - Roof | 3 | 3 | 0% | 2023-08-07 08:00 | 2023-08-09 17:00 | -125 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 02460 | 0 | 0 | SG7-02460 | Construction | Roof | Construction.4.4.5.3 | Install Smoke Detection/Fire Alarm Equipment - Roof | 2 | 2 | 0% | 2023-08-14 08:00 | 2023-08-15 17:00 | -91 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 02465 | 0 | 0 | SG7-02465 | Construction | Roof | Construction.4.4.5.3 | Install Receptacles - Roof | 3 | 3 | 0% | 2023-08-09 08:00 | 2023-08-11 17:00 | -122 | FSE | RECEPTACLES | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 02455 | 0 | 0 | SG7-02455 | Construction | Roof | Construction.4.4.5.3 | Install Light/Emergency Fixtures - Roof | 5 | 5 | 0% | 2023-08-14 08:00 | 2023-08-18 17:00 | -132 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 02425 | 0 | 0 | SG7-02425 | Construction | Roof | Construction.4.4.5.3 | Install Lightning protection Air terminals - Roof | 5 | 5 | 0% | 2023-04-05 08:00 | 2023-04-11 17:00 | -43 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 02470 | 0 | 0 | SG7-02470 | Construction | Roof | Construction.4.4.5.3 | Install Grounding & Ground Equipment - Roof | 2 | 2 | 0% | 2023-04-12 08:00 | 2023-04-13 17:00 | -43 | FSE | GROUNDING EQUIP | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 02450 | 0 | 0 | SG7-02450 | Construction | Roof | Construction.4.4.5.3 | Pull Fire Alarm Wiring - Roof | 2 | 2 | 0% | 2023-08-07 08:00 | 2023-08-08 17:00 | -122 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 02480 | 0 | 0 | SG7-02480 | Construction | Roof | Construction.4.4.5.3 | Terminate Light Fixtures - Roof | 5 | 5 | 0% | 2023-08-21 08:00 | 2023-08-25 17:00 | -132 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 02475 | 0 | 0 | SG7-02475 | Construction | Roof | Construction.4.4.5.3 | Install Firestopping | 4 | 4 | 0% | 2023-07-31 08:00 | 2023-08-03 17:00 | -116 | MLJ | FIRESTOPPING | NEW BUILDING | 07-1300 | 07-1300-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 02485 | 0 | 0 | SG7-02485 | Construction | Roof | Construction.4.4.5.3 | Tag & Terminate Fire Alarm Equipment - Roof | 2 | 2 | 0% | 2023-08-16 08:00 | 2023-08-17 17:00 | -91 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 02495 | 0 | 0 | SG7-02495 | Construction | Roof | Construction.4.4.5.3 | Install Panelboard - Roof | 2 | 2 | 0% | 2023-02-23 08:00 | 2023-02-24 17:00 | -24 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 02430 | 0 | 0 | SG7-02430 | Construction | Roof | Construction.4.4.5.3 | Rig Generator SG3 - Roof | 1 | 1 | 0% | 2023-03-08 08:00 | 2023-03-08 17:00 | -34 | WELKIN | GENERATOR | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 02490 | 0 | 0 | SG7-02490 | Construction | Roof | Construction.4.4.5.3 | Install & Wire Generator SG3 - Roof | 10 | 10 | 0% | 2023-03-09 08:00 | 2023-03-22 17:00 | -34 | FSE | GENERATOR | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 02500 | 0 | 0 | SG7-02500 | Construction | Roof | Construction.4.4.5.3 | Install Feeder Conduit & Pull Cable - Roof | 10 | 10 | 0% | 2023-02-27 08:00 | 2023-03-10 17:00 | -20 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 02505 | 0 | 0 | SG7-02505 | Construction | Roof | Construction.4.4.5.3 | Terminate Panelboards - Roof | 1 | 1 | 0% | 2023-03-13 08:00 | 2023-03-13 17:00 | -20 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.6 | SG7 | SG7 | 02625 | 0 | 0 | SG7-02625 | Construction | Testing & Start-Up | Construction.4.4.5.6 | Fire Alarm Operational & FDNY Acceptance Testing - SG7 | 5 | 5 | 0% | 2023-09-22 08:00 | 2023-09-28 17:00 | -101 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.6 | SG7 | SG7 | 02615 | 0 | 0 | SG7-02615 | Construction | Testing & Start-Up | Construction.4.4.5.6 | Provide Load Bank & Perform Acceptance Testing for Generator SG1 - SG7 | 2 | 2 | 0% | 2023-09-05 08:00 | 2023-09-06 17:00 | -131 | UNSURE | STARTUP | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.6 | SG7 | SG7 | 02605 | 0 | 0 | SG7-02605 | Construction | Testing & Start-Up | Construction.4.4.5.6 | Perform Electrical Inspections for SG7 | 5 | 5 | 0% | 2023-08-28 08:00 | 2023-09-01 17:00 | -132 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.6 | SG7 | SG7 | 02610 | 0 | 0 | SG7-02610 | Construction | Testing & Start-Up | Construction.4.4.5.6 | Notify NYCHA of Fire Alarm Testing - SG7 | 14 | 14 | 0% | 2023-09-01 08:00 | 2023-09-21 17:00 | -101 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.6 | SG7 | SG7 | 02620 | 0 | 0 | SG7-02620 | Construction | Testing & Start-Up | Construction.4.4.5.6 | Provide Load Bank & Perform Acceptance Testing for Generator SG2 - SG7 | 2 | 2 | 0% | 2023-09-07 08:00 | 2023-09-08 17:00 | -131 | UNSURE | STARTUP | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.6 | SG7 | SG7 | 02630 | 0 | 0 | SG7-02630 | Construction | Testing & Start-Up | Construction.4.4.5.6 | Provide Load Bank & Perform Acceptance Testing for Generator SG3 - SG7 | 2 | 2 | 0% | 2023-09-11 08:00 | 2023-09-12 17:00 | -131 | UNSURE | STARTUP | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.6 | SG7 | SG7 | 02635 | 0 | 0 | SG7-02635 | Construction | Testing & Start-Up | Construction.4.4.5.6 | Notify NYCHA of Generator Acceptance Testing- SG7 | 15 | 15 | 0% | 2023-08-14 08:00 | 2023-09-01 17:00 | -131 | UNSURE | STARTUP | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.6.1 | SG7 | SG7 | 02650 | 0 | 0 | SG7-02650 | Construction | SG1 | Construction.4.4.5.6.1 | Perform 3rd Party Testing of SG1 Switchgear - SG7 | 2 | 2 | 0% | 2023-09-05 08:00 | 2023-09-06 17:00 | -132 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.6.1 | SG7 | SG7 | 02655 | 0 | 0 | SG7-02655 | Construction | SG1 | Construction.4.4.5.6.1 | Energize SG1 Switchgear Equipment - SG7 | 4 | 4 | 0% | 2023-09-05 08:00 | 2023-09-08 17:00 | -130 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.6.1 | SG7 | SG7 | 02660 | 0 | 0 | SG7-02660 | Construction | SG1 | Construction.4.4.5.6.1 | Start-Up SG1 Switchgear/Generator - SG7 | 4 | 4 | 0% | 2023-09-18 08:00 | 2023-09-21 17:00 | -116 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.6.2 | SG7 | SG7 | 02675 | 0 | 0 | SG7-02675 | Construction | SG2 | Construction.4.4.5.6.2 | Energize SG2 Switchgear Equipment - SG7 | 4 | 4 | 0% | 2023-09-07 08:00 | 2023-09-12 17:00 | -132 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.6.2 | SG7 | SG7 | 02680 | 0 | 0 | SG7-02680 | Construction | SG2 | Construction.4.4.5.6.2 | Perform 3rd Party Testing of SG2 Switchgear - SG7 | 2 | 2 | 0% | 2023-09-05 08:00 | 2023-09-06 17:00 | -132 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.6.2 | SG7 | SG7 | 02685 | 0 | 0 | SG7-02685 | Construction | SG2 | Construction.4.4.5.6.2 | Start-Up SG2 Switchgear/Generator - SG7 | 4 | 4 | 0% | 2023-09-20 08:00 | 2023-09-25 17:00 | -118 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 02005 | 0 | 0 | SG2-02005 | Construction | Cellar | Construction.4.2.4.1 | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 25 | FSE | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 02010 | 0 | 0 | SG2-02010 | Construction | Cellar | Construction.4.2.4.1 | Install Bypass Connections - Cellar | 6 | 6 | 0% | 2022-12-02 08:00 | 2022-12-09 17:00 | 25 | MEP | 0 | 0 | 0 | 0-SG2
In Progress | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 02015 | 0 | 0 | SG2-02015 | Construction | Cellar | Construction.4.2.4.1 | Relocate (E) & Install Temporary Lighting - Cellar | 5 | 4 | 25% | 2022-06-15 | 2022-12-09 17:00 | 25 | FSE | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 02025 | 0 | 0 | SG2-02025 | Construction | Cellar | Construction.4.2.4.1 | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - Cellar | 5 | 5 | 0% | 2023-03-06 08:00 | 2023-03-10 17:00 | -11 | FSE | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 02045 | 0 | 0 | SG2-02045 | Construction | Cellar | Construction.4.2.4.1 | Link & Seal Conduit Sleeves - Cellar | 10 | 0 | 100% | 2021-10-22 | 2021-10-22 |  | 0 | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 02055 | 0 | 0 | SG2-02055 | Construction | Cellar | Construction.4.2.4.1 | Pull Lighting Wiring - Cellar | 3 | 3 | 0% | 2023-03-13 08:00 | 2023-03-15 17:00 | -11 | FSE | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 02065 | 0 | 0 | SG2-02065 | Construction | Cellar | Construction.4.2.4.1 | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 3 | 3 | 0% | 2023-03-16 08:00 | 2023-03-20 17:00 | -11 | FSE | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 02040 | 0 | 0 | SG2-02040 | Construction | Cellar | Construction.4.2.4.1 | Install Heat Trace for Plumbing Lines - Cellar | 5 | 5 | 0% | 2023-03-13 08:00 | 2023-03-17 17:00 | -10 | FSE | 0 | 0 | 0 | 0-SG2
In Progress | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 02050 | 0 | 0 | SG2-02050 | Construction | Cellar | Construction.4.2.4.1 | Core Drill & Install Feeder Conduits Risers & Racks to 1st Floor - Cellar | 15 | 14 | 10% | 2022-06-15 | 2022-12-14 12:00 | 31 | FSE | CORE DRILL | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 02060 | 0 | 0 | SG2-02060 | Construction | Cellar | Construction.4.2.4.1 | Install Panelboards (Misc.) | 2 | 2 | 0% | 2023-02-01 08:00 | 2023-02-02 17:00 | -11 | FSE | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 02020 | 0 | 0 | SG2-02020 | Construction | Cellar | Construction.4.2.4.1 | Install Branch Conduit | 15 | 15 | 0% | 2023-02-03 08:00 | 2023-02-24 17:00 | -11 | FSE | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 02035 | 0 | 0 | SG2-02035 | Construction | Cellar | Construction.4.2.4.1 | Pull Branch Wiring | 5 | 5 | 0% | 2023-02-27 08:00 | 2023-03-03 17:00 | -11 | FSE | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 02030 | 0 | 0 | SG2-02030 | Construction | Cellar | Construction.4.2.4.1 | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 10 | 10 | 0% | 2022-12-12 08:00 | 2022-12-23 17:00 | 40 | FSE | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.2 | SG2 | SG2 | 02110 | 0 | 0 | SG2-02110 | Construction | 1st Floor | Construction.4.2.4.2 | Install Pull/Splice Boxes - 1st Floor | 5 | 5 | 0% | 2022-12-14 13:00 | 2022-12-21 12:00 | 32 | MEP | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.2 | SG2 | SG2 | 02120 | 0 | 0 | SG2-02120 | Construction | 1st Floor | Construction.4.2.4.2 | Supply Power to Exterior Building Signage | 2 | 2 | 0% | 2023-01-06 13:00 | 2023-01-10 12:00 | 32 | FSE | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.2 | SG2 | SG2 | 02125 | 0 | 0 | SG2-02125 | Construction | 1st Floor | Construction.4.2.4.2 | Install Firestopping - 1st Floor | 5 | 5 | 0% | 2023-01-10 13:00 | 2023-01-18 12:00 | 32 | MLJ | FIRESTOPPING | EXISTING BUILDING | 07-1200 | 07-1200-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.2 | SG2 | SG2 | 02130 | 0 | 0 | SG2-02130 | Construction | 1st Floor | Construction.4.2.4.2 | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 3 | 3 | 0% | 2022-12-29 13:00 | 2023-01-04 12:00 | 43 | FSE | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.2 | SG2 | SG2 | 02135 | 0 | 0 | SG2-02135 | Construction | 1st Floor | Construction.4.2.4.2 | Pull Feeder Cable from Cellar to 1st Floor - 1st Floor | 10 | 10 | 0% | 2022-12-21 13:00 | 2023-01-06 12:00 | 32 | FSE | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.2 | SG2 | SG2 | 02105 | 0 | 0 | SG2-02105 | Construction | 1st Floor | Construction.4.2.4.2 | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - 1st Floor | 3 | 3 | 0% | 2023-03-13 08:00 | 2023-03-15 17:00 | -8 | FSE | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.2 | SG2 | SG2 | 02115 | 0 | 0 | SG2-02115 | Construction | 1st Floor | Construction.4.2.4.2 | Install Branch Conduit - 1st Floor | 5 | 5 | 0% | 2022-12-21 13:00 | 2022-12-29 12:00 | 41 | FSE | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.3 | SG2 | SG2 | 02505 | 0 | 0 | SG2-02505 | Construction | Testing & Start-Up | Construction.4.2.4.3 | Perform Tie-In's to Exisiting Equipment - SG2 | 5 | 5 | 0% | 2023-09-13 08:00 | 2023-09-19 17:00 | -132 | UNSURE | STARTUP | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.3 | SG2 | SG2 | 02510 | 0 | 0 | SG2-02510 | Construction | Testing & Start-Up | Construction.4.2.4.3 | Perform Electrical Inspections - SG2 | 2 | 2 | 0% | 2023-03-21 08:00 | 2023-03-22 17:00 | -11 | FSE | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 02005 | 0 | 0 | SG3-02005 | Construction | Cellar | Construction.4.3.8.1 | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 4 | 4 | 0% | 2022-11-25 08:00 | 2022-11-30 17:00 | 59 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 02010 | 0 | 0 | SG3-02010 | Construction | Cellar | Construction.4.3.8.1 | Install Bypass Connections - Cellar | 6 | 6 | 0% | 2022-12-01 08:00 | 2022-12-08 17:00 | 59 | MEP | 0 | 0 | 0 | 0-SG3
In Progress | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 02020 | 0 | 0 | SG3-02020 | Construction | Cellar | Construction.4.3.8.1 | Relocate (E) & Install Temporary Lighting - Cellar | 4 | 3 | 25% | 2022-06-06 | 2022-11-29 17:00 | 66 | FSE | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 02025 | 0 | 0 | SG3-02025 | Construction | Cellar | Construction.4.3.8.1 | Core Drill & Install Incoming Feeder Conduits & Racks - Cellar | 20 | 0 | 100% | 2022-06-07 | 2022-06-24 |  | 0 | 0 | 0 | 0 | 0-SG3
In Progress | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 02015 | 0 | 0 | SG3-02015 | Construction | Cellar | Construction.4.3.8.1 | Install Branch Conduit - Cellar | 20 | 12 | 40% | 2022-09-30 08:00 | 2022-12-12 17:00 | 2 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 02030 | 0 | 0 | SG3-02030 | Construction | Cellar | Construction.4.3.8.1 | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 20 | 20 | 0% | 2022-12-09 08:00 | 2023-01-09 17:00 | 59 | FSE | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 02050 | 0 | 0 | SG3-02050 | Construction | Cellar | Construction.4.3.8.1 | Link & Seal Conduit Sleeves - Cellar | 10 | 0 | 100% | 2021-10-22 | 2021-10-22 |  | 0 | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 02055 | 0 | 0 | SG3-02055 | Construction | Cellar | Construction.4.3.8.1 | Pull Lighting Wiring - Cellar | 5 | 5 | 0% | 2023-01-10 08:00 | 2023-01-17 17:00 | 59 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 02065 | 0 | 0 | SG3-02065 | Construction | Cellar | Construction.4.3.8.1 | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 5 | 5 | 0% | 2023-01-18 08:00 | 2023-01-24 17:00 | 59 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 02035 | 0 | 0 | SG3-02035 | Construction | Cellar | Construction.4.3.8.1 | Pull Branch Wiring - Cellar | 7 | 7 | 0% | 2022-12-13 08:00 | 2022-12-21 17:00 | 2 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 02040 | 0 | 0 | SG3-02040 | Construction | Cellar | Construction.4.3.8.1 | Install Heat Trace for Plumbing Lines - Cellar | 2 | 2 | 0% | 2022-12-22 08:00 | 2022-12-23 17:00 | 32 | FSE | 0 | 0 | 0 | 0-SG3
In Progress | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 02060 | 0 | 0 | SG3-02060 | Construction | Cellar | Construction.4.3.8.1 | Core Drill & Install Conduits Risers & Racks to 1st Floor - Cellar | 15 | 1 | 95% | 2022-06-01 | 2022-11-25 15:00 | 25 | FSE | CORE DRILL | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 02045 | 0 | 0 | SG3-02045 | Construction | Cellar | Construction.4.3.8.1 | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - Cellar | 5 | 5 | 0% | 2023-01-06 08:00 | 2023-01-12 17:00 | 20 | FSE | 0 | 0 | 0 | 0-SG3
In Progress | CI NYCHA Update #22.Construction.4.3.8.2 | SG3 | SG3 | 02115 | 0 | 0 | SG3-02115 | Construction | 1st Floor | Construction.4.3.8.2 | Install Feeder Conduit Risers & Racks to 2nd Floor - 1st Floor | 12 | 1 | 90% | 2022-10-15 | 2022-11-28 09:36 | 25 | FSE | 0 | 0 | 0 | 0-SG3
In Progress | CI NYCHA Update #22.Construction.4.3.8.2 | SG3 | SG3 | 02135 | 0 | 0 | SG3-02135 | Construction | 1st Floor | Construction.4.3.8.2 | Install Pull Boxes - 1st Floor | 4 | 0 | 90% | 2022-10-23 | 2022-11-30 09:36 | 33 | FSE | PULL BOXES | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.2 | SG3 | SG3 | 02105 | 0 | 0 | SG3-02105 | Construction | 1st Floor | Construction.4.3.8.2 | Install Branch Conduit - 1st Floor | 12 | 12 | 0% | 2022-12-22 08:00 | 2023-01-10 17:00 | 2 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.2 | SG3 | SG3 | 02110 | 0 | 0 | SG3-02110 | Construction | 1st Floor | Construction.4.3.8.2 | Pull Branch Wiring - 1st Floor | 6 | 6 | 0% | 2023-01-11 08:00 | 2023-01-19 17:00 | 2 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.2 | SG3 | SG3 | 02120 | 0 | 0 | SG3-02120 | Construction | 1st Floor | Construction.4.3.8.2 | Install Fire Alarm Control Panel (FACP) & Smoke Detectors - 1st Floor | 2 | 2 | 0% | 2023-01-20 08:00 | 2023-01-23 17:00 | 2 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.2 | SG3 | SG3 | 02130 | 0 | 0 | SG3-02130 | Construction | 1st Floor | Construction.4.3.8.2 | Pull Fire Alarm Wiring - 1st Floor | 2 | 2 | 0% | 2023-01-24 08:00 | 2023-01-25 17:00 | 48 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.2 | SG3 | SG3 | 02125 | 0 | 0 | SG3-02125 | Construction | 1st Floor | Construction.4.3.8.2 | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 5 | 5 | 0% | 2023-01-25 08:00 | 2023-01-31 17:00 | 59 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.2 | SG3 | SG3 | 02140 | 0 | 0 | SG3-02140 | Construction | 1st Floor | Construction.4.3.8.2 | Supply Power to Exterior Building Signage | 2 | 2 | 0% | 2023-08-04 08:00 | 2023-08-07 17:00 | -128 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.2 | SG3 | SG3 | 02145 | 0 | 0 | SG3-02145 | Construction | 1st Floor | Construction.4.3.8.2 | Install Firestopping - 1st Floor | 5 | 5 | 0% | 2023-08-08 08:00 | 2023-08-14 17:00 | -128 | MLJ | FIRESTOPPING | EXISTING BUILDING | 07-1200 | 07-1200-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.2 | SG3 | SG3 | 02150 | 0 | 0 | SG3-02150 | Construction | 1st Floor | Construction.4.3.8.2 | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - 1st Floor | 5 | 5 | 0% | 2023-01-20 08:00 | 2023-01-26 17:00 | 11 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 02205 | 0 | 0 | SG3-02205 | Construction | 2nd Floor | Construction.4.3.8.3 | Install Switchboards - 2nd Floor | 10 | 10 | 0% | 2023-06-09 08:00 | 2023-06-22 17:00 | -136 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 02210 | 0 | 0 | SG3-02210 | Construction | 2nd Floor | Construction.4.3.8.3 | Install ACTTS - 2nd Floor | 4 | 4 | 0% | 2023-06-23 08:00 | 2023-06-28 17:00 | -136 | FSE | ACTTS | 0 | 0 | 0-SG3
In Progress | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 02215 | 0 | 0 | SG3-02215 | Construction | 2nd Floor | Construction.4.3.8.3 | Install Feeder Conduits & Racks to Switchgear Equipment - 2nd Floor | 20 | 5 | 75% | 2022-10-17 08:00 | 2023-07-06 17:00 | -136 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 02220 | 0 | 0 | SG3-02220 | Construction | 2nd Floor | Construction.4.3.8.3 | Install Panelboards - 2nd Floor | 4 | 4 | 0% | 2023-07-07 08:00 | 2023-07-12 17:00 | -136 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 02225 | 0 | 0 | SG3-02225 | Construction | 2nd Floor | Construction.4.3.8.3 | Install Branch Conduit - 2nd Floor | 15 | 15 | 0% | 2023-07-13 08:00 | 2023-08-02 17:00 | -136 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 02235 | 0 | 0 | SG3-02235 | Construction | 2nd Floor | Construction.4.3.8.3 | Pull Branch Wiring - 2nd Floor | 5 | 5 | 0% | 2023-08-03 08:00 | 2023-08-09 17:00 | -136 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 02240 | 0 | 0 | SG3-02240 | Construction | 2nd Floor | Construction.4.3.8.3 | Install Lighting Fixtures & Controls - 2nd Floor | 4 | 4 | 0% | 2023-08-10 08:00 | 2023-08-15 17:00 | -74 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 02245 | 0 | 0 | SG3-02245 | Construction | 2nd Floor | Construction.4.3.8.3 | Install Smoke Detection Equipment - 2nd Floor | 5 | 5 | 0% | 2023-08-10 08:00 | 2023-08-16 17:00 | -89 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 02250 | 0 | 0 | SG3-02250 | Construction | 2nd Floor | Construction.4.3.8.3 | Install Receptacles - 2nd Floor | 4 | 4 | 0% | 2023-08-10 08:00 | 2023-08-15 17:00 | -136 | FSE | RECEPTACLES | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 02255 | 0 | 0 | SG3-02255 | Construction | 2nd Floor | Construction.4.3.8.3 | Install Fire Stopping - 2nd Floor | 4 | 4 | 0% | 2023-08-03 08:00 | 2023-08-08 17:00 | -124 | MLJ | FIRESTOPPING | EXISTING BUILDING | 07-1200 | 07-1200-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 02265 | 0 | 0 | SG3-02265 | Construction | 2nd Floor | Construction.4.3.8.3 | Tag & Terminate Switchgear Equipment | 5 | 5 | 0% | 2023-08-16 08:00 | 2023-08-22 17:00 | -136 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 02275 | 0 | 0 | SG3-02275 | Construction | 2nd Floor | Construction.4.3.8.3 | Tag & Terminate Panelboards | 2 | 2 | 0% | 2023-08-23 08:00 | 2023-08-24 17:00 | -136 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 02230 | 0 | 0 | SG3-02230 | Construction | 2nd Floor | Construction.4.3.8.3 | Ground Equipment | 5 | 5 | 0% | 2023-07-13 08:00 | 2023-07-19 17:00 | -117 | FSE | GROUNDING EQUIP | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 02280 | 0 | 0 | SG3-02280 | Construction | 2nd Floor | Construction.4.3.8.3 | Terminate Fire Alarm System | 2 | 2 | 0% | 2023-08-23 08:00 | 2023-08-24 17:00 | -81 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 02260 | 0 | 0 | SG3-02260 | Construction | 2nd Floor | Construction.4.3.8.3 | Pull CON-ED Feeder Cable - Cellar to SG-5 Switchgear - 2nd Floor | 10 | 10 | 0% | 2023-07-21 08:00 | 2023-08-03 17:00 | -128 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 02270 | 0 | 0 | SG3-02270 | Construction | 2nd Floor | Construction.4.3.8.3 | Install Controls & Pull Wire to Mechanical & Plumbing Equipment - 2nd Floor | 5 | 5 | 0% | 2023-08-04 08:00 | 2023-08-10 17:00 | -126 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.4 | SG3 | SG3 | 02530 | 0 | 0 | SG3-02530 | Construction | Testing & Start-Up | Construction.4.3.8.4 | Start-Up Generator/Switchgear - SG3 | 4 | 4 | 0% | 2023-09-20 08:00 | 2023-09-25 17:00 | -136 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.4 | SG3 | SG3 | 02535 | 0 | 0 | SG3-02535 | Construction | Testing & Start-Up | Construction.4.3.8.4 | Fire Alarm Operational & FDNY Acceptance Testing - SG3 | 5 | 5 | 0% | 2023-09-26 08:00 | 2023-10-02 17:00 | -102 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.4 | SG3 | SG3 | 02515 | 0 | 0 | SG3-02515 | Construction | Testing & Start-Up | Construction.4.3.8.4 | Energize Switchgear - SG3 | 5 | 5 | 0% | 2023-09-06 08:00 | 2023-09-12 17:00 | -136 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.4 | SG3 | SG3 | 02505 | 0 | 0 | SG3-02505 | Construction | Testing & Start-Up | Construction.4.3.8.4 | Perform Electrical Inspections - SG3 | 5 | 5 | 0% | 2023-08-25 08:00 | 2023-08-31 17:00 | -136 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.4 | SG3 | SG3 | 02520 | 0 | 0 | SG3-02520 | Construction | Testing & Start-Up | Construction.4.3.8.4 | Perform Tie-Ins to Existing | 5 | 5 | 0% | 2023-09-13 08:00 | 2023-09-19 17:00 | -136 | UNSURE | STARTUP | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.4 | SG3 | SG3 | 02510 | 0 | 0 | SG3-02510 | Construction | Testing & Start-Up | Construction.4.3.8.4 | Perform 3rd Party Test at SG3 | 2 | 2 | 0% | 2023-09-01 08:00 | 2023-09-05 17:00 | -136 | UNSURE | STARTUP | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.4 | SG3 | SG3 | 02525 | 0 | 0 | SG3-02525 | Construction | Testing & Start-Up | Construction.4.3.8.4 | Notify NYCHA of Fire Alarm Acceptance Testing | 14 | 14 | 0% | 2023-09-06 08:00 | 2023-09-25 17:00 | -102 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 02005 | 0 | 0 | SG1-02005 | Construction | Cellar | Construction.4.7.8.1 | Identify Existing & Remove Abandoned Feeder Conduit - Cellar | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 21 | FSE | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 02010 | 0 | 0 | SG1-02010 | Construction | Cellar | Construction.4.7.8.1 | Install Bypass Connections - Cellar | 6 | 6 | 0% | 2022-12-02 08:00 | 2022-12-09 17:00 | 21 | MEP | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 02025 | 0 | 0 | SG1-02025 | Construction | Cellar | Construction.4.7.8.1 | Relocate (E) & Install Temporary Lighting - Cellar | 5 | 5 | 0% | 2022-12-12 08:00 | 2022-12-16 17:00 | 21 | FSE | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 02040 | 0 | 0 | SG1-02040 | Construction | Cellar | Construction.4.7.8.1 | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - Cellar | 5 | 5 | 0% | 2023-02-10 08:00 | 2023-02-16 17:00 | 5 | FSE | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 02045 | 0 | 0 | SG1-02045 | Construction | Cellar | Construction.4.7.8.1 | Link & Seal Conduit Sleeves - Cellar | 9 | 0 | 100% | 2021-10-22 | 2021-10-22 |  | 0 | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 02055 | 0 | 0 | SG1-02055 | Construction | Cellar | Construction.4.7.8.1 | Pull Lighting Wiring - Cellar | 3 | 3 | 0% | 2023-01-04 08:00 | 2023-01-06 17:00 | 29 | FSE | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 02060 | 0 | 0 | SG1-02060 | Construction | Cellar | Construction.4.7.8.1 | Intall Exterior Lighting & Install Controls/Sensors to (E) Light Fixtures - Cellar | 4 | 4 | 0% | 2023-01-09 08:00 | 2023-01-12 17:00 | 29 | FSE | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 02015 | 0 | 0 | SG1-02015 | Construction | Cellar | Construction.4.7.8.1 | Install Heat Trace for Plumbing Lines - Cellar | 5 | 5 | 0% | 2023-02-17 08:00 | 2023-02-24 17:00 | 5 | FSE | 0 | 0 | 0 | 0-SG1
In Progress | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 02030 | 0 | 0 | SG1-02030 | Construction | Cellar | Construction.4.7.8.1 | Core Drill & Install Cellar Conduits - Cellar | 15 | 14 | 10% | 2022-05-15 | 2022-12-14 12:00 | 31 | FSE | CORE DRILL | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 02020 | 0 | 0 | SG1-02020 | Construction | Cellar | Construction.4.7.8.1 | Install Panelboards (Misc.) | 2 | 2 | 0% | 2023-01-10 08:00 | 2023-01-11 17:00 | 5 | FSE | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 02035 | 0 | 0 | SG1-02035 | Construction | Cellar | Construction.4.7.8.1 | Install Branch Conduit - Cellar | 15 | 15 | 0% | 2023-01-12 08:00 | 2023-02-02 17:00 | 5 | FSE | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 02065 | 0 | 0 | SG1-02065 | Construction | Cellar | Construction.4.7.8.1 | Pull Branch Wiring - Cellar | 5 | 5 | 0% | 2023-02-03 08:00 | 2023-02-09 17:00 | 5 | FSE | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 02050 | 0 | 0 | SG1-02050 | Construction | Cellar | Construction.4.7.8.1 | Remove (E) & Install New Conduit for (E) Light Fixtures - Cellar | 10 | 10 | 0% | 2022-12-19 08:00 | 2023-01-03 17:00 | 29 | FSE | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.2 | SG1 | SG1 | 02105 | 0 | 0 | SG1-02105 | Construction | 1st Floor | Construction.4.7.8.2 | Install Pull/Splice Boxes - 1st Floor | 4 | 4 | 0% | 2022-12-14 13:00 | 2022-12-20 12:00 | 33 | MEP | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.2 | SG1 | SG1 | 02110 | 0 | 0 | SG1-02110 | Construction | 1st Floor | Construction.4.7.8.2 | Supply Power to Exterior Building Signage | 2 | 2 | 0% | 2023-01-05 13:00 | 2023-01-09 12:00 | 33 | FSE | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.2 | SG1 | SG1 | 02120 | 0 | 0 | SG1-02120 | Construction | 1st Floor | Construction.4.7.8.2 | Install Firestopping - 1st Floor | 5 | 5 | 0% | 2023-01-13 08:00 | 2023-01-20 17:00 | 29 | MLJ | FIRESTOPPING | EXISTING BUILDING | 07-1200 | 07-1200-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.2 | SG1 | SG1 | 02115 | 0 | 0 | SG1-02115 | Construction | 1st Floor | Construction.4.7.8.2 | Rewire (E) Light Fixtures & Install Controls - 1st Floor | 3 | 3 | 0% | 2022-12-28 13:00 | 2023-01-03 12:00 | 72 | FSE | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.2 | SG1 | SG1 | 02130 | 0 | 0 | SG1-02130 | Construction | 1st Floor | Construction.4.7.8.2 | Pull Feeder Cable from Cellar to 1st Floor - 1st Floor | 10 | 10 | 0% | 2022-12-20 13:00 | 2023-01-05 12:00 | 33 | FSE | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.2 | SG1 | SG1 | 02125 | 0 | 0 | SG1-02125 | Construction | 1st Floor | Construction.4.7.8.2 | Install Controls & Pull Wire to Mechanical/Plumbing Equipment - 1st Floor | 3 | 3 | 0% | 2023-02-17 08:00 | 2023-02-22 17:00 | 7 | FSE | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.2 | SG1 | SG1 | 02135 | 0 | 0 | SG1-02135 | Construction | 1st Floor | Construction.4.7.8.2 | Install Branch Conduit - 1st Floor | 5 | 5 | 0% | 2022-12-20 13:00 | 2022-12-28 12:00 | 38 | FSE | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.3 | SG1 | SG1 | 02505 | 0 | 0 | SG1-02505 | Construction | Testing & Start-Up | Construction.4.7.8.3 | Perform Tie-In's to Exisiting Equipment - SG1 | 5 | 5 | 0% | 2023-09-11 08:00 | 2023-09-15 17:00 | -130 | UNSURE | STARTUP | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.3 | SG1 | SG1 | 02510 | 0 | 0 | SG1-02510 | Construction | Testing & Start-Up | Construction.4.7.8.3 | Perform Electrical Inspections - SG1 | 2 | 2 | 0% | 2023-03-14 08:00 | 2023-03-15 17:00 | -6 | FSE | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 02005 | 0 | 0 | PERMIT-02005 | Procurement | Permits | Procurement.Div 1.Permits | File for Fence Permit | 10 | 0 | 100% | 2020-09-25 | 2020-09-25 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG5 | PERMIT | 02010 | 0 | 0 | PERMIT-02010 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Fence Permit (OG5 & 6 require L2 forms) | 20 | 0 | 100% | 2020-09-28 | 2021-01-06 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG6 | PERMIT | 03005 | 0 | 0 | PERMIT-03005 | Procurement | Permits | Procurement.Div 1.Permits | File for New buildings Permit - SG-6 | 10 | 0 | 100% | 2020-11-01 | 2020-12-01 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG6 | PERMIT | 03010 | 0 | 0 | PERMIT-03010 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue New buildings Permit - SG-6 | 20 | 0 | 100% | 2020-12-01 | 2021-02-02 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.5.Removals | SGN | SGN | 01015 | 0 | 0 | SGN-01015 | Construction | Site Protection & Removals | Construction.2.5.Removals | Install Overhead Protection - NA | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.Removals | SGN | SGN | 01020 | 0 | 0 | SGN-01020 | Construction | Site Protection & Removals | Construction.2.5.Removals | Install Tree Protection | 10 | 0 | 100% | 2020-11-03 | 2020-11-12 17:00 |  | 0 | 0 | 0 | 31-1900 | 31-1900-SGN
Completed | CI NYCHA Update #22.Construction.2.5.Removals | SGN | SGN | 01025 | 0 | 0 | SGN-01025 | Construction | Site Protection & Removals | Construction.2.5.Removals | Remove Trees | 2 | 0 | 100% | 2021-01-14 | 2021-01-19 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.Removals | SGN | SGN | 01000 | 0 | 0 | SGN-01000 | Construction | Site Protection & Removals | Construction.2.5.Removals | Remove Curbs And Existing Fencing | 10 | 0 | 100% | 2020-12-16 | 2021-01-25 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.Removals | SGN | SGN | 01035 | 0 | 0 | SGN-01035 | Construction | Site Protection & Removals | Construction.2.5.Removals | Install Erosion Control | 5 | 0 | 100% | 2021-03-19 | 2021-03-25 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.Removals | SGN | SGN | 01010 | 0 | 0 | SGN-01010 | Construction | Site Protection & Removals | Construction.2.5.Removals | Set Up Yard and Staging | 5 | 0 | 100% | 2021-02-25 08:00 | 2021-03-04 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.Removals | SGN | SGN | 01045 | 0 | 0 | SGN-01045 | Construction | Site Protection & Removals | Construction.2.5.Removals | Clear & Grub (South Area left for Residence Use) | 5 | 0 | 100% | 2021-01-11 | 2022-01-21 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.Removals | SGN | SGN | 01050 | 0 | 0 | SGN-01050 | Construction | Site Protection & Removals | Construction.2.5.Removals | Scrape & Store Topsoil | 10 | 0 | 100% | 2021-01-18 | 2021-03-24 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.Removals | SGN | SGN | 01055 | 0 | 0 | SGN-01055 | Construction | Site Protection & Removals | Construction.2.5.Removals | Soil Testing | 10 | 0 | 100% | 2021-02-11 | 2021-02-25 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.Removals | SGN | SGN | 01060 | 0 | 0 | SGN-01060 | Construction | Site Protection & Removals | Construction.2.5.Removals | Demo Playgrounds And Misc Site Furniture (South Area left for Residence Use) | 5 | 0 | 100% | 2021-01-11 | 2021-07-23 17:00 |  | 0 | 0 | 0 | 02-2000 | 02-2000-SGN
Completed | CI NYCHA Update #22.Construction.2.5.Removals | SGN | SGN | 01065 | 0 | 0 | SGN-01065 | Construction | Site Protection & Removals | Construction.2.5.Removals | Remove Retaining Walls | 10 | 0 | 100% | 2021-01-18 | 2022-01-21 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.Removals | SGN | SGN | 01070 | 0 | 0 | SGN-01070 | Construction | Site Protection & Removals | Construction.2.5.Removals | Install Deep Wells For Dewatering - N/R | 10 | 0 | 100% | 2021-05-25 | 2021-05-25 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.Removals | SGN | SGN | 01075 | 0 | 0 | SGN-01075 | Construction | Site Protection & Removals | Construction.2.5.Removals | Install Piping For Deep Wells - N/R | 5 | 0 | 100% | 2021-05-25 | 2021-05-25 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.Removals | SGN | SGN | 01080 | 0 | 0 | SGN-01080 | Construction | Site Protection & Removals | Construction.2.5.Removals | Install Discharge Connection For Dewatering - N/R | 10 | 0 | 100% | 2021-05-25 | 2021-05-25 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.Removals | SGN | SGN | 01085 | 0 | 0 | SGN-01085 | Construction | Site Protection & Removals | Construction.2.5.Removals | Run Electric For Dewatering - N/R | 10 | 0 | 100% | 2021-05-25 | 2021-05-25 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01105 | 0 | 0 | SGN-01105 | Construction | Site Utilities | Construction.2.5.1 | Excavate for HW & CW - SG6 --> SG4 | 10 | 0 | 100% | 2021-08-15 | 2021-08-20 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01110 | 0 | 0 | SGN-01110 | Construction | Site Utilities | Construction.2.5.1 | Install HW & CW piping - SG6--> SG4 | 15 | 0 | 100% | 2021-09-09 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01115 | 0 | 0 | SGN-01115 | Construction | Site Utilities | Construction.2.5.1 | Test HW & CW Piping - SG6 --> SG4 | 10 | 0 | 100% | 2021-11-25 08:00 | 2021-11-30 17:00 |  | WELKIN | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01120 | 0 | 0 | SGN-01120 | Construction | Site Utilities | Construction.2.5.1 | Backfill HW & CW Piping - SG6 --> SG4 | 5 | 0 | 100% | 2022-04-27 | 2022-04-29 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01125 | 0 | 0 | SGN-01125 | Construction | Site Utilities | Construction.2.5.1 | Excavate for Steam - SG6 --> SG4 | 10 | 0 | 100% | 2021-08-16 08:00 | 2021-08-18 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01130 | 0 | 0 | SGN-01130 | Construction | Site Utilities | Construction.2.5.1 | Install Steam piping - SG6--> SG4 | 10 | 0 | 100% | 2021-09-26 | 2021-10-02 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01135 | 0 | 0 | SGN-01135 | Construction | Site Utilities | Construction.2.5.1 | Test Steam Piping - SG6 --> SG4 | 4 | 0 | 100% | 2021-11-26 08:00 | 2021-11-26 17:00 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01140 | 0 | 0 | SGN-01140 | Construction | Site Utilities | Construction.2.5.1 | Backfill Steam Piping - SG6 --> SG4 | 5 | 0 | 100% | 2022-05-26 | 2022-05-30 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01150 | 0 | 0 | SGN-01150 | Construction | Site Utilities | Construction.2.5.1 | Excavate for Electric SG6--> SG4 | 10 | 0 | 100% | 2021-06-07 | 2021-08-05 17:00 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01155 | 0 | 0 | SGN-01155 | Construction | Site Utilities | Construction.2.5.1 | Install Electrical Conduit SG6--> SG4 | 10 | 0 | 100% | 2021-06-14 | 2021-08-23 17:00 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01160 | 0 | 0 | SGN-01160 | Construction | Site Utilities | Construction.2.5.1 | Encase conduit in concrete SG6-->SG4 | 5 | 0 | 100% | 2021-06-25 08:00 | 2021-11-26 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01165 | 0 | 0 | SGN-01165 | Construction | Site Utilities | Construction.2.5.1 | Backfill Electrical SG6 --> SG4 | 5 | 0 | 100% | 2021-06-30 08:00 | 2021-09-10 17:00 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01175 | 0 | 0 | SGN-01175 | Construction | Site Utilities | Construction.2.5.1 | Excavate for gas SG6 --> W33rd Street | 5 | 0 | 100% | 2022-09-20 | 2022-09-23 |  | MLJ | Excavation | UTILITY EXC | 33-3100 | 33-3100-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01180 | 0 | 0 | SGN-01180 | Construction | Site Utilities | Construction.2.5.1 | Install Gas SG6--> W33rd Street | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | 78 | NATIONAL GRID | GAS INSTALL | 0 | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01185 | 0 | 0 | SGN-01185 | Construction | Site Utilities | Construction.2.5.1 | Backfill gas SG6 --> W33rd Street | 3 | 3 | 0% | 2022-11-29 08:00 | 2022-12-01 17:00 | 117 | MLJ | BACKFILL | BACKFILL UTILITY | 31-2200 | 31-2200-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01205 | 0 | 0 | SGN-01205 | Construction | Site Utilities | Construction.2.5.1 | Excavate for Electric SG4--> MH | 3 | 0 | 100% | 2021-08-24 08:00 | 2021-09-15 17:00 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01210 | 0 | 0 | SGN-01210 | Construction | Site Utilities | Construction.2.5.1 | Install Electrical Conduit SG4--> MH | 2 | 0 | 100% | 2021-09-22 08:00 | 2021-10-20 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01215 | 0 | 0 | SGN-01215 | Construction | Site Utilities | Construction.2.5.1 | Encase conduit in concrete SG4--> MH | 2 | 0 | 100% | 2021-09-30 | 2021-10-22 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01220 | 0 | 0 | SGN-01220 | Construction | Site Utilities | Construction.2.5.1 | Backfill Elecrtical SG4 --> MH | 2 | 0 | 100% | 2021-10-06 | 2021-10-22 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01230 | 0 | 0 | SGN-01230 | Construction | Site Utilities | Construction.2.5.1 | Excavate for Electric SG6 -> SG5 | 10 | 0 | 100% | 2021-07-20 08:00 | 2021-08-09 17:00 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01235 | 0 | 0 | SGN-01235 | Construction | Site Utilities | Construction.2.5.1 | Install Electrical Conduit SG6--> SG5 | 5 | 0 | 100% | 2021-06-14 | 2021-08-23 17:00 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01240 | 0 | 0 | SGN-01240 | Construction | Site Utilities | Construction.2.5.1 | Encase conduit in concrete SG6--> SG5 | 3 | 0 | 100% | 2021-07-26 08:00 | 2021-09-12 17:00 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01245 | 0 | 0 | SGN-01245 | Construction | Site Utilities | Construction.2.5.1 | Backfill Elecrtical SG6 --> SG5 | 5 | 0 | 100% | 2021-08-02 08:00 | 2021-09-12 17:00 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01255 | 0 | 0 | SGN-01255 | Construction | Site Utilities | Construction.2.5.1 | Excavate for Electric SG5--> MH | 3 | 0 | 100% | 2021-09-10 08:00 | 2021-09-14 17:00 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01260 | 0 | 0 | SGN-01260 | Construction | Site Utilities | Construction.2.5.1 | Install Electrical Conduit SG5--> MH | 2 | 0 | 100% | 2021-09-13 08:00 | 2021-09-24 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01265 | 0 | 0 | SGN-01265 | Construction | Site Utilities | Construction.2.5.1 | Encase conduit in concrete SG5--> MH | 2 | 0 | 100% | 2021-10-02 | 2021-10-06 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01270 | 0 | 0 | SGN-01270 | Construction | Site Utilities | Construction.2.5.1 | Backfill Elecrtical SG5 --> MH | 2 | 0 | 100% | 2021-10-07 | 2021-10-11 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01275 | 0 | 0 | SGN-01275 | Construction | Site Utilities | Construction.2.5.1 | Excavate for Steam & HW SG4--> SG5 | 15 | 0 | 100% | 2021-09-20 08:00 | 2021-09-24 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01280 | 0 | 0 | SGN-01280 | Construction | Site Utilities | Construction.2.5.1 | Install Steam and HW piping SG4--> SG5 | 20 | 0 | 100% | 2021-09-26 | 2022-06-16 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01285 | 0 | 0 | SGN-01285 | Construction | Site Utilities | Construction.2.5.1 | Test Steam & HW Piping SG4--> SG5 | 8 | 0 | 100% | 2022-06-13 | 2022-06-17 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01290 | 0 | 0 | SGN-01290 | Construction | Site Utilities | Construction.2.5.1 | Backfill Steam & HW Piping SG4 --> SG5 | 10 | 0 | 100% | 2022-06-20 | 2022-06-24 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01305 | 0 | 0 | SGN-01305 | Construction | Site Utilities | Construction.2.5.1 | Excavate for water line to drinking fountain SGN --> Water Main W32nd Street | 2 | 0 | 100% | 2022-09-22 | 2022-09-23 |  | MLJ | Excavation | PLAYGROUND | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01310 | 0 | 0 | SGN-01310 | Construction | Site Utilities | Construction.2.5.1 | Install water line to drinking fountain SGN --> Water Main W32nd Street | 5 | 0 | 100% | 2022-11-04 | 2022-11-23 |  | 0 | 0 | PLAYGROUND | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01315 | 0 | 0 | SGN-01315 | Construction | Site Utilities | Construction.2.5.1 | Tap water main for drinking fountain water line SGN --> Water Main W32nd Street | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | 112 | UNSURE | PLAYGROUND | PLUMBING | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01320 | 0 | 0 | SGN-01320 | Construction | Site Utilities | Construction.2.5.1 | Backfill water line drinking fountain SGN --> Water Main W32nd Street | 2 | 2 | 0% | 2022-11-29 08:00 | 2022-11-30 17:00 | 112 | MLJ | BACKFILL | BACKFILL SITE | 31-2200 | 31-2200-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01330 | 0 | 0 | SGN-01330 | Construction | Site Utilities | Construction.2.5.1 | Excavate for water line to water play items SGN --> Water Main W33rd Street | 2 | 0 | 100% | 2022-09-22 | 2022-09-23 |  | MLJ | Excavation | PLAYGROUND | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01335 | 0 | 0 | SGN-01335 | Construction | Site Utilities | Construction.2.5.1 | Install water line and RPZ box for water play items SGN --> Water Main W33rd Street | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 109 | UNSURE | PLAYGROUND | PLUMBING | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01340 | 0 | 0 | SGN-01340 | Construction | Site Utilities | Construction.2.5.1 | Tap water main for drinking fountain water line SGN --> Water Main W33rd Street | 2 | 2 | 0% | 2022-12-02 08:00 | 2022-12-05 17:00 | 109 | UNSURE | PLAYGROUND | PLUMBING | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01345 | 0 | 0 | SGN-01345 | Construction | Site Utilities | Construction.2.5.1 | Backfill water line drinking fountain SGN --> Water Main W33rd Street | 2 | 2 | 0% | 2022-12-06 08:00 | 2022-12-07 17:00 | 109 | MLJ | BACKFILL | BACKFILL SITE | 31-2200 | 31-2200-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01355 | 0 | 0 | SGN-01355 | Construction | Site Utilities | Construction.2.5.1 | Excavate for Sanitary sewer SG6 --> W32nd Street | 3 | 0 | 100% | 2022-08-29 | 2022-08-31 |  | MLJ | Excavation | UTILITY EXC | 33-3100 | 33-3100-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01360 | 0 | 0 | SGN-01360 | Construction | Site Utilities | Construction.2.5.1 | Install sanitary pipe SG6 --> Sanitary Sewer W32nd Street | 2 | 0 | 100% | 2022-08-31 | 2022-09-07 |  | 0 | UG PIPE | 0 | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01365 | 0 | 0 | SGN-01365 | Construction | Site Utilities | Construction.2.5.1 | Backfill Sanitary Sewer SG6 --> Sanitary Sewer W32nd Street | 2 | 2 | 0% | 2022-12-08 08:00 | 2022-12-09 17:00 | 109 | MLJ | BACKFILL | BACKFILL UTILITY | 31-2200 | 31-2200-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01375 | 0 | 0 | SGN-01375 | Construction | Site Utilities | Construction.2.5.1 | Excavate and Install Area Drains 10 & 11 and piping / SG4 yard pumps tie in | 5 | 5 | 0% | 2023-01-11 08:00 | 2023-01-18 17:00 | 84 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01380 | 0 | 0 | SGN-01380 | Construction | Site Utilities | Construction.2.5.1 | Backfill Area Drains 10 & 11 and piping | 2 | 2 | 0% | 2023-01-19 08:00 | 2023-01-20 17:00 | 84 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01385 | 0 | 0 | SGN-01385 | Construction | Site Utilities | Construction.2.5.1 | Excavate and Install Area Drains 12, 13, 14, 15 and piping | 10 | 0 | 100% | 2022-08-29 | 2022-09-02 |  | MLJ | Excavation | AREA DRAIN | 33-2600 | 33-2600-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01390 | 0 | 0 | SGN-01390 | Construction | Site Utilities | Construction.2.5.1 | Backfill Area Drains 12, 13, 14, 15 and piping | 3 | 0 | 100% | 2022-09-05 | 2022-09-06 |  | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01405 | 0 | 0 | SGN-01405 | Construction | Site Utilities | Construction.2.5.1 | Excavate and Install Area Drains 5, 6, 7, 18, 19 and piping / cellar pump tie in | 12 | 0 | 100% | 2022-08-23 | 2022-08-29 |  | MLJ | Excavation | AREA DRAIN | 33-2600 | 33-2600-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01410 | 0 | 0 | SGN-01410 | Construction | Site Utilities | Construction.2.5.1 | Backfill Area Drains 5, 6, 7, 18, 19 and piping | 5 | 0 | 100% | 2022-08-30 | 2022-09-02 |  | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01420 | 0 | 0 | SGN-01420 | Construction | Site Utilities | Construction.2.5.1 | Excavate and Install Area Drains 22 and piping / SG6 storm tie in | 3 | 0 | 100% | 2022-10-25 | 2022-10-27 |  | MLJ | Excavation | AREA DRAIN | 33-2600 | 33-2600-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01425 | 0 | 0 | SGN-01425 | Construction | Site Utilities | Construction.2.5.1 | Backfill Area Drains 22 and piping | 2 | 0 | 100% | 2022-10-28 | 2022-10-28 |  | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01435 | 0 | 0 | SGN-01435 | Construction | Site Utilities | Construction.2.5.1 | Excavate and Install Area Drains 1, 2, 4, 9 and piping | 10 | 0 | 100% | 2022-06-06 | 2022-06-17 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01440 | 0 | 0 | SGN-01440 | Construction | Site Utilities | Construction.2.5.1 | Backfill Area Drains 1, 2, 4, 9 and piping | 3 | 0 | 100% | 2022-06-27 | 2022-07-05 |  | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01450 | 0 | 0 | SGN-01450 | Construction | Site Utilities | Construction.2.5.1 | Excavate and Install Area Drains 16, 17, and piping | 5 | 0 | 100% | 2022-09-12 | 2022-09-16 |  | MLJ | Excavation | AREA DRAIN | 33-2600 | 33-2600-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01455 | 0 | 0 | SGN-01455 | Construction | Site Utilities | Construction.2.5.1 | Backfill Area Drains 16, 17, and piping | 2 | 0 | 100% | 2022-09-18 | 2022-09-19 |  | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01460 | 0 | 0 | SGN-01460 | Construction | Site Utilities | Construction.2.5.1 | Excavate and Install Area Drains 3 and piping / yard pumps tie in | 3 | 0 | 100% | 2022-09-20 | 2022-10-25 |  | MLJ | Excavation | AREA DRAIN | 33-2600 | 33-2600-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01465 | 0 | 0 | SGN-01465 | Construction | Site Utilities | Construction.2.5.1 | Backfill Area Drains 3, and piping | 2 | 0 | 100% | 2022-01-26 | 2022-10-27 |  | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01470 | 0 | 0 | SGN-01470 | Construction | Site Utilities | Construction.2.5.1 | Excavate and Install piping - yard pumps tie in to sewer | 2 | 0 | 100% | 2022-10-26 | 2022-10-27 |  | MLJ | Excavation | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01475 | 0 | 0 | SGN-01475 | Construction | Site Utilities | Construction.2.5.1 | Backfill piping - yard pumps tie in to sewer | 1 | 0 | 100% | 2022-10-28 | 2022-10-28 |  | MLJ | BACKFILL | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01480 | 0 | 0 | SGN-01480 | Construction | Site Utilities | Construction.2.5.1 | Excavate and Install Area Drains 8 and piping / SG5 cellar pump tie in | 2 | 0 | 100% | 2022-09-12 | 2022-09-16 |  | MLJ | Excavation | AREA DRAIN | 33-2600 | 33-2600-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01485 | 0 | 0 | SGN-01485 | Construction | Site Utilities | Construction.2.5.1 | Backfill Area Drains 3, and piping | 1 | 0 | 100% | 2022-09-16 | 2022-09-17 |  | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-SGN
Completed | CI NYCHA Update #22.Construction.2.5.4 | SGN | SGN | 01505 | 0 | 0 | SGN-01505 | Construction | Retaining Walls | Construction.2.5.4 | Excavate for retaining wall --> SGN | 2 | 0 | 100% | 2022-08-06 | 2022-08-10 |  | MLJ | Excavation | EXC RETAINING | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.4 | SGN | SGN | 01510 | 0 | 0 | SGN-01510 | Construction | Retaining Walls | Construction.2.5.4 | Form Retaining wall footing --> SGN | 2 | 0 | 100% | 2022-08-11 | 2022-08-12 |  | MLJ | Formwork | SITE FORMWORK | 03-1600 | 03-1600-SGN
Completed | CI NYCHA Update #22.Construction.2.5.4 | SGN | SGN | 01515 | 0 | 0 | SGN-01515 | Construction | Retaining Walls | Construction.2.5.4 | Rebar Retaining wall footing --> SGN | 2 | 0 | 100% | 2022-08-15 | 2022-08-16 |  | 0 | REBAR | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.4 | SGN | SGN | 01520 | 0 | 0 | SGN-01520 | Construction | Retaining Walls | Construction.2.5.4 | Pour Retaining wall footing --> SGN | 1 | 0 | 100% | 2022-08-16 | 2022-08-16 |  | MLJ | Concrete | SITE CONCRETE | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.4 | SGN | SGN | 01525 | 0 | 0 | SGN-01525 | Construction | Retaining Walls | Construction.2.5.4 | Strip Retaining wall footing --> SGN | 1 | 0 | 100% | 2022-08-19 | 2022-08-19 |  | 0 | Formwork | SITE FORMWORK | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.4 | SGN | SGN | 01530 | 0 | 0 | SGN-01530 | Construction | Retaining Walls | Construction.2.5.4 | Form Retaining wall --> SGN | 3 | 0 | 100% | 2022-08-22 | 2022-08-23 |  | MLJ | Formwork | SITE FORMWORK | 03-1600 | 03-1600-SGN
Completed | CI NYCHA Update #22.Construction.2.5.4 | SGN | SGN | 01535 | 0 | 0 | SGN-01535 | Construction | Retaining Walls | Construction.2.5.4 | Rebar Retaining wall --> SGN | 3 | 0 | 100% | 2022-08-23 | 2022-08-24 |  | 0 | REBAR | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.4 | SGN | SGN | 01540 | 0 | 0 | SGN-01540 | Construction | Retaining Walls | Construction.2.5.4 | Pour Retaining wall --> SGN | 1 | 0 | 100% | 2022-08-25 | 2022-08-25 |  | MLJ | Concrete | SITE CONCRETE | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.4 | SGN | SGN | 01545 | 0 | 0 | SGN-01545 | Construction | Retaining Walls | Construction.2.5.4 | Strip Retaining wall --> SGN | 1 | 0 | 100% | 2022-08-27 | 2022-08-27 |  | 0 | Formwork | SITE FORMWORK | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.5 | SGN | SGN | 01605 | 0 | 0 | SGN-01605 | Construction | Site Restoration | Construction.2.5.5 | Install Street Curbs --> SGN | 15 | 15 | 0% | 2023-01-17 08:00 | 2023-02-06 17:00 | -2 | MLJ | CURBS | 0 | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.5 | SGN | SGN | 01610 | 0 | 0 | SGN-01610 | Construction | Site Restoration | Construction.2.5.5 | Install sidewalks --> SGN | 10 | 10 | 0% | 2023-02-22 08:00 | 2023-03-07 17:00 | -2 | JMC | SIDEWALKS | 0 | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.5 | SGN | SGN | 01615 | 0 | 0 | SGN-01615 | Construction | Site Restoration | Construction.2.5.5 | Install curb around play area --> SGN | 5 | 5 | 0% | 2023-03-08 08:00 | 2023-03-14 17:00 | -2 | MLJ | CURBS | 0 | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.5 | SGN | SGN | 01620 | 0 | 0 | SGN-01620 | Construction | Site Restoration | Construction.2.5.5 | Install Safety Surface --> SGN | 5 | 5 | 0% | 2023-03-15 08:00 | 2023-03-21 17:00 | -2 | UNSURE | PLAYGROUND | SAFETY SURFACE | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.5 | SGN | SGN | 01625 | 0 | 0 | SGN-01625 | Construction | Site Restoration | Construction.2.5.5 | Install site furniture concrete foundations --> SGN | 10 | 10 | 0% | 2023-02-07 08:00 | 2023-02-21 17:00 | -2 | MLJ | CONCRETE | SITE CONCRETE | 03-2200 | 03-2200-SGN
In Progress | CI NYCHA Update #22.Construction.2.5.5 | SGN | SGN | 01630 | 0 | 0 | SGN-01630 | Construction | Site Restoration | Construction.2.5.5 | Install integrally colored concrete walkways --> SGN | 20 | 15 | 25% | 2022-09-12 | 2023-04-11 17:00 | -2 | JMC | COLORED CONCRETE | 0 | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.5 | SGN | SGN | 01635 | 0 | 0 | SGN-01635 | Construction | Site Restoration | Construction.2.5.5 | Install Play area items --> SGN | 5 | 5 | 0% | 2023-04-12 08:00 | 2023-04-18 17:00 | -2 | BRIGHTON | PLAYGROUND | INSTALL | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.5 | SGN | SGN | 01640 | 0 | 0 | SGN-01640 | Construction | Site Restoration | Construction.2.5.5 | Install fence around play area --> SGN | 10 | 10 | 0% | 2023-04-19 08:00 | 2023-05-02 17:00 | -2 | MLJ | FENCING | PLAYGROUND | 32-6520 | 32-6520-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.5 | SGN | SGN | 01645 | 0 | 0 | SGN-01645 | Construction | Site Restoration | Construction.2.5.5 | Install Fence at building --> SG6 | 5 | 5 | 0% | 2023-05-03 08:00 | 2023-05-09 17:00 | -2 | ATLAS | SITE RESTORATION | 0 | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.5 | SGN | SGN | 01650 | 0 | 0 | SGN-01650 | Construction | Site Restoration | Construction.2.5.5 | Place Site Furniture --> SGN | 10 | 10 | 0% | 2023-05-10 08:00 | 2023-05-23 17:00 | -2 | MLJ | SITE RESTORATION | SITE FURNITURE | 31-2600 | 31-2600-SGN
In Progress | CI NYCHA Update #22.Construction.2.5.5 | SGN | SGN | 01675 | 0 | 0 | SGN-01675 | Construction | Site Restoration | Construction.2.5.5 | Place topsoil --> SGN | 3 | 2 | 33% | 2022-10-05 | 2023-04-04 17:00 | 24 | ASPEN | TOPSOIL | 0 | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.5 | SGN | SGN | 01680 | 0 | 0 | SGN-01680 | Construction | Site Restoration | Construction.2.5.5 | Place trees and plantings --> SGN | 5 | 5 | 0% | 2023-04-05 08:00 | 2023-04-11 17:00 | 24 | ASPEN | 0 | 0 | 0 | 0-SGN
In Progress | CI NYCHA Update #22.Construction.2.5.5 | SGN | SGN | 01685 | 0 | 0 | SGN-01685 | Construction | Site Restoration | Construction.2.5.5 | Place lawn --> SGN | 5 | 2 | 60% | 2022-10-12 | 2023-04-04 17:00 | 29 | ASPEN | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01030 | 0 | 0 | SG6-01030 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Form Plumbing Shafts & Ftgs Below Water Table --> SG6 | 10 | 0 | 100% | 2021-04-05 | 2021-04-06 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01035 | 0 | 0 | SG6-01035 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Rebar Plumbing Shafts & Ftgs Below Water Table --> SG6 | 5 | 0 | 100% | 2021-04-08 | 2021-04-12 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01040 | 0 | 0 | SG6-01040 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Pour Plumbing Shafts & Ftgs Below Water Table --> SG6 | 2 | 0 | 100% | 2021-04-08 | 2021-04-14 |  | MLJ | concrete | NB CONCRETE | 03-1900 | 03-1900-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01045 | 0 | 0 | SG6-01045 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Strip Forms Plumbing Shafts & Ftgs Below Water Table --> SG6 | 5 | 0 | 100% | 2021-04-12 | 2021-04-12 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01025 | 0 | 0 | SG6-01025 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Waterproof/Insulation Plumbing Shaft ----> SG6 - N/A | 5 | 0 | 100% | 2021-03-01 | 2021-03-01 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01005 | 0 | 0 | SG6-01005 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Excavate For Plumbing Shaft & Ftgs/Piers Below Water Table --> SG6 | 5 | 0 | 100% | 2021-03-02 | 2021-03-31 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01020 | 0 | 0 | SG6-01020 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Prepare Subgrade For Plumbing Shafts & Ftgs / Piers Below Water Table --> SG6 | 3 | 0 | 100% | 2021-03-31 | 2021-03-31 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01055 | 0 | 0 | SG6-01055 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Backfill Plumbing Shaft & Ftgs/Piers --> SG6 | 5 | 0 | 100% | 2021-04-16 | 2021-04-16 |  | 0 | SG6 | 0 | 31-1400 | 31-1400-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01065 | 0 | 0 | SG6-01065 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Excavate For Remaining Ftgs/Pier/Grade Beams --> SG6 | 10 | 0 | 100% | 2021-04-02 | 2021-05-21 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01070 | 0 | 0 | SG6-01070 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Form Remaining Ftgs/Piers/Grade Beams --> SG6 | 10 | 0 | 100% | 2021-04-19 | 2021-07-07 17:00 |  | 0 | FORMWORK | FORMWORK NB | 03-1000 | 03-1000-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01075 | 0 | 0 | SG6-01075 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Rebar Remaining Ftgs/Piers/Grade Beams --> SG6 | 10 | 0 | 100% | 2021-04-25 | 2021-07-07 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01080 | 0 | 0 | SG6-01080 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Pour Remaining Ftgs/Piers/Grade Beams --> SG6 | 5 | 0 | 100% | 2021-07-13 | 2021-07-13 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01085 | 0 | 0 | SG6-01085 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Strip Forms Remaining Ftgs/Piers/Grade Beams --> SG6 | 5 | 0 | 100% | 2021-07-14 | 2021-07-15 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01090 | 0 | 0 | SG6-01090 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Remaining Steam Into SG6 (5' from the building) | 5 | 0 | 100% | 2021-09-26 | 2021-09-30 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01095 | 0 | 0 | SG6-01095 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Backfill Remaining Ftgs/Piers/Grade Beams / Prepare Subgrade --> SG6 | 5 | 0 | 100% | 2021-05-06 | 2021-07-23 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01105 | 0 | 0 | SG6-01105 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Structural Steel Framing - 1st Floor --> SG6 | 10 | 0 | 100% | 2021-08-03 | 2021-08-11 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01110 | 0 | 0 | SG6-01110 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Metal Deck --> SG6 | 2 | 0 | 100% | 2021-08-12 08:00 | 2021-08-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01115 | 0 | 0 | SG6-01115 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Form Pour Strip Concrete Stair South Side ---> SG6 | 5 | 0 | 100% | 2021-12-06 08:00 | 2021-12-10 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01120 | 0 | 0 | SG6-01120 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Metal Stairs --> SG6 | 2 | 0 | 100% | 2021-10-18 | 2021-12-17 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01125 | 0 | 0 | SG6-01125 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Place Insulation Below First Floor --> SG6 | 5 | 0 | 100% | 2021-06-28 08:00 | 2021-07-05 17:00 |  | 0 | 0 | 0 | 07-1100 | 07-1100-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01130 | 0 | 0 | SG6-01130 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Place WWF First Floor Slab --> SG6 | 2 | 0 | 100% | 2021-07-02 08:00 | 2021-07-12 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01135 | 0 | 0 | SG6-01135 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Pour First Floor Slab --> SG6 | 1 | 0 | 100% | 2021-07-13 08:00 | 2021-07-13 17:00 |  | MLJ | concrete | NB CONCRETE | 03-1900 | 03-1900-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01150 | 0 | 0 | SG6-01150 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Form First Floor Concrete Walls First Face And Col Encasements--> SG6 | 3 | 0 | 100% | 2021-09-07 | 2021-09-20 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01155 | 0 | 0 | SG6-01155 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Rebar First Floor Concrete Walls --> SG6 | 3 | 0 | 100% | 2021-09-09 08:00 | 2021-09-22 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01160 | 0 | 0 | SG6-01160 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Form First Floor Concrete Walls 2nd Face --> SG6 | 5 | 0 | 100% | 2021-09-23 08:00 | 2021-10-05 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01165 | 0 | 0 | SG6-01165 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Form, Rebar & Pour Concrete Pads 1st Floor --> SG6 | 6 | 0 | 100% | 2021-09-01 | 2021-09-06 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01170 | 0 | 0 | SG6-01170 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Place WWF 2nd Floor Slab --> SG6 | 2 | 0 | 100% | 2021-10-06 | 2021-10-08 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01175 | 0 | 0 | SG6-01175 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Pour 2nd Floor Slab / First Floor Walls & Col Encasements --> SG6 | 5 | 0 | 100% | 2021-10-08 | 2021-10-13 |  | MLJ | concrete | NB CONCRETE | 03-1900 | 03-1900-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01180 | 0 | 0 | SG6-01180 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Strip Forms First Floor Walls & Col Encasements --> SG6 | 3 | 0 | 100% | 2021-10-11 | 2021-10-13 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01185 | 0 | 0 | SG6-01185 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Form Concrete Pads 2nd Floor -->SG6 | 2 | 0 | 100% | 2022-02-08 | 2022-02-08 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01205 | 0 | 0 | SG6-01205 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Place WWF Roof Slab --> SG6 | 2 | 0 | 100% | 2021-12-01 08:00 | 2021-12-02 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01210 | 0 | 0 | SG6-01210 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Pour Roof Slab and 2nd Floor Conc Pads -->SG6 | 1 | 0 | 100% | 2021-12-03 08:00 | 2021-12-03 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01215 | 0 | 0 | SG6-01215 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Strip Forms Concrete Pads 2nd Floor -->SG6 | 3 | 0 | 100% | 2022-02-09 | 2022-02-10 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01225 | 0 | 0 | SG6-01225 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Spray-On Fireproofing on St Stl --> SG6 | 5 | 0 | 100% | 2021-12-10 08:00 | 2021-12-23 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01230 | 0 | 0 | SG6-01230 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Place CMU 1st, 2nd Floors and Roof --> SG6 | 20 | 0 | 100% | 2021-12-21 08:00 | 2022-04-22 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01240 | 0 | 0 | SG6-01240 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Stud Framing 1st, 2nd Floors and Roof --> SG6 | 5 | 0 | 100% | 2022-05-16 | 2022-07-01 |  | CCC | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01245 | 0 | 0 | SG6-01245 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Doors --> SG6 | 3 | 2 | 33% | 2022-10-12 | 2022-12-05 17:00 | 103 | CCC | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01250 | 0 | 0 | SG6-01250 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Cast Stone Panels --> SG6 | 1 | 0 | 100% | 2022-09-12 | 2022-10-14 |  | 0 | CAST STONE | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01255 | 0 | 0 | SG6-01255 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Insulated Metal Panels/Louvers --> SG6 | 10 | 2 | 80% | 2022-06-20 | 2022-11-28 17:00 | -14 | NAVILLUS | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01260 | 0 | 0 | SG6-01260 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install MEP Roof Penetrations & Drains - SG6 | 1 | 0 | 100% | 2022-03-15 | 2022-03-15 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01265 | 0 | 0 | SG6-01265 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Roofing --> SG6 | 15 | 0 | 100% | 2022-07-18 | 2022-10-12 |  | TRIANGLE | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01270 | 0 | 0 | SG6-01270 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Dunnage Gratings --> SG6 | 2 | 0 | 100% | 2021-08-18 08:00 | 2021-08-19 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01275 | 0 | 0 | SG6-01275 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Brick Façade & Stone --> SG6 | 20 | 0 | 100% | 2022-04-22 | 2022-05-20 |  | 0 | 0 | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01285 | 0 | 0 | SG6-01285 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Flood Vents And Small Louvers --> SG6 | 3 | 3 | 0% | 2022-11-25 08:00 | 2022-11-29 17:00 | 107 | MLJ | FLOOD PROTECTION | FLOOD VENTS | 08-1700 | 08-1700-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01290 | 0 | 0 | SG6-01290 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Stair And Roof Platform Railings --> SG6 | 5 | 0 | 100% | 2022-01-26 | 2022-02-05 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01295 | 0 | 0 | SG6-01295 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Ladders --> SG6 | 3 | 0 | 100% | 2022-03-14 | 2022-03-15 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01305 | 0 | 0 | SG6-01305 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Sheetrock and Stucco --> SG6 | 10 | 0 | 100% | 2022-11-07 08:00 | 2022-11-18 17:00 |  | CCC | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01310 | 0 | 0 | SG6-01310 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Ceramic Tile --> SG6 | 2 | 0 | 100% | 2022-11-18 | 2022-11-21 |  | 0 | FLOORING | CERAMIC | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01315 | 0 | 0 | SG6-01315 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Acoustical Ceiling --> SG6 | 2 | 0 | 100% | 2022-11-17 | 2022-11-18 |  | 0 | CEILING | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01320 | 0 | 0 | SG6-01320 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Place Crystaline Waterproofing In Plumbing Shaft --> SG6 | 3 | 0 | 100% | 2022-02-16 | 2022-03-01 |  | 0 | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01325 | 0 | 0 | SG6-01325 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Paint All Areas --> SG6 | 15 | 10 | 33% | 2022-11-07 | 2022-12-15 17:00 | 95 | GG PAINT | 0 | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01330 | 0 | 0 | SG6-01330 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Signs --> SG6 | 2 | 2 | 0% | 2022-12-23 08:00 | 2022-12-27 17:00 | 90 | MLJ | SIGNS | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01235 | 0 | 0 | SG6-01235 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Waterproofing to Parapet --> SG6 | 3 | 0 | 100% | 2022-07-25 08:00 | 2022-07-29 |  | 0 | WATERPROOFING | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01280 | 0 | 0 | SG6-01280 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Stucco Soffit --> SG6 | 5 | 5 | 0% | 2022-12-02 08:00 | 2022-12-08 17:00 | 95 | CCC | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 03105 | 0 | 0 | SG6-03105 | Construction | 1st Floor | Construction.2.4.7.1 | Rough-In Plumbing Piping & Appurtenances - 1st Floor | 15 | 0 | 100% | 2021-11-28 08:00 | 2021-12-30 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.5 | SG6 | SG6 | 03005 | 0 | 0 | SG6-03005 | Construction | Foundation/Plumbing Shaft | Construction.2.4.7.5 | Rough-In Plumbing - Plumbing Shaft | 10 | 0 | 100% | 2022-03-21 | 2022-06-17 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.5 | SG6 | SG6 | 03010 | 0 | 0 | SG6-03010 | Construction | Foundation/Plumbing Shaft | Construction.2.4.7.5 | Install Condensate Pump - Foundation Level | 10 | 0 | 100% | 2022-01-17 08:00 | 2022-01-28 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 03110 | 0 | 0 | SG6-03110 | Construction | 1st Floor | Construction.2.4.7.1 | Rig Fuel Oil Tank & Piping - 1st Floor | 3 | 0 | 100% | 2021-09-21 08:00 | 2021-10-24 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 03125 | 0 | 0 | SG6-03125 | Construction | 1st Floor | Construction.2.4.7.1 | Install Remaining Piping & Appurtenances - 1st Floor | 10 | 0 | 100% | 2022-01-17 08:00 | 2022-01-28 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 03130 | 0 | 0 | SG6-03130 | Construction | 1st Floor | Construction.2.4.7.1 | Install Conduit for Controls - 1st Floor | 20 | 0 | 100% | 2022-06-13 | 2022-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 03135 | 0 | 0 | SG6-03135 | Construction | 1st Floor | Construction.2.4.7.1 | Perform Hydrostatic Testing - 1st Floor | 5 | 0 | 100% | 2022-06-27 08:00 | 2022-07-01 17:00 |  | WELKIN | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 03140 | 0 | 0 | SG6-03140 | Construction | 1st Floor | Construction.2.4.7.1 | Install Plumbing Equipment - 1st Floor | 15 | 0 | 100% | 2021-12-27 | 2022-01-11 |  | 0 | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 03145 | 0 | 0 | SG6-03145 | Construction | 1st Floor | Construction.2.4.7.1 | Mechanical Equipment Start-up & Balance - 1st Floor | 5 | 2 | 60% | 2022-06-20 | 2022-11-28 17:00 | -14 | WELKIN | 0 | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 03150 | 0 | 0 | SG6-03150 | Construction | 1st Floor | Construction.2.4.7.1 | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 0% | 2022-12-02 08:00 | 2022-12-30 17:00 | -17 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.2 | SG6 | SG6 | 03205 | 0 | 0 | SG6-03205 | Construction | 2nd Floor | Construction.2.4.7.2 | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 15 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.2 | SG6 | SG6 | 03210 | 0 | 0 | SG6-03210 | Construction | 2nd Floor | Construction.2.4.7.2 | Rig Boiler Equipment & Piping - 2nd Floor | 10 | 0 | 100% | 2021-10-28 | 2022-01-14 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.2 | SG6 | SG6 | 03225 | 0 | 0 | SG6-03225 | Construction | 2nd Floor | Construction.2.4.7.2 | Install Remaining Piping & Appurtenances - 2nd Floor | 20 | 0 | 100% | 2022-02-06 | 2022-09-23 13:48 |  | 0 | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.2 | SG6 | SG6 | 03230 | 0 | 0 | SG6-03230 | Construction | 2nd Floor | Construction.2.4.7.2 | Install Conduit for Boiler Controls - 2nd Floor | 20 | 1 | 95% | 2022-08-01 08:00 | 2022-11-28 17:00 | -14 | FSE | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.2 | SG6 | SG6 | 03235 | 0 | 0 | SG6-03235 | Construction | 2nd Floor | Construction.2.4.7.2 | Perform Hydrostatic Testing - 2nd Floor | 5 | 0 | 100% | 2022-06-20 | 2022-07-01 17:00 |  | WELKIN | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.2 | SG6 | SG6 | 03240 | 0 | 0 | SG6-03240 | Construction | 2nd Floor | Construction.2.4.7.2 | Install Plumbing Equipment - 2nd Floor - N/A | 15 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.2.4.7.2 | SG6 | SG6 | 03245 | 0 | 0 | SG6-03245 | Construction | 2nd Floor | Construction.2.4.7.2 | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 0% | 2022-12-09 08:00 | 2022-12-22 17:00 | -22 | WELKIN | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.2 | SG6 | SG6 | 03250 | 0 | 0 | SG6-03250 | Construction | 2nd Floor | Construction.2.4.7.2 | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 10 | 50% | 2022-11-21 08:00 | 2023-01-09 17:00 | -22 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.2.4.7.6 | SG6 | SG6 | 03505 | 0 | 0 | SG6-03505 | Construction | Testing & Start-Up | Construction.2.4.7.6 | DOB Mechanical/Plumbing Inspection - SG6 | 4 | 4 | 0% | 2023-01-10 08:00 | 2023-01-13 17:00 | -22 | UNSURE | INSPECTION | INSPECTION | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 03315 | 0 | 0 | SG6-03315 | Construction | Roof | Construction.2.4.7.3 | Install Insulation - Roof | 15 | 0 | 100% | 2022-09-06 08:00 | 2022-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.2.4.7.6 | SG6 | SG6 | 03510 | 0 | 0 | SG6-03510 | Construction | Testing & Start-Up | Construction.2.4.7.6 | Perform Start-Up Testing & Sign-off - Boiler - SG6 | 15 | 15 | 0% | 2023-04-26 08:00 | 2023-05-16 17:00 | -92 | UNSURE | STARTUP | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.2.4.7.6 | SG6 | SG6 | 03515 | 0 | 0 | SG6-03515 | Construction | Testing & Start-Up | Construction.2.4.7.6 | Start-Up Testing & Commissioning Mechanical/Plumbing - SG6 | 16 | 16 | 0% | 2023-05-17 08:00 | 2023-06-08 17:00 | -49 | UNSURE | STARTUP | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.2.4.7.6 | SG6 | SG6 | 03520 | 0 | 0 | SG6-03520 | Construction | Testing & Start-Up | Construction.2.4.7.6 | Perform Punch List - Electrical/Mechanical/Plumbing Work - SG6 | 5 | 5 | 0% | 2023-06-09 08:00 | 2023-06-15 17:00 | -49 | FSE | 0 | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.2.4.7.6 | SG6 | SG6 | 03530 | 0 | 0 | SG6-03530 | Construction | Testing & Start-Up | Construction.2.4.7.6 | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - SG6 | 4 | 4 | 0% | 2023-06-19 08:00 | 2023-06-22 17:00 | -23 | FSE | 0 | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.2.4.7.6 | SG6 | SG6 | 03525 | 0 | 0 | SG6-03525 | Construction | Testing & Start-Up | Construction.2.4.7.6 | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - SG6 | 1 | 1 | 0% | 2023-06-16 08:00 | 2023-06-16 17:00 | -49 | FSE | INSPECTION | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.2.2.5.1 | SG4 | SG4 | 01005 | 0 | 0 | SG4-01005 | Construction | Asbestos Abatement | Construction.2.2.5.1 | Asbestos Abatement - gaskets - cellar - SG4 | 3 | 3 | 0% | 2023-06-09 08:00 | 2023-06-13 17:00 | -41 | ATCO | ABESTOS | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.1 | SG4 | SG4 | 01010 | 0 | 0 | SG4-01010 | Construction | Asbestos Abatement | Construction.2.2.5.1 | Asbestos Abatement - wire insulation - cellar --> SG4 | 3 | 0 | 100% | 2021-09-13 08:00 | 2021-09-17 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.1 | SG4 | SG4 | 01015 | 0 | 0 | SG4-01015 | Construction | Asbestos Abatement | Construction.2.2.5.1 | Asbestos Abatement - flooring materials at slab penetrations 1st floor to cellar --> SG4 | 3 | 0 | 100% | 2021-12-21 | 2021-12-24 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.1 | SG4 | SG4 | 01020 | 0 | 0 | SG4-01020 | Construction | Asbestos Abatement | Construction.2.2.5.1 | Asbestos Abatement - pipe insulation - cellar --> SG4 | 3 | 0 | 100% | 2021-09-13 | 2021-09-17 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.1 | SG4 | SG4 | 01025 | 0 | 0 | SG4-01025 | Construction | Asbestos Abatement | Construction.2.2.5.1 | Asbestos Abatement - Window Sills - 1st Floor --> SG4 | 5 | 0 | 100% | 2021-04-05 | 2021-04-05 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.1 | SG4 | SG4 | 01030 | 0 | 0 | SG4-01030 | Construction | Asbestos Abatement | Construction.2.2.5.1 | Asbestos Abatement - caulk @ windows and areaway vents --> SG4 | 1 | 0 | 100% | 2021-04-25 | 2021-04-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.2 | SG4 | SG4 | 01105 | 0 | 0 | SG4-01105 | Construction | Interior Demolition | Construction.2.2.5.2 | Selective Demo (Plaster walls, Doors, windows, pumps etc..) - Cellar --> SG4 | 10 | 0 | 100% | 2021-06-26 | 2022-05-20 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.2 | SG4 | SG4 | 01110 | 0 | 0 | SG4-01110 | Construction | Interior Demolition | Construction.2.2.5.2 | Selective Demo (Doors, windows) - 1st Floor --> SG4 | 5 | 0 | 100% | 2021-06-26 | 2022-04-20 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.2 | SG4 | SG4 | 01115 | 0 | 0 | SG4-01115 | Construction | Interior Demolition | Construction.2.2.5.2 | Selective Demo (Areaway drain, slab, wall) --> SG4 | 10 | 0 | 100% | 2021-04-29 | 2022-05-21 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.2 | SG4 | SG4 | 01205 | 0 | 0 | SG4-01205 | Construction | Interior Demolition | Construction.2.2.5.2 | Selective Demo (Existing Ramp, railing) - 1st Floor --> SG4 | 5 | 0 | 100% | 2022-02-14 | 2022-02-17 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.2 | SG4 | SG4 | 01210 | 0 | 0 | SG4-01210 | Construction | Interior Demolition | Construction.2.2.5.2 | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> SG4 | 5 | 0 | 100% | 2021-12-28 | 2021-12-30 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.2 | SG4 | SG4 | 01215 | 0 | 0 | SG4-01215 | Construction | Interior Demolition | Construction.2.2.5.2 | Selective Demo - 2nd Floor Apartment for Electrical Room --> SG4 | 5 | 0 | 100% | 2021-09-22 | 2021-09-24 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.4 | SG4 | SG4 | 01310 | 0 | 0 | SG4-01310 | Construction | Interior Renovations | Construction.2.2.5.4 | Make openings in floor for conduit penetrations - 2nd floor apartments --> SG4 | 5 | 0 | 100% | 2021-12-28 | 2021-12-30 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.4 | SG4 | SG4 | 01315 | 0 | 0 | SG4-01315 | Construction | Interior Renovations | Construction.2.2.5.4 | Install beams below floor - 2nd floor apartments --> SG4 | 5 | 0 | 100% | 2021-10-15 | 2021-11-03 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.4 | SG4 | SG4 | 01320 | 0 | 0 | SG4-01320 | Construction | Interior Renovations | Construction.2.2.5.4 | Install FRP around floor openings - 2nd floor apartments --> SG4 | 5 | 0 | 100% | 2022-02-07 | 2022-02-09 |  | 0 | 0 | 0 | 0 | 0-SG4
In Progress | CI NYCHA Update #22.Construction.2.2.5.4 | SG4 | SG4 | 01325 | 0 | 0 | SG4-01325 | Construction | Interior Renovations | Construction.2.2.5.4 | Frame walls / install door for electrical room - 2nd floor --> SG4 | 3 | 1 | 66% | 2022-02-10 | 2022-11-25 17:00 | 94 | CCC | 0 | 0 | 0 | 0-SG4
In Progress | CI NYCHA Update #22.Construction.2.2.5.4 | SG4 | SG4 | 01330 | 0 | 0 | SG4-01330 | Construction | Interior Renovations | Construction.2.2.5.4 | Install drywall / tape / spackle - electrical room - 2nd floor --> SG4 | 5 | 1 | 80% | 2022-02-10 | 2022-11-25 17:00 | 94 | CCC | 0 | 0 | 0 | 0-SG4
In Progress | CI NYCHA Update #22.Construction.2.2.5.4 | SG4 | SG4 | 01335 | 0 | 0 | SG4-01335 | Construction | Interior Renovations | Construction.2.2.5.4 | Paint walls and seal floor electrical room - 2nd Floor --> SG4 | 10 | 1 | 90% | 2022-06-14 | 2022-11-25 17:00 | 94 | CCC | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.5.4 | SG4 | SG4 | 01340 | 0 | 0 | SG4-01340 | Construction | Interior Renovations | Construction.2.2.5.4 | Install VCT @ electrical room - 2nd Floor --> SG4 | 2 | 2 | 0% | 2022-12-09 08:00 | 2022-12-12 17:00 | 85 | UNSURE | FLOORING | VCT | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.1 | SG4 | SG4 | 01405 | 0 | 0 | SG4-01405 | Construction | East Elevation | Construction.2.2.5.EFPC.1 | Excavate at Curtain Wall for flood protection (East Side) --> SG4 | 8 | 0 | 100% | 2022-01-20 | 2022-02-18 |  | 0 | EXCAVATION | 0 | 31-1000 | 31-1000-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.1 | SG4 | SG4 | 01410 | 0 | 0 | SG4-01410 | Construction | East Elevation | Construction.2.2.5.EFPC.1 | Form concrete footings at Curtain Wall for flood protection (East Side) --> SG4 | 10 | 0 | 100% | 2022-02-14 | 2022-02-23 |  | 0 | FORMWORK | FORMWORK EB | 03-1100 | 03-1100-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.1 | SG4 | SG4 | 01415 | 0 | 0 | SG4-01415 | Construction | East Elevation | Construction.2.2.5.EFPC.1 | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> SG4 | 5 | 0 | 100% | 2022-02-02 | 2022-02-23 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.1 | SG4 | SG4 | 01420 | 0 | 0 | SG4-01420 | Construction | East Elevation | Construction.2.2.5.EFPC.1 | Pour concrete footings at Curtain Wall for flood protection (East Side) --> SG4 | 4 | 0 | 100% | 2022-02-24 | 2022-02-24 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.1 | SG4 | SG4 | 01425 | 0 | 0 | SG4-01425 | Construction | East Elevation | Construction.2.2.5.EFPC.1 | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> SG4 | 5 | 0 | 100% | 2022-02-28 | 2022-03-04 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.1 | SG4 | SG4 | 01430 | 0 | 0 | SG4-01430 | Construction | East Elevation | Construction.2.2.5.EFPC.1 | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG4 | 8 | 0 | 100% | 2022-03-07 | 2022-03-12 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.1 | SG4 | SG4 | 01435 | 0 | 0 | SG4-01435 | Construction | East Elevation | Construction.2.2.5.EFPC.1 | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG4 | 6 | 0 | 100% | 2022-03-14 | 2022-03-19 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.1 | SG4 | SG4 | 01440 | 0 | 0 | SG4-01440 | Construction | East Elevation | Construction.2.2.5.EFPC.1 | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG4 | 4 | 0 | 100% | 2022-03-21 | 2022-03-21 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.1 | SG4 | SG4 | 01445 | 0 | 0 | SG4-01445 | Construction | East Elevation | Construction.2.2.5.EFPC.1 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG4 | 4 | 0 | 100% | 2022-03-23 | 2022-04-21 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.1 | SG4 | SG4 | 01450 | 0 | 0 | SG4-01450 | Construction | East Elevation | Construction.2.2.5.EFPC.1 | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> SG4 | 4 | 0 | 100% | 2022-05-17 | 2022-06-15 |  | FAXA | CMU | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.1 | SG4 | SG4 | 01455 | 0 | 0 | SG4-01455 | Construction | East Elevation | Construction.2.2.5.EFPC.1 | Backfill at Curtain Wall for flood protection (East Side) --> SG4 | 5 | 0 | 100% | 2022-05-25 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.1 | SG4 | SG4 | 01460 | 0 | 0 | SG4-01460 | Construction | East Elevation | Construction.2.2.5.EFPC.1 | Form for slab at Curtain Wall for flood protection (East Side) --> SG4 | 4 | 0 | 100% | 2022-06-27 | 2022-07-08 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.1 | SG4 | SG4 | 01465 | 0 | 0 | SG4-01465 | Construction | East Elevation | Construction.2.2.5.EFPC.1 | Rebar & inserts for slab at Curtain Wall for flood protection (East Side) --> SG4 | 6 | 0 | 100% | 2022-07-19 | 2022-07-22 |  | 0 | REBAR | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.1 | SG4 | SG4 | 01470 | 0 | 0 | SG4-01470 | Construction | East Elevation | Construction.2.2.5.EFPC.1 | Pour slab at Curtain Wall for flood protection (East Side) --> SG4 | 4 | 0 | 100% | 2022-08-10 | 2022-08-12 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.1 | SG4 | SG4 | 01475 | 0 | 0 | SG4-01475 | Construction | East Elevation | Construction.2.2.5.EFPC.1 |  | 2 | 0 | 100% | 2022-08-15 | 2022-08-16 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.1 | SG4 | SG4 | 01480 | 0 | 0 | SG4-01480 | Construction | East Elevation | Construction.2.2.5.EFPC.1 | Backfill surounding area at Curtain Wall for flood protection (East Side) --> SG4 | 4 | 0 | 100% | 2022-08-17 | 2022-08-18 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG4
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01840 | 0 | 0 | 0 | 01840 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Prepare & Submit Surveyor | 5 | 0 | 100% | 2020-07-13 | 2020-07-13 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01845 | 0 | 0 | 0 | 01845 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Review & Approve Surveyor | 10 | 0 | 100% | 2020-07-14 | 2022-03-11 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Construction.2.5.Removals | SGN | SGN | 01090 | 0 | 0 | SGN-01090 | Construction | Site Protection & Removals | Construction.2.5.Removals | Activate Dewatering System | 1 | 0 | 100% | 2021-05-25 | 2021-05-25 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.Removals | SGN | SGN | 01095 | 0 | 0 | SGN-01095 | Construction | Site Protection & Removals | Construction.2.5.Removals | Maintain Dewatering | 232 | 0 | 100% | 2021-05-25 | 2021-05-25 |  | 0 | dewatering | 0 | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.5 | SGN | SGN | 01690 | 0 | 0 | SGN-01690 | Construction | Site Restoration | Construction.2.5.5 | Demobilize from SGN | 5 | 5 | 0% | 2023-07-26 08:00 | 2023-08-01 17:00 | -45 | MLJ | DEMOB | 0 | 99-4000 | 99-4000-SGN
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.2 | SG4 | SG4 | 01505 | 0 | 0 | SG4-01505 | Construction | South Elevation | Construction.2.2.5.EFPC.2 | Excavate at Curtain Wall for flood protection (South Side) --> SG4 | 8 | 0 | 100% | 2022-01-20 | 2022-02-18 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.2 | SG4 | SG4 | 01510 | 0 | 0 | SG4-01510 | Construction | South Elevation | Construction.2.2.5.EFPC.2 | Form concrete footings at Curtain Wall for flood protection (South Side) --> SG4 | 10 | 0 | 100% | 2022-02-14 | 2022-02-23 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.2 | SG4 | SG4 | 01515 | 0 | 0 | SG4-01515 | Construction | South Elevation | Construction.2.2.5.EFPC.2 | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> SG4 | 5 | 0 | 100% | 2022-02-02 | 2022-02-23 08:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.2 | SG4 | SG4 | 01520 | 0 | 0 | SG4-01520 | Construction | South Elevation | Construction.2.2.5.EFPC.2 | Pour concrete footings at Curtain Wall for flood protection (South Side) --> SG4 | 4 | 0 | 100% | 2022-02-24 | 2022-02-24 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.2 | SG4 | SG4 | 01525 | 0 | 0 | SG4-01525 | Construction | South Elevation | Construction.2.2.5.EFPC.2 | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> SG4 | 5 | 0 | 100% | 2022-02-28 | 2022-03-04 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.2 | SG4 | SG4 | 01530 | 0 | 0 | SG4-01530 | Construction | South Elevation | Construction.2.2.5.EFPC.2 | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG4 | 8 | 0 | 100% | 2022-03-07 | 2022-03-12 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.2 | SG4 | SG4 | 01535 | 0 | 0 | SG4-01535 | Construction | South Elevation | Construction.2.2.5.EFPC.2 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG4 | 6 | 0 | 100% | 2022-03-14 | 2022-03-19 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.2 | SG4 | SG4 | 01540 | 0 | 0 | SG4-01540 | Construction | South Elevation | Construction.2.2.5.EFPC.2 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG4 | 4 | 0 | 100% | 2022-03-21 | 2022-03-21 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.2 | SG4 | SG4 | 01545 | 0 | 0 | SG4-01545 | Construction | South Elevation | Construction.2.2.5.EFPC.2 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG4 | 4 | 0 | 100% | 2022-03-23 | 2022-04-20 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.2 | SG4 | SG4 | 01550 | 0 | 0 | SG4-01550 | Construction | South Elevation | Construction.2.2.5.EFPC.2 | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> SG4 (Waterproofing Delay) | 4 | 0 | 100% | 2022-05-19 | 2022-09-16 |  | FAXA | CMU | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.2 | SG4 | SG4 | 01555 | 0 | 0 | SG4-01555 | Construction | South Elevation | Construction.2.2.5.EFPC.2 | Backfill at Curtain Wall for flood protection (South Side) --> SG4 | 5 | 0 | 100% | 2022-03-07 | 2022-03-12 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.2 | SG4 | SG4 | 01560 | 0 | 0 | SG4-01560 | Construction | South Elevation | Construction.2.2.5.EFPC.2 | Form for slab at Curtain Wall for flood protection (South Side) --> SG4 | 4 | 0 | 100% | 2022-03-14 | 2022-03-19 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.2 | SG4 | SG4 | 01565 | 0 | 0 | SG4-01565 | Construction | South Elevation | Construction.2.2.5.EFPC.2 | Rebar & inserts for slab at Curtain Wall for flood protection (South Side) --> SG4 | 6 | 0 | 100% | 2022-03-14 | 2022-03-19 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.2 | SG4 | SG4 | 01570 | 0 | 0 | SG4-01570 | Construction | South Elevation | Construction.2.2.5.EFPC.2 | Pour slab at Curtain Wall for flood protection (South Side) --> SG4 | 4 | 0 | 100% | 2022-03-21 | 2022-03-21 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.2 | SG4 | SG4 | 01575 | 0 | 0 | SG4-01575 | Construction | South Elevation | Construction.2.2.5.EFPC.2 | Strip Forms for slab at Curtain Wall for flood protection (South Side) --> SG4 | 2 | 0 | 100% | 2022-03-23 | 2022-04-20 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.2 | SG4 | SG4 | 01580 | 0 | 0 | SG4-01580 | Construction | South Elevation | Construction.2.2.5.EFPC.2 | Backfill surounding area at Curtain Wall for flood protection (South Side) --> SG4 | 4 | 0 | 100% | 2022-05-25 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.3 | SG4 | SG4 | 01605 | 0 | 0 | SG4-01605 | Construction | North Elevation | Construction.2.2.5.EFPC.3 | Excavate at Curtain Wall for flood protection (North Side) --> SG4 | 8 | 0 | 100% | 2022-03-18 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.3 | SG4 | SG4 | 01610 | 0 | 0 | SG4-01610 | Construction | North Elevation | Construction.2.2.5.EFPC.3 | Form concrete footings at Curtain Wall for flood protection (North Side) --> SG4 | 10 | 0 | 100% | 2022-03-21 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.3 | SG4 | SG4 | 01615 | 0 | 0 | SG4-01615 | Construction | North Elevation | Construction.2.2.5.EFPC.3 | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> SG4 | 5 | 0 | 100% | 2022-03-23 | 2022-03-31 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.3 | SG4 | SG4 | 01620 | 0 | 0 | SG4-01620 | Construction | North Elevation | Construction.2.2.5.EFPC.3 | Pour concrete footings at Curtain Wall for flood protection (North Side) --> SG4 | 4 | 0 | 100% | 2022-04-15 | 2022-04-15 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.3 | SG4 | SG4 | 01625 | 0 | 0 | SG4-01625 | Construction | North Elevation | Construction.2.2.5.EFPC.3 | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> SG4 | 5 | 0 | 100% | 2022-04-18 | 2022-04-18 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.3 | SG4 | SG4 | 01630 | 0 | 0 | SG4-01630 | Construction | North Elevation | Construction.2.2.5.EFPC.3 | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG4 | 8 | 0 | 100% | 2022-04-22 | 2022-05-25 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.3 | SG4 | SG4 | 01635 | 0 | 0 | SG4-01635 | Construction | North Elevation | Construction.2.2.5.EFPC.3 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG4 | 6 | 0 | 100% | 2022-04-25 | 2022-04-30 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.3 | SG4 | SG4 | 01640 | 0 | 0 | SG4-01640 | Construction | North Elevation | Construction.2.2.5.EFPC.3 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG4 | 4 | 0 | 100% | 2022-04-30 | 2022-05-01 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.3 | SG4 | SG4 | 01645 | 0 | 0 | SG4-01645 | Construction | North Elevation | Construction.2.2.5.EFPC.3 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG4 | 4 | 0 | 100% | 2022-05-06 | 2022-05-08 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.3 | SG4 | SG4 | 01650 | 0 | 0 | SG4-01650 | Construction | North Elevation | Construction.2.2.5.EFPC.3 | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> SG4 (Waterproofing Delay) | 4 | 0 | 100% | 2022-05-24 | 2022-09-16 |  | FAXA | CMU | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.3 | SG4 | SG4 | 01655 | 0 | 0 | SG4-01655 | Construction | North Elevation | Construction.2.2.5.EFPC.3 | Backfill at Curtain Wall for flood protection (North Side) --> SG4 | 5 | 0 | 100% | 2022-05-09 | 2022-05-13 |  | 0 | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.5.EFPC.3 | SG4 | SG4 | 01660 | 0 | 0 | SG4-01660 | Construction | North Elevation | Construction.2.2.5.EFPC.3 | Form for slab at Curtain Wall for flood protection (North Side) --> SG4 | 4 | 4 | 0% | 2022-11-25 08:00 | 2022-11-30 17:00 | 73 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.5.EFPC.3 | SG4 | SG4 | 01665 | 0 | 0 | SG4-01665 | Construction | North Elevation | Construction.2.2.5.EFPC.3 | Rebar & inserts for slab at Curtain Wall for flood protection (North Side) --> SG4 | 6 | 6 | 0% | 2022-12-01 08:00 | 2022-12-08 17:00 | 73 | TONAGE | REBAR | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.5.EFPC.3 | SG4 | SG4 | 01670 | 0 | 0 | SG4-01670 | Construction | North Elevation | Construction.2.2.5.EFPC.3 | Pour slab at Curtain Wall for flood protection (North Side) --> SG4 | 4 | 4 | 0% | 2022-12-09 08:00 | 2022-12-14 17:00 | 73 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.5.EFPC.3 | SG4 | SG4 | 01675 | 0 | 0 | SG4-01675 | Construction | North Elevation | Construction.2.2.5.EFPC.3 | Strip Forms for slab at Curtain Wall for flood protection (North Side) --> SG4 | 2 | 2 | 0% | 2022-12-15 08:00 | 2022-12-16 17:00 | 76 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.5.EFPC.3 | SG4 | SG4 | 01680 | 0 | 0 | SG4-01680 | Construction | North Elevation | Construction.2.2.5.EFPC.3 | Backfill surounding area at Curtain Wall for flood protection (North Side) --> SG4 | 4 | 4 | 0% | 2022-12-22 08:00 | 2022-12-28 17:00 | 73 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.4 | SG4 | SG4 | 01705 | 0 | 0 | SG4-01705 | Construction | West Elevation | Construction.2.2.5.EFPC.4 | Excavate at Curtain Wall for flood protection (West Side) --> SG4 | 8 | 0 | 100% | 2022-01-20 | 2022-02-18 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.4 | SG4 | SG4 | 01710 | 0 | 0 | SG4-01710 | Construction | West Elevation | Construction.2.2.5.EFPC.4 | Form concrete footings at Curtain Wall for flood protection (West Side) --> SG4 | 10 | 0 | 100% | 2022-02-14 | 2022-02-23 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.4 | SG4 | SG4 | 01715 | 0 | 0 | SG4-01715 | Construction | West Elevation | Construction.2.2.5.EFPC.4 | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> SG4 | 5 | 0 | 100% | 2022-02-02 | 2022-02-23 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.4 | SG4 | SG4 | 01720 | 0 | 0 | SG4-01720 | Construction | West Elevation | Construction.2.2.5.EFPC.4 | Pour concrete footings at Curtain Wall for flood protection (West Side) --> SG4 | 4 | 0 | 100% | 2022-02-24 | 2022-02-24 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.4 | SG4 | SG4 | 01725 | 0 | 0 | SG4-01725 | Construction | West Elevation | Construction.2.2.5.EFPC.4 | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> SG4 | 5 | 0 | 100% | 2022-04-15 | 2022-04-20 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.4 | SG4 | SG4 | 01730 | 0 | 0 | SG4-01730 | Construction | West Elevation | Construction.2.2.5.EFPC.4 | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG4 | 8 | 0 | 100% | 2022-03-07 | 2022-03-12 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.4 | SG4 | SG4 | 01735 | 0 | 0 | SG4-01735 | Construction | West Elevation | Construction.2.2.5.EFPC.4 | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG4 | 6 | 0 | 100% | 2022-03-14 | 2022-03-19 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.4 | SG4 | SG4 | 01740 | 0 | 0 | SG4-01740 | Construction | West Elevation | Construction.2.2.5.EFPC.4 | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG4 | 4 | 0 | 100% | 2022-03-21 | 2022-03-21 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.4 | SG4 | SG4 | 01745 | 0 | 0 | SG4-01745 | Construction | West Elevation | Construction.2.2.5.EFPC.4 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG4 | 4 | 0 | 100% | 2022-03-23 | 2022-04-20 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.4 | SG4 | SG4 | 01750 | 0 | 0 | SG4-01750 | Construction | West Elevation | Construction.2.2.5.EFPC.4 | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> SG4 | 4 | 0 | 100% | 2022-09-01 | 2022-09-05 |  | FAXA | CMU | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.4 | SG4 | SG4 | 01755 | 0 | 0 | SG4-01755 | Construction | West Elevation | Construction.2.2.5.EFPC.4 | Backfill at Curtain Wall for flood protection (West Side) --> SG4 | 5 | 0 | 100% | 2022-09-05 | 2022-09-08 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.4 | SG4 | SG4 | 01760 | 0 | 0 | SG4-01760 | Construction | West Elevation | Construction.2.2.5.EFPC.4 | Form for slab at Curtain Wall for flood protection (West Side) --> SG4 | 4 | 0 | 100% | 2022-08-09 | 2022-08-12 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.5.EFPC.4 | SG4 | SG4 | 01765 | 0 | 0 | SG4-01765 | Construction | West Elevation | Construction.2.2.5.EFPC.4 | Rebar & inserts for slab at Curtain Wall for flood protection (West Side) --> SG4 | 6 | 6 | 0% | 2022-11-25 08:00 | 2022-12-02 17:00 | 77 | TONAGE | REBAR | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.5.EFPC.4 | SG4 | SG4 | 01770 | 0 | 0 | SG4-01770 | Construction | West Elevation | Construction.2.2.5.EFPC.4 | Pour slab at Curtain Wall for flood protection (West Side) --> SG4 | 4 | 4 | 0% | 2022-12-05 08:00 | 2022-12-08 17:00 | 77 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.5.EFPC.4 | SG4 | SG4 | 01775 | 0 | 0 | SG4-01775 | Construction | West Elevation | Construction.2.2.5.EFPC.4 | Strip Forms for slab at Curtain Wall for flood protection (West Side) --> SG4 | 2 | 2 | 0% | 2022-12-09 08:00 | 2022-12-12 17:00 | 80 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.5.EFPC.4 | SG4 | SG4 | 01780 | 0 | 0 | SG4-01780 | Construction | West Elevation | Construction.2.2.5.EFPC.4 | Backfill surounding area at Curtain Wall for flood protection (West Side) --> SG4 | 4 | 4 | 0% | 2022-12-16 08:00 | 2022-12-21 17:00 | 77 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 03005 | 0 | 0 | SG4-03005 | Construction | Cellar | Construction.2.2.6.1 | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 100% | 2021-02-08 | 2021-06-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 03010 | 0 | 0 | SG4-03010 | Construction | Cellar | Construction.2.2.6.1 | Install Condensate Pump - Cellar | 10 | 0 | 100% | 2022-06-13 | 2022-06-23 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 03020 | 0 | 0 | SG4-03020 | Construction | Cellar | Construction.2.2.6.1 | Install Pump Controls - Cellar | 20 | 0 | 100% | 2022-06-13 | 2022-06-23 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 03025 | 0 | 0 | SG4-03025 | Construction | Cellar | Construction.2.2.6.1 | Perform Hydrostatic Testing - Cellar | 5 | 0 | 100% | 2022-08-01 08:00 | 2022-08-08 17:00 |  | WELKIN | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 03030 | 0 | 0 | SG4-03030 | Construction | Cellar | Construction.2.2.6.1 | Install Plumbing Equipment - Cellar | 15 | 0 | 100% | 2022-05-26 | 2022-06-22 |  | 0 | 0 | 0 | 0 | 0-SG4
In Progress | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 03035 | 0 | 0 | SG4-03035 | Construction | Cellar | Construction.2.2.6.1 | Pump Equipment Start-up & Balance - Cellar | 10 | 5 | 50% | 2022-06-22 | 2022-12-01 17:00 | 2 | UNSURE | STARTUP | 0 | 0 | 0-SG4
In Progress | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 03040 | 0 | 0 | SG4-03040 | Construction | Cellar | Construction.2.2.6.1 | Plumbing/Mechanical Insulation - Cellar | 20 | 1 | 95% | 2022-11-01 08:00 | 2022-12-02 17:00 | 2 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 03015 | 0 | 0 | SG4-03015 | Construction | Cellar | Construction.2.2.6.1 | Install Steam Traps - Cellar | 2 | 0 | 100% | 2021-04-14 | 2022-01-26 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.2 | SG4 | SG4 | 03105 | 0 | 0 | SG4-03105 | Construction | 1st Floor | Construction.2.2.6.2 | Rough-In Plumbing Piping & Appurtenances - 1st Floor - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-SG4
In Progress | CI NYCHA Update #22.Construction.2.2.6.2 | SG4 | SG4 | 03120 | 0 | 0 | SG4-03120 | Construction | 1st Floor | Construction.2.2.6.2 | Install HVAC Controls - 1st Floor | 20 | 15 | 25% | 2022-10-21 | 2023-01-10 15:00 | -58 | WELKIN | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.2 | SG4 | SG4 | 03125 | 0 | 0 | SG4-03125 | Construction | 1st Floor | Construction.2.2.6.2 | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 0% | 2023-01-10 15:00 | 2023-01-18 15:00 | -58 | WELKIN | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.2 | SG4 | SG4 | 03130 | 0 | 0 | SG4-03130 | Construction | 1st Floor | Construction.2.2.6.2 | Install Mechanical Louvers - 1st Floor | 15 | 15 | 0% | 2022-11-25 15:00 | 2022-12-16 15:00 | -83 | UNSURE | MECHANICAL LOUVERS | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.2 | SG4 | SG4 | 03135 | 0 | 0 | SG4-03135 | Construction | 1st Floor | Construction.2.2.6.2 | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 0% | 2023-01-18 15:00 | 2023-02-01 15:00 | -58 | WELKIN | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.2 | SG4 | SG4 | 03140 | 0 | 0 | SG4-03140 | Construction | 1st Floor | Construction.2.2.6.2 | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 0% | 2023-02-01 15:00 | 2023-03-02 15:00 | -58 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.2 | SG4 | SG4 | 03115 | 0 | 0 | SG4-03115 | Construction | 1st Floor | Construction.2.2.6.2 | Install Steam Traps - 1st Floor | 1 | 0 | 100% | 2022-01-26 | 2022-01-28 |  | 0 | 0 | 0 | 0 | 0-SG4
In Progress | CI NYCHA Update #22.Construction.2.2.6.2 | SG4 | SG4 | 03110 | 0 | 0 | SG4-03110 | Construction | 1st Floor | Construction.2.2.6.2 | Install Ductwork and Appurtenances - 1st Floor | 5 | 1 | 85% | 2021-05-19 | 2022-11-25 15:00 | -83 | WELKIN | DUCTWORK | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.2 | SG4 | SG4 | 03112 | 0 | 0 | SG4-03112 | Construction | 1st Floor | Construction.2.2.6.2 | Install HV & EF Units - 1st Floor | 5 | 0 | 100% | 2021-12-26 | 2022-09-27 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 03205 | 0 | 0 | SG4-03205 | Construction | 2nd Floor | Construction.2.2.6.3 | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 10 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 03220 | 0 | 0 | SG4-03220 | Construction | 2nd Floor | Construction.2.2.6.3 | Install HVAC Controls - 2nd Floor | 20 | 20 | 0% | 2023-01-25 15:00 | 2023-02-23 15:00 | -83 | WELKIN | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 03230 | 0 | 0 | SG4-03230 | Construction | 2nd Floor | Construction.2.2.6.3 | Install Mechanical Louvers - 2nd Floor | 15 | 15 | 0% | 2023-01-03 15:00 | 2023-01-25 15:00 | -83 | UNSURE | MECHANICAL LOUVERS | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 03235 | 0 | 0 | SG4-03235 | Construction | 2nd Floor | Construction.2.2.6.3 | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 0% | 2023-02-23 15:00 | 2023-03-09 15:00 | -83 | WELKIN | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 03240 | 0 | 0 | SG4-03240 | Construction | 2nd Floor | Construction.2.2.6.3 | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 0% | 2023-03-09 15:00 | 2023-04-06 15:00 | -83 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 03210 | 0 | 0 | SG4-03210 | Construction | 2nd Floor | Construction.2.2.6.3 | Install Ductwork and Appurtenances - 2nd Floor | 5 | 5 | 0% | 2022-12-16 15:00 | 2022-12-23 15:00 | -83 | WELKIN | DUCTWORK | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.3 | SG4 | SG4 | 03215 | 0 | 0 | SG4-03215 | Construction | 2nd Floor | Construction.2.2.6.3 | Install EF Units - 2nd Floor | 5 | 5 | 0% | 2022-12-23 15:00 | 2023-01-03 15:00 | -83 | MEP | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.4 | SG4 | SG4 | 03305 | 0 | 0 | SG4-03305 | Construction | Testing & Start-Up | Construction.2.2.6.4 | DOB Mechanical/Plumbing Inspection - SG4 | 4 | 4 | 0% | 2023-04-06 15:00 | 2023-04-12 15:00 | -83 | UNSURE | INSPECTION | INSPECTION | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.4 | SG4 | SG4 | 03310 | 0 | 0 | SG4-03310 | Construction | Testing & Start-Up | Construction.2.2.6.4 | Perform Start-Up Testing - SG4 | 15 | 15 | 0% | 2023-04-26 08:00 | 2023-05-16 17:00 | -92 | UNSURE | STARTUP | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.4 | SG4 | SG4 | 03315 | 0 | 0 | SG4-03315 | Construction | Testing & Start-Up | Construction.2.2.6.4 | Start-Up Testing & Commissioning Mechanical/Plumbing - SG4 | 16 | 16 | 0% | 2023-05-17 08:00 | 2023-06-08 17:00 | -41 | UNSURE | STARTUP | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.4 | SG4 | SG4 | 03320 | 0 | 0 | SG4-03320 | Construction | Testing & Start-Up | Construction.2.2.6.4 | Perform Punch List - Electrical/Mechanical/Plumbing Work - SG4 | 5 | 5 | 0% | 2023-06-09 08:00 | 2023-06-15 17:00 | -23 | FSE | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.4 | SG4 | SG4 | 03330 | 0 | 0 | SG4-03330 | Construction | Testing & Start-Up | Construction.2.2.6.4 | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - SG4 | 4 | 4 | 0% | 2023-06-19 08:00 | 2023-06-22 17:00 | -23 | FSE | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.6.4 | SG4 | SG4 | 03325 | 0 | 0 | SG4-03325 | Construction | Testing & Start-Up | Construction.2.2.6.4 | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - SG4 | 1 | 1 | 0% | 2023-06-16 08:00 | 2023-06-16 17:00 | -23 | FSE | INSPECTION | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.3.5.1 | SG5 | SG5 | 01005 | 0 | 0 | SG5-01005 | Construction | Asbestos Abatement | Construction.2.3.5.1 | Asbestos Abatement - gaskets - cellar - SG5 | 3 | 0 | 100% | 2021-06-14 | 2021-06-24 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.1 | SG5 | SG5 | 01010 | 0 | 0 | SG5-01010 | Construction | Asbestos Abatement | Construction.2.3.5.1 | Asbestos Abatement - wire insulation - cellar --> SG5 | 3 | 0 | 100% | 2021-06-14 | 2021-06-24 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.1 | SG5 | SG5 | 01015 | 0 | 0 | SG5-01015 | Construction | Asbestos Abatement | Construction.2.3.5.1 | Asbestos Abatement - flooring materials at slab penetrations - cellar --> SG5 | 3 | 0 | 100% | 2021-06-14 | 2021-06-24 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.1 | SG5 | SG5 | 01020 | 0 | 0 | SG5-01020 | Construction | Asbestos Abatement | Construction.2.3.5.1 | Asbestos Abatement - pipe insulation - cellar --> SG5 | 3 | 0 | 100% | 2021-06-14 | 2021-06-24 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.1 | SG5 | SG5 | 01025 | 0 | 0 | SG5-01025 | Construction | Asbestos Abatement | Construction.2.3.5.1 | Asbestos Abatement - Window Sills - 1st Floor --> SG5 | 5 | 0 | 100% | 2021-06-14 | 2021-06-24 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.1 | SG5 | SG5 | 01030 | 0 | 0 | SG5-01030 | Construction | Asbestos Abatement | Construction.2.3.5.1 | Asbestos Abatement - caulk @ windows and areaway vents --> SG5 | 5 | 0 | 100% | 2021-04-25 | 2021-04-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.2 | SG5 | SG5 | 01105 | 0 | 0 | SG5-01105 | Construction | Interior Demolition | Construction.2.3.5.2 | Selective Demo (Plaster walls, Doors,Windows) - Cellar --> SG5 | 10 | 0 | 100% | 2021-04-25 | 2022-04-01 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.2 | SG5 | SG5 | 01110 | 0 | 0 | SG5-01110 | Construction | Interior Demolition | Construction.2.3.5.2 | Selective Demo (Doors, windows) - 1st Floor --> SG5 | 5 | 0 | 100% | 2021-06-30 08:00 | 2022-04-15 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.2 | SG5 | SG5 | 01115 | 0 | 0 | SG5-01115 | Construction | Interior Demolition | Construction.2.3.5.2 | Selective Demo (Areaway drain, slab, wall) --> SG5 | 10 | 0 | 100% | 2021-10-10 | 2022-01-14 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.2 | SG5 | SG5 | 01205 | 0 | 0 | SG5-01205 | Construction | Interior Demolition | Construction.2.3.5.2 | Selective Demo (Existing Ramp, railing) - 1st Floor --> SG5 | 5 | 0 | 100% | 2022-02-21 | 2022-02-24 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.2 | SG5 | SG5 | 01210 | 0 | 0 | SG5-01210 | Construction | Interior Demolition | Construction.2.3.5.2 | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> SG5 | 5 | 0 | 100% | 2022-03-29 | 2022-03-31 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.2 | SG5 | SG5 | 01215 | 0 | 0 | SG5-01215 | Construction | Interior Demolition | Construction.2.3.5.2 | Selective Demo - 2nd Floor Apartment for Electrical Room --> SG5 | 5 | 0 | 100% | 2022-09-13 | 2022-09-16 |  | MLJ | DEMO | DEMO 2ND FLOOR | 02-6060 | 02-6060-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.4 | SG5 | SG5 | 01310 | 0 | 0 | SG5-01310 | Construction | Interior Renovations | Construction.2.3.5.4 | Make openings in floor for conduit penetrations - 2nd floor apartments --> SG5 | 5 | 0 | 100% | 2022-09-20 | 2022-09-23 |  | MLJ | CORE DRILL | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.4 | SG5 | SG5 | 01315 | 0 | 0 | SG5-01315 | Construction | Interior Renovations | Construction.2.3.5.4 | Install beams below floor - 2nd floor apartments --> SG5 | 5 | 0 | 100% | 2021-12-20 08:00 | 2022-04-15 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.4 | SG5 | SG5 | 01320 | 0 | 0 | SG5-01320 | Construction | Interior Renovations | Construction.2.3.5.4 | Install FRP around floor openings - 2nd floor apartments --> SG5 | 5 | 0 | 100% | 2022-03-21 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-SG5
In Progress | CI NYCHA Update #22.Construction.2.3.5.4 | SG5 | SG5 | 01325 | 0 | 0 | SG5-01325 | Construction | Interior Renovations | Construction.2.3.5.4 | Frame walls / install door for electrical room - 2nd floor --> SG5 | 3 | 1 | 66% | 2022-09-15 | 2022-11-25 17:00 | -16 | CCC | 0 | 0 | 0 | 0-SG5
In Progress | CI NYCHA Update #22.Construction.2.3.5.4 | SG5 | SG5 | 01330 | 0 | 0 | SG5-01330 | Construction | Interior Renovations | Construction.2.3.5.4 | Install drywall / tape / spackle - electrical room - 2nd floor --> SG5 | 5 | 1 | 80% | 2022-09-20 | 2022-11-25 17:00 | -16 | CCC | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.4 | SG5 | SG5 | 01335 | 0 | 0 | SG5-01335 | Construction | Interior Renovations | Construction.2.3.5.4 | Paint walls and seal floor electrical room - 2nd Floor --> SG5 | 10 | 10 | 0% | 2022-11-28 08:00 | 2022-12-09 17:00 | 84 | CCC | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.4 | SG5 | SG5 | 01340 | 0 | 0 | SG5-01340 | Construction | Interior Renovations | Construction.2.3.5.4 | Install VCT @ electrical room - 2nd Floor --> SG5 | 2 | 2 | 0% | 2022-12-12 08:00 | 2022-12-13 17:00 | 84 | UNSURE | FLOORING | VCT | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.1 | SG5 | SG5 | 01405 | 0 | 0 | SG5-01405 | Construction | East Elevation | Construction.2.3.5.EFPC.1 | Excavate at Curtain Wall for flood protection (East Side) --> SG5 | 8 | 0 | 100% | 2021-10-18 | 2021-12-28 |  | 0 | EXCAVATION | 0 | 31-1000 | 31-1000-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.1 | SG5 | SG5 | 01410 | 0 | 0 | SG5-01410 | Construction | East Elevation | Construction.2.3.5.EFPC.1 | Form concrete footings at Curtain Wall for flood protection (East Side) --> SG5 | 10 | 0 | 100% | 2022-02-16 | 2022-02-17 |  | 0 | FORMWORK | FORMWORK EB | 03-1100 | 03-1100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.1 | SG5 | SG5 | 01415 | 0 | 0 | SG5-01415 | Construction | East Elevation | Construction.2.3.5.EFPC.1 | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> SG5 | 5 | 0 | 100% | 2022-02-17 | 2022-02-18 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.1 | SG5 | SG5 | 01420 | 0 | 0 | SG5-01420 | Construction | East Elevation | Construction.2.3.5.EFPC.1 | Pour concrete footings at Curtain Wall for flood protection (East Side) --> SG5 | 4 | 0 | 100% | 2022-02-21 | 2022-02-21 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.1 | SG5 | SG5 | 01425 | 0 | 0 | SG5-01425 | Construction | East Elevation | Construction.2.3.5.EFPC.1 | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> SG5 | 5 | 0 | 100% | 2022-05-25 | 2022-05-27 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.1 | SG5 | SG5 | 01430 | 0 | 0 | SG5-01430 | Construction | East Elevation | Construction.2.3.5.EFPC.1 | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG5 | 8 | 0 | 100% | 2022-07-01 | 2022-07-08 17:00 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.1 | SG5 | SG5 | 01435 | 0 | 0 | SG5-01435 | Construction | East Elevation | Construction.2.3.5.EFPC.1 | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG5 | 6 | 0 | 100% | 2022-07-11 08:00 | 2022-07-12 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.1 | SG5 | SG5 | 01440 | 0 | 0 | SG5-01440 | Construction | East Elevation | Construction.2.3.5.EFPC.1 | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG5 | 4 | 0 | 100% | 2022-08-10 | 2022-08-12 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.1 | SG5 | SG5 | 01445 | 0 | 0 | SG5-01445 | Construction | East Elevation | Construction.2.3.5.EFPC.1 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG5 | 4 | 0 | 100% | 2022-08-15 | 2022-08-17 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.1 | SG5 | SG5 | 01450 | 0 | 0 | SG5-01450 | Construction | East Elevation | Construction.2.3.5.EFPC.1 | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> SG5 | 4 | 0 | 100% | 2022-05-09 | 2022-05-30 |  | FAXA | CMU | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.1 | SG5 | SG5 | 01455 | 0 | 0 | SG5-01455 | Construction | East Elevation | Construction.2.3.5.EFPC.1 | Backfill at Curtain Wall for flood protection (East Side) --> SG5 | 5 | 0 | 100% | 2022-05-26 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.1 | SG5 | SG5 | 01460 | 0 | 0 | SG5-01460 | Construction | East Elevation | Construction.2.3.5.EFPC.1 | Form for slab at Curtain Wall for flood protection (East Side) --> SG5 | 4 | 0 | 100% | 2022-09-01 | 2022-09-02 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.1 | SG5 | SG5 | 01465 | 0 | 0 | SG5-01465 | Construction | East Elevation | Construction.2.3.5.EFPC.1 | Rebar & inserts for slab at Curtain Wall for flood protection (East Side) --> SG5 | 6 | 0 | 100% | 2022-09-06 | 2022-09-08 |  | 0 | REBAR | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.1 | SG5 | SG5 | 01470 | 0 | 0 | SG5-01470 | Construction | East Elevation | Construction.2.3.5.EFPC.1 | Pour slab at Curtain Wall for flood protection (East Side) --> SG5 | 4 | 0 | 100% | 2022-09-09 | 2022-09-09 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.1 | SG5 | SG5 | 01475 | 0 | 0 | SG5-01475 | Construction | East Elevation | Construction.2.3.5.EFPC.1 | Strip Forms for slab at Curtain Wall for flood protection (East Side) --> SG5 | 2 | 0 | 100% | 2022-09-12 | 2022-09-13 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.1 | SG5 | SG5 | 01480 | 0 | 0 | SG5-01480 | Construction | East Elevation | Construction.2.3.5.EFPC.1 | Backfill surounding area at Curtain Wall for flood protection (East Side) --> SG5 | 4 | 0 | 100% | 2022-09-14 | 2022-09-15 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.2 | SG5 | SG5 | 01505 | 0 | 0 | SG5-01505 | Construction | South Elevation | Construction.2.3.5.EFPC.2 | Excavate at Curtain Wall for flood protection (South Side) --> SG5 | 8 | 0 | 100% | 2021-12-26 | 2021-12-29 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.2 | SG5 | SG5 | 01510 | 0 | 0 | SG5-01510 | Construction | South Elevation | Construction.2.3.5.EFPC.2 | Form concrete footings at Curtain Wall for flood protection (South Side) --> SG5 | 10 | 0 | 100% | 2022-07-26 | 2022-07-27 17:00 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.2 | SG5 | SG5 | 01515 | 0 | 0 | SG5-01515 | Construction | South Elevation | Construction.2.3.5.EFPC.2 | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> SG5 | 5 | 0 | 100% | 2022-07-28 08:00 | 2022-07-29 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.2 | SG5 | SG5 | 01520 | 0 | 0 | SG5-01520 | Construction | South Elevation | Construction.2.3.5.EFPC.2 | Pour concrete footings at Curtain Wall for flood protection (South Side) --> SG5 | 4 | 0 | 100% | 2022-08-01 | 2022-08-01 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.2 | SG5 | SG5 | 01525 | 0 | 0 | SG5-01525 | Construction | South Elevation | Construction.2.3.5.EFPC.2 | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> SG5 | 5 | 0 | 100% | 2022-08-02 | 2022-08-03 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.2 | SG5 | SG5 | 01530 | 0 | 0 | SG5-01530 | Construction | South Elevation | Construction.2.3.5.EFPC.2 | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG5 | 8 | 0 | 100% | 2022-07-26 08:00 | 2022-07-27 17:00 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.2 | SG5 | SG5 | 01535 | 0 | 0 | SG5-01535 | Construction | South Elevation | Construction.2.3.5.EFPC.2 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG5 | 6 | 0 | 100% | 2022-07-28 08:00 | 2022-07-29 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.2 | SG5 | SG5 | 01540 | 0 | 0 | SG5-01540 | Construction | South Elevation | Construction.2.3.5.EFPC.2 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG5 | 4 | 0 | 100% | 2022-08-01 08:00 | 2022-08-01 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.2 | SG5 | SG5 | 01545 | 0 | 0 | SG5-01545 | Construction | South Elevation | Construction.2.3.5.EFPC.2 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG5 | 4 | 0 | 100% | 2022-08-02 08:00 | 2022-08-03 17:00 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.2 | SG5 | SG5 | 01550 | 0 | 0 | SG5-01550 | Construction | South Elevation | Construction.2.3.5.EFPC.2 | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> SG5 | 4 | 0 | 100% | 2022-05-12 | 2022-09-27 17:00 |  | FAXA | CMU | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.2 | SG5 | SG5 | 01555 | 0 | 0 | SG5-01555 | Construction | South Elevation | Construction.2.3.5.EFPC.2 | Backfill at Curtain Wall for flood protection (South Side) --> SG5 | 5 | 0 | 100% | 2022-09-28 08:00 | 2022-10-04 17:00 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.2 | SG5 | SG5 | 01560 | 0 | 0 | SG5-01560 | Construction | South Elevation | Construction.2.3.5.EFPC.2 | Form for slab at Curtain Wall for flood protection (South Side) --> SG5 | 4 | 4 | 0% | 2022-11-25 08:00 | 2022-11-30 17:00 | 69 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.2 | SG5 | SG5 | 01565 | 0 | 0 | SG5-01565 | Construction | South Elevation | Construction.2.3.5.EFPC.2 | Rebar & inserts for slab at Curtain Wall for flood protection (South Side) --> SG5 | 6 | 6 | 0% | 2022-12-01 08:00 | 2022-12-08 17:00 | 69 | TONAGE | REBAR | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.2 | SG5 | SG5 | 01570 | 0 | 0 | SG5-01570 | Construction | South Elevation | Construction.2.3.5.EFPC.2 | Pour slab at Curtain Wall for flood protection (South Side) --> SG5 | 4 | 4 | 0% | 2022-12-09 08:00 | 2022-12-14 17:00 | 69 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.2 | SG5 | SG5 | 01575 | 0 | 0 | SG5-01575 | Construction | South Elevation | Construction.2.3.5.EFPC.2 | Strip Forms for slab at Curtain Wall for flood protection (South Side) --> SG5 | 2 | 2 | 0% | 2022-12-15 08:00 | 2022-12-16 17:00 | 72 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.2 | SG5 | SG5 | 01580 | 0 | 0 | SG5-01580 | Construction | South Elevation | Construction.2.3.5.EFPC.2 | Backfill surounding area at Curtain Wall for flood protection (South Side) --> SG5 | 4 | 4 | 0% | 2022-12-22 08:00 | 2022-12-28 17:00 | 69 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.3 | SG5 | SG5 | 01605 | 0 | 0 | SG5-01605 | Construction | North Elevation | Construction.2.3.5.EFPC.3 | Excavate at Curtain Wall for flood protection (North Side) --> SG5 | 8 | 0 | 100% | 2021-12-27 | 2021-12-31 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.3 | SG5 | SG5 | 01610 | 0 | 0 | SG5-01610 | Construction | North Elevation | Construction.2.3.5.EFPC.3 | Form concrete footings at Curtain Wall for flood protection (North Side) --> SG5 | 10 | 0 | 100% | 2022-02-16 | 2022-02-17 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.3 | SG5 | SG5 | 01615 | 0 | 0 | SG5-01615 | Construction | North Elevation | Construction.2.3.5.EFPC.3 | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> SG5 | 5 | 0 | 100% | 2022-02-17 | 2022-02-18 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.3 | SG5 | SG5 | 01620 | 0 | 0 | SG5-01620 | Construction | North Elevation | Construction.2.3.5.EFPC.3 | Pour concrete footings at Curtain Wall for flood protection (North Side) --> SG5 | 4 | 0 | 100% | 2022-02-21 | 2022-02-21 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.3 | SG5 | SG5 | 01625 | 0 | 0 | SG5-01625 | Construction | North Elevation | Construction.2.3.5.EFPC.3 | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> SG5 | 5 | 0 | 100% | 2022-10-25 | 2022-10-25 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.3 | SG5 | SG5 | 01630 | 0 | 0 | SG5-01630 | Construction | North Elevation | Construction.2.3.5.EFPC.3 | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG5 | 8 | 0 | 100% | 2022-10-25 | 2022-10-27 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.3 | SG5 | SG5 | 01635 | 0 | 0 | SG5-01635 | Construction | North Elevation | Construction.2.3.5.EFPC.3 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG5 | 6 | 0 | 100% | 2022-10-26 | 2022-10-26 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.3 | SG5 | SG5 | 01640 | 0 | 0 | SG5-01640 | Construction | North Elevation | Construction.2.3.5.EFPC.3 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG5 | 4 | 0 | 100% | 2022-10-28 | 2022-10-28 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.3 | SG5 | SG5 | 01645 | 0 | 0 | SG5-01645 | Construction | North Elevation | Construction.2.3.5.EFPC.3 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG5 | 4 | 0 | 100% | 2022-11-01 | 2022-11-04 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.3 | SG5 | SG5 | 01650 | 0 | 0 | SG5-01650 | Construction | North Elevation | Construction.2.3.5.EFPC.3 | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> SG5 | 4 | 4 | 0% | 2022-12-02 08:00 | 2022-12-07 17:00 | 59 | FAXA | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.3 | SG5 | SG5 | 01655 | 0 | 0 | SG5-01655 | Construction | North Elevation | Construction.2.3.5.EFPC.3 | Backfill at Curtain Wall for flood protection (North Side) --> SG5 | 5 | 5 | 0% | 2022-12-08 08:00 | 2022-12-14 17:00 | 59 | MLJ | BACKFILL | EXISTING BUILDING | 31-1100 | 31-1100-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.3 | SG5 | SG5 | 01660 | 0 | 0 | SG5-01660 | Construction | North Elevation | Construction.2.3.5.EFPC.3 | Form for slab at Curtain Wall for flood protection (North Side) --> SG5 | 4 | 4 | 0% | 2022-12-15 08:00 | 2022-12-20 17:00 | 59 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.3 | SG5 | SG5 | 01665 | 0 | 0 | SG5-01665 | Construction | North Elevation | Construction.2.3.5.EFPC.3 | Rebar & inserts for slab at Curtain Wall for flood protection (North Side) --> SG5 | 6 | 6 | 0% | 2022-12-21 08:00 | 2022-12-29 17:00 | 59 | TONAGE | REBAR | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.3 | SG5 | SG5 | 01670 | 0 | 0 | SG5-01670 | Construction | North Elevation | Construction.2.3.5.EFPC.3 | Pour slab at Curtain Wall for flood protection (North Side) --> SG5 | 4 | 4 | 0% | 2022-12-30 08:00 | 2023-01-05 17:00 | 59 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.3 | SG5 | SG5 | 01675 | 0 | 0 | SG5-01675 | Construction | North Elevation | Construction.2.3.5.EFPC.3 | Strip Forms for slab at Curtain Wall for flood protection (North Side) --> SG5 | 2 | 2 | 0% | 2023-01-06 08:00 | 2023-01-09 17:00 | 62 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.3 | SG5 | SG5 | 01680 | 0 | 0 | SG5-01680 | Construction | North Elevation | Construction.2.3.5.EFPC.3 | Backfill surounding area at Curtain Wall for flood protection (North Side) --> SG5 | 4 | 4 | 0% | 2023-01-13 08:00 | 2023-01-19 17:00 | 59 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.4 | SG5 | SG5 | 01705 | 0 | 0 | SG5-01705 | Construction | West Elevation | Construction.2.3.5.EFPC.4 | Excavate at Curtain Wall for flood protection (West Side) --> SG5 | 8 | 0 | 100% | 2021-12-28 | 2021-12-31 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.4 | SG5 | SG5 | 01710 | 0 | 0 | SG5-01710 | Construction | West Elevation | Construction.2.3.5.EFPC.4 | Form concrete footings at Curtain Wall for flood protection (West Side) --> SG5 | 10 | 0 | 100% | 2022-02-16 | 2022-02-17 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.4 | SG5 | SG5 | 01715 | 0 | 0 | SG5-01715 | Construction | West Elevation | Construction.2.3.5.EFPC.4 | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> SG5 | 5 | 0 | 100% | 2022-02-17 | 2022-02-18 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.4 | SG5 | SG5 | 01720 | 0 | 0 | SG5-01720 | Construction | West Elevation | Construction.2.3.5.EFPC.4 | Pour concrete footings at Curtain Wall for flood protection (West Side) --> SG5 | 4 | 0 | 100% | 2022-02-21 | 2022-03-21 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.4 | SG5 | SG5 | 01725 | 0 | 0 | SG5-01725 | Construction | West Elevation | Construction.2.3.5.EFPC.4 | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> SG5 | 5 | 0 | 100% | 2022-07-01 | 2022-07-08 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.4 | SG5 | SG5 | 01730 | 0 | 0 | SG5-01730 | Construction | West Elevation | Construction.2.3.5.EFPC.4 | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG5 | 8 | 0 | 100% | 2022-07-01 | 2022-07-08 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.4 | SG5 | SG5 | 01735 | 0 | 0 | SG5-01735 | Construction | West Elevation | Construction.2.3.5.EFPC.4 | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG5 | 6 | 0 | 100% | 2022-07-11 08:00 | 2022-07-12 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.4 | SG5 | SG5 | 01740 | 0 | 0 | SG5-01740 | Construction | West Elevation | Construction.2.3.5.EFPC.4 | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG5 | 4 | 0 | 100% | 2022-08-10 | 2022-08-12 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.4 | SG5 | SG5 | 01745 | 0 | 0 | SG5-01745 | Construction | West Elevation | Construction.2.3.5.EFPC.4 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG5 | 4 | 0 | 100% | 2022-08-15 | 2022-08-17 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.4 | SG5 | SG5 | 01750 | 0 | 0 | SG5-01750 | Construction | West Elevation | Construction.2.3.5.EFPC.4 | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> SG5 | 4 | 0 | 100% | 2022-05-13 | 2022-06-17 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.4 | SG5 | SG5 | 01755 | 0 | 0 | SG5-01755 | Construction | West Elevation | Construction.2.3.5.EFPC.4 | Backfill at Curtain Wall for flood protection (West Side) --> SG5 | 5 | 0 | 100% | 2022-06-20 | 2022-06-24 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.4 | SG5 | SG5 | 01760 | 0 | 0 | SG5-01760 | Construction | West Elevation | Construction.2.3.5.EFPC.4 | Form for slab at Curtain Wall for flood protection (West Side) --> SG5 | 4 | 0 | 100% | 2022-09-01 | 2022-09-02 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.4 | SG5 | SG5 | 01765 | 0 | 0 | SG5-01765 | Construction | West Elevation | Construction.2.3.5.EFPC.4 | Rebar & inserts for slab at Curtain Wall for flood protection (West Side) --> SG5 | 6 | 0 | 100% | 2022-09-06 | 2022-09-08 |  | 0 | REBAR | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.4 | SG5 | SG5 | 01770 | 0 | 0 | SG5-01770 | Construction | West Elevation | Construction.2.3.5.EFPC.4 | Pour slab at Curtain Wall for flood protection (West Side) --> SG5 | 4 | 0 | 100% | 2022-09-09 | 2022-09-09 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.4 | SG5 | SG5 | 01775 | 0 | 0 | SG5-01775 | Construction | West Elevation | Construction.2.3.5.EFPC.4 | Strip Forms for slab at Curtain Wall for flood protection (West Side) --> SG5 | 2 | 0 | 100% | 2022-09-12 | 2022-09-13 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.4 | SG5 | SG5 | 01780 | 0 | 0 | SG5-01780 | Construction | West Elevation | Construction.2.3.5.EFPC.4 | Backfill surounding area at Curtain Wall for flood protection (West Side) --> SG5 | 4 | 0 | 100% | 2022-09-14 | 2022-09-15 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 03005 | 0 | 0 | SG5-03005 | Construction | Cellar | Construction.2.3.6.1 | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 100% | 2021-09-26 | 2021-12-01 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 03010 | 0 | 0 | SG5-03010 | Construction | Cellar | Construction.2.3.6.1 | Install Condensate Pump - Cellar | 10 | 0 | 100% | 2022-07-05 | 2022-10-26 |  | WELKIN | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 03020 | 0 | 0 | SG5-03020 | Construction | Cellar | Construction.2.3.6.1 | Install Pump Controls - Cellar | 20 | 0 | 100% | 2022-09-28 | 2022-10-21 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 03025 | 0 | 0 | SG5-03025 | Construction | Cellar | Construction.2.3.6.1 | Perform Hydrostatic Testing - Cellar | 5 | 0 | 100% | 2022-08-01 08:00 | 2022-08-08 17:00 |  | WELKIN | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 03030 | 0 | 0 | SG5-03030 | Construction | Cellar | Construction.2.3.6.1 | Install Plumbing Equipment - Cellar | 15 | 0 | 100% | 2022-05-25 | 2022-06-08 |  | 0 | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 03035 | 0 | 0 | SG5-03035 | Construction | Cellar | Construction.2.3.6.1 | Mechanical Equipment Start-up & Balance - Cellar | 10 | 10 | 0% | 2022-12-09 08:00 | 2022-12-22 17:00 | -12 | WELKIN | 0 | 0 | 0 | 0-SG5
In Progress | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 03040 | 0 | 0 | SG5-03040 | Construction | Cellar | Construction.2.3.6.1 | Plumbing/Mechanical Insulation & Tag - Cellar | 20 | 1 | 95% | 2022-11-01 08:00 | 2022-12-22 17:00 | -12 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 03015 | 0 | 0 | SG5-03015 | Construction | Cellar | Construction.2.3.6.1 | Install Steam Traps - Cellar | 2 | 0 | 100% | 2021-07-26 08:00 | 2021-07-28 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.6.2 | SG5 | SG5 | 03105 | 0 | 0 | SG5-03105 | Construction | 1st Floor | Construction.2.3.6.2 | Rough-In Plumbing Piping & Appurtenances - 1st Floor - N/A | 10 | 0 | 100% | 2022-03-25 08:00 | 2022-03-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
In Progress | CI NYCHA Update #22.Construction.2.3.6.2 | SG5 | SG5 | 03120 | 0 | 0 | SG5-03120 | Construction | 1st Floor | Construction.2.3.6.2 | Install HVAC Controls - 1st Floor | 20 | 15 | 25% | 2022-10-21 | 2022-12-15 17:00 | -42 | WELKIN | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.2 | SG5 | SG5 | 03125 | 0 | 0 | SG5-03125 | Construction | 1st Floor | Construction.2.3.6.2 | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -42 | WELKIN | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.2 | SG5 | SG5 | 03130 | 0 | 0 | SG5-03130 | Construction | 1st Floor | Construction.2.3.6.2 | Install Mechanical Louvers - 1st Floor | 15 | 15 | 0% | 2022-11-25 08:00 | 2022-12-15 17:00 | -42 | UNSURE | MECHANICAL LOUVERS | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.2 | SG5 | SG5 | 03135 | 0 | 0 | SG5-03135 | Construction | 1st Floor | Construction.2.3.6.2 | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 0% | 2022-12-23 08:00 | 2023-01-09 17:00 | -42 | WELKIN | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.2 | SG5 | SG5 | 03140 | 0 | 0 | SG5-03140 | Construction | 1st Floor | Construction.2.3.6.2 | Plumbing/Mechanical Insulation & Tag- 1st Floor | 20 | 20 | 0% | 2023-01-10 08:00 | 2023-02-07 17:00 | -42 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.6.2 | SG5 | SG5 | 03115 | 0 | 0 | SG5-03115 | Construction | 1st Floor | Construction.2.3.6.2 | Install Steam Traps - 1st Floor | 1 | 0 | 100% | 2022-09-15 08:00 | 2022-09-16 17:00 |  | WELKIN | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.2 | SG5 | SG5 | 03110 | 0 | 0 | SG5-03110 | Construction | 1st Floor | Construction.2.3.6.2 | Install Ductwork and Appurtenances - 1st Floor | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -42 | WELKIN | DUCTWORK | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.6.2 | SG5 | SG5 | 03112 | 0 | 0 | SG5-03112 | Construction | 1st Floor | Construction.2.3.6.2 | Install HV & EF Units - 1st Floor | 5 | 0 | 100% | 2022-09-19 08:00 | 2022-09-30 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 03205 | 0 | 0 | SG5-03205 | Construction | 2nd Floor | Construction.2.3.6.3 | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 10 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 03220 | 0 | 0 | SG5-03220 | Construction | 2nd Floor | Construction.2.3.6.3 | Install HVAC Controls - 2nd Floor | 15 | 15 | 0% | 2023-01-03 08:00 | 2023-01-24 17:00 | -52 | WELKIN | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 03230 | 0 | 0 | SG5-03230 | Construction | 2nd Floor | Construction.2.3.6.3 | Install Mechanical Louvers - 2nd Floor | 15 | 15 | 0% | 2022-11-25 08:00 | 2022-12-15 17:00 | -52 | UNSURE | MECHANICAL LOUVERS | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 03235 | 0 | 0 | SG5-03235 | Construction | 2nd Floor | Construction.2.3.6.3 | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 0% | 2023-01-25 08:00 | 2023-02-07 17:00 | -52 | WELKIN | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 03240 | 0 | 0 | SG5-03240 | Construction | 2nd Floor | Construction.2.3.6.3 | Plumbing/Mechanical Insulation & Tag - 2nd Floor | 10 | 10 | 0% | 2023-02-08 08:00 | 2023-02-22 17:00 | -52 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 03210 | 0 | 0 | SG5-03210 | Construction | 2nd Floor | Construction.2.3.6.3 | Install Ductwork and Appurtenances - 2nd Floor | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -52 | WELKIN | DUCTWORK | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.3 | SG5 | SG5 | 03215 | 0 | 0 | SG5-03215 | Construction | 2nd Floor | Construction.2.3.6.3 | Install EF Units - 2nd Floor | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | -52 | MEP | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.4 | SG5 | SG5 | 03305 | 0 | 0 | SG5-03305 | Construction | Testing & Start-Up | Construction.2.3.6.4 | DOB Mechanical/Plumbing Inspection - SG5 | 4 | 4 | 0% | 2023-02-23 08:00 | 2023-02-28 17:00 | -52 | UNSURE | INSPECTION | INSPECTION | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.4 | SG5 | SG5 | 03310 | 0 | 0 | SG5-03310 | Construction | Testing & Start-Up | Construction.2.3.6.4 | Perform Start-Up Testing - SG5 | 15 | 15 | 0% | 2023-05-26 08:00 | 2023-06-16 17:00 | -114 | UNSURE | STARTUP | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.4 | SG5 | SG5 | 03315 | 0 | 0 | SG5-03315 | Construction | Testing & Start-Up | Construction.2.3.6.4 | Start-Up Testing & Commissioning Mechanical/Plumbing - SG5 | 16 | 16 | 0% | 2023-06-19 08:00 | 2023-07-11 17:00 | -45 | UNSURE | STARTUP | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.4 | SG5 | SG5 | 03320 | 0 | 0 | SG5-03320 | Construction | Testing & Start-Up | Construction.2.3.6.4 | Perform Punch List - Electrical/Mechanical/Plumbing Work - SG5 | 5 | 5 | 0% | 2023-07-12 08:00 | 2023-07-18 17:00 | -45 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.4 | SG5 | SG5 | 03330 | 0 | 0 | SG5-03330 | Construction | Testing & Start-Up | Construction.2.3.6.4 | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - SG5 | 4 | 4 | 0% | 2023-07-20 08:00 | 2023-07-25 17:00 | -45 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.6.4 | SG5 | SG5 | 03325 | 0 | 0 | SG5-03325 | Construction | Testing & Start-Up | Construction.2.3.6.4 | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - SG5 | 1 | 1 | 0% | 2023-07-19 08:00 | 2023-07-19 17:00 | -45 | FSE | INSPECTION | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.5 | SG4 | SG4 | 01805 | 0 | 0 | SG4-01805 | Construction | Concrete Shelf Construction | Construction.2.2.5.EFPC.5 | Excavate for concrete shelf around bldg perimeter --> SG4 | 10 | 0 | 100% | 2022-02-28 | 2022-03-05 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.5 | SG4 | SG4 | 01810 | 0 | 0 | SG4-01810 | Construction | Concrete Shelf Construction | Construction.2.2.5.EFPC.5 | Place rebar for concrete shelf around bldg perimeter --> SG4 | 5 | 0 | 100% | 2022-03-07 | 2022-03-12 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.5 | SG4 | SG4 | 01815 | 0 | 0 | SG4-01815 | Construction | Concrete Shelf Construction | Construction.2.2.5.EFPC.5 | Pour concrete shelf around bldg perimeter --> SG4 | 5 | 0 | 100% | 2022-03-21 | 2022-03-21 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.5 | SG4 | SG4 | 01820 | 0 | 0 | SG4-01820 | Construction | Concrete Shelf Construction | Construction.2.2.5.EFPC.5 | Place infill concrete in area ways around bldg perimeter --> SG4 | 5 | 0 | 100% | 2022-03-14 08:00 | 2022-03-21 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.5 | SG4 | SG4 | 01825 | 0 | 0 | SG4-01825 | Construction | Concrete Shelf Construction | Construction.2.2.5.EFPC.5 | Place waterproofing on concrete shelf around bldg perimeter --> SG4 | 10 | 0 | 100% | 2022-05-17 08:00 | 2022-08-19 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.5 | SG4 | SG4 | 01830 | 0 | 0 | SG4-01830 | Construction | Concrete Shelf Construction | Construction.2.2.5.EFPC.5 | Place CMU around bldg perimeter --SG4 | 15 | 0 | 100% | 2022-05-17 | 2022-08-19 17:00 |  | FAXA | CMU | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.5 | SG4 | SG4 | 01835 | 0 | 0 | SG4-01835 | Construction | Concrete Shelf Construction | Construction.2.2.5.EFPC.5 | Place waterproofing on CMU around bldg perimeter --> SG4 (Waterproofing Delay) | 10 | 0 | 100% | 2022-06-06 | 2022-08-16 17:00 |  | 0 | WATERPROOFING | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.5 | SG4 | SG4 | 01840 | 0 | 0 | SG4-01840 | Construction | Concrete Shelf Construction | Construction.2.2.5.EFPC.5 | Place window frames around bldg perimeter --> SG4 | 10 | 0 | 100% | 2022-06-13 | 2022-08-19 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.5 | SG4 | SG4 | 01845 | 0 | 0 | SG4-01845 | Construction | Concrete Shelf Construction | Construction.2.2.5.EFPC.5 | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> SG4 | 20 | 0 | 100% | 2022-06-13 | 2022-08-24 17:00 |  | FAXA | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.5 | SG4 | SG4 | 01850 | 0 | 0 | SG4-01850 | Construction | Concrete Shelf Construction | Construction.2.2.5.EFPC.5 | Backfill around bdg perimeter --> SG4 | 5 | 0 | 100% | 2022-09-26 08:00 | 2022-09-30 17:00 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.5.EFPC.5 | SG4 | SG4 | 01855 | 0 | 0 | SG4-01855 | Construction | Concrete Shelf Construction | Construction.2.2.5.EFPC.5 | Place frame / stucco / and signs at entrances --> SG4 | 4 | 4 | 0% | 2022-12-23 08:00 | 2022-12-29 17:00 | 95 | CCC | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.5.EFPC.5 | SG4 | SG4 | 01860 | 0 | 0 | SG4-01860 | Construction | Concrete Shelf Construction | Construction.2.2.5.EFPC.5 | Place window floodgates at windows --> SG4 | 5 | 5 | 0% | 2022-12-30 08:00 | 2023-01-06 17:00 | 95 | MLJ | FLOOD PROTECTION | FLOOD WINDOWS | 10-1400 | 10-1400-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.5.EFPC.5 | SG4 | SG4 | 01865 | 0 | 0 | SG4-01865 | Construction | Concrete Shelf Construction | Construction.2.2.5.EFPC.5 | Install signs --> SG4 | 3 | 3 | 0% | 2023-01-09 08:00 | 2023-01-11 17:00 | 95 | MLJ | SIGNS | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.5 | SG4 | SG4 | 01350 | 0 | 0 | SG4-01350 | Construction | Boiler Room Construction | Construction.2.2.5.5 | Drill dowels and place rebar for boiler room concrete walls --> SG4 | 5 | 0 | 100% | 2021-05-11 | 2021-05-13 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.5 | SG4 | SG4 | 01355 | 0 | 0 | SG4-01355 | Construction | Boiler Room Construction | Construction.2.2.5.5 | Form boiler room concrete walls --> SG4 | 5 | 0 | 100% | 2021-05-12 | 2021-05-13 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.5 | SG4 | SG4 | 01360 | 0 | 0 | SG4-01360 | Construction | Boiler Room Construction | Construction.2.2.5.5 | Pour Concrete boiler room walls --> SG4 | 2 | 0 | 100% | 2021-05-14 | 2021-05-14 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.5 | SG4 | SG4 | 01365 | 0 | 0 | SG4-01365 | Construction | Boiler Room Construction | Construction.2.2.5.5 | Strip Forms boiler room concrete walls --> SG4 | 3 | 0 | 100% | 2021-05-19 | 2021-05-20 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.5 | SG4 | SG4 | 01370 | 0 | 0 | SG4-01370 | Construction | Boiler Room Construction | Construction.2.2.5.5 | Place crystaline waterproofing on perimeter walls - cellar --> SG4 - N/R, Bulletin 5 | 10 | 0 | 100% | 2022-07-01 | 2022-07-01 |  | 0 | WATERPROOFING | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.6 | SG4 | SG4 | 01385 | 0 | 0 | SG4-01385 | Construction | Elevator Refurbishment | Construction.2.2.5.6 | Refurbish Elevator 1 --> SG4 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.6 | SG4 | SG4 | 01390 | 0 | 0 | SG4-01390 | Construction | Elevator Refurbishment | Construction.2.2.5.6 | Refurbish Elevator 2 --> SG4 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.3.5.6 | SG5 | SG5 | 01380 | 0 | 0 | SG5-01380 | Construction | Elevator Refurbishment | Construction.2.3.5.6 | Refurbish Elevator 1 --> SG5 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.6 | SG5 | SG5 | 01385 | 0 | 0 | SG5-01385 | Construction | Elevator Refurbishment | Construction.2.3.5.6 | Refurbish Elevator 2 --> SG5 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.5 | SG5 | SG5 | 01805 | 0 | 0 | SG5-01805 | Construction | Concrete Shelf Construction | Construction.2.3.5.EFPC.5 | Excavate for concrete shelf around bldg perimeter --> SG5 | 10 | 0 | 100% | 2021-11-25 08:00 | 2021-12-02 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.5 | SG5 | SG5 | 01810 | 0 | 0 | SG5-01810 | Construction | Concrete Shelf Construction | Construction.2.3.5.EFPC.5 | Place rebar for concrete shelf around bldg perimeter --> SG5 | 5 | 0 | 100% | 2022-03-07 | 2022-03-11 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.5 | SG5 | SG5 | 01815 | 0 | 0 | SG5-01815 | Construction | Concrete Shelf Construction | Construction.2.3.5.EFPC.5 | Pour concrete shelf around bldg perimeter --> SG5 | 5 | 0 | 100% | 2022-03-21 | 2022-03-21 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.5 | SG5 | SG5 | 01820 | 0 | 0 | SG5-01820 | Construction | Concrete Shelf Construction | Construction.2.3.5.EFPC.5 | Place infill concrete in area ways around bldg perimeter --> SG5 | 5 | 0 | 100% | 2022-03-14 08:00 | 2022-03-21 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.5 | SG5 | SG5 | 01825 | 0 | 0 | SG5-01825 | Construction | Concrete Shelf Construction | Construction.2.3.5.EFPC.5 | Place waterproofing on concrete shelf around bldg perimeter --> SG5 | 10 | 0 | 100% | 2022-05-26 | 2022-05-31 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.5 | SG5 | SG5 | 01830 | 0 | 0 | SG5-01830 | Construction | Concrete Shelf Construction | Construction.2.3.5.EFPC.5 | Place CMU around bldg perimeter --SG5 | 15 | 0 | 100% | 2022-05-09 | 2022-06-15 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.5 | SG5 | SG5 | 01835 | 0 | 0 | SG5-01835 | Construction | Concrete Shelf Construction | Construction.2.3.5.EFPC.5 | Place waterproofing on CMU around bldg perimeter --> SG5 | 10 | 0 | 100% | 2022-05-26 | 2022-06-06 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.5 | SG5 | SG5 | 01840 | 0 | 0 | SG5-01840 | Construction | Concrete Shelf Construction | Construction.2.3.5.EFPC.5 | Place window frames around bldg perimeter --> SG5 | 10 | 0 | 100% | 2022-06-06 | 2022-06-15 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.5 | SG5 | SG5 | 01845 | 0 | 0 | SG5-01845 | Construction | Concrete Shelf Construction | Construction.2.3.5.EFPC.5 | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> SG5 | 20 | 0 | 100% | 2022-06-15 | 2022-08-19 17:00 |  | FAXA | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.5 | SG5 | SG5 | 01850 | 0 | 0 | SG5-01850 | Construction | Concrete Shelf Construction | Construction.2.3.5.EFPC.5 | Backfill around bdg perimeter --> SG5 | 5 | 0 | 100% | 2022-05-05 | 2022-05-10 |  | 0 | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.5 | SG5 | SG5 | 01855 | 0 | 0 | SG5-01855 | Construction | Concrete Shelf Construction | Construction.2.3.5.EFPC.5 | Place frame / stucco / and signs at entrances --> SG5 | 4 | 4 | 0% | 2022-12-23 08:00 | 2022-12-29 17:00 | 65 | CCC | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.5 | SG5 | SG5 | 01860 | 0 | 0 | SG5-01860 | Construction | Concrete Shelf Construction | Construction.2.3.5.EFPC.5 | Place window floodgates at windows --> SG5 | 5 | 5 | 0% | 2022-12-30 08:00 | 2023-01-06 17:00 | 65 | MLJ | FLOOD PROTECTION | FLOOD WINDOWS | 10-1400 | 10-1400-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.5 | SG5 | SG5 | 01865 | 0 | 0 | SG5-01865 | Construction | Concrete Shelf Construction | Construction.2.3.5.EFPC.5 | Install signs --> SG5 | 3 | 3 | 0% | 2023-01-09 08:00 | 2023-01-11 17:00 | 65 | MLJ | SIGNS | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.2.5.6 | SG4 | SG4 | 01380 | 0 | 0 | SG4-01380 | Construction | Elevator Refurbishment | Construction.2.2.5.6 | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01137 | 0 | 0 | SGN-01137 | Construction | Site Utilities | Construction.2.5.1 | Install Automatic Temperature Control Conduit - SG6 --> SG4 | 2 | 0 | 100% | 2022-06-15 | 2022-06-22 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.2 | SGN | SGN | 02130 | 0 | 0 | SGN-02130 | Construction | Cable Pulls | Construction.2.5.2 | Pull & Terminate Automatic Temperature Control Cable - SG-6 --> SG-4 | 10 | 0 | 100% | 2022-06-15 | 2022-06-22 |  | FSE | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.2 | SGN | SGN | 02150 | 0 | 0 | SGN-02150 | Construction | Cable Pulls | Construction.2.5.2 | Pull & Terminate Automatic Temperature Control Cable - SG-5 --> SG-4 | 10 | 0 | 100% | 2022-06-15 | 2022-06-22 |  | FSE | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.1 | SGN | SGN | 01287 | 0 | 0 | SGN-01287 | Construction | Site Utilities | Construction.2.5.1 | Install Automatic Temperature Control Conduit - SG4 --> SG5 | 2 | 0 | 100% | 2022-07-25 08:00 | 2022-07-26 17:00 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01317 | 0 | 0 | SG6-01317 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Insulated Metal Panels left out for Access --> SG6 | 5 | 0 | 100% | 2022-10-14 | 2022-10-18 |  | NAVILLUS | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.5.Removals | SGN | SGN | 01100 | 0 | 0 | SGN-01100 | Construction | Site Protection & Removals | Construction.2.5.Removals | De-Activate Dewatering - N/A | 1 | 0 | 100% | 2021-05-25 | 2021-05-25 |  | 0 | 0 | 0 | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.2.5.7 | SG6 | SG6 | 09005 | 0 | 0 | SG6-09005 | Construction | Civil/Architectural Inspections | Construction.2.5.7 | Perform Inspections & Issue Punch List | 5 | 5 | 0% | 2022-12-28 08:00 | 2023-01-04 17:00 | 90 | MLJ | PUNCH LIST | INSPECTION | 99-8200 | 99-8200-SG6
Not Started | CI NYCHA Update #22.Construction.2.5.7 | SG6 | SG6 | 09010 | 0 | 0 | SG6-09010 | Construction | Civil/Architectural Inspections | Construction.2.5.7 | Perform Punch List | 10 | 10 | 0% | 2023-01-05 08:00 | 2023-01-19 17:00 | 90 | MLJ | PUNCH LIST | 0 | 99-8200 | 99-8200-SG6
Not Started | CI NYCHA Update #22.Construction.2.2.5.7 | SG4 | SG4 | 09005 | 0 | 0 | SG4-09005 | Construction | Civil/Architectural Inspections | Construction.2.2.5.7 | Perform Inspections & Issue Punch List | 5 | 5 | 0% | 2023-06-14 08:00 | 2023-06-20 17:00 | -41 | MLJ | PUNCH LIST | INSPECTION | 99-8200 | 99-8200-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.5.7 | SG4 | SG4 | 09010 | 0 | 0 | SG4-09010 | Construction | Civil/Architectural Inspections | Construction.2.2.5.7 | Perform Punch List | 10 | 10 | 0% | 2023-06-21 08:00 | 2023-07-05 17:00 | -26 | MLJ | PUNCH LIST | 0 | 99-8200 | 99-8200-SG4
Not Started | CI NYCHA Update #22.Construction.2.3.5.7 | SG5 | SG5 | 09005 | 0 | 0 | SG5-09005 | Construction | Civil/Architectural Inspections | Construction.2.3.5.7 | Perform Inspections & Issue Punch List | 5 | 5 | 0% | 2023-01-23 08:00 | 2023-01-27 17:00 | 59 | MLJ | PUNCH LIST | INSPECTION | 99-8200 | 99-8200-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.7 | SG5 | SG5 | 09010 | 0 | 0 | SG5-09010 | Construction | Civil/Architectural Inspections | Construction.2.3.5.7 | Perform Punch List | 10 | 10 | 0% | 2023-01-30 08:00 | 2023-02-10 17:00 | 74 | MLJ | PUNCH LIST | 0 | 99-8200 | 99-8200-SG5
Completed | CI NYCHA Update #22.Construction.3.5.Removals | OGP1 | OGP1 | 01005 | 0 | 0 | OGP1-01005 | Construction | Site Protection & Removals | Construction.3.5.Removals | Install Site Fencing - O'Dwyer Gardens - Part 1 | 10 | 0 | 100% | 2021-02-08 | 2021-02-18 17:00 |  | 0 | 0 | 0 | 0 | 0-OGP1
In Progress | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 02000 | 0 | 0 | OGP1-02000 | Construction | Site Utilities | Construction.3.5.4 | Remove, Relocate or Abandon Exisiting Feeder Conduit & Cable | 5 | 3 | 50% | 2021-11-29 | 2022-11-29 12:00 | -25 | FSE | 0 | 0 | 0 | 0-OGP1
In Progress | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 02002 | 0 | 0 | OGP1-02002 | Construction | Site Utilities | Construction.3.5.4 | Install Manholes & Grounding | 8 | 4 | 50% | 2021-11-22 | 2022-11-30 17:00 | -26 | FSE | GROUNDING EQUIP | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.Removals | OGP1 | OGP1 | 01015 | 0 | 0 | OGP1-01015 | Construction | Site Protection & Removals | Construction.3.5.Removals | Install Overhead Protection - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.Removals | OGP1 | OGP1 | 01020 | 0 | 0 | OGP1-01020 | Construction | Site Protection & Removals | Construction.3.5.Removals | Install Tree Protection | 5 | 0 | 100% | 2020-11-05 | 2020-11-11 17:00 |  | 0 | 0 | 0 | 31-1900 | 31-1900-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.Removals | OGP1 | OGP1 | 01025 | 0 | 0 | OGP1-01025 | Construction | Site Protection & Removals | Construction.3.5.Removals | Remove Trees | 2 | 0 | 100% | 2021-01-12 | 2021-01-15 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.Removals | OGP1 | OGP1 | 01000 | 0 | 0 | OGP1-01000 | Construction | Site Protection & Removals | Construction.3.5.Removals | Remove Curbs And Existing Fencing | 10 | 0 | 100% | 2021-07-19 08:00 | 2022-03-03 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.Removals | OGP1 | OGP1 | 01035 | 0 | 0 | OGP1-01035 | Construction | Site Protection & Removals | Construction.3.5.Removals | Install Erosion Control | 5 | 0 | 100% | 2021-09-26 | 2021-09-30 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.Removals | OGP1 | OGP1 | 01010 | 0 | 0 | OGP1-01010 | Construction | Site Protection & Removals | Construction.3.5.Removals | Set Up Yard and Staging - N/A | 10 | 0 | 100% | 2021-02-01 | 2021-02-01 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.Removals | OGP1 | OGP1 | 01045 | 0 | 0 | OGP1-01045 | Construction | Site Protection & Removals | Construction.3.5.Removals | Clear & Grub | 10 | 0 | 100% | 2021-06-15 | 2021-06-22 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.Removals | OGP1 | OGP1 | 01050 | 0 | 0 | OGP1-01050 | Construction | Site Protection & Removals | Construction.3.5.Removals | Scrape & Store Topsoil | 10 | 0 | 100% | 2021-06-15 | 2021-06-23 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.Removals | OGP1 | OGP1 | 01055 | 0 | 0 | OGP1-01055 | Construction | Site Protection & Removals | Construction.3.5.Removals | Soil Testing | 10 | 0 | 100% | 2021-02-25 | 2021-03-08 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.Removals | OGP1 | OGP1 | 01060 | 0 | 0 | OGP1-01060 | Construction | Site Protection & Removals | Construction.3.5.Removals | Demo Playgrounds And Misc Site Furniture | 5 | 0 | 100% | 2021-07-19 08:00 | 2021-07-20 17:00 |  | 0 | 0 | 0 | 02-2000 | 02-2000-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.Removals | OGP1 | OGP1 | 01065 | 0 | 0 | OGP1-01065 | Construction | Site Protection & Removals | Construction.3.5.Removals | Remove Retaining Walls | 10 | 0 | 100% | 2022-03-28 | 2022-04-01 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.Removals | OGP1 | OGP1 | 01070 | 0 | 0 | OGP1-01070 | Construction | Site Protection & Removals | Construction.3.5.Removals | Install Deep Wells For Dewatering - N/A | 10 | 0 | 100% | 2021-06-23 | 2021-06-23 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.Removals | OGP1 | OGP1 | 01075 | 0 | 0 | OGP1-01075 | Construction | Site Protection & Removals | Construction.3.5.Removals | Install Piping For Deep Wells - N/A | 5 | 0 | 100% | 2021-06-23 | 2021-06-23 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.Removals | OGP1 | OGP1 | 01080 | 0 | 0 | OGP1-01080 | Construction | Site Protection & Removals | Construction.3.5.Removals | Install Discharge Connection For Dewatering - N/A | 10 | 0 | 100% | 2022-03-25 08:00 | 2022-03-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.Removals | OGP1 | OGP1 | 01085 | 0 | 0 | OGP1-01085 | Construction | Site Protection & Removals | Construction.3.5.Removals | Run Electric For Dewatering - N/A | 10 | 0 | 100% | 2021-06-23 | 2021-06-23 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01105 | 0 | 0 | OGP1-01105 | Construction | Site Utilities | Construction.3.5.4 | Excavate for CW Pipe - OG4 --> OG8 | 10 | 0 | 100% | 2021-10-06 | 2021-10-07 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01110 | 0 | 0 | OGP1-01110 | Construction | Site Utilities | Construction.3.5.4 | Install CW Piping - OG4 --> OG8 | 15 | 0 | 100% | 2021-10-21 | 2022-01-03 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01115 | 0 | 0 | OGP1-01115 | Construction | Site Utilities | Construction.3.5.4 | Test CW Piping - OG4 --> OG8 | 10 | 0 | 100% | 2022-01-04 | 2022-01-05 |  | WELKIN | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01120 | 0 | 0 | OGP1-01120 | Construction | Site Utilities | Construction.3.5.4 | Backfill CW Piping - OG4 --> OG8 | 5 | 0 | 100% | 2022-05-03 | 2022-05-03 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01150 | 0 | 0 | OGP1-01150 | Construction | Site Utilities | Construction.3.5.4 | Excavate for Electric OG4--> OG8 | 10 | 0 | 100% | 2021-10-19 | 2021-10-27 17:00 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01155 | 0 | 0 | OGP1-01155 | Construction | Site Utilities | Construction.3.5.4 | Install Electrical Conduit OG4--> OG8 | 10 | 0 | 100% | 2021-10-27 | 2022-04-12 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01160 | 0 | 0 | OGP1-01160 | Construction | Site Utilities | Construction.3.5.4 | Encase conduit in concrete OG4--> OG8 | 5 | 0 | 100% | 2022-05-12 | 2022-05-12 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01165 | 0 | 0 | OGP1-01165 | Construction | Site Utilities | Construction.3.5.4 | Backfill Electrical OG4--> OG8 | 5 | 0 | 100% | 2022-05-16 | 2022-05-18 |  | 0 | 0 | 0 | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01405 | 0 | 0 | OGP1-01405 | Construction | Site Utilities | Construction.3.5.4 | Excavate for Gas Line - OG8 --> W33rd Street | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | -67 | MLJ | EXCAVATION | UTILITY EXC | 33-3100 | 33-3100-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01205 | 0 | 0 | OGP1-01205 | Construction | Site Utilities | Construction.3.5.4 | Excavate for Electric OG4--> MH | 3 | 0 | 100% | 2021-12-16 | 2021-12-31 |  | 0 | EXCAVATION | 0 | 33-3100 | 33-3100-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01210 | 0 | 0 | OGP1-01210 | Construction | Site Utilities | Construction.3.5.4 | Install Electrical Conduit OG4--> MH | 2 | 0 | 100% | 2021-12-16 | 2022-04-15 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01215 | 0 | 0 | OGP1-01215 | Construction | Site Utilities | Construction.3.5.4 | Encase conduit in concrete OG4--> MH | 2 | 0 | 100% | 2022-05-12 | 2022-05-12 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01220 | 0 | 0 | OGP1-01220 | Construction | Site Utilities | Construction.3.5.4 | Backfill Electrical OG4 --> MH | 2 | 0 | 100% | 2022-05-16 | 2022-05-18 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01230 | 0 | 0 | OGP1-01230 | Construction | Site Utilities | Construction.3.5.4 | Excavate for Electric OG8 -> OG5 | 10 | 0 | 100% | 2021-09-28 | 2021-11-26 17:00 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01235 | 0 | 0 | OGP1-01235 | Construction | Site Utilities | Construction.3.5.4 | Install Electrical Conduit & MH OG8 -> OG5 | 10 | 0 | 100% | 2021-10-27 | 2022-01-07 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01240 | 0 | 0 | OGP1-01240 | Construction | Site Utilities | Construction.3.5.4 | Encase conduit in concrete OG8 -> OG5 | 3 | 0 | 100% | 2021-12-05 08:00 | 2021-12-06 17:00 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01245 | 0 | 0 | OGP1-01245 | Construction | Site Utilities | Construction.3.5.4 | Backfill Electrical OG8 -> OG5 | 5 | 0 | 100% | 2021-12-07 08:00 | 2021-12-09 17:00 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01255 | 0 | 0 | OGP1-01255 | Construction | Site Utilities | Construction.3.5.4 | Excavate for Electric OG5--> MH | 3 | 0 | 100% | 2021-12-10 | 2021-12-13 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01260 | 0 | 0 | OGP1-01260 | Construction | Site Utilities | Construction.3.5.4 | Install Electrical Conduit OG5--> MH | 2 | 0 | 100% | 2021-12-13 | 2022-01-14 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01265 | 0 | 0 | OGP1-01265 | Construction | Site Utilities | Construction.3.5.4 | Encase conduit in concrete OG5--> MH | 2 | 0 | 100% | 2022-04-26 | 2022-04-28 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01270 | 0 | 0 | OGP1-01270 | Construction | Site Utilities | Construction.3.5.4 | Backfill Electrical OG5 --> MH | 2 | 0 | 100% | 2022-04-29 | 2022-05-02 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01275 | 0 | 0 | OGP1-01275 | Construction | Site Utilities | Construction.3.5.4 | Excavate for Steam & HW OG4--> OG8 | 15 | 0 | 100% | 2021-09-28 | 2021-10-05 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01280 | 0 | 0 | OGP1-01280 | Construction | Site Utilities | Construction.3.5.4 | Install Steam and HW piping OG4--> OG8 | 20 | 0 | 100% | 2021-10-20 | 2021-12-02 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01285 | 0 | 0 | OGP1-01285 | Construction | Site Utilities | Construction.3.5.4 | Test Steam & HW Piping OG4--> OG8 | 8 | 0 | 100% | 2022-01-04 | 2022-02-02 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01290 | 0 | 0 | OGP1-01290 | Construction | Site Utilities | Construction.3.5.4 | Backfill Steam & HW Piping OG4--> OG8 | 10 | 0 | 100% | 2022-05-16 | 2022-05-18 |  | 0 | 0 | 0 | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01505 | 0 | 0 | OGP1-01505 | Construction | Site Utilities | Construction.3.5.4 | Excavate for water line to drinking fountain SGN --> Water Main W32nd Street | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | 8 | MLJ | EXCAVATION | UTILITY EXC | 33-3100 | 33-3100-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01510 | 0 | 0 | OGP1-01510 | Construction | Site Utilities | Construction.3.5.4 | Install water line to drinking fountain SGN --> Water Main W32nd Street | 5 | 5 | 0% | 2022-12-12 08:00 | 2022-12-16 17:00 | 6 | UNSURE | PLAYGROUND | PLUMBING | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01515 | 0 | 0 | OGP1-01515 | Construction | Site Utilities | Construction.3.5.4 | Tap water main for drinking fountain water line SGN --> Water Main W32nd Street | 2 | 2 | 0% | 2022-12-19 08:00 | 2022-12-20 17:00 | 6 | UNSURE | PLAYGROUND | PLUMBING | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01520 | 0 | 0 | OGP1-01520 | Construction | Site Utilities | Construction.3.5.4 | Backfill water line drinking fountain SGN --> Water Main W32nd Street | 2 | 2 | 0% | 2022-12-21 08:00 | 2022-12-22 17:00 | 6 | MLJ | BACKFILL | BACKFILL SITE | 31-2200 | 31-2200-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01525 | 0 | 0 | OGP1-01525 | Construction | Site Utilities | Construction.3.5.4 | Excavate for water line to water play items SGN --> Water Main W33rd Street | 2 | 2 | 0% | 2022-11-29 08:00 | 2022-11-30 17:00 | 8 | MLJ | EXCAVATION | UTILITY EXC | 33-3100 | 33-3100-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01530 | 0 | 0 | OGP1-01530 | Construction | Site Utilities | Construction.3.5.4 | Install water line and RPZ box for water play items SGN --> Water Main W33rd Street | 5 | 5 | 0% | 2022-12-01 08:00 | 2022-12-07 17:00 | 15 | UNSURE | PLAYGROUND | PLUMBING | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01535 | 0 | 0 | OGP1-01535 | Construction | Site Utilities | Construction.3.5.4 | Tap water main for drinking fountain water line SGN --> Water Main W33rd Street | 2 | 2 | 0% | 2022-12-08 08:00 | 2022-12-09 17:00 | 15 | UNSURE | PLAYGROUND | PLUMBING | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01540 | 0 | 0 | OGP1-01540 | Construction | Site Utilities | Construction.3.5.4 | Backfill water line drinking fountain SGN --> Water Main W33rd Street | 2 | 2 | 0% | 2022-12-23 08:00 | 2022-12-27 17:00 | 6 | MLJ | BACKFILL | BACKFILL SITE | 31-2200 | 31-2200-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01545 | 0 | 0 | OGP1-01545 | Construction | Site Utilities | Construction.3.5.4 | Excavate for Sanitary Sewer OG4 --> OG8 | 3 | 3 | 0% | 2022-12-01 08:00 | 2022-12-05 17:00 | 8 | MLJ | EXCAVATION | UTILITY EXC | 33-3100 | 33-3100-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01550 | 0 | 0 | OGP1-01550 | Construction | Site Utilities | Construction.3.5.4 | Install sanitary pipe OG4 --> OG8 | 2 | 2 | 0% | 2023-01-11 08:00 | 2023-01-12 17:00 | -5 | MLJ | DRAINAGE | SANITARY | 33-2500 | 33-2500-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01555 | 0 | 0 | OGP1-01555 | Construction | Site Utilities | Construction.3.5.4 | Backfill Sanitary Sewer OG4 --> OG8 | 2 | 2 | 0% | 2023-01-13 08:00 | 2023-01-17 17:00 | -5 | MLJ | BACKFILL | BACKFILL UTILITY | 31-2200 | 31-2200-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01560 | 0 | 0 | OGP1-01560 | Construction | Site Utilities | Construction.3.5.4 | Excavate and Install Area Drains AD18 to AD4 and AD6, AD5 Piping & into Tie-in to Existing | 15 | 15 | 0% | 2022-12-06 08:00 | 2022-12-27 17:00 | 8 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01565 | 0 | 0 | OGP1-01565 | Construction | Site Utilities | Construction.3.5.4 | Backfill Area Drains AD18 to AD4 and AD6, AD5 & Piping | 5 | 5 | 0% | 2023-01-18 08:00 | 2023-01-24 17:00 | -5 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.Removals | OGP1 | OGP1 | 01090 | 0 | 0 | OGP1-01090 | Construction | Site Protection & Removals | Construction.3.5.Removals | Activate Dewatering System - N/A | 1 | 0 | 100% | 2022-03-25 08:00 | 2022-03-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.Removals | OGP1 | OGP1 | 01095 | 0 | 0 | OGP1-01095 | Construction | Site Protection & Removals | Construction.3.5.Removals | Maintain Dewatering | 172 | 0 | 100% | 2022-03-25 17:00 | 2022-04-25 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01287 | 0 | 0 | OGP1-01287 | Construction | Site Utilities | Construction.3.5.4 | Install Automatic Temperature Control Conduit - OG4--> OG8 | 2 | 0 | 100% | 2022-05-16 | 2022-05-16 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.Removals | OGP1 | OGP1 | 01100 | 0 | 0 | OGP1-01100 | Construction | Site Protection & Removals | Construction.3.5.Removals | De-Activate Dewatering | 1 | 0 | 100% | 2022-05-18 | 2022-05-18 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 04005 | 0 | 0 | PERMIT-04005 | Procurement | Permits | Procurement.Div 1.Permits | Obtain Dewatering Permit | 60 | 0 | 100% | 2020-11-27 | 2021-10-24 |  | 0 | 0 | 0 | 0 | 0-0
Not Started | CI NYCHA Update #22.Construction.2.3.5.2 | SG5 | SG5 | 01220 | 0 | 0 | SG5-01220 | Construction | Interior Demolition | Construction.2.3.5.2 | Selective Demo (pumps etc..) - Cellar --> SG5 | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 3 | MLJ | DEMO | DEMO PUMPS | 02-6010 | 02-6010-SG5
In Progress | CI NYCHA Update #22.Construction.2.2.6.4 | SG4 | SG4 | 03335 | 0 | 0 | SG4-03335 | Construction | Testing & Start-Up | Construction.2.2.6.4 | Remove Redundant Services - SG4 | 10 | 5 | 50% | 2022-03-07 | 2023-06-15 17:00 | -18 | UNSURE | STARTUP | 0 | 0 | 0-SG4
In Progress | CI NYCHA Update #22.Construction.2.3.6.4 | SG5 | SG5 | 03335 | 0 | 0 | SG5-03335 | Construction | Testing & Start-Up | Construction.2.3.6.4 | Remove Redundant Services - SG5 | 10 | 5 | 50% | 2022-03-14 | 2023-07-18 17:00 | -40 | UNSURE | STARTUP | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.3.2 | OGP1 | SURV | OGP1 | G | 01005 | SURV-OGP1-G-01005 | Construction | Mobilization & Survey | Construction.3.2 | Perform Survey of Site/Building - Odwyer Gardens - Part 1 (OG-4 & OG-5) | 10 | 0 | 100% | 2020-11-02 | 2020-11-18 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.2 | OGP1 | SURV | OGP1 | E | 01010 | SURV-OGP1-E-01010 | Construction | Mobilization & Survey | Construction.3.2 | Conduct Electrical Site Survey - Odwyer Gardens - Part 1 (OG-4 & OG-5) | 10 | 0 | 100% | 2021-04-19 | 2021-06-03 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Procurement.Div. 33 | SGN | 33505 | 0 | 0 | 0 | 33505 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Prepare & Submit Utility Coord. Dwgs - Surfside Gardens North | 20 | 0 | 100% | 2020-12-07 | 2021-02-23 17:00 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Procurement.Div. 33 | SGN | 33510 | 0 | 0 | 0 | 33510 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Review & Approve Utility Coord. Dwgs - Surfside Gardens North | 10 | 0 | 100% | 2021-02-24 | 2021-03-04 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Procurement.Div. 33 | OGW | 33520 | 0 | 0 | 0 | 33520 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Prepare & Submit Utility Coord. Dwgs - Odwyer Gardens - Part 1 | 20 | 0 | 100% | 2021-02-23 | 2021-07-29 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Procurement.Div. 33 | OGW | 33525 | 0 | 0 | 0 | 33525 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Review & Approve Utility Coord. Dwgs - Odwyer Gardens - Part 1 | 10 | 0 | 100% | 2021-06-30 08:00 | 2021-07-13 17:00 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01117 | 0 | 0 | OGP1-01117 | Construction | Site Utilities | Construction.3.5.4 | Install Automatic Temperature Control Conduit - OG4 --> OG8 | 2 | 0 | 100% | 2022-05-16 | 2022-05-16 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01295 | 0 | 0 | OGP1-01295 | Construction | Site Utilities | Construction.3.5.4 | Excavate for Steam & HW OG5--> OG8 | 15 | 0 | 100% | 2021-12-26 | 2022-01-04 |  | 0 | 0 | 0 | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01300 | 0 | 0 | OGP1-01300 | Construction | Site Utilities | Construction.3.5.4 | Install Steam and HW piping OG5--> OG8 | 20 | 20 | 0% | 2023-07-31 08:00 | 2023-08-25 17:00 | -193 | WELKIN | UG PIPE | 0 | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01305 | 0 | 0 | OGP1-01305 | Construction | Site Utilities | Construction.3.5.4 | Test Steam & HW Piping OG5--> OG8 | 8 | 8 | 0% | 2023-08-28 08:00 | 2023-09-07 17:00 | -193 | WELKIN | UG PIPE | 0 | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01315 | 0 | 0 | OGP1-01315 | Construction | Site Utilities | Construction.3.5.4 | Backfill Steam & HW Piping OG5--> OG8 | 10 | 10 | 0% | 2023-09-12 08:00 | 2023-09-25 17:00 | -193 | MLJ | BACKFILL | BACKFILL UTILITY | 31-2200 | 31-2200-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01310 | 0 | 0 | OGP1-01310 | Construction | Site Utilities | Construction.3.5.4 | Install Automatic Temperature Control Conduit - OG5--> OG8 | 2 | 2 | 0% | 2023-09-08 08:00 | 2023-09-11 17:00 | -193 | FSE | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01092 | 0 | 0 | SG6-01092 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Remaining HW/CW Into SG6 (5' from the building) | 5 | 0 | 100% | 2021-09-20 | 2021-09-25 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01094 | 0 | 0 | SG6-01094 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Remaining Electrical POE Into SG6 | 5 | 0 | 100% | 2021-07-26 08:00 | 2021-07-30 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 03107 | 0 | 0 | SG6-03107 | Construction | 1st Floor | Construction.2.4.7.1 | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 15 | 0 | 100% | 2022-01-04 | 2022-01-28 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 03142 | 0 | 0 | SG6-03142 | Construction | 1st Floor | Construction.2.4.7.1 | Install Mechanical Equipment - 1st Floor | 20 | 0 | 100% | 2022-01-17 | 2022-01-28 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.2 | SG6 | SG6 | 03207 | 0 | 0 | SG6-03207 | Construction | 2nd Floor | Construction.2.4.7.2 | Rough-In Mechanical Piping & Appurtenances - 2nd Floor | 20 | 0 | 100% | 2022-01-06 | 2022-09-23 09:36 |  | WELKIN | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.2 | SG6 | SG6 | 03242 | 0 | 0 | SG6-03242 | Construction | 2nd Floor | Construction.2.4.7.2 | Install Mechanical Equipment - 2nd Floor | 20 | 0 | 100% | 2022-01-17 08:00 | 2022-08-15 17:00 |  | WELKIN | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 03007 | 0 | 0 | SG4-03007 | Construction | Cellar | Construction.2.2.6.1 | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 0 | 100% | 2021-04-25 | 2021-10-15 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 03032 | 0 | 0 | SG4-03032 | Construction | Cellar | Construction.2.2.6.1 | Install Mechanical Equipment - Cellar | 20 | 0 | 100% | 2021-07-30 08:00 | 2021-10-15 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.6.2 | SG4 | SG4 | 03107 | 0 | 0 | SG4-03107 | Construction | 1st Floor | Construction.2.2.6.2 | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 0 | 100% | 2022-08-15 08:00 | 2022-08-24 |  | WELKIN | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.3.5.6 | SG5 | SG5 | 01370 | 0 | 0 | SG5-01370 | Construction | Elevator Refurbishment | Construction.2.3.5.6 | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 03007 | 0 | 0 | SG5-03007 | Construction | Cellar | Construction.2.3.6.1 | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 0 | 100% | 2021-07-26 08:00 | 2021-10-15 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 03032 | 0 | 0 | SG5-03032 | Construction | Cellar | Construction.2.3.6.1 | Install Mechanical Equipment - Cellar | 20 | 0 | 100% | 2021-07-26 08:00 | 2021-10-15 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.6.2 | SG5 | SG5 | 03107 | 0 | 0 | SG5-03107 | Construction | 1st Floor | Construction.2.3.6.2 | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 0 | 100% | 2022-07-25 08:00 | 2022-08-05 17:00 |  | WELKIN | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01030 | 0 | 0 | OG8-01030 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Form Plumbing Shafts & Ftgs Below Water Table --> OG8 | 10 | 0 | 100% | 2021-07-27 | 2021-07-30 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01035 | 0 | 0 | OG8-01035 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Rebar Plumbing Shafts & Ftgs Below Water Table --> OG8 | 5 | 0 | 100% | 2021-07-30 08:00 | 2021-08-09 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01040 | 0 | 0 | OG8-01040 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Pour Plumbing Shafts & Ftgs Below Water Table --> OG8 | 2 | 0 | 100% | 2021-08-10 | 2021-08-10 |  | MLJ | concrete | NB CONCRETE | 03-1900 | 03-1900-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01045 | 0 | 0 | OG8-01045 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Strip Forms Plumbing Shafts & Ftgs Below Water Table --> OG8 | 5 | 0 | 100% | 2021-08-11 | 2021-08-12 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01025 | 0 | 0 | OG8-01025 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Waterproof/Insulation Plumbing Shaft ----> OG8 | 5 | 0 | 100% | 2021-08-10 | 2021-08-10 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01005 | 0 | 0 | OG8-01005 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Excavate For Plumbing Shaft & Ftgs/Piers Below Water Table --> OG8 | 5 | 0 | 100% | 2021-07-02 | 2021-07-09 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01020 | 0 | 0 | OG8-01020 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Prepare Subgrade For Plumbing Shafts & Ftgs / Piers Below Water Table --> OG8 | 3 | 0 | 100% | 2021-07-12 | 2021-07-23 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01055 | 0 | 0 | OG8-01055 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Backfill Plumbing Shaft & Ftgs/Piers --> OG8 | 5 | 0 | 100% | 2021-08-13 08:00 | 2021-11-01 17:00 |  | 0 | OG8 | 0 | 31-1400 | 31-1400-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01065 | 0 | 0 | OG8-01065 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Excavate For Remaining Ftgs/Pier/Grade Beams --> OG8 | 10 | 0 | 100% | 2021-07-02 | 2021-10-30 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01070 | 0 | 0 | OG8-01070 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Form Remaining Ftgs/Piers/Grade Beams --> OG8 | 10 | 0 | 100% | 2021-08-16 | 2021-12-05 |  | 0 | FORMWORK | FORMWORK NB | 03-1000 | 03-1000-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01075 | 0 | 0 | OG8-01075 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Rebar Remaining Ftgs/Piers/Grade Beams --> OG8 | 10 | 0 | 100% | 2021-08-17 | 2021-12-06 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01080 | 0 | 0 | OG8-01080 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Pour Remaining Ftgs/Piers/Grade Beams --> OG8 | 5 | 0 | 100% | 2021-12-01 08:00 | 2021-12-07 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01085 | 0 | 0 | OG8-01085 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Strip Forms Remaining Ftgs/Piers/Grade Beams --> OG8 | 5 | 0 | 100% | 2021-12-07 | 2021-12-08 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01090 | 0 | 0 | OG8-01090 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Remaining Steam Into OG8 (5' from the building) | 5 | 0 | 100% | 2021-11-01 08:00 | 2021-11-05 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01095 | 0 | 0 | OG8-01095 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Backfill Remaining Ftgs/Piers/Grade Beams / Prepare Subgrade --> OG8 | 5 | 0 | 100% | 2021-12-14 08:00 | 2021-12-16 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01105 | 0 | 0 | OG8-01105 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Structural Steel Framing - 1st Foor --> OG8 | 7 | 0 | 100% | 2021-12-20 08:00 | 2022-01-21 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01110 | 0 | 0 | OG8-01110 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Metal Deck --> OG8 | 2 | 0 | 100% | 2022-02-22 08:00 | 2022-04-18 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01115 | 0 | 0 | OG8-01115 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Form Pour Strip Concrete Stair South Side ---> OG8 | 5 | 0 | 100% | 2022-03-01 08:00 | 2022-03-04 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01120 | 0 | 0 | OG8-01120 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Metal Stairs --> OG8 | 2 | 0 | 100% | 2022-03-16 | 2022-04-22 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01125 | 0 | 0 | OG8-01125 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Place Insulation Below First Floor --> OG8 | 5 | 0 | 100% | 2022-02-28 | 2022-03-01 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01130 | 0 | 0 | OG8-01130 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Place WWF First Floor Slab --> OG8 | 2 | 0 | 100% | 2022-03-03 | 2022-03-04 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01135 | 0 | 0 | OG8-01135 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Pour First Floor Slab --> OG8 | 1 | 0 | 100% | 2022-03-07 | 2022-03-07 |  | MLJ | concrete | NB CONCRETE | 03-1900 | 03-1900-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01150 | 0 | 0 | OG8-01150 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Form First Floor Concrete Walls First Face And Col Encasements--> OG8 | 3 | 0 | 100% | 2022-03-15 | 2022-04-22 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01155 | 0 | 0 | OG8-01155 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Rebar First Floor Concrete Walls --> OG8 | 3 | 0 | 100% | 2022-03-18 | 2022-04-20 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01160 | 0 | 0 | OG8-01160 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Form First Floor Concrete Walls 2Nd Face --> OG8 | 5 | 0 | 100% | 2022-04-01 | 2022-04-07 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01165 | 0 | 0 | OG8-01165 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Form, Rebar & Pour Concrete Pads 1st Floor --> OG8 | 6 | 0 | 100% | 2022-03-28 | 2022-04-01 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01170 | 0 | 0 | OG8-01170 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Place WWF 2nd Floor Slab --> OG8 | 2 | 0 | 100% | 2022-04-01 | 2022-04-04 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01175 | 0 | 0 | OG8-01175 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Pour 2nd Floor Slab / First Floor Walls & Col Encasements --> OG8 | 2 | 0 | 100% | 2022-04-05 | 2022-04-05 |  | MLJ | concrete | NB CONCRETE | 03-1900 | 03-1900-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01180 | 0 | 0 | OG8-01180 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Strip Forms First Floor Walls & Col Encasements --> OG8 | 3 | 0 | 100% | 2022-04-06 | 2022-04-27 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01185 | 0 | 0 | OG8-01185 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Form Concrete Pads 2nd Floor -->OG8 | 2 | 0 | 100% | 2022-04-07 | 2022-04-07 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01205 | 0 | 0 | OG8-01205 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Place WWF Roof Slab --> OG8 | 2 | 0 | 100% | 2022-05-05 | 2022-05-06 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01210 | 0 | 0 | OG8-01210 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Pour Roof Slab and 2nd Floor Conc Pads -->OG8 | 1 | 0 | 100% | 2022-05-09 | 2022-05-09 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01215 | 0 | 0 | OG8-01215 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Strip Forms Concrete Pads 2nd Floor -->OG8 | 2 | 0 | 100% | 2022-04-26 | 2022-04-28 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01225 | 0 | 0 | OG8-01225 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Spray-On Fireproofing on St Stl --> OG8 | 5 | 0 | 100% | 2022-05-09 | 2022-05-24 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01230 | 0 | 0 | OG8-01230 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Place CMU 1st, 2nd Floors and Roof --> OG8 | 20 | 0 | 100% | 2022-05-16 | 2022-07-15 |  | FAXA | CMU | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01240 | 0 | 0 | OG8-01240 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Stud Framing 1st, 2nd Floors and Roof --> OG8 | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | 56 | CCC | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01245 | 0 | 0 | OG8-01245 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Doors --> OG8 | 3 | 3 | 0% | 2023-01-18 08:00 | 2023-01-20 17:00 | 41 | CCC | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01250 | 0 | 0 | OG8-01250 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Cast Stone Panels --> OG8 | 1 | 1 | 0% | 2023-01-23 08:00 | 2023-01-23 17:00 | 41 | JMC | CAST STONE | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01255 | 0 | 0 | OG8-01255 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Insulated Metal Panels/Louvers --> OG8 | 10 | 10 | 0% | 2023-01-24 08:00 | 2023-02-06 17:00 | 41 | NAVILLUS | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01260 | 0 | 0 | OG8-01260 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install MEP Roof Penetrations & Drains - OG8 | 1 | 0 | 100% | 2022-06-08 | 2022-06-08 |  | 0 | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01265 | 0 | 0 | OG8-01265 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Roofing --> OG8 | 15 | 10 | 33% | 2022-09-05 | 2022-12-08 17:00 | -49 | TRIANGLE | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01270 | 0 | 0 | OG8-01270 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Dunnage Gratings --> OG8 | 2 | 0 | 100% | 2022-03-12 | 2022-03-14 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01275 | 0 | 0 | OG8-01275 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Brick Façade & Stone --> OG8 | 20 | 0 | 100% | 2022-08-22 | 2022-10-27 |  | FAXA | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01285 | 0 | 0 | OG8-01285 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Flood Vents And Small Louvers --> OG8 | 3 | 3 | 0% | 2022-11-25 08:00 | 2022-11-29 17:00 | 95 | MLJ | FLOOD PROTECTION | FLOOD VENTS | 08-1700 | 08-1700-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01290 | 0 | 0 | OG8-01290 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Stair And Roof Platform Railings --> OG8 | 5 | 0 | 100% | 2022-04-04 | 2022-04-26 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01295 | 0 | 0 | OG8-01295 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Ladders --> OG8 | 3 | 0 | 100% | 2022-10-03 | 2022-10-05 |  | 0 | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01305 | 0 | 0 | OG8-01305 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Sheetrock and Stucco --> OG8 | 10 | 10 | 0% | 2023-01-25 08:00 | 2023-02-07 17:00 | 58 | CCC | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01310 | 0 | 0 | OG8-01310 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Ceramic Tile --> OG8 | 2 | 2 | 0% | 2023-02-08 08:00 | 2023-02-09 17:00 | 58 | UNSURE | FLOORING | CERAMIC | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01315 | 0 | 0 | OG8-01315 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Acoustical Ceiling --> OG8 | 2 | 2 | 0% | 2023-02-10 08:00 | 2023-02-13 17:00 | 58 | UNSURE | CEILING | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01320 | 0 | 0 | OG8-01320 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Place Crystaline Waterproofing In Plumbing Shaft --> OG8 | 3 | 0 | 100% | 2022-11-17 | 2022-11-18 |  | 0 | WATERPROOFING | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01325 | 0 | 0 | OG8-01325 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Paint All Areas --> OG8 | 15 | 15 | 0% | 2023-04-11 08:00 | 2023-05-01 17:00 | 2 | GG PAINT | PAINT | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01330 | 0 | 0 | OG8-01330 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Signs --> OG8 | 2 | 2 | 0% | 2023-05-02 08:00 | 2023-05-03 17:00 | 2 | MLJ | SIGNS | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01235 | 0 | 0 | OG8-01235 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Waterproofing to Parapet --> OG8 | 3 | 3 | 0% | 2022-12-09 08:00 | 2022-12-13 17:00 | 77 | UNSURE | WATERPROOFING | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01280 | 0 | 0 | OG8-01280 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Stucco Soffit --> OG8 | 5 | 5 | 0% | 2022-12-14 08:00 | 2022-12-20 17:00 | 77 | CCC | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01317 | 0 | 0 | OG8-01317 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Insulated Metal Panels left out for Access --> OG8 | 5 | 5 | 0% | 2023-04-04 08:00 | 2023-04-10 17:00 | 2 | NAVILLUS | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01092 | 0 | 0 | OG8-01092 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Remaining HW/CW Into OG8 (5' from the building) | 5 | 0 | 100% | 2022-01-04 | 2022-01-08 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01094 | 0 | 0 | OG8-01094 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Remaining Electrical POE Into OG8 | 5 | 0 | 100% | 2021-11-26 | 2021-11-30 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.5.1 | OGP1 | OGP1 | 01605 | 0 | 0 | OGP1-01605 | Construction | Retaining Walls | Construction.3.5.1 | Excavate for retaining wall --> OG Phase 2A - N/A | 2 | 0 | 100% | 2022-07-25 08:00 | 2022-07-25 17:00 |  | MLJ | Excavation | EXC RETAINING | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.1 | OGP1 | OGP1 | 01610 | 0 | 0 | OGP1-01610 | Construction | Retaining Walls | Construction.3.5.1 | Form Retaining wall footing --> OG Phase 2A - N/A | 2 | 0 | 100% | 2022-07-25 08:00 | 2022-07-25 17:00 |  | MLJ | Formwork | SITE FORMWORK | 03-1600 | 03-1600-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.1 | OGP1 | OGP1 | 01615 | 0 | 0 | OGP1-01615 | Construction | Retaining Walls | Construction.3.5.1 | Rebar Retaining wall footing --> OG Phase 2A - N/A | 2 | 0 | 100% | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0 | REBAR | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.1 | OGP1 | OGP1 | 01620 | 0 | 0 | OGP1-01620 | Construction | Retaining Walls | Construction.3.5.1 | Pour Retaining wall footing --> OG Phase 2A - N/A | 1 | 0 | 100% | 2022-07-25 08:00 | 2022-07-25 17:00 |  | MLJ | Concrete | SITE CONCRETE | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.1 | OGP1 | OGP1 | 01625 | 0 | 0 | OGP1-01625 | Construction | Retaining Walls | Construction.3.5.1 | Strip Retaining wall footing --> OG Phase 2A | 1 | 0 | 100% | 2022-09-26 | 2022-09-26 |  | 0 | Formwork | SITE FORMWORK | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.1 | OGP1 | OGP1 | 01630 | 0 | 0 | OGP1-01630 | Construction | Retaining Walls | Construction.3.5.1 | Form Retaining wall --> OG Phase 2A - N/A | 3 | 0 | 100% | 2022-07-25 08:00 | 2022-07-25 17:00 |  | MLJ | Formwork | SITE FORMWORK | 03-1600 | 03-1600-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.1 | OGP1 | OGP1 | 01635 | 0 | 0 | OGP1-01635 | Construction | Retaining Walls | Construction.3.5.1 | Rebar Retaining wall --> OG Phase 2A - N/A | 3 | 0 | 100% | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0 | REBAR | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.1 | OGP1 | OGP1 | 01640 | 0 | 0 | OGP1-01640 | Construction | Retaining Walls | Construction.3.5.1 | Pour Retaining wall --> OG Phase 2A - N/A | 1 | 0 | 100% | 2022-07-25 08:00 | 2022-07-25 17:00 |  | MLJ | Concrete | SITE CONCRETE | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.1 | OGP1 | OGP1 | 01645 | 0 | 0 | OGP1-01645 | Construction | Retaining Walls | Construction.3.5.1 | Strip Retaining wall --> OG Phase 2A - N/A | 1 | 0 | 100% | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0 | Formwork | SITE FORMWORK | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.5 | OGP1 | OGP1 | 01705 | 0 | 0 | OGP1-01705 | Construction | Site Restoration | Construction.3.5.5 | Install Street Curbs --> OG Phase 2A | 15 | 15 | 0% | 2023-10-10 08:00 | 2023-10-31 17:00 | -185 | MLJ | CURBS | 0 | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.5 | OGP1 | OGP1 | 01710 | 0 | 0 | OGP1-01710 | Construction | Site Restoration | Construction.3.5.5 | Install sidewalks --> OG Phase 2A | 10 | 10 | 0% | 2023-11-17 08:00 | 2023-12-01 17:00 | -185 | JMC | SIDEWALKS | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.5 | OGP1 | OGP1 | 01715 | 0 | 0 | OGP1-01715 | Construction | Site Restoration | Construction.3.5.5 | Install curb around play area --> OG Phase 2A | 5 | 0 | 100% | 2022-10-25 | 2022-10-25 17:00 |  | 0 | CURBS | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.5 | OGP1 | OGP1 | 01720 | 0 | 0 | OGP1-01720 | Construction | Site Restoration | Construction.3.5.5 | Install Safety Surface --> OG Phase 2A | 5 | 0 | 100% | 2022-10-25 | 2022-10-25 |  | 0 | 0 | PLAYGROUND | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.5 | OGP1 | OGP1 | 01725 | 0 | 0 | OGP1-01725 | Construction | Site Restoration | Construction.3.5.5 | Install site furniture concrete foundations --> OG Phase 2A | 10 | 10 | 0% | 2023-11-01 08:00 | 2023-11-16 17:00 | -185 | MLJ | CONCRETE | SITE CONCRETE | 03-2200 | 03-2200-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.5 | OGP1 | OGP1 | 01730 | 0 | 0 | OGP1-01730 | Construction | Site Restoration | Construction.3.5.5 | Install integrally colored concrete walkways --> OG Phase 2A | 20 | 20 | 0% | 2023-12-04 08:00 | 2024-01-02 17:00 | -185 | JMC | COLORED CONCRETE | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.5 | OGP1 | OGP1 | 01735 | 0 | 0 | OGP1-01735 | Construction | Site Restoration | Construction.3.5.5 | Install Play area items --> OG Phase 2A | 5 | 0 | 100% | 2022-10-25 | 2022-10-25 17:00 |  | 0 | 0 | PLAYGROUND | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.5 | OGP1 | OGP1 | 01740 | 0 | 0 | OGP1-01740 | Construction | Site Restoration | Construction.3.5.5 | Install fence around play area --> OG Phase 2A | 10 | 0 | 100% | 2022-10-25 | 2022-10-25 17:00 |  | 0 | 0 | PLAYGROUND | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.5 | OGP1 | OGP1 | 01745 | 0 | 0 | OGP1-01745 | Construction | Site Restoration | Construction.3.5.5 | Install Fence at building --> OGP1 | 5 | 5 | 0% | 2024-01-03 08:00 | 2024-01-09 17:00 | -185 | ATLAS | SITE RESTORATION | 0 | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.5 | OGP1 | OGP1 | 01750 | 0 | 0 | OGP1-01750 | Construction | Site Restoration | Construction.3.5.5 | Place Site Furniture --> OG Phase 2A | 10 | 10 | 0% | 2024-01-10 08:00 | 2024-01-23 17:00 | -185 | MLJ | SITE RESTORATION | SITE FURNITURE | 31-2600 | 31-2600-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.5 | OGP1 | OGP1 | 01755 | 0 | 0 | OGP1-01755 | Construction | Site Restoration | Construction.3.5.5 | Place topsoil --> OG Phase 2A | 3 | 3 | 0% | 2024-04-01 08:00 | 2024-04-03 17:00 | -69 | ASPEN | TOPSOIL | 0 | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.5 | OGP1 | OGP1 | 01760 | 0 | 0 | OGP1-01760 | Construction | Site Restoration | Construction.3.5.5 | Place trees and plantings --> OG Phase 2A | 5 | 5 | 0% | 2024-04-04 08:00 | 2024-04-10 17:00 | -69 | ASPEN | 0 | 0 | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.5 | OGP1 | OGP1 | 01765 | 0 | 0 | OGP1-01765 | Construction | Site Restoration | Construction.3.5.5 | Place lawn --> OG Phase 2A | 5 | 5 | 0% | 2024-04-11 08:00 | 2024-04-17 17:00 | -69 | ASPEN | 0 | 0 | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.5 | OGP1 | OGP1 | 01770 | 0 | 0 | OGP1-01770 | Construction | Site Restoration | Construction.3.5.5 | Demobilize from OG Phase 2A | 5 | 5 | 0% | 2024-04-18 08:00 | 2024-04-24 17:00 | -228 | MLJ | DEMOB | 0 | 99-4000 | 99-4000-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.7 | OGP1 | OGP1 | 01805 | 0 | 0 | OGP1-01805 | Construction | Civil/Architectural Inspections | Construction.3.5.7 | Perform Inspections & Issue Punch List | 5 | 5 | 0% | 2023-05-04 08:00 | 2023-05-10 17:00 | 2 | MLJ | PUNCH LIST | INSPECTION | 99-8200 | 99-8200-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.7 | OGP1 | OGP1 | 01810 | 0 | 0 | OGP1-01810 | Construction | Civil/Architectural Inspections | Construction.3.5.7 | Perform Punch List | 10 | 10 | 0% | 2023-05-11 08:00 | 2023-05-24 17:00 | 2 | MLJ | PUNCH LIST | 0 | 99-8200 | 99-8200-OGP1
Completed | CI NYCHA Update #22.Construction.3.1.8.4 | OG8 | OG8 | 03005 | 0 | 0 | OG8-03005 | Construction | Foundation | Construction.3.1.8.4 | Rough-In Plumbing & Appurtenances - Plumbing Shaft | 10 | 0 | 100% | 2022-09-27 | 2022-10-21 |  | WELKIN | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.8.4 | OG8 | OG8 | 03010 | 0 | 0 | OG8-03010 | Construction | Foundation | Construction.3.1.8.4 | Install Condensate Pump - Foundation Level | 10 | 0 | 100% | 2022-10-24 | 2022-11-07 |  | WELKIN | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 03105 | 0 | 0 | OG8-03105 | Construction | 1st Floor | Construction.3.1.8.1 | Rough-In Plumbing Piping & Appurtenances - 1st Floor | 15 | 0 | 100% | 2022-05-27 | 2022-06-20 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 03110 | 0 | 0 | OG8-03110 | Construction | 1st Floor | Construction.3.1.8.1 | Rig Fuel Oil Tank & Piping - 1st Floor | 3 | 0 | 100% | 2022-03-22 | 2022-03-23 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 03125 | 0 | 0 | OG8-03125 | Construction | 1st Floor | Construction.3.1.8.1 | Install Remaining Piping & Appurtenances - 1st Floor | 10 | 0 | 100% | 2022-06-21 | 2022-10-18 |  | 0 | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 03130 | 0 | 0 | OG8-03130 | Construction | 1st Floor | Construction.3.1.8.1 | Install Conduit for FOT Controls - 1st Floor | 20 | 16 | 20% | 2022-08-01 08:00 | 2022-12-16 17:00 | -43 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 03135 | 0 | 0 | OG8-03135 | Construction | 1st Floor | Construction.3.1.8.1 | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 0% | 2023-01-19 08:00 | 2023-01-25 17:00 | -43 | WELKIN | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 03140 | 0 | 0 | OG8-03140 | Construction | 1st Floor | Construction.3.1.8.1 | Install Plumbing Equipment - 1st Floor | 15 | 0 | 100% | 2022-10-04 | 2022-10-21 |  | 0 | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 03145 | 0 | 0 | OG8-03145 | Construction | 1st Floor | Construction.3.1.8.1 | Mechanical Equipment Start-up & Balance - 1st Floor | 5 | 5 | 0% | 2023-01-26 08:00 | 2023-02-01 17:00 | -43 | WELKIN | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 03150 | 0 | 0 | OG8-03150 | Construction | 1st Floor | Construction.3.1.8.1 | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 0% | 2023-02-02 08:00 | 2023-03-02 17:00 | -43 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 03107 | 0 | 0 | OG8-03107 | Construction | 1st Floor | Construction.3.1.8.1 | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 15 | 0 | 100% | 2022-06-13 | 2022-10-18 13:48 |  | WELKIN | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 03142 | 0 | 0 | OG8-03142 | Construction | 1st Floor | Construction.3.1.8.1 | Install Mechanical Equipment - 1st Floor | 15 | 1 | 95% | 2022-08-01 08:00 | 2022-11-25 15:00 | -8 | WELKIN | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 03205 | 0 | 0 | OG8-03205 | Construction | 2nd Floor | Construction.3.1.8.2 | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 15 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 03210 | 0 | 0 | OG8-03210 | Construction | 2nd Floor | Construction.3.1.8.2 | Rig Boiler Equipment & Piping - 2nd Floor | 5 | 0 | 100% | 2022-04-11 | 2022-04-13 |  | 0 | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 03225 | 0 | 0 | OG8-03225 | Construction | 2nd Floor | Construction.3.1.8.2 | Install Remaining Piping & Appurtenances - 2nd Floor | 20 | 3 | 85% | 2022-06-13 08:00 | 2022-12-09 17:00 | -65 | VITAL | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 03230 | 0 | 0 | OG8-03230 | Construction | 2nd Floor | Construction.3.1.8.2 | Install Conduit for Boiler Controls - 2nd Floor | 20 | 16 | 20% | 2022-09-01 | 2023-01-18 17:00 | -65 | FSE | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 03235 | 0 | 0 | OG8-03235 | Construction | 2nd Floor | Construction.3.1.8.2 | Perform Hydrostatic Testing - 2nd Floor | 5 | 2 | 60% | 2022-11-14 | 2023-02-17 17:00 | -65 | WELKIN | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 03240 | 0 | 0 | OG8-03240 | Construction | 2nd Floor | Construction.3.1.8.2 | Install Plumbing Equipment - 2nd Floor - N/A | 15 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 03245 | 0 | 0 | OG8-03245 | Construction | 2nd Floor | Construction.3.1.8.2 | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 0% | 2023-02-21 08:00 | 2023-03-06 17:00 | -65 | WELKIN | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 03250 | 0 | 0 | OG8-03250 | Construction | 2nd Floor | Construction.3.1.8.2 | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 0% | 2023-03-07 08:00 | 2023-04-03 17:00 | -65 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 03207 | 0 | 0 | OG8-03207 | Construction | 2nd Floor | Construction.3.1.8.2 | Rough-In Mechanical Piping & Appurtenances - 2nd Floor | 20 | 1 | 95% | 2022-06-13 | 2022-11-25 17:00 | -65 | WELKIN | 0 | 0 | 0 | 0-OG8
In Progress | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 03242 | 0 | 0 | OG8-03242 | Construction | 2nd Floor | Construction.3.1.8.2 | Install Mechanical Equipment - 2nd Floor | 20 | 2 | 90% | 2022-07-11 08:00 | 2022-11-28 17:00 | -11 | WELKIN | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 03405 | 0 | 0 | OG8-03405 | Construction | Roof | Construction.3.1.3 | Install Ductwork & Appurtenances - Roof - N/A | 4 | 0 | 100% | 2021-02-01 | 2021-02-01 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 03410 | 0 | 0 | OG8-03410 | Construction | Roof | Construction.3.1.3 | Install & Connect Exhaust Fans - Roof - N/A | 6 | 0 | 100% | 2021-02-01 | 2021-02-01 |  | 0 | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.3 | OG8 | OG8 | 03415 | 0 | 0 | OG8-03415 | Construction | Roof | Construction.3.1.3 | Install Insulation - Roof | 15 | 15 | 0% | 2022-11-25 08:00 | 2022-12-15 17:00 | 8 | TRIANGLE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.6 | OG8 | OG8 | 03505 | 0 | 0 | OG8-03505 | Construction | Testing & Start-Up | Construction.3.1.6 | DOB Mechanical/Plumbing Inspection - OG8 | 4 | 4 | 0% | 2023-04-04 08:00 | 2023-04-07 17:00 | -65 | UNSURE | INSPECTION | INSPECTION | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.6 | OG8 | OG8 | 03510 | 0 | 0 | OG8-03510 | Construction | Testing & Start-Up | Construction.3.1.6 | Perform Start-Up Testing & Sign-off - Boilers - OG8 | 15 | 15 | 0% | 2023-06-19 08:00 | 2023-07-10 17:00 | -114 | UNSURE | STARTUP | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.6 | OG8 | OG8 | 03515 | 0 | 0 | OG8-03515 | Construction | Testing & Start-Up | Construction.3.1.6 | Start-Up Testing & Commissioning Mechanical/Plumbing - OG8 | 16 | 16 | 0% | 2023-07-11 08:00 | 2023-08-01 17:00 | -60 | UNSURE | STARTUP | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.6 | OG8 | OG8 | 03520 | 0 | 0 | OG8-03520 | Construction | Testing & Start-Up | Construction.3.1.6 | Perform Punch List - Electrical/Mechanical/Plumbing Work - OG8 | 5 | 5 | 0% | 2023-08-02 08:00 | 2023-08-08 17:00 | -60 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.6 | OG8 | OG8 | 03530 | 0 | 0 | OG8-03530 | Construction | Testing & Start-Up | Construction.3.1.6 | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - OG8 | 4 | 4 | 0% | 2023-08-10 08:00 | 2023-08-15 17:00 | -60 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.6 | OG8 | OG8 | 03525 | 0 | 0 | OG8-03525 | Construction | Testing & Start-Up | Construction.3.1.6 | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - OG8 | 1 | 1 | 0% | 2023-08-09 08:00 | 2023-08-09 17:00 | -60 | FSE | INSPECTION | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.6.5.1 | OG4 | OG4 | 01005 | 0 | 0 | OG4-01005 | Construction | Asbestos Abatement | Construction.3.6.5.1 | Asbestos Abatement - gaskets - cellar - OG4 | 3 | 3 | 0% | 2023-08-16 08:00 | 2023-08-18 17:00 | -88 | ATCO | ABESTOS | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.1 | OG4 | OG4 | 01010 | 0 | 0 | OG4-01010 | Construction | Asbestos Abatement | Construction.3.6.5.1 | Asbestos Abatement - wire insulation - cellar --> OG4 | 3 | 0 | 100% | 2021-09-20 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.1 | OG4 | OG4 | 01015 | 0 | 0 | OG4-01015 | Construction | Asbestos Abatement | Construction.3.6.5.1 | Asbestos Abatement - flooring materials at slab penetrations - cellar --> OG4 | 3 | 0 | 100% | 2022-01-17 08:00 | 2022-01-20 17:00 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.1 | OG4 | OG4 | 01020 | 0 | 0 | OG4-01020 | Construction | Asbestos Abatement | Construction.3.6.5.1 | Asbestos Abatement - pipe insulation - cellar --> OG4 | 3 | 0 | 100% | 2021-09-20 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.1 | OG4 | OG4 | 01025 | 0 | 0 | OG4-01025 | Construction | Asbestos Abatement | Construction.3.6.5.1 | Asbestos Abatement - Window Sills - 1st Floor --> OG4 | 5 | 0 | 100% | 2022-07-12 | 2022-07-15 17:00 |  | ATCO | ABESTOS | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.1 | OG4 | OG4 | 01030 | 0 | 0 | OG4-01030 | Construction | Asbestos Abatement | Construction.3.6.5.1 | Asbestos Abatement - caulk @ windows and areaway vents --> OG4 | 5 | 0 | 100% | 2022-07-12 | 2022-07-15 17:00 |  | ATCO | ABESTOS | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.2 | OG4 | OG4 | 01105 | 0 | 0 | OG4-01105 | Construction | Interior Demolition | Construction.3.6.5.2 | Selective Demo (Plaster walls, Doors, windows) - Cellar --> OG4 | 10 | 0 | 100% | 2021-05-21 | 2022-09-01 |  | MLJ | DEMO | DEMO CELLAR WALLS | 02-6005 | 02-6005-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.2 | OG4 | OG4 | 01110 | 0 | 0 | OG4-01110 | Construction | Interior Demolition | Construction.3.6.5.2 | Selective Demo (Doors, windows) - 1st Floor --> OG4 | 5 | 0 | 100% | 2022-08-29 | 2022-09-01 |  | MLJ | DEMO | DEMO DOORS WINDOWS | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.2 | OG4 | OG4 | 01115 | 0 | 0 | OG4-01115 | Construction | Interior Demolition | Construction.3.6.5.2 | Selective Demo (Areaway drain, slab, wall) --> OG4 | 10 | 0 | 100% | 2021-06-26 08:00 | 2022-09-01 |  | MLJ | DEMO | DEMO AREAWAY | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.2 | OG4 | OG4 | 01205 | 0 | 0 | OG4-01205 | Construction | Interior Demolition | Construction.3.6.5.2 | Selective Demo (Existing Ramp, railing) - 1st Floor --> OG4 | 5 | 0 | 100% | 2022-09-05 | 2022-09-07 |  | MLJ | DEMO | DEMO RAMP | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.2 | OG4 | OG4 | 01210 | 0 | 0 | OG4-01210 | Construction | Interior Demolition | Construction.3.6.5.2 | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> OG4 | 5 | 0 | 100% | 2022-06-20 | 2022-06-24 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.2 | OG4 | OG4 | 01215 | 0 | 0 | OG4-01215 | Construction | Interior Demolition | Construction.3.6.5.2 | Selective Demo - 2nd Floor Apartment for Electrical Room --> OG4 | 5 | 0 | 100% | 2021-10-04 | 2022-01-19 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.4 | OG4 | OG4 | 01310 | 0 | 0 | OG4-01310 | Construction | Interior Renovations | Construction.3.6.5.4 | Make openings in floor for conduit penetrations - 2nd floor apartments --> OG4 | 5 | 0 | 100% | 2022-03-28 | 2022-04-01 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.4 | OG4 | OG4 | 01315 | 0 | 0 | OG4-01315 | Construction | Interior Renovations | Construction.3.6.5.4 | Install beams below floor - 2nd floor apartments --> OG4 | 5 | 0 | 100% | 2022-04-18 | 2022-04-25 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.4 | OG4 | OG4 | 01320 | 0 | 0 | OG4-01320 | Construction | Interior Renovations | Construction.3.6.5.4 | Install FRP around floor openings - 2nd floor apartments --> OG4 | 5 | 0 | 100% | 2022-05-27 | 2022-06-08 |  | 0 | 0 | 0 | 0 | 0-OG4
In Progress | CI NYCHA Update #22.Construction.3.6.5.4 | OG4 | OG4 | 01325 | 0 | 0 | OG4-01325 | Construction | Interior Renovations | Construction.3.6.5.4 | Frame walls / install door for electrical room - 2nd floor --> OG4 | 3 | 1 | 66% | 2022-03-18 | 2022-11-25 17:00 | -2 | CCC | 0 | 0 | 0 | 0-OG4
In Progress | CI NYCHA Update #22.Construction.3.6.5.4 | OG4 | OG4 | 01330 | 0 | 0 | OG4-01330 | Construction | Interior Renovations | Construction.3.6.5.4 | Install drywall / tape / spackle - electrical room - 2nd floor --> OG4 | 5 | 1 | 80% | 2022-04-28 | 2022-11-25 17:00 | -2 | CCC | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.5.4 | OG4 | OG4 | 01335 | 0 | 0 | OG4-01335 | Construction | Interior Renovations | Construction.3.6.5.4 | Paint walls and seal floor electrical room - 2nd Floor --> OG4 | 10 | 10 | 0% | 2023-03-02 08:00 | 2023-03-15 17:00 | 20 | CCC | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.5.4 | OG4 | OG4 | 01340 | 0 | 0 | OG4-01340 | Construction | Interior Renovations | Construction.3.6.5.4 | Install VCT @ electrical room - 2nd Floor --> OG4 | 2 | 2 | 0% | 2023-03-16 08:00 | 2023-03-17 17:00 | 20 | UNSURE | FLOORING | VCT | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.1 | OG4 | OG4 | 01405 | 0 | 0 | OG4-01405 | Construction | East Elevation | Construction.3.6.5.EFPC.1 | Excavate at Curtain Wall for flood protection (East Side) --> OG4 | 7 | 0 | 100% | 2022-05-30 | 2022-06-03 |  | 0 | EXCAVATION | 0 | 31-1000 | 31-1000-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.1 | OG4 | OG4 | 01410 | 0 | 0 | OG4-01410 | Construction | East Elevation | Construction.3.6.5.EFPC.1 | Form concrete footings at Curtain Wall for flood protection (East Side) --> OG4 | 9 | 0 | 100% | 2022-06-17 | 2022-06-20 |  | 0 | FORMWORK | FORMWORK EB | 03-1100 | 03-1100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.1 | OG4 | OG4 | 01415 | 0 | 0 | OG4-01415 | Construction | East Elevation | Construction.3.6.5.EFPC.1 | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> OG4 | 4 | 0 | 100% | 2022-06-06 | 2022-06-14 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.1 | OG4 | OG4 | 01420 | 0 | 0 | OG4-01420 | Construction | East Elevation | Construction.3.6.5.EFPC.1 | Pour concrete footings at Curtain Wall for flood protection (East Side) --> OG4 | 3 | 0 | 100% | 2022-06-21 | 2022-06-21 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.1 | OG4 | OG4 | 01425 | 0 | 0 | OG4-01425 | Construction | East Elevation | Construction.3.6.5.EFPC.1 | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> OG4 | 4 | 0 | 100% | 2022-06-17 | 2022-06-20 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.1 | OG4 | OG4 | 01430 | 0 | 0 | OG4-01430 | Construction | East Elevation | Construction.3.6.5.EFPC.1 | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG4 | 7 | 0 | 100% | 2022-06-17 | 2022-06-20 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.1 | OG4 | OG4 | 01435 | 0 | 0 | OG4-01435 | Construction | East Elevation | Construction.3.6.5.EFPC.1 | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG4 | 5 | 0 | 100% | 2022-06-06 | 2022-06-14 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.1 | OG4 | OG4 | 01440 | 0 | 0 | OG4-01440 | Construction | East Elevation | Construction.3.6.5.EFPC.1 | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG4 | 3 | 0 | 100% | 2022-06-21 | 2022-06-21 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.1 | OG4 | OG4 | 01445 | 0 | 0 | OG4-01445 | Construction | East Elevation | Construction.3.6.5.EFPC.1 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG4 | 3 | 0 | 100% | 2022-06-17 | 2022-06-20 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.1 | OG4 | OG4 | 01450 | 0 | 0 | OG4-01450 | Construction | East Elevation | Construction.3.6.5.EFPC.1 | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> OG4 | 3 | 0 | 100% | 2022-09-26 | 2022-09-30 |  | FAXA | CMU | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.1 | OG4 | OG4 | 01455 | 0 | 0 | OG4-01455 | Construction | East Elevation | Construction.3.6.5.EFPC.1 | Backfill at Curtain Wall for flood protection (East Side) --> OG4 | 4 | 0 | 100% | 2022-10-03 | 2022-10-06 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.2 | OG4 | OG4 | 01505 | 0 | 0 | OG4-01505 | Construction | South Elevation | Construction.3.6.5.EFPC.2 | Excavate at Curtain Wall for flood protection (South Side) --> OG4 | 8 | 0 | 100% | 2022-05-30 | 2022-06-03 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.2 | OG4 | OG4 | 01510 | 0 | 0 | OG4-01510 | Construction | South Elevation | Construction.3.6.5.EFPC.2 | Form concrete footings at Curtain Wall for flood protection (South Side) --> OG4 | 10 | 0 | 100% | 2022-06-17 | 2022-06-20 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.2 | OG4 | OG4 | 01515 | 0 | 0 | OG4-01515 | Construction | South Elevation | Construction.3.6.5.EFPC.2 | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> OG4 | 5 | 0 | 100% | 2022-06-06 | 2022-06-14 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.2 | OG4 | OG4 | 01520 | 0 | 0 | OG4-01520 | Construction | South Elevation | Construction.3.6.5.EFPC.2 | Pour concrete footings at Curtain Wall for flood protection (South Side) --> OG4 | 4 | 0 | 100% | 2022-06-21 | 2022-06-21 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.2 | OG4 | OG4 | 01525 | 0 | 0 | OG4-01525 | Construction | South Elevation | Construction.3.6.5.EFPC.2 | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> OG4 | 5 | 0 | 100% | 2022-06-17 | 2022-06-20 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.2 | OG4 | OG4 | 01530 | 0 | 0 | OG4-01530 | Construction | South Elevation | Construction.3.6.5.EFPC.2 | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG4 | 8 | 0 | 100% | 2022-10-07 | 2022-10-14 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.2 | OG4 | OG4 | 01535 | 0 | 0 | OG4-01535 | Construction | South Elevation | Construction.3.6.5.EFPC.2 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG4 | 6 | 0 | 100% | 2022-10-17 | 2022-10-24 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.5.EFPC.2 | OG4 | OG4 | 01540 | 0 | 0 | OG4-01540 | Construction | South Elevation | Construction.3.6.5.EFPC.2 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG4 | 4 | 4 | 0% | 2022-11-25 08:00 | 2022-11-30 17:00 | 63 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.5.EFPC.2 | OG4 | OG4 | 01545 | 0 | 0 | OG4-01545 | Construction | South Elevation | Construction.3.6.5.EFPC.2 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG4 | 4 | 4 | 0% | 2022-12-01 08:00 | 2022-12-06 17:00 | 64 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.5.EFPC.2 | OG4 | OG4 | 01550 | 0 | 0 | OG4-01550 | Construction | South Elevation | Construction.3.6.5.EFPC.2 | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> OG4 | 4 | 4 | 0% | 2022-12-08 08:00 | 2022-12-13 17:00 | 63 | FAXA | CMU | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.5.EFPC.2 | OG4 | OG4 | 01555 | 0 | 0 | OG4-01555 | Construction | South Elevation | Construction.3.6.5.EFPC.2 | Backfill at Curtain Wall for flood protection (South Side) --> OG4 | 5 | 5 | 0% | 2022-12-14 08:00 | 2022-12-20 17:00 | 63 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.3 | OG4 | OG4 | 01605 | 0 | 0 | OG4-01605 | Construction | North Elevation | Construction.3.6.5.EFPC.3 | Excavate at Curtain Wall for flood protection (North Side) --> OG4 | 8 | 0 | 100% | 2022-06-13 08:00 | 2022-06-17 17:00 |  | MLJ | Excavation | EB EXC | 31-1000 | 31-1000-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.3 | OG4 | OG4 | 01610 | 0 | 0 | OG4-01610 | Construction | North Elevation | Construction.3.6.5.EFPC.3 | Form concrete footings at Curtain Wall for flood protection (North Side) --> OG4 | 10 | 0 | 100% | 2022-06-17 | 2022-06-20 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.3 | OG4 | OG4 | 01615 | 0 | 0 | OG4-01615 | Construction | North Elevation | Construction.3.6.5.EFPC.3 | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> OG4 | 5 | 0 | 100% | 2022-06-06 | 2022-06-14 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.3 | OG4 | OG4 | 01620 | 0 | 0 | OG4-01620 | Construction | North Elevation | Construction.3.6.5.EFPC.3 | Pour concrete footings at Curtain Wall for flood protection (North Side) --> OG4 | 4 | 0 | 100% | 2022-06-21 | 2022-06-21 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.3 | OG4 | OG4 | 01625 | 0 | 0 | OG4-01625 | Construction | North Elevation | Construction.3.6.5.EFPC.3 | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> OG4 | 5 | 0 | 100% | 2022-06-17 | 2022-06-20 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.3 | OG4 | OG4 | 01630 | 0 | 0 | OG4-01630 | Construction | North Elevation | Construction.3.6.5.EFPC.3 | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG4 | 8 | 0 | 100% | 2022-10-03 | 2022-10-06 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.3 | OG4 | OG4 | 01635 | 0 | 0 | OG4-01635 | Construction | North Elevation | Construction.3.6.5.EFPC.3 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG4 | 6 | 0 | 100% | 2022-10-07 | 2022-10-11 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.3 | OG4 | OG4 | 01640 | 0 | 0 | OG4-01640 | Construction | North Elevation | Construction.3.6.5.EFPC.3 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG4 | 4 | 0 | 100% | 2022-10-12 | 2022-10-14 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.3 | OG4 | OG4 | 01645 | 0 | 0 | OG4-01645 | Construction | North Elevation | Construction.3.6.5.EFPC.3 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG4 | 4 | 0 | 100% | 2022-10-17 | 2022-10-17 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.3 | OG4 | OG4 | 01650 | 0 | 0 | OG4-01650 | Construction | North Elevation | Construction.3.6.5.EFPC.3 | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> OG4 | 4 | 0 | 100% | 2022-10-18 | 2022-10-24 |  | FAXA | CMU | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.3 | OG4 | OG4 | 01655 | 0 | 0 | OG4-01655 | Construction | North Elevation | Construction.3.6.5.EFPC.3 | Backfill at Curtain Wall for flood protection (North Side) --> OG4 | 5 | 0 | 100% | 2022-10-25 | 2022-10-26 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.4 | OG4 | OG4 | 01705 | 0 | 0 | OG4-01705 | Construction | West Elevation | Construction.3.6.5.EFPC.4 | Excavate at Curtain Wall for flood protection (West Side) --> OG4 | 7 | 0 | 100% | 2022-05-30 | 2022-06-03 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.4 | OG4 | OG4 | 01710 | 0 | 0 | OG4-01710 | Construction | West Elevation | Construction.3.6.5.EFPC.4 | Form concrete footings at Curtain Wall for flood protection (West Side) --> OG4 | 9 | 0 | 100% | 2022-06-17 | 2022-06-20 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.4 | OG4 | OG4 | 01715 | 0 | 0 | OG4-01715 | Construction | West Elevation | Construction.3.6.5.EFPC.4 | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> OG4 | 4 | 0 | 100% | 2022-06-06 | 2022-06-14 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.4 | OG4 | OG4 | 01720 | 0 | 0 | OG4-01720 | Construction | West Elevation | Construction.3.6.5.EFPC.4 | Pour concrete footings at Curtain Wall for flood protection (West Side) --> OG4 | 3 | 0 | 100% | 2022-06-21 | 2022-06-21 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.4 | OG4 | OG4 | 01725 | 0 | 0 | OG4-01725 | Construction | West Elevation | Construction.3.6.5.EFPC.4 | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> OG4 | 4 | 0 | 100% | 2022-06-17 | 2022-06-20 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.4 | OG4 | OG4 | 01730 | 0 | 0 | OG4-01730 | Construction | West Elevation | Construction.3.6.5.EFPC.4 | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG4 | 7 | 0 | 100% | 2022-09-26 | 2022-09-30 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.4 | OG4 | OG4 | 01735 | 0 | 0 | OG4-01735 | Construction | West Elevation | Construction.3.6.5.EFPC.4 | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG4 | 5 | 0 | 100% | 2022-10-03 | 2022-10-06 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.4 | OG4 | OG4 | 01740 | 0 | 0 | OG4-01740 | Construction | West Elevation | Construction.3.6.5.EFPC.4 | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG4 | 3 | 0 | 100% | 2022-10-07 | 2022-10-14 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.4 | OG4 | OG4 | 01745 | 0 | 0 | OG4-01745 | Construction | West Elevation | Construction.3.6.5.EFPC.4 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG4 | 3 | 0 | 100% | 2022-10-17 | 2022-10-24 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.4 | OG4 | OG4 | 01750 | 0 | 0 | OG4-01750 | Construction | West Elevation | Construction.3.6.5.EFPC.4 | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> OG4 | 3 | 0 | 100% | 2022-10-25 | 2022-10-26 |  | FAXA | CMU | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.4 | OG4 | OG4 | 01755 | 0 | 0 | OG4-01755 | Construction | West Elevation | Construction.3.6.5.EFPC.4 | Backfill at Curtain Wall for flood protection (West Side) --> OG4 | 4 | 0 | 100% | 2022-10-27 | 2022-10-28 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.5 | OG4 | OG4 | 01805 | 0 | 0 | OG4-01805 | Construction | Concrete Shelf Construction | Construction.3.6.5.EFPC.5 | Excavate for concrete shelf around bldg perimeter --> OG4 | 10 | 0 | 100% | 2022-05-30 | 2022-06-06 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.5 | OG4 | OG4 | 01810 | 0 | 0 | OG4-01810 | Construction | Concrete Shelf Construction | Construction.3.6.5.EFPC.5 | Place rebar for concrete shelf around bldg perimeter --> OG4 | 5 | 0 | 100% | 2022-06-06 | 2022-06-14 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.5 | OG4 | OG4 | 01815 | 0 | 0 | OG4-01815 | Construction | Concrete Shelf Construction | Construction.3.6.5.EFPC.5 | Pour concrete shelf around bldg perimeter --> OG4 | 5 | 0 | 100% | 2022-06-21 | 2022-06-21 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.5 | OG4 | OG4 | 01820 | 0 | 0 | OG4-01820 | Construction | Concrete Shelf Construction | Construction.3.6.5.EFPC.5 | Place infill concrete in area ways around bldg perimeter --> OG4 | 5 | 0 | 100% | 2022-06-29 08:00 | 2022-07-01 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.5 | OG4 | OG4 | 01825 | 0 | 0 | OG4-01825 | Construction | Concrete Shelf Construction | Construction.3.6.5.EFPC.5 | Place waterproofing on concrete shelf around bldg perimeter --> OG4 | 10 | 0 | 100% | 2022-07-02 08:00 | 2022-07-07 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.5 | OG4 | OG4 | 01830 | 0 | 0 | OG4-01830 | Construction | Concrete Shelf Construction | Construction.3.6.5.EFPC.5 | Place CMU around bldg perimeter --OG4 | 15 | 0 | 100% | 2022-07-08 | 2022-08-18 17:00 |  | FAXA | CMU | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.5 | OG4 | OG4 | 01835 | 0 | 0 | OG4-01835 | Construction | Concrete Shelf Construction | Construction.3.6.5.EFPC.5 | Place waterproofing on CMU around bldg perimeter --> OG4 | 10 | 0 | 100% | 2022-08-16 08:00 | 2022-08-24 17:00 |  | 0 | WATERPROOFING | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.5.EFPC.5 | OG4 | OG4 | 01840 | 0 | 0 | OG4-01840 | Construction | Concrete Shelf Construction | Construction.3.6.5.EFPC.5 | Place window frames around bldg perimeter --> OG4 | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | 109 | MLJ | CONCRETE SHELF | PLACE WINDOWS | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.5 | OG4 | OG4 | 01845 | 0 | 0 | OG4-01845 | Construction | Concrete Shelf Construction | Construction.3.6.5.EFPC.5 | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> OG4 | 20 | 0 | 100% | 2022-10-19 | 2022-10-28 |  | FAXA | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.5 | OG4 | OG4 | 01850 | 0 | 0 | OG4-01850 | Construction | Concrete Shelf Construction | Construction.3.6.5.EFPC.5 | Backfill around bdg perimeter --> OG4 | 5 | 0 | 100% | 2022-10-31 | 2022-11-03 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.5.EFPC.5 | OG4 | OG4 | 01855 | 0 | 0 | OG4-01855 | Construction | Concrete Shelf Construction | Construction.3.6.5.EFPC.5 | Place frame / stucco / and signs at entrances --> OG4 | 4 | 4 | 0% | 2022-11-25 08:00 | 2022-11-30 17:00 | 115 | CCC | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.5.EFPC.5 | OG4 | OG4 | 01860 | 0 | 0 | OG4-01860 | Construction | Concrete Shelf Construction | Construction.3.6.5.EFPC.5 | Place window floodgates at windows --> OG4 | 5 | 5 | 0% | 2022-12-09 08:00 | 2022-12-15 17:00 | 109 | MLJ | FLOOD PROTECTION | FLOOD WINDOWS | 10-1400 | 10-1400-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.5.EFPC.5 | OG4 | OG4 | 01865 | 0 | 0 | OG4-01865 | Construction | Concrete Shelf Construction | Construction.3.6.5.EFPC.5 | Install signs --> OG4 | 3 | 3 | 0% | 2022-12-16 08:00 | 2022-12-20 17:00 | 109 | MLJ | SIGNS | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.5 | OG4 | OG4 | 01350 | 0 | 0 | OG4-01350 | Construction | Boiler Room Construction | Construction.3.6.5.5 | Drill dowels and place rebar for boiler room concrete walls --> OG4 | 5 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | MLJ | 0 | DRILL & DOWEL | 03-1400 | 03-1400-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.5 | OG4 | OG4 | 01355 | 0 | 0 | OG4-01355 | Construction | Boiler Room Construction | Construction.3.6.5.5 | Form boiler room concrete walls --> OG4 | 5 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.5 | OG4 | OG4 | 01360 | 0 | 0 | OG4-01360 | Construction | Boiler Room Construction | Construction.3.6.5.5 | Pour Concrete boiler room walls --> OG4 | 2 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.5 | OG4 | OG4 | 01365 | 0 | 0 | OG4-01365 | Construction | Boiler Room Construction | Construction.3.6.5.5 | Strip Forms boiler room concrete walls --> OG4 | 3 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.5 | OG4 | OG4 | 01370 | 0 | 0 | OG4-01370 | Construction | Boiler Room Construction | Construction.3.6.5.5 | Place crystaline waterproofing on perimeter walls - cellar --> OG4 - N/A | 10 | 0 | 100% | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0 | WATERPROOFING | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.6 | OG4 | OG4 | 01385 | 0 | 0 | OG4-01385 | Construction | Elevator Refurbishment | Construction.3.6.5.6 | Refurbish Elevator 1 --> OG4 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.6 | OG4 | OG4 | 01390 | 0 | 0 | OG4-01390 | Construction | Elevator Refurbishment | Construction.3.6.5.6 | Refurbish Elevator 2 --> OG4 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.6 | OG4 | OG4 | 01380 | 0 | 0 | OG4-01380 | Construction | Elevator Refurbishment | Construction.3.6.5.6 | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.5.7 | OG4 | OG4 | 09005 | 0 | 0 | OG4-09005 | Construction | Civil/Architectural Inspections | Construction.3.6.5.7 | Perform Inspections & Issue Punch List | 5 | 5 | 0% | 2023-08-21 08:00 | 2023-08-25 17:00 | -88 | MLJ | PUNCH LIST | INSPECTION | 99-8200 | 99-8200-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.5.7 | OG4 | OG4 | 09010 | 0 | 0 | OG4-09010 | Construction | Civil/Architectural Inspections | Construction.3.6.5.7 | Perform Punch List | 10 | 10 | 0% | 2023-08-28 08:00 | 2023-09-11 17:00 | -73 | MLJ | PUNCH LIST | 0 | 99-8200 | 99-8200-OG4
Completed | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 03005 | 0 | 0 | OG4-03005 | Construction | Cellar | Construction.3.6.8.1 | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 100% | 2021-05-26 | 2022-04-22 |  | 0 | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 03010 | 0 | 0 | OG4-03010 | Construction | Cellar | Construction.3.6.8.1 | Install Condensate Pump - Cellar | 10 | 10 | 0% | 2023-01-03 08:00 | 2023-01-17 17:00 | -62 | WELKIN | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 03020 | 0 | 0 | OG4-03020 | Construction | Cellar | Construction.3.6.8.1 | Install Pump Controls - Cellar | 20 | 20 | 0% | 2022-11-25 08:00 | 2022-12-22 17:00 | -62 | MEP | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 03025 | 0 | 0 | OG4-03025 | Construction | Cellar | Construction.3.6.8.1 | Perform Hydrostatic Testing - Cellar | 5 | 5 | 0% | 2023-02-08 08:00 | 2023-02-14 17:00 | -62 | WELKIN | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 03030 | 0 | 0 | OG4-03030 | Construction | Cellar | Construction.3.6.8.1 | Install Plumbing Equipment - Cellar | 15 | 15 | 0% | 2023-01-18 08:00 | 2023-02-07 17:00 | -62 | VITAL | PLUMBING EQUIP | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 03035 | 0 | 0 | OG4-03035 | Construction | Cellar | Construction.3.6.8.1 | Pump Equipment Start-up & Balance - Cellar | 10 | 10 | 0% | 2023-02-15 08:00 | 2023-03-01 17:00 | -62 | UNSURE | STARTUP | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 03040 | 0 | 0 | OG4-03040 | Construction | Cellar | Construction.3.6.8.1 | Plumbing/Mechanical Insulation - Cellar | 20 | 20 | 0% | 2023-03-02 08:00 | 2023-03-29 17:00 | -62 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 03015 | 0 | 0 | OG4-03015 | Construction | Cellar | Construction.3.6.8.1 | Install Steam Traps - Cellar | 2 | 0 | 100% | 2022-11-10 08:00 | 2022-11-11 17:00 |  | WELKIN | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 03007 | 0 | 0 | OG4-03007 | Construction | Cellar | Construction.3.6.8.1 | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 0 | 100% | 2022-08-01 | 2022-11-11 17:00 |  | WELKIN | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 03032 | 0 | 0 | OG4-03032 | Construction | Cellar | Construction.3.6.8.1 | Install Mechanical Equipment - Cellar | 20 | 0 | 100% | 2022-09-26 08:00 | 2022-10-24 17:00 |  | WELKIN | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.8.2 | OG4 | OG4 | 03105 | 0 | 0 | OG4-03105 | Construction | 1st Floor | Construction.3.6.8.2 | Rough-In Plumbing Piping & Appurtenances - 1st Floor - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG4
In Progress | CI NYCHA Update #22.Construction.3.6.8.2 | OG4 | OG4 | 03120 | 0 | 0 | OG4-03120 | Construction | 1st Floor | Construction.3.6.8.2 | Install HVAC Controls - 1st Floor | 20 | 10 | 50% | 2022-04-01 08:00 | 2023-01-12 17:00 | -45 | WELKIN | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.2 | OG4 | OG4 | 03125 | 0 | 0 | OG4-03125 | Construction | 1st Floor | Construction.3.6.8.2 | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 0% | 2023-01-13 08:00 | 2023-01-20 17:00 | -45 | WELKIN | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.2 | OG4 | OG4 | 03130 | 0 | 0 | OG4-03130 | Construction | 1st Floor | Construction.3.6.8.2 | Install Mechanical Louvers - 1st Floor | 15 | 15 | 0% | 2022-11-25 08:00 | 2022-12-15 17:00 | -45 | UNSURE | MECHANICAL LOUVERS | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.2 | OG4 | OG4 | 03135 | 0 | 0 | OG4-03135 | Construction | 1st Floor | Construction.3.6.8.2 | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 0% | 2023-01-23 08:00 | 2023-02-03 17:00 | -45 | WELKIN | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.2 | OG4 | OG4 | 03140 | 0 | 0 | OG4-03140 | Construction | 1st Floor | Construction.3.6.8.2 | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 0% | 2023-02-06 08:00 | 2023-03-06 17:00 | -45 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.2 | OG4 | OG4 | 03115 | 0 | 0 | OG4-03115 | Construction | 1st Floor | Construction.3.6.8.2 | Install Steam Traps - 1st Floor | 3 | 3 | 0% | 2022-12-09 08:00 | 2022-12-13 17:00 | -25 | WELKIN | 0 | 0 | 0 | 0-OG4
In Progress | CI NYCHA Update #22.Construction.3.6.8.2 | OG4 | OG4 | 03110 | 0 | 0 | OG4-03110 | Construction | 1st Floor | Construction.3.6.8.2 | Install Ductwork and Appurtenances - 1st Floor | 5 | 3 | 40% | 2022-04-01 08:00 | 2022-12-20 17:00 | -45 | WELKIN | DUCTWORK | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.2 | OG4 | OG4 | 03112 | 0 | 0 | OG4-03112 | Construction | 1st Floor | Construction.3.6.8.2 | Install HV & EF Units - 1st Floor | 5 | 5 | 0% | 2022-12-21 08:00 | 2022-12-28 17:00 | -45 | MEP | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.2 | OG4 | OG4 | 03107 | 0 | 0 | OG4-03107 | Construction | 1st Floor | Construction.3.6.8.2 | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 5 | 5 | 0% | 2022-12-02 08:00 | 2022-12-08 17:00 | -47 | WELKIN | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 03205 | 0 | 0 | OG4-03205 | Construction | 2nd Floor | Construction.3.6.8.3 | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 10 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 03220 | 0 | 0 | OG4-03220 | Construction | 2nd Floor | Construction.3.6.8.3 | Install HVAC Controls - 2nd Floor | 20 | 20 | 0% | 2023-01-03 08:00 | 2023-01-31 17:00 | -52 | WELKIN | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 03230 | 0 | 0 | OG4-03230 | Construction | 2nd Floor | Construction.3.6.8.3 | Install Mechanical Louvers - 2nd Floor | 15 | 15 | 0% | 2022-11-25 08:00 | 2022-12-15 17:00 | -52 | UNSURE | MECHANICAL LOUVERS | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 03235 | 0 | 0 | OG4-03235 | Construction | 2nd Floor | Construction.3.6.8.3 | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 0% | 2023-02-01 08:00 | 2023-02-14 17:00 | -52 | WELKIN | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 03240 | 0 | 0 | OG4-03240 | Construction | 2nd Floor | Construction.3.6.8.3 | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 0% | 2023-02-15 08:00 | 2023-03-15 17:00 | -52 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 03210 | 0 | 0 | OG4-03210 | Construction | 2nd Floor | Construction.3.6.8.3 | Install Ductwork and Appurtenances - 2nd Floor | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -52 | WELKIN | DUCTWORK | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.3 | OG4 | OG4 | 03215 | 0 | 0 | OG4-03215 | Construction | 2nd Floor | Construction.3.6.8.3 | Install EF Units - 2nd Floor | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | -52 | MEP | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.4 | OG4 | OG4 | 03305 | 0 | 0 | OG4-03305 | Construction | Testing & Start-Up | Construction.3.6.8.4 | DOB Mechanical/Plumbing Inspection - OG4 | 4 | 4 | 0% | 2023-03-30 08:00 | 2023-04-04 17:00 | -62 | UNSURE | INSPECTION | INSPECTION | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.4 | OG4 | OG4 | 03310 | 0 | 0 | OG4-03310 | Construction | Testing & Start-Up | Construction.3.6.8.4 | Perform Start-Up Testing - OG4 | 15 | 15 | 0% | 2023-06-19 08:00 | 2023-07-10 17:00 | -114 | UNSURE | STARTUP | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.4 | OG4 | OG4 | 03315 | 0 | 0 | OG4-03315 | Construction | Testing & Start-Up | Construction.3.6.8.4 | Start-Up Testing & Commissioning Mechanical/Plumbing - OG4 | 16 | 16 | 0% | 2023-07-11 08:00 | 2023-08-01 17:00 | -88 | UNSURE | STARTUP | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.4 | OG4 | OG4 | 03320 | 0 | 0 | OG4-03320 | Construction | Testing & Start-Up | Construction.3.6.8.4 | Perform Punch List - Electrical/Mechanical/Plumbing Work - OG4 | 5 | 5 | 0% | 2023-08-02 08:00 | 2023-08-08 17:00 | -60 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.4 | OG4 | OG4 | 03330 | 0 | 0 | OG4-03330 | Construction | Testing & Start-Up | Construction.3.6.8.4 | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - OG4 | 4 | 4 | 0% | 2023-08-10 08:00 | 2023-08-15 17:00 | -60 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.4 | OG4 | OG4 | 03325 | 0 | 0 | OG4-03325 | Construction | Testing & Start-Up | Construction.3.6.8.4 | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - OG4 | 1 | 1 | 0% | 2023-08-09 08:00 | 2023-08-09 17:00 | -60 | FSE | INSPECTION | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.8.4 | OG4 | OG4 | 03335 | 0 | 0 | OG4-03335 | Construction | Testing & Start-Up | Construction.3.6.8.4 | Remove Redundant Services - OG4 | 10 | 10 | 0% | 2023-08-02 08:00 | 2023-08-15 17:00 | -88 | UNSURE | STARTUP | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.3.5.1 | OG5 | OG5 | 01005 | 0 | 0 | OG5-01005 | Construction | Asbestos Abatement | Construction.3.3.5.1 | Asbestos Abatement - gaskets - cellar - OG5 | 3 | 3 | 0% | 2023-12-12 08:00 | 2023-12-14 17:00 | -167 | ATCO | ABESTOS | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.5.1 | OG5 | OG5 | 01010 | 0 | 0 | OG5-01010 | Construction | Asbestos Abatement | Construction.3.3.5.1 | Asbestos Abatement - wire insulation - cellar --> OG5 | 3 | 3 | 0% | 2023-12-12 08:00 | 2023-12-14 17:00 | -167 | ATCO | ABESTOS | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.1 | OG5 | OG5 | 01015 | 0 | 0 | OG5-01015 | Construction | Asbestos Abatement | Construction.3.3.5.1 | Asbestos Abatement - flooring materials at slab penetrations - cellar --> OG5 | 3 | 0 | 100% | 2021-12-27 08:00 | 2021-12-30 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.1 | OG5 | OG5 | 01020 | 0 | 0 | OG5-01020 | Construction | Asbestos Abatement | Construction.3.3.5.1 | Asbestos Abatement - pipe insulation - cellar --> OG5 | 3 | 0 | 100% | 2021-11-01 08:00 | 2021-11-10 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.1 | OG5 | OG5 | 01025 | 0 | 0 | OG5-01025 | Construction | Asbestos Abatement | Construction.3.3.5.1 | Asbestos Abatement - Window Sills - 1st Floor --> OG5 | 5 | 0 | 100% | 2022-07-13 08:00 | 2022-07-13 17:00 |  | ATCO | ABESTOS | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.1 | OG5 | OG5 | 01030 | 0 | 0 | OG5-01030 | Construction | Asbestos Abatement | Construction.3.3.5.1 | Asbestos Abatement - caulk @ windows and areaway vents --> OG5 | 5 | 0 | 100% | 2022-10-03 08:00 | 2022-10-07 17:00 |  | ATCO | ABESTOS | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.2 | OG5 | OG5 | 01105 | 0 | 0 | OG5-01105 | Construction | Interior Demolition | Construction.3.3.5.2 | Selective Demo (Plaster walls, Doors, windows) - Cellar --> OG5 | 10 | 0 | 100% | 2021-04-25 | 2022-06-01 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.2 | OG5 | OG5 | 01110 | 0 | 0 | OG5-01110 | Construction | Interior Demolition | Construction.3.3.5.2 | Selective Demo (Doors, windows) - 1st Floor --> OG5 | 5 | 0 | 100% | 2022-06-01 | 2022-06-06 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.2 | OG5 | OG5 | 01115 | 0 | 0 | OG5-01115 | Construction | Interior Demolition | Construction.3.3.5.2 | Selective Demo (Areaway drain, slab, wall) --> OG5 | 10 | 0 | 100% | 2021-06-26 08:00 | 2022-07-01 |  | MLJ | DEMO | DEMO AREAWAY | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.2 | OG5 | OG5 | 01205 | 0 | 0 | OG5-01205 | Construction | Interior Demolition | Construction.3.3.5.2 | Selective Demo (Existing Ramp, railing) - 1st Floor --> OG5 | 5 | 0 | 100% | 2022-10-17 08:00 | 2022-10-21 17:00 |  | MLJ | DEMO | DEMO RAMP | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.2 | OG5 | OG5 | 01210 | 0 | 0 | OG5-01210 | Construction | Interior Demolition | Construction.3.3.5.2 | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> OG5 | 5 | 0 | 100% | 2021-10-05 | 2022-07-06 |  | MLJ | DEMO | DEMO SLAB OPEN FOR MECH | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.2 | OG5 | OG5 | 01215 | 0 | 0 | OG5-01215 | Construction | Interior Demolition | Construction.3.3.5.2 | Selective Demo - 2nd Floor Apartment for Electrical Room --> OG5 | 5 | 0 | 100% | 2021-10-26 08:00 | 2022-01-25 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.4 | OG5 | OG5 | 01310 | 0 | 0 | OG5-01310 | Construction | Interior Renovations | Construction.3.3.5.4 | Make openings in floor for conduit penetrations - 2nd floor apartments --> OG5 | 5 | 0 | 100% | 2022-06-20 | 2022-06-24 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.4 | OG5 | OG5 | 01315 | 0 | 0 | OG5-01315 | Construction | Interior Renovations | Construction.3.3.5.4 | Install beams below floor - 2nd floor apartments --> OG5 | 5 | 0 | 100% | 2022-04-25 | 2022-04-28 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.4 | OG5 | OG5 | 01320 | 0 | 0 | OG5-01320 | Construction | Interior Renovations | Construction.3.3.5.4 | Install FRP around floor openings - 2nd floor apartments --> OG5 | 5 | 0 | 100% | 2022-06-08 | 2022-06-24 |  | 0 | 0 | 0 | 0 | 0-OG5
In Progress | CI NYCHA Update #22.Construction.3.3.5.4 | OG5 | OG5 | 01325 | 0 | 0 | OG5-01325 | Construction | Interior Renovations | Construction.3.3.5.4 | Frame walls / install door for electrical room - 2nd floor --> OG5 | 3 | 1 | 66% | 2022-04-26 | 2022-11-25 17:00 | 1 | CCC | 0 | 0 | 0 | 0-OG5
In Progress | CI NYCHA Update #22.Construction.3.3.5.4 | OG5 | OG5 | 01330 | 0 | 0 | OG5-01330 | Construction | Interior Renovations | Construction.3.3.5.4 | Install drywall / tape / spackle - electrical room - 2nd floor --> OG5 | 5 | 1 | 80% | 2022-05-11 | 2022-11-25 17:00 | 1 | CCC | 0 | 0 | 0 | 0-OG5
In Progress | CI NYCHA Update #22.Construction.3.3.5.4 | OG5 | OG5 | 01335 | 0 | 0 | OG5-01335 | Construction | Interior Renovations | Construction.3.3.5.4 | Paint walls and seal floor electrical room - 2nd Floor --> OG5 | 10 | 1 | 90% | 2022-06-20 | 2022-11-25 17:00 | 94 | CCC | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.5.4 | OG5 | OG5 | 01340 | 0 | 0 | OG5-01340 | Construction | Interior Renovations | Construction.3.3.5.4 | Install VCT @ electrical room - 2nd Floor --> OG5 | 2 | 2 | 0% | 2022-12-09 08:00 | 2022-12-12 17:00 | 85 | UNSURE | FLOORING | VCT | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.1 | OG5 | OG5 | 01405 | 0 | 0 | OG5-01405 | Construction | East Elevation | Construction.3.3.5.EFPC.1 | Excavate at Curtain Wall for flood protection (East Side) --> OG5 | 7 | 0 | 100% | 2022-05-26 | 2022-05-31 |  | 0 | EXCAVATION | 0 | 31-1000 | 31-1000-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.1 | OG5 | OG5 | 01410 | 0 | 0 | OG5-01410 | Construction | East Elevation | Construction.3.3.5.EFPC.1 | Form concrete footings at Curtain Wall for flood protection (East Side) --> OG5 | 9 | 0 | 100% | 2022-05-31 | 2022-06-02 |  | 0 | FORMWORK | FORMWORK EB | 03-1100 | 03-1100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.1 | OG5 | OG5 | 01415 | 0 | 0 | OG5-01415 | Construction | East Elevation | Construction.3.3.5.EFPC.1 | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> OG5 | 4 | 0 | 100% | 2022-06-06 | 2022-06-08 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.1 | OG5 | OG5 | 01420 | 0 | 0 | OG5-01420 | Construction | East Elevation | Construction.3.3.5.EFPC.1 | Pour concrete footings at Curtain Wall for flood protection (East Side) --> OG5 | 3 | 0 | 100% | 2022-06-09 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.1 | OG5 | OG5 | 01425 | 0 | 0 | OG5-01425 | Construction | East Elevation | Construction.3.3.5.EFPC.1 | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> OG5 | 4 | 0 | 100% | 2022-06-10 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.1 | OG5 | OG5 | 01430 | 0 | 0 | OG5-01430 | Construction | East Elevation | Construction.3.3.5.EFPC.1 | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG5 | 7 | 0 | 100% | 2022-09-30 | 2022-10-05 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.1 | OG5 | OG5 | 01435 | 0 | 0 | OG5-01435 | Construction | East Elevation | Construction.3.3.5.EFPC.1 | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG5 | 5 | 0 | 100% | 2022-10-06 | 2022-10-10 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.1 | OG5 | OG5 | 01440 | 0 | 0 | OG5-01440 | Construction | East Elevation | Construction.3.3.5.EFPC.1 | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG5 | 3 | 0 | 100% | 2022-10-11 | 2022-10-11 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.1 | OG5 | OG5 | 01445 | 0 | 0 | OG5-01445 | Construction | East Elevation | Construction.3.3.5.EFPC.1 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG5 | 3 | 0 | 100% | 2022-10-12 | 2022-10-14 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.1 | OG5 | OG5 | 01450 | 0 | 0 | OG5-01450 | Construction | East Elevation | Construction.3.3.5.EFPC.1 | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> OG5 | 3 | 0 | 100% | 2022-10-17 | 2022-10-21 |  | FAXA | CMU | 0 | 0 | 0-OG5
In Progress | CI NYCHA Update #22.Construction.3.3.5.EFPC.1 | OG5 | OG5 | 01455 | 0 | 0 | OG5-01455 | Construction | East Elevation | Construction.3.3.5.EFPC.1 | Backfill at Curtain Wall for flood protection (East Side) --> OG5 | 4 | 3 | 25% | 2022-10-24 | 2022-11-29 17:00 | 94 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.2 | OG5 | OG5 | 01505 | 0 | 0 | OG5-01505 | Construction | South Elevation | Construction.3.3.5.EFPC.2 | Excavate at Curtain Wall for flood protection (South Side) --> OG5 | 8 | 0 | 100% | 2022-05-26 | 2022-05-31 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.2 | OG5 | OG5 | 01510 | 0 | 0 | OG5-01510 | Construction | South Elevation | Construction.3.3.5.EFPC.2 | Form concrete footings at Curtain Wall for flood protection (South Side) --> OG5 | 10 | 0 | 100% | 2022-05-31 | 2022-06-02 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.2 | OG5 | OG5 | 01515 | 0 | 0 | OG5-01515 | Construction | South Elevation | Construction.3.3.5.EFPC.2 | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> OG5 | 5 | 0 | 100% | 2022-06-06 | 2022-06-08 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.2 | OG5 | OG5 | 01520 | 0 | 0 | OG5-01520 | Construction | South Elevation | Construction.3.3.5.EFPC.2 | Pour concrete footings at Curtain Wall for flood protection (South Side) --> OG5 | 4 | 0 | 100% | 2022-06-09 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.2 | OG5 | OG5 | 01525 | 0 | 0 | OG5-01525 | Construction | South Elevation | Construction.3.3.5.EFPC.2 | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> OG5 | 5 | 0 | 100% | 2022-06-10 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.2 | OG5 | OG5 | 01530 | 0 | 0 | OG5-01530 | Construction | South Elevation | Construction.3.3.5.EFPC.2 | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG5 | 8 | 0 | 100% | 2022-06-13 | 2022-06-22 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.2 | OG5 | OG5 | 01535 | 0 | 0 | OG5-01535 | Construction | South Elevation | Construction.3.3.5.EFPC.2 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG5 | 6 | 0 | 100% | 2022-06-16 | 2022-06-20 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.2 | OG5 | OG5 | 01540 | 0 | 0 | OG5-01540 | Construction | South Elevation | Construction.3.3.5.EFPC.2 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG5 | 4 | 0 | 100% | 2022-06-24 | 2022-06-24 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.2 | OG5 | OG5 | 01545 | 0 | 0 | OG5-01545 | Construction | South Elevation | Construction.3.3.5.EFPC.2 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG5 | 4 | 0 | 100% | 2022-08-23 | 2022-08-24 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.2 | OG5 | OG5 | 01550 | 0 | 0 | OG5-01550 | Construction | South Elevation | Construction.3.3.5.EFPC.2 | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> OG5 | 4 | 0 | 100% | 2022-08-25 08:00 | 2022-09-02 17:00 |  | FAXA | CMU | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.2 | OG5 | OG5 | 01555 | 0 | 0 | OG5-01555 | Construction | South Elevation | Construction.3.3.5.EFPC.2 | Backfill at Curtain Wall for flood protection (South Side) --> OG5 | 5 | 0 | 100% | 2022-08-15 | 2022-08-16 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.2 | OG5 | OG5 | 01560 | 0 | 0 | OG5-01560 | Construction | South Elevation | Construction.3.3.5.EFPC.2 | Form for slab at Curtain Wall for flood protection (South Side) --> OG5 | 4 | 0 | 100% | 2022-08-18 | 2022-08-18 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.2 | OG5 | OG5 | 01565 | 0 | 0 | OG5-01565 | Construction | South Elevation | Construction.3.3.5.EFPC.2 | Rebar & inserts for slab at Curtain Wall for flood protection (South Side) --> OG5 | 6 | 0 | 100% | 2022-08-19 | 2022-08-19 17:00 |  | 0 | REBAR | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.2 | OG5 | OG5 | 01570 | 0 | 0 | OG5-01570 | Construction | South Elevation | Construction.3.3.5.EFPC.2 | Pour slab at Curtain Wall for flood protection (South Side) --> OG5 | 4 | 0 | 100% | 2022-08-22 08:00 | 2022-08-22 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.2 | OG5 | OG5 | 01575 | 0 | 0 | OG5-01575 | Construction | South Elevation | Construction.3.3.5.EFPC.2 | Strip Forms for slab at Curtain Wall for flood protection (South Side) --> OG5 | 2 | 0 | 100% | 2022-08-23 08:00 | 2022-08-24 17:00 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.5.EFPC.2 | OG5 | OG5 | 01580 | 0 | 0 | OG5-01580 | Construction | South Elevation | Construction.3.3.5.EFPC.2 | Backfill surounding area at Curtain Wall for flood protection (South Side) --> OG5 | 4 | 4 | 0% | 2022-11-25 08:00 | 2022-11-30 17:00 | 100 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.3 | OG5 | OG5 | 01605 | 0 | 0 | OG5-01605 | Construction | North Elevation | Construction.3.3.5.EFPC.3 | Excavate at Curtain Wall for flood protection (North Side) --> OG5 | 8 | 0 | 100% | 2022-05-16 | 2022-05-20 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.3 | OG5 | OG5 | 01610 | 0 | 0 | OG5-01610 | Construction | North Elevation | Construction.3.3.5.EFPC.3 | Form concrete footings at Curtain Wall for flood protection (North Side) --> OG5 | 10 | 0 | 100% | 2022-05-26 | 2022-05-31 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.3 | OG5 | OG5 | 01615 | 0 | 0 | OG5-01615 | Construction | North Elevation | Construction.3.3.5.EFPC.3 | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> OG5 | 5 | 0 | 100% | 2022-05-31 | 2022-06-02 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.3 | OG5 | OG5 | 01620 | 0 | 0 | OG5-01620 | Construction | North Elevation | Construction.3.3.5.EFPC.3 | Pour concrete footings at Curtain Wall for flood protection (North Side) --> OG5 | 4 | 0 | 100% | 2022-06-06 | 2022-06-08 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.3 | OG5 | OG5 | 01625 | 0 | 0 | OG5-01625 | Construction | North Elevation | Construction.3.3.5.EFPC.3 | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> OG5 | 5 | 0 | 100% | 2022-06-09 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.3 | OG5 | OG5 | 01630 | 0 | 0 | OG5-01630 | Construction | North Elevation | Construction.3.3.5.EFPC.3 | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG5 | 8 | 0 | 100% | 2022-06-10 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.3 | OG5 | OG5 | 01635 | 0 | 0 | OG5-01635 | Construction | North Elevation | Construction.3.3.5.EFPC.3 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG5 | 6 | 0 | 100% | 2022-08-01 | 2022-08-03 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.3 | OG5 | OG5 | 01640 | 0 | 0 | OG5-01640 | Construction | North Elevation | Construction.3.3.5.EFPC.3 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG5 | 4 | 0 | 100% | 2022-08-07 | 2022-08-08 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.3 | OG5 | OG5 | 01645 | 0 | 0 | OG5-01645 | Construction | North Elevation | Construction.3.3.5.EFPC.3 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG5 | 4 | 0 | 100% | 2022-08-10 | 2022-08-12 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.3 | OG5 | OG5 | 01650 | 0 | 0 | OG5-01650 | Construction | North Elevation | Construction.3.3.5.EFPC.3 | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> OG5 | 4 | 0 | 100% | 2022-08-15 | 2022-08-19 |  | FAXA | CMU | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.3 | OG5 | OG5 | 01655 | 0 | 0 | OG5-01655 | Construction | North Elevation | Construction.3.3.5.EFPC.3 | Backfill at Curtain Wall for flood protection (North Side) --> OG5 | 5 | 0 | 100% | 2022-08-22 | 2022-08-25 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.4 | OG5 | OG5 | 01705 | 0 | 0 | OG5-01705 | Construction | West Elevation | Construction.3.3.5.EFPC.4 | Excavate at Curtain Wall for flood protection (West Side) --> OG5 | 7 | 0 | 100% | 2022-05-16 08:00 | 2022-05-20 17:00 |  | MLJ | Excavation | EB EXC | 31-1000 | 31-1000-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.4 | OG5 | OG5 | 01710 | 0 | 0 | OG5-01710 | Construction | West Elevation | Construction.3.3.5.EFPC.4 | Form concrete footings at Curtain Wall for flood protection (West Side) --> OG5 | 9 | 0 | 100% | 2022-05-26 | 2022-05-31 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.4 | OG5 | OG5 | 01715 | 0 | 0 | OG5-01715 | Construction | West Elevation | Construction.3.3.5.EFPC.4 | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> OG5 | 4 | 0 | 100% | 2022-05-31 | 2022-06-02 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.4 | OG5 | OG5 | 01720 | 0 | 0 | OG5-01720 | Construction | West Elevation | Construction.3.3.5.EFPC.4 | Pour concrete footings at Curtain Wall for flood protection (West Side) --> OG5 | 3 | 0 | 100% | 2022-06-06 | 2022-06-08 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.4 | OG5 | OG5 | 01725 | 0 | 0 | OG5-01725 | Construction | West Elevation | Construction.3.3.5.EFPC.4 | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> OG5 | 4 | 0 | 100% | 2022-06-09 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.4 | OG5 | OG5 | 01730 | 0 | 0 | OG5-01730 | Construction | West Elevation | Construction.3.3.5.EFPC.4 | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG5 | 7 | 0 | 100% | 2022-06-10 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.5.EFPC.4 | OG5 | OG5 | 01735 | 0 | 0 | OG5-01735 | Construction | West Elevation | Construction.3.3.5.EFPC.4 | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG5 | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 85 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.5.EFPC.4 | OG5 | OG5 | 01740 | 0 | 0 | OG5-01740 | Construction | West Elevation | Construction.3.3.5.EFPC.4 | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG5 | 3 | 3 | 0% | 2022-12-02 08:00 | 2022-12-06 17:00 | 85 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.5.EFPC.4 | OG5 | OG5 | 01745 | 0 | 0 | OG5-01745 | Construction | West Elevation | Construction.3.3.5.EFPC.4 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG5 | 3 | 3 | 0% | 2022-12-07 08:00 | 2022-12-09 17:00 | 87 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.5.EFPC.4 | OG5 | OG5 | 01750 | 0 | 0 | OG5-01750 | Construction | West Elevation | Construction.3.3.5.EFPC.4 | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> OG5 | 3 | 3 | 0% | 2022-12-14 08:00 | 2022-12-16 17:00 | 85 | FAXA | CMU | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.5.EFPC.4 | OG5 | OG5 | 01755 | 0 | 0 | OG5-01755 | Construction | West Elevation | Construction.3.3.5.EFPC.4 | Backfill at Curtain Wall for flood protection (West Side) --> OG5 | 4 | 4 | 0% | 2022-12-19 08:00 | 2022-12-22 17:00 | 85 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.5 | OG5 | OG5 | 01805 | 0 | 0 | OG5-01805 | Construction | Concrete Shelf Construction | Construction.3.3.5.EFPC.5 | Excavate for concrete shelf around bldg perimeter --> OG5 | 10 | 0 | 100% | 2022-05-05 08:00 | 2022-05-20 17:00 |  | MLJ | Excavation | EB EXC | 31-1000 | 31-1000-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.5 | OG5 | OG5 | 01810 | 0 | 0 | OG5-01810 | Construction | Concrete Shelf Construction | Construction.3.3.5.EFPC.5 | Place rebar for concrete shelf around bldg perimeter --> OG5 | 5 | 0 | 100% | 2022-06-08 | 2022-06-09 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.5 | OG5 | OG5 | 01815 | 0 | 0 | OG5-01815 | Construction | Concrete Shelf Construction | Construction.3.3.5.EFPC.5 | Pour concrete shelf around bldg perimeter --> OG5 | 5 | 0 | 100% | 2022-06-09 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.5 | OG5 | OG5 | 01820 | 0 | 0 | OG5-01820 | Construction | Concrete Shelf Construction | Construction.3.3.5.EFPC.5 | Place infill concrete in area ways around bldg perimeter --> OG5 | 5 | 0 | 100% | 2022-06-30 08:00 | 2022-07-07 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.5 | OG5 | OG5 | 01825 | 0 | 0 | OG5-01825 | Construction | Concrete Shelf Construction | Construction.3.3.5.EFPC.5 | Place waterproofing on concrete shelf around bldg perimeter --> OG5 | 10 | 0 | 100% | 2022-08-01 08:00 | 2022-08-05 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.5 | OG5 | OG5 | 01830 | 0 | 0 | OG5-01830 | Construction | Concrete Shelf Construction | Construction.3.3.5.EFPC.5 | Place CMU around bldg perimeter --OG5 | 15 | 0 | 100% | 2022-07-22 | 2022-08-11 17:00 |  | FAXA | CMU | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.5 | OG5 | OG5 | 01835 | 0 | 0 | OG5-01835 | Construction | Concrete Shelf Construction | Construction.3.3.5.EFPC.5 | Place waterproofing on CMU around bldg perimeter --> OG5 | 10 | 0 | 100% | 2022-08-01 08:00 | 2022-08-05 17:00 |  | 0 | WATERPROOFING | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.5.EFPC.5 | OG5 | OG5 | 01840 | 0 | 0 | OG5-01840 | Construction | Concrete Shelf Construction | Construction.3.3.5.EFPC.5 | Place window frames around bldg perimeter --> OG5 | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | 109 | MLJ | CONCRETE SHELF | PLACE WINDOWS | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.5 | OG5 | OG5 | 01845 | 0 | 0 | OG5-01845 | Construction | Concrete Shelf Construction | Construction.3.3.5.EFPC.5 | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> OG5 | 20 | 0 | 100% | 2022-09-12 | 2022-10-24 |  | FAXA | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.5 | OG5 | OG5 | 01850 | 0 | 0 | OG5-01850 | Construction | Concrete Shelf Construction | Construction.3.3.5.EFPC.5 | Backfill around bdg perimeter --> OG5 | 5 | 0 | 100% | 2022-11-14 | 2022-11-18 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.5.EFPC.5 | OG5 | OG5 | 01855 | 0 | 0 | OG5-01855 | Construction | Concrete Shelf Construction | Construction.3.3.5.EFPC.5 | Place frame / stucco / and signs at entrances --> OG5 | 4 | 4 | 0% | 2022-11-25 08:00 | 2022-11-30 17:00 | 115 | CCC | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.5.EFPC.5 | OG5 | OG5 | 01860 | 0 | 0 | OG5-01860 | Construction | Concrete Shelf Construction | Construction.3.3.5.EFPC.5 | Place window floodgates at windows --> OG5 | 5 | 5 | 0% | 2022-12-09 08:00 | 2022-12-15 17:00 | 109 | MLJ | FLOOD PROTECTION | FLOOD WINDOWS | 10-1400 | 10-1400-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.5.EFPC.5 | OG5 | OG5 | 01865 | 0 | 0 | OG5-01865 | Construction | Concrete Shelf Construction | Construction.3.3.5.EFPC.5 | Install signs --> OG5 | 3 | 3 | 0% | 2022-12-16 08:00 | 2022-12-20 17:00 | 109 | MLJ | SIGNS | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.5 | OG5 | OG5 | 01350 | 0 | 0 | OG5-01350 | Construction | Boiler Room Construction | Construction.3.3.5.5 | Drill dowels and place rebar for boiler room concrete walls --> OG5 | 5 | 0 | 100% | 2022-10-27 | 2022-10-28 |  | MLJ | 0 | DRILL & DOWEL | 03-1400 | 03-1400-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.5 | OG5 | OG5 | 01355 | 0 | 0 | OG5-01355 | Construction | Boiler Room Construction | Construction.3.3.5.5 | Form boiler room concrete walls --> OG5 | 5 | 0 | 100% | 2022-11-02 | 2022-11-08 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.5 | OG5 | OG5 | 01360 | 0 | 0 | OG5-01360 | Construction | Boiler Room Construction | Construction.3.3.5.5 | Pour Concrete boiler room walls --> OG5 | 2 | 0 | 100% | 2022-11-09 | 2022-11-10 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.5 | OG5 | OG5 | 01365 | 0 | 0 | OG5-01365 | Construction | Boiler Room Construction | Construction.3.3.5.5 | Strip Forms boiler room concrete walls --> OG5 | 3 | 0 | 100% | 2022-11-14 | 2022-11-16 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.5 | OG5 | OG5 | 01370 | 0 | 0 | OG5-01370 | Construction | Boiler Room Construction | Construction.3.3.5.5 | Place crystaline waterproofing on perimeter walls - cellar --> OG5 - N/A | 10 | 0 | 100% | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0 | WATERPROOFING | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.6 | OG5 | OG5 | 01385 | 0 | 0 | OG5-01385 | Construction | Elevator Refurbishment | Construction.3.3.5.6 | Refurbish Elevator 1 --> OG5 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.6 | OG5 | OG5 | 01390 | 0 | 0 | OG5-01390 | Construction | Elevator Refurbishment | Construction.3.3.5.6 | Refurbish Elevator 2 --> OG5 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.6 | OG5 | OG5 | 01380 | 0 | 0 | OG5-01380 | Construction | Elevator Refurbishment | Construction.3.3.5.6 | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.5.7 | OG5 | OG5 | 09005 | 0 | 0 | OG5-09005 | Construction | Civil/Architectural Inspections | Construction.3.3.5.7 | Perform Inspections & Issue Punch List | 5 | 5 | 0% | 2023-12-15 08:00 | 2023-12-21 17:00 | -167 | MLJ | PUNCH LIST | INSPECTION | 99-8200 | 99-8200-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.5.7 | OG5 | OG5 | 09010 | 0 | 0 | OG5-09010 | Construction | Civil/Architectural Inspections | Construction.3.3.5.7 | Perform Punch List | 10 | 10 | 0% | 2023-12-22 08:00 | 2024-01-08 17:00 | -152 | MLJ | PUNCH LIST | 0 | 99-8200 | 99-8200-OG5
Not Started | CI NYCHA Update #22.Construction.3.6.5.2 | OG4 | OG4 | 01220 | 0 | 0 | OG4-01220 | Construction | Interior Demolition | Construction.3.6.5.2 | Selective Demo (Pumps etc..) - Cellar --> OG4 | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | -62 | MLJ | DEMO | DEMO PUMPS | 02-6010 | 02-6010-OG4
Completed | CI NYCHA Update #22.Construction.3.3.5.2 | OG5 | OG5 | 01220 | 0 | 0 | OG5-01220 | Construction | Interior Demolition | Construction.3.3.5.2 | Selective Demo (Pumps etc..) - Cellar --> OG5 | 5 | 0 | 100% | 2022-10-03 08:00 | 2022-10-07 17:00 |  | MLJ | DEMO | DEMO PUMPS | 02-6010 | 02-6010-OG5
Completed | CI NYCHA Update #22.Construction.3.5.2 | OGP1 | OGP1 | 02130 | 0 | 0 | OGP1-02130 | Construction | Cable Pulls | Construction.3.5.2 | Pull & Terminate Automatic Temperature Control Cable - OG-8 --> OG-4 | 10 | 0 | 100% | 2022-04-12 | 2022-04-16 |  | 0 | 0 | 0 | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.2 | OGP1 | OGP1 | 02150 | 0 | 0 | OGP1-02150 | Construction | Cable Pulls | Construction.3.5.2 | Pull & Terminate Automatic Temperature Control Cable - OG-8 --> OG-5 | 10 | 10 | 0% | 2023-09-26 08:00 | 2023-10-09 17:00 | -193 | FSE | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 03005 | 0 | 0 | OG5-03005 | Construction | Cellar | Construction.3.3.8.1 | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 100% | 2022-08-01 | 2022-09-01 |  | WELKIN | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 03010 | 0 | 0 | OG5-03010 | Construction | Cellar | Construction.3.3.8.1 | Install Condensate Pump - Cellar | 10 | 0 | 100% | 2022-09-26 | 2022-10-14 |  | WELKIN | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 03020 | 0 | 0 | OG5-03020 | Construction | Cellar | Construction.3.3.8.1 | Install Pump Controls - Cellar | 20 | 20 | 0% | 2022-12-09 08:00 | 2023-01-09 17:00 | -42 | MEP | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 03025 | 0 | 0 | OG5-03025 | Construction | Cellar | Construction.3.3.8.1 | Perform Hydrostatic Testing - Cellar | 5 | 5 | 0% | 2023-01-10 08:00 | 2023-01-17 17:00 | -42 | WELKIN | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 03030 | 0 | 0 | OG5-03030 | Construction | Cellar | Construction.3.3.8.1 | Install Plumbing Equipment - Cellar | 15 | 0 | 100% | 2022-09-01 | 2022-09-15 |  | 0 | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 03035 | 0 | 0 | OG5-03035 | Construction | Cellar | Construction.3.3.8.1 | Pump Equipment Start-up & Balance - Cellar | 10 | 10 | 0% | 2023-01-18 08:00 | 2023-01-31 17:00 | -42 | UNSURE | STARTUP | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 03040 | 0 | 0 | OG5-03040 | Construction | Cellar | Construction.3.3.8.1 | Plumbing/Mechanical Insulation - Cellar | 20 | 20 | 0% | 2023-02-01 08:00 | 2023-03-01 17:00 | -42 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 03015 | 0 | 0 | OG5-03015 | Construction | Cellar | Construction.3.3.8.1 | Install Steam Traps - Cellar | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | -14 | WELKIN | 0 | 0 | 0 | 0-OG5
In Progress | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 03007 | 0 | 0 | OG5-03007 | Construction | Cellar | Construction.3.3.8.1 | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 10 | 50% | 2022-04-01 08:00 | 2022-12-08 17:00 | -72 | WELKIN | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 03032 | 0 | 0 | OG5-03032 | Construction | Cellar | Construction.3.3.8.1 | Install Mechanical Equipment - Cellar | 20 | 20 | 0% | 2022-12-09 08:00 | 2023-01-09 17:00 | -42 | WELKIN | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.8.2 | OG5 | OG5 | 03105 | 0 | 0 | OG5-03105 | Construction | 1st Floor | Construction.3.3.8.2 | Rough-In Plumbing Piping & Appurtenances - 1st Floor - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.2 | OG5 | OG5 | 03120 | 0 | 0 | OG5-03120 | Construction | 1st Floor | Construction.3.3.8.2 | Install HVAC Controls - 1st Floor | 20 | 20 | 0% | 2023-01-18 08:00 | 2023-02-14 17:00 | -67 | WELKIN | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.2 | OG5 | OG5 | 03125 | 0 | 0 | OG5-03125 | Construction | 1st Floor | Construction.3.3.8.2 | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 0% | 2023-02-15 08:00 | 2023-02-22 17:00 | -67 | WELKIN | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.2 | OG5 | OG5 | 03130 | 0 | 0 | OG5-03130 | Construction | 1st Floor | Construction.3.3.8.2 | Install Mechanical Louvers - 1st Floor | 15 | 15 | 0% | 2022-12-23 08:00 | 2023-01-17 17:00 | -67 | UNSURE | MECHANICAL LOUVERS | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.2 | OG5 | OG5 | 03135 | 0 | 0 | OG5-03135 | Construction | 1st Floor | Construction.3.3.8.2 | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 0% | 2023-02-23 08:00 | 2023-03-08 17:00 | -67 | WELKIN | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.2 | OG5 | OG5 | 03140 | 0 | 0 | OG5-03140 | Construction | 1st Floor | Construction.3.3.8.2 | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 0% | 2023-03-09 08:00 | 2023-04-05 17:00 | -67 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG5
In Progress | CI NYCHA Update #22.Construction.3.3.8.2 | OG5 | OG5 | 03115 | 0 | 0 | OG5-03115 | Construction | 1st Floor | Construction.3.3.8.2 | Install Steam Traps - 1st Floor | 1 | 1 | 0% | 2022-11-21 08:00 | 2022-11-25 17:00 | -13 | WELKIN | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.2 | OG5 | OG5 | 03110 | 0 | 0 | OG5-03110 | Construction | 1st Floor | Construction.3.3.8.2 | Install Ductwork and Appurtenances - 1st Floor | 5 | 5 | 0% | 2022-12-09 08:00 | 2022-12-15 17:00 | -67 | WELKIN | DUCTWORK | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.2 | OG5 | OG5 | 03112 | 0 | 0 | OG5-03112 | Construction | 1st Floor | Construction.3.3.8.2 | Install HV & EF Units - 1st Floor | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -67 | MEP | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.2 | OG5 | OG5 | 03107 | 0 | 0 | OG5-03107 | Construction | 1st Floor | Construction.3.3.8.2 | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 10 | 0% | 2022-12-09 08:00 | 2022-12-22 17:00 | -72 | WELKIN | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 03205 | 0 | 0 | OG5-03205 | Construction | 2nd Floor | Construction.3.3.8.3 | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 10 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 03220 | 0 | 0 | OG5-03220 | Construction | 2nd Floor | Construction.3.3.8.3 | Install HVAC Controls - 2nd Floor | 20 | 20 | 0% | 2023-02-01 08:00 | 2023-03-01 17:00 | -72 | WELKIN | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 03230 | 0 | 0 | OG5-03230 | Construction | 2nd Floor | Construction.3.3.8.3 | Install Mechanical Louvers - 2nd Floor | 15 | 15 | 0% | 2023-01-10 08:00 | 2023-01-31 17:00 | -72 | UNSURE | MECHANICAL LOUVERS | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 03235 | 0 | 0 | OG5-03235 | Construction | 2nd Floor | Construction.3.3.8.3 | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 0% | 2023-03-02 08:00 | 2023-03-15 17:00 | -72 | WELKIN | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 03240 | 0 | 0 | OG5-03240 | Construction | 2nd Floor | Construction.3.3.8.3 | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 0% | 2023-03-16 08:00 | 2023-04-12 17:00 | -72 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 03210 | 0 | 0 | OG5-03210 | Construction | 2nd Floor | Construction.3.3.8.3 | Install Ductwork and Appurtenances - 2nd Floor | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | -72 | WELKIN | DUCTWORK | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.3 | OG5 | OG5 | 03215 | 0 | 0 | OG5-03215 | Construction | 2nd Floor | Construction.3.3.8.3 | Install EF Units - 2nd Floor | 5 | 5 | 0% | 2023-01-03 08:00 | 2023-01-09 17:00 | -72 | MEP | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.4 | OG5 | OG5 | 03305 | 0 | 0 | OG5-03305 | Construction | Testing & Start-Up | Construction.3.3.8.4 | DOB Mechanical/Plumbing Inspection - OG5 | 4 | 4 | 0% | 2023-09-26 08:00 | 2023-09-29 17:00 | -187 | UNSURE | INSPECTION | INSPECTION | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.4 | OG5 | OG5 | 03310 | 0 | 0 | OG5-03310 | Construction | Testing & Start-Up | Construction.3.3.8.4 | Perform Start-Up Testing - OG5 | 15 | 15 | 0% | 2023-10-10 08:00 | 2023-10-31 17:00 | -193 | UNSURE | STARTUP | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.4 | OG5 | OG5 | 03315 | 0 | 0 | OG5-03315 | Construction | Testing & Start-Up | Construction.3.3.8.4 | Start-Up Testing & Commissioning Mechanical/Plumbing - OG5 | 16 | 16 | 0% | 2023-11-01 08:00 | 2023-11-27 17:00 | -167 | UNSURE | STARTUP | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.4 | OG5 | OG5 | 03320 | 0 | 0 | OG5-03320 | Construction | Testing & Start-Up | Construction.3.3.8.4 | Perform Punch List - Electrical/Mechanical/Plumbing Work - OG5 | 5 | 5 | 0% | 2023-11-28 08:00 | 2023-12-04 17:00 | -139 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.4 | OG5 | OG5 | 03330 | 0 | 0 | OG5-03330 | Construction | Testing & Start-Up | Construction.3.3.8.4 | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - OG5 | 4 | 4 | 0% | 2023-12-06 08:00 | 2023-12-11 17:00 | -139 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.4 | OG5 | OG5 | 03325 | 0 | 0 | OG5-03325 | Construction | Testing & Start-Up | Construction.3.3.8.4 | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - OG5 | 1 | 1 | 0% | 2023-12-05 08:00 | 2023-12-05 17:00 | -139 | FSE | INSPECTION | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.8.4 | OG5 | OG5 | 03335 | 0 | 0 | OG5-03335 | Construction | Testing & Start-Up | Construction.3.3.8.4 | Remove Redundant Services - OG5 | 10 | 10 | 0% | 2023-11-28 08:00 | 2023-12-11 17:00 | -167 | UNSURE | STARTUP | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Construction.5.6.Removals1 | OGW | OGW | 01005 | 0 | 0 | OGW-01005 | Construction | Site Protection & Removals | Construction.5.6.Removals1 | Install Site Fencing - O'Dwyer Gardens - West (OG-9) | 10 | 0 | 100% | 2021-02-15 | 2021-02-18 17:00 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.Removals1 | OGW | OGW | 01015 | 0 | 0 | OGW-01015 | Construction | Site Protection & Removals | Construction.5.6.Removals1 | Install Overhead Protection - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.Removals1 | OGW | OGW | 01020 | 0 | 0 | OGW-01020 | Construction | Site Protection & Removals | Construction.5.6.Removals1 | Install Tree Protection | 5 | 0 | 100% | 2020-11-05 | 2020-11-11 17:00 |  | 0 | 0 | 0 | 31-1900 | 31-1900-OGW
Completed | CI NYCHA Update #22.Construction.5.6.Removals1 | OGW | OGW | 01025 | 0 | 0 | OGW-01025 | Construction | Site Protection & Removals | Construction.5.6.Removals1 | Remove Trees | 2 | 0 | 100% | 2021-01-14 | 2021-01-16 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.Removals1 | OGW | OGW | 01000 | 0 | 0 | OGW-01000 | Construction | Site Protection & Removals | Construction.5.6.Removals1 | Remove Curbs And Existing Fencing | 10 | 0 | 100% | 2021-02-23 | 2022-02-02 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.Removals1 | OGW | OGW | 01035 | 0 | 0 | OGW-01035 | Construction | Site Protection & Removals | Construction.5.6.Removals1 | Install Erosion Control | 5 | 0 | 100% | 2022-02-02 | 2022-02-04 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.Removals1 | OGW | OGW | 01010 | 0 | 0 | OGW-01010 | Construction | Site Protection & Removals | Construction.5.6.Removals1 | Set Up Yard and Staging - N/A | 10 | 0 | 100% | 2021-02-01 | 2021-02-01 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.Removals1 | OGW | OGW | 01045 | 0 | 0 | OGW-01045 | Construction | Site Protection & Removals | Construction.5.6.Removals1 | Clear & Grub | 10 | 0 | 100% | 2021-03-26 | 2022-02-02 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.Removals1 | OGW | OGW | 01050 | 0 | 0 | OGW-01050 | Construction | Site Protection & Removals | Construction.5.6.Removals1 | Scrape & Store Topsoil | 10 | 0 | 100% | 2021-03-26 | 2022-02-02 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.Removals1 | OGW | OGW | 01055 | 0 | 0 | OGW-01055 | Construction | Site Protection & Removals | Construction.5.6.Removals1 | Soil Testing | 10 | 0 | 100% | 2021-03-04 | 2021-03-14 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.Removals1 | OGW | OGW | 01060 | 0 | 0 | OGW-01060 | Construction | Site Protection & Removals | Construction.5.6.Removals1 | Demo Playgrounds And Misc Site Furniture | 5 | 0 | 100% | 2021-04-26 | 2022-02-02 |  | 0 | 0 | 0 | 02-2000 | 02-2000-OGW
Completed | CI NYCHA Update #22.Construction.5.6.Removals1 | OGW | OGW | 01065 | 0 | 0 | OGW-01065 | Construction | Site Protection & Removals | Construction.5.6.Removals1 | Remove Retaining Walls | 10 | 0 | 100% | 2022-01-21 | 2022-03-18 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.Removals1 | OGW | OGW | 01070 | 0 | 0 | OGW-01070 | Construction | Site Protection & Removals | Construction.5.6.Removals1 | Install Deep Wells For Dewatering - N/A | 10 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.Removals1 | OGW | OGW | 01075 | 0 | 0 | OGW-01075 | Construction | Site Protection & Removals | Construction.5.6.Removals1 | Install Piping For Deep Wells - N/A | 5 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.Removals1 | OGW | OGW | 01080 | 0 | 0 | OGW-01080 | Construction | Site Protection & Removals | Construction.5.6.Removals1 | Install Discharge Connection For Dewatering - N/A | 10 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.Removals1 | OGW | OGW | 01085 | 0 | 0 | OGW-01085 | Construction | Site Protection & Removals | Construction.5.6.Removals1 | Run Electric For Dewatering - N/A | 10 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01105 | 0 | 0 | OGW-01105 | Construction | Site Utilities | Construction.5.6.6 | Excavate for CW Pipe - OG3 --> OG9 | 10 | 0 | 100% | 2021-09-02 | 2021-09-24 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01110 | 0 | 0 | OGW-01110 | Construction | Site Utilities | Construction.5.6.6 | Install CW Piping - OG3 --> OG9 | 15 | 0 | 100% | 2021-11-26 08:00 | 2021-12-29 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01115 | 0 | 0 | OGW-01115 | Construction | Site Utilities | Construction.5.6.6 | Test CW Piping - OG3 --> OG9 | 10 | 0 | 100% | 2021-12-29 | 2022-01-04 |  | WELKIN | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01120 | 0 | 0 | OGW-01120 | Construction | Site Utilities | Construction.5.6.6 | Backfill CW Piping - OG3 --> OG9 | 5 | 0 | 100% | 2022-05-04 | 2022-05-10 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01150 | 0 | 0 | OGW-01150 | Construction | Site Utilities | Construction.5.6.6 | Excavate for Electric OG3--> OG9 | 10 | 0 | 100% | 2021-10-04 | 2021-10-13 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01155 | 0 | 0 | OGW-01155 | Construction | Site Utilities | Construction.5.6.6 | Install Electrical Conduit OG3--> OG9 | 10 | 0 | 100% | 2021-10-05 | 2021-12-30 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01160 | 0 | 0 | OGW-01160 | Construction | Site Utilities | Construction.5.6.6 | Encase conduit in concrete OG3--> OG9 | 5 | 0 | 100% | 2021-12-01 | 2022-01-12 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01165 | 0 | 0 | OGW-01165 | Construction | Site Utilities | Construction.5.6.6 | Backfill Electrical OG3--> OG9 | 5 | 0 | 100% | 2022-01-03 | 2022-01-14 |  | 0 | 0 | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01405 | 0 | 0 | OGW-01405 | Construction | Site Utilities | Construction.5.6.6 | National Gas to Install Line - W35th --> OG9 | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 91 | NATIONAL GRID | GAS INSTALL | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01205 | 0 | 0 | OGW-01205 | Construction | Site Utilities | Construction.5.6.6 | Excavate for Electric OG3--> MH | 3 | 0 | 100% | 2021-10-10 | 2021-10-13 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01210 | 0 | 0 | OGW-01210 | Construction | Site Utilities | Construction.5.6.6 | Install Electrical Conduit OG3--> MH | 2 | 0 | 100% | 2021-11-26 | 2021-12-29 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01215 | 0 | 0 | OGW-01215 | Construction | Site Utilities | Construction.5.6.6 | Encase conduit in concrete OG3--> MH | 2 | 0 | 100% | 2022-01-10 | 2022-01-12 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01220 | 0 | 0 | OGW-01220 | Construction | Site Utilities | Construction.5.6.6 | Backfill Electrical OG3 --> MH | 2 | 0 | 100% | 2022-01-03 | 2022-01-14 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01230 | 0 | 0 | OGW-01230 | Construction | Site Utilities | Construction.5.6.6 | Excavate for Electric OG2 -> OG9 | 10 | 0 | 100% | 2021-10-13 | 2021-12-10 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01235 | 0 | 0 | OGW-01235 | Construction | Site Utilities | Construction.5.6.6 | Install Electrical Conduit & MH OG2 -> OG9 | 10 | 0 | 100% | 2021-10-05 | 2022-01-05 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01240 | 0 | 0 | OGW-01240 | Construction | Site Utilities | Construction.5.6.6 | Encase conduit in concrete OG2 -> OG9 | 3 | 0 | 100% | 2021-12-01 | 2022-01-05 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01245 | 0 | 0 | OGW-01245 | Construction | Site Utilities | Construction.5.6.6 | Backfill Electrical OG2 -> OG9 | 5 | 0 | 100% | 2021-12-05 | 2022-01-06 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01255 | 0 | 0 | OGW-01255 | Construction | Site Utilities | Construction.5.6.6 | Excavate for Electric OG2--> MH | 3 | 0 | 100% | 2022-01-14 | 2022-01-18 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01260 | 0 | 0 | OGW-01260 | Construction | Site Utilities | Construction.5.6.6 | Install Electrical Conduit OG2--> MH | 2 | 0 | 100% | 2021-12-08 | 2022-02-16 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01265 | 0 | 0 | OGW-01265 | Construction | Site Utilities | Construction.5.6.6 | Encase conduit in concrete OG2--> MH | 2 | 0 | 100% | 2022-01-20 | 2022-02-04 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01270 | 0 | 0 | OGW-01270 | Construction | Site Utilities | Construction.5.6.6 | Backfill Electrical OG2 --> MH | 2 | 0 | 100% | 2022-02-07 | 2022-02-08 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01275 | 0 | 0 | OGW-01275 | Construction | Site Utilities | Construction.5.6.6 | Excavate for Steam OG4--> OG3 | 15 | 0 | 100% | 2021-12-14 | 2022-02-16 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01280 | 0 | 0 | OGW-01280 | Construction | Site Utilities | Construction.5.6.6 | Install Steam piping OG4--> OG3 - | 20 | 0 | 100% | 2022-04-18 | 2022-06-06 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01285 | 0 | 0 | OGW-01285 | Construction | Site Utilities | Construction.5.6.6 | Test Steam Piping OG4--> OG3 | 8 | 0 | 100% | 2022-06-07 | 2022-06-13 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01290 | 0 | 0 | OGW-01290 | Construction | Site Utilities | Construction.5.6.6 | Backfill Steam Piping OG4--> OG3 | 10 | 0 | 100% | 2022-06-14 | 2022-06-20 |  | 0 | 0 | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01505 | 0 | 0 | OGW-01505 | Construction | Site Utilities | Construction.5.6.6 | Excavate for water line to drinking fountain OGW --> Water Main W32nd Street | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | -6 | MLJ | EXCAVATION | UTILITY EXC | 33-3100 | 33-3100-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01510 | 0 | 0 | OGW-01510 | Construction | Site Utilities | Construction.5.6.6 | Install water line to drinking fountain OGW --> Water Main W32nd Street | 5 | 5 | 0% | 2022-12-12 08:00 | 2022-12-16 17:00 | -15 | UNSURE | PLAYGROUND | PLUMBING | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01515 | 0 | 0 | OGW-01515 | Construction | Site Utilities | Construction.5.6.6 | Tap water main for drinking fountain water line OGW --> Water Main W32nd Street | 2 | 2 | 0% | 2022-12-19 08:00 | 2022-12-20 17:00 | -15 | UNSURE | PLAYGROUND | PLUMBING | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01520 | 0 | 0 | OGW-01520 | Construction | Site Utilities | Construction.5.6.6 | Backfill water line drinking fountain OGW --> Water Main W32nd Street | 2 | 2 | 0% | 2023-09-12 08:00 | 2023-09-13 17:00 | -197 | MLJ | BACKFILL | BACKFILL SITE | 31-2200 | 31-2200-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01560 | 0 | 0 | OGW-01560 | Construction | Site Utilities | Construction.5.6.6 | Excavate and Install Area Drains AD14 to AD13 TO AD7 Piping & Tie-in to Existing | 15 | 0 | 100% | 2022-08-08 08:00 | 2022-08-19 17:00 |  | MLJ | Excavation | AREA DRAIN | 33-2600 | 33-2600-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01565 | 0 | 0 | OGW-01565 | Construction | Site Utilities | Construction.5.6.6 | Backfill Area Drains AD14 to AD13 TO AD7 Piping | 5 | 0 | 100% | 2022-08-25 | 2022-08-29 |  | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGW
Completed | CI NYCHA Update #22.Construction.5.6.Removals1 | OGW | OGW | 01090 | 0 | 0 | OGW-01090 | Construction | Site Protection & Removals | Construction.5.6.Removals1 | Activate Dewatering System - N/A | 1 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.Removals1 | OGW | OGW | 01095 | 0 | 0 | OGW-01095 | Construction | Site Protection & Removals | Construction.5.6.Removals1 | Maintain Dewatering | 242 | 0 | 100% | 2021-08-02 17:00 | 2022-05-25 |  | 0 | dewatering | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01287 | 0 | 0 | OGW-01287 | Construction | Site Utilities | Construction.5.6.6 | Install Automatic Temperature Control Conduit - OG4--> OG3 | 2 | 0 | 100% | 2022-05-04 | 2022-05-04 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.Removals1 | OGW | OGW | 01100 | 0 | 0 | OGW-01100 | Construction | Site Protection & Removals | Construction.5.6.Removals1 | De-Activate Dewatering | 1 | 0 | 100% | 2022-05-25 | 2022-05-25 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01117 | 0 | 0 | OGW-01117 | Construction | Site Utilities | Construction.5.6.6 | Install Automatic Temperature Control Conduit - OG3 --> OG9 | 2 | 0 | 100% | 2022-05-18 | 2022-05-18 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01295 | 0 | 0 | OGW-01295 | Construction | Site Utilities | Construction.5.6.6 | Excavate for Steam & HW OG3--> OG2 | 15 | 0 | 100% | 2021-12-01 | 2022-06-06 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01300 | 0 | 0 | OGW-01300 | Construction | Site Utilities | Construction.5.6.6 | Install Steam and HW piping OG3--> OG2 | 20 | 0 | 100% | 2022-09-14 | 2022-11-18 |  | WELKIN | UG PIPE | 0 | 0 | 0-OGW
In Progress | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01305 | 0 | 0 | OGW-01305 | Construction | Site Utilities | Construction.5.6.6 | Test Steam & HW Piping OG3--> OG2 | 8 | 4 | 50% | 2022-11-21 | 2022-11-30 17:00 | -28 | WELKIN | UG PIPE | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01315 | 0 | 0 | OGW-01315 | Construction | Site Utilities | Construction.5.6.6 | Backfill Steam & HW Piping OG3--> OG2 | 10 | 10 | 0% | 2022-12-05 08:00 | 2022-12-16 17:00 | -18 | MLJ | BACKFILL | BACKFILL UTILITY | 31-2200 | 31-2200-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01310 | 0 | 0 | OGW-01310 | Construction | Site Utilities | Construction.5.6.6 | Install Automatic Temperature Control Conduit - OG3--> OG2 | 2 | 2 | 0% | 2022-12-01 08:00 | 2022-12-02 17:00 | -28 | FSE | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.1 | OGW | OGW | 01605 | 0 | 0 | OGW-01605 | Construction | Retaining Walls | Construction.5.6.1 | Excavate for retaining wall --> OG Phase 3A | 2 | 0 | 100% | 2022-09-12 08:00 | 2022-09-16 17:00 |  | MLJ | Excavation | EXC RETAINING | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.1 | OGW | OGW | 01610 | 0 | 0 | OGW-01610 | Construction | Retaining Walls | Construction.5.6.1 | Form Retaining wall footing --> OG Phase 3A | 2 | 0 | 100% | 2022-09-19 | 2022-09-20 |  | MLJ | Formwork | SITE FORMWORK | 03-1600 | 03-1600-OGW
Completed | CI NYCHA Update #22.Construction.5.6.1 | OGW | OGW | 01615 | 0 | 0 | OGW-01615 | Construction | Retaining Walls | Construction.5.6.1 | Rebar Retaining wall footing --> OG Phase 3A | 2 | 0 | 100% | 2022-09-20 | 2022-09-20 |  | 0 | REBAR | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.1 | OGW | OGW | 01620 | 0 | 0 | OGW-01620 | Construction | Retaining Walls | Construction.5.6.1 | Pour Retaining wall footing --> OG Phase 3A | 1 | 0 | 100% | 2022-09-21 | 2022-09-21 |  | MLJ | Concrete | SITE CONCRETE | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.1 | OGW | OGW | 01625 | 0 | 0 | OGW-01625 | Construction | Retaining Walls | Construction.5.6.1 | Strip Retaining wall footing --> OG Phase 3A | 1 | 0 | 100% | 2022-09-22 | 2022-09-22 |  | 0 | Formwork | SITE FORMWORK | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.1 | OGW | OGW | 01630 | 0 | 0 | OGW-01630 | Construction | Retaining Walls | Construction.5.6.1 | Form Retaining wall --> OG Phase 3A | 3 | 0 | 100% | 2022-09-22 | 2022-09-23 |  | MLJ | Formwork | SITE FORMWORK | 03-1600 | 03-1600-OGW
Completed | CI NYCHA Update #22.Construction.5.6.1 | OGW | OGW | 01635 | 0 | 0 | OGW-01635 | Construction | Retaining Walls | Construction.5.6.1 | Rebar Retaining wall --> OG Phase 3A | 3 | 0 | 100% | 2022-10-11 | 2022-10-12 |  | 0 | REBAR | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.1 | OGW | OGW | 01640 | 0 | 0 | OGW-01640 | Construction | Retaining Walls | Construction.5.6.1 | Pour Retaining wall --> OG Phase 3A | 1 | 0 | 100% | 2022-10-18 | 2022-10-18 |  | MLJ | Concrete | SITE CONCRETE | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.1 | OGW | OGW | 01645 | 0 | 0 | OGW-01645 | Construction | Retaining Walls | Construction.5.6.1 | Strip Retaining wall --> OG Phase 3A | 1 | 0 | 100% | 2022-10-19 | 2022-10-21 |  | 0 | Formwork | SITE FORMWORK | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.5 | OGW | OGW | 01705 | 0 | 0 | OGW-01705 | Construction | Site Restoration | Construction.5.6.5 | Install Street Curbs --> OG Phase 3A | 15 | 15 | 0% | 2023-09-21 08:00 | 2023-10-11 17:00 | -197 | MLJ | CURBS | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.5 | OGW | OGW | 01710 | 0 | 0 | OGW-01710 | Construction | Site Restoration | Construction.5.6.5 | Install sidewalks --> OG Phase 3A | 10 | 10 | 0% | 2023-10-27 08:00 | 2023-11-13 17:00 | -197 | JMC | SIDEWALKS | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.5 | OGW | OGW | 01715 | 0 | 0 | OGW-01715 | Construction | Site Restoration | Construction.5.6.5 | Install curb around play area --> OG Phase 3A | 5 | 5 | 0% | 2023-11-14 08:00 | 2023-11-20 17:00 | -197 | MLJ | CURBS | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.5 | OGW | OGW | 01720 | 0 | 0 | OGW-01720 | Construction | Site Restoration | Construction.5.6.5 | Install Safety Surface --> OG Phase 3A | 5 | 5 | 0% | 2023-11-21 08:00 | 2023-11-28 17:00 | -197 | UNSURE | PLAYGROUND | SAFETY SURFACE | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.5 | OGW | OGW | 01725 | 0 | 0 | OGW-01725 | Construction | Site Restoration | Construction.5.6.5 | Install site furniture concrete foundations --> OG Phase 3A | 10 | 10 | 0% | 2023-10-12 08:00 | 2023-10-26 17:00 | -197 | MLJ | CONCRETE | SITE CONCRETE | 03-2200 | 03-2200-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.5 | OGW | OGW | 01730 | 0 | 0 | OGW-01730 | Construction | Site Restoration | Construction.5.6.5 | Install integrally colored concrete walkways --> OG Phase 3A | 20 | 20 | 0% | 2023-11-29 08:00 | 2023-12-27 17:00 | -197 | JMC | COLORED CONCRETE | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.5 | OGW | OGW | 01735 | 0 | 0 | OGW-01735 | Construction | Site Restoration | Construction.5.6.5 | Install Play area items --> OG Phase 3A | 5 | 5 | 0% | 2023-12-28 08:00 | 2024-01-04 17:00 | -197 | BRIGHTON | PLAYGROUND | INSTALL | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.5 | OGW | OGW | 01740 | 0 | 0 | OGW-01740 | Construction | Site Restoration | Construction.5.6.5 | Install fence around play area --> OG Phase 3A | 10 | 10 | 0% | 2024-01-05 08:00 | 2024-01-18 17:00 | -197 | MLJ | FENCING | PLAYGROUND | 32-6520 | 32-6520-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.5 | OGW | OGW | 01745 | 0 | 0 | OGW-01745 | Construction | Site Restoration | Construction.5.6.5 | Install Fence at building --> OG9 | 5 | 5 | 0% | 2024-01-19 08:00 | 2024-01-25 17:00 | -197 | ATLAS | SITE RESTORATION | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.5 | OGW | OGW | 01750 | 0 | 0 | OGW-01750 | Construction | Site Restoration | Construction.5.6.5 | Place Site Furniture --> OG Phase 3A | 10 | 10 | 0% | 2024-01-26 08:00 | 2024-02-08 17:00 | -197 | MLJ | SITE RESTORATION | SITE FURNITURE | 31-2600 | 31-2600-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.5 | OGW | OGW | 01755 | 0 | 0 | OGW-01755 | Construction | Site Restoration | Construction.5.6.5 | Place topsoil --> OG Phase 3A | 3 | 3 | 0% | 2024-04-01 08:00 | 2024-04-03 17:00 | -69 | ASPEN | TOPSOIL | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.5 | OGW | OGW | 01760 | 0 | 0 | OGW-01760 | Construction | Site Restoration | Construction.5.6.5 | Place trees and plantings --> OG Phase 3A | 5 | 5 | 0% | 2024-04-04 08:00 | 2024-04-10 17:00 | -69 | ASPEN | 0 | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.5 | OGW | OGW | 01765 | 0 | 0 | OGW-01765 | Construction | Site Restoration | Construction.5.6.5 | Place lawn --> OG Phase 3A | 5 | 5 | 0% | 2024-04-11 08:00 | 2024-04-17 17:00 | -69 | ASPEN | 0 | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.5 | OGW | OGW | 01770 | 0 | 0 | OGW-01770 | Construction | Site Restoration | Construction.5.6.5 | Demobilize from OG Phase 3A | 5 | 5 | 0% | 2024-04-18 08:00 | 2024-04-24 17:00 | -228 | MLJ | DEMOB | 0 | 99-4000 | 99-4000-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.7 | OGW | OGW | 01805 | 0 | 0 | OGW-01805 | Construction | Civil/Architectural Inspections | Construction.5.6.7 | Perform Inspections & Issue Punch List | 5 | 5 | 0% | 2023-04-17 08:00 | 2023-04-21 17:00 | 0 | MLJ | PUNCH LIST | INSPECTION | 99-8200 | 99-8200-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.7 | OGW | OGW | 01810 | 0 | 0 | OGW-01810 | Construction | Civil/Architectural Inspections | Construction.5.6.7 | Perform Punch List | 10 | 10 | 0% | 2023-04-24 08:00 | 2023-05-05 17:00 | 15 | MLJ | PUNCH LIST | 0 | 99-8200 | 99-8200-OGW
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01030 | 0 | 0 | OG9-01030 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Form Plumbing Shafts & Ftgs Below Water Table --> OG9 | 10 | 0 | 100% | 2021-09-13 | 2021-09-14 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01035 | 0 | 0 | OG9-01035 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Rebar Plumbing Shafts & Ftgs Below Water Table --> OG9 | 5 | 0 | 100% | 2021-09-14 | 2021-09-15 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01040 | 0 | 0 | OG9-01040 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Pour Plumbing Shafts & Ftgs Below Water Table --> OG9 | 2 | 0 | 100% | 2021-09-16 08:00 | 2021-09-16 17:00 |  | MLJ | concrete | NB CONCRETE | 03-1900 | 03-1900-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01045 | 0 | 0 | OG9-01045 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Strip Forms Plumbing Shafts & Ftgs Below Water Table --> OG9 | 5 | 0 | 100% | 2021-09-17 08:00 | 2021-09-20 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01025 | 0 | 0 | OG9-01025 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Waterproof/Insulation Plumbing Shaft ----> OG9 | 5 | 0 | 100% | 2021-09-16 08:00 | 2021-09-16 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01005 | 0 | 0 | OG9-01005 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Excavate For Plumbing Shaft & Ftgs/Piers Below Water Table --> OG9 | 5 | 0 | 100% | 2021-08-03 08:00 | 2021-08-10 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01020 | 0 | 0 | OG9-01020 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Prepare Subgrade For Plumbing Shafts & Ftgs / Piers Below Water Table --> OG9 | 3 | 0 | 100% | 2021-08-10 | 2021-08-20 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01055 | 0 | 0 | OG9-01055 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Backfill Plumbing Shaft & Ftgs/Piers --> OG9 | 5 | 0 | 100% | 2021-09-21 08:00 | 2021-10-29 |  | 0 | OG9 | 0 | 31-1400 | 31-1400-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01065 | 0 | 0 | OG9-01065 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Excavate For Remaining Ftgs/Pier/Grade Beams --> OG9 | 10 | 0 | 100% | 2021-08-03 | 2021-08-10 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01070 | 0 | 0 | OG9-01070 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Form Remaining Ftgs/Piers/Grade Beams --> OG9 | 10 | 0 | 100% | 2021-09-13 08:00 | 2021-11-01 17:00 |  | 0 | FORMWORK | FORMWORK NB | 03-1000 | 03-1000-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01075 | 0 | 0 | OG9-01075 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Rebar Remaining Ftgs/Piers/Grade Beams --> OG9 | 10 | 0 | 100% | 2021-09-14 | 2021-11-01 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01080 | 0 | 0 | OG9-01080 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Pour Remaining Ftgs/Piers/Grade Beams --> OG9 | 5 | 0 | 100% | 2021-09-16 08:00 | 2021-11-02 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01085 | 0 | 0 | OG9-01085 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Strip Forms Remaining Ftgs/Piers/Grade Beams --> OG9 | 5 | 0 | 100% | 2021-09-17 08:00 | 2021-11-03 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01090 | 0 | 0 | OG9-01090 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Remaining Steam Into OG9 (5' from the building) | 5 | 0 | 100% | 2021-10-27 08:00 | 2021-11-05 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01095 | 0 | 0 | OG9-01095 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Backfill Remaining Ftgs/Piers/Grade Beams / Prepare Subgrade --> OG9 | 5 | 0 | 100% | 2021-11-01 | 2021-11-04 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01105 | 0 | 0 | OG9-01105 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Structural Steel Framing - 1st Floor --> OG9 | 10 | 0 | 100% | 2021-11-09 | 2021-11-24 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01110 | 0 | 0 | OG9-01110 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Metal Deck --> OG9 | 2 | 0 | 100% | 2021-11-29 08:00 | 2021-12-01 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01115 | 0 | 0 | OG9-01115 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Form Pour Strip Concrete Stair South Side ---> OG9 | 5 | 0 | 100% | 2021-12-15 | 2021-12-20 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01120 | 0 | 0 | OG9-01120 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Metal Stairs --> OG9 | 2 | 0 | 100% | 2021-12-20 | 2022-01-03 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01125 | 0 | 0 | OG9-01125 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Place Insulation Below First Floor --> OG9 | 5 | 0 | 100% | 2021-12-13 | 2021-12-13 |  | 0 | 0 | 0 | 07-1100 | 07-1100-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01130 | 0 | 0 | OG9-01130 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Place WWF First Floor Slab --> OG9 | 2 | 0 | 100% | 2021-12-14 | 2021-12-14 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01135 | 0 | 0 | OG9-01135 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Pour First Floor Slab --> OG9 | 1 | 0 | 100% | 2021-12-15 | 2021-12-15 |  | MLJ | concrete | NB CONCRETE | 03-1900 | 03-1900-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01150 | 0 | 0 | OG9-01150 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Form First Floor Concrete Walls First Face And Col Encasements--> OG9 | 3 | 0 | 100% | 2021-12-13 | 2021-12-17 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01155 | 0 | 0 | OG9-01155 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Rebar First Floor Concrete Walls --> OG9 | 3 | 0 | 100% | 2021-12-20 | 2021-12-22 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01160 | 0 | 0 | OG9-01160 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Form First Floor Concrete Walls 2Nd Face --> OG9 | 5 | 0 | 100% | 2021-12-24 | 2021-12-29 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01165 | 0 | 0 | OG9-01165 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Form, Rebar & Pour Concrete Pads 1st Floor --> OG9 - N/A | 6 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01170 | 0 | 0 | OG9-01170 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Place WWF 2nd Floor Slab --> OG9 | 2 | 0 | 100% | 2022-01-13 | 2022-01-14 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01175 | 0 | 0 | OG9-01175 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Pour 2nd Floor Slab / First Floor Walls & Col Encasements --> OG9 | 2 | 0 | 100% | 2022-02-02 | 2022-02-02 |  | MLJ | concrete | NB CONCRETE | 03-1900 | 03-1900-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01180 | 0 | 0 | OG9-01180 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Strip Forms First Floor Walls & Col Encasements --> OG9 | 3 | 0 | 100% | 2022-01-03 | 2022-01-05 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01185 | 0 | 0 | OG9-01185 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Form Concrete Pads 2nd Floor -->OG9 | 2 | 0 | 100% | 2022-05-02 | 2022-05-02 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01205 | 0 | 0 | OG9-01205 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Place WWF Roof Slab --> OG9 | 2 | 0 | 100% | 2022-01-24 | 2022-01-26 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01210 | 0 | 0 | OG9-01210 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Pour Roof Slab and 2nd Floor Conc Pads -->OG9 | 1 | 0 | 100% | 2022-02-02 | 2022-02-02 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01215 | 0 | 0 | OG9-01215 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Strip Forms Concrete Pads 2nd Floor -->OG9 | 2 | 0 | 100% | 2022-02-14 | 2022-02-18 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01225 | 0 | 0 | OG9-01225 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Spray-On Fireproofing on St Stl --> OG9 | 5 | 0 | 100% | 2022-03-17 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01230 | 0 | 0 | OG9-01230 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Place CMU 1st, 2nd Floors and Roof --> OG9 | 20 | 0 | 100% | 2022-03-30 | 2022-06-15 |  | FAXA | CMU | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01240 | 0 | 0 | OG9-01240 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Stud Framing 1st, 2nd Floors and Roof --> OG9 | 5 | 0 | 100% | 2022-07-05 | 2022-07-25 |  | CCC | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01245 | 0 | 0 | OG9-01245 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Doors --> OG9 | 3 | 3 | 0% | 2023-01-10 08:00 | 2023-01-12 17:00 | 33 | CCC | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01250 | 0 | 0 | OG9-01250 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Cast Stone Panels --> OG9 | 4 | 4 | 0% | 2023-01-13 08:00 | 2023-01-19 17:00 | 60 | JMC | CAST STONE | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01255 | 0 | 0 | OG9-01255 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Insulated Metal Panels/Louvers --> OG9 | 10 | 0 | 100% | 2022-09-08 | 2022-11-18 |  | NAVILLUS | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01260 | 0 | 0 | OG9-01260 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install MEP Roof Penetrations & Drains - OG9 | 1 | 0 | 100% | 2022-06-15 | 2022-06-20 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01265 | 0 | 0 | OG9-01265 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Roofing --> OG9 | 15 | 0 | 100% | 2022-07-13 | 2022-08-24 17:00 |  | TRIANGLE | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01270 | 0 | 0 | OG9-01270 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Dunnage Gratings --> OG9 | 2 | 0 | 100% | 2021-12-02 08:00 | 2021-12-03 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01275 | 0 | 0 | OG9-01275 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Brick Façade & Stone --> OG9 | 20 | 0 | 100% | 2022-06-16 08:00 | 2022-08-05 17:00 |  | FAXA | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01285 | 0 | 0 | OG9-01285 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Flood Vents And Small Louvers --> OG9 | 3 | 3 | 0% | 2022-11-25 08:00 | 2022-11-29 17:00 | 63 | MLJ | FLOOD PROTECTION | FLOOD VENTS | 08-1700 | 08-1700-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01290 | 0 | 0 | OG9-01290 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Stair And Roof Platform Railings --> OG9 | 5 | 0 | 100% | 2022-03-10 | 2022-03-15 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01295 | 0 | 0 | OG9-01295 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Ladders --> OG9 | 3 | 0 | 100% | 2022-05-01 | 2022-05-03 |  | 0 | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01305 | 0 | 0 | OG9-01305 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Sheetrock and Stucco --> OG9 | 10 | 10 | 0% | 2023-01-25 08:00 | 2023-02-07 17:00 | 26 | CCC | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01310 | 0 | 0 | OG9-01310 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Ceramic Tile --> OG9 | 2 | 2 | 0% | 2023-02-08 08:00 | 2023-02-09 17:00 | 26 | UNSURE | FLOORING | CERAMIC | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01315 | 0 | 0 | OG9-01315 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Acoustical Ceiling --> OG9 | 2 | 2 | 0% | 2023-02-10 08:00 | 2023-02-13 17:00 | 26 | UNSURE | CEILING | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01320 | 0 | 0 | OG9-01320 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Place Crystaline Waterproofing In Plumbing Shaft --> OG9 | 3 | 0 | 100% | 2022-03-01 | 2022-03-03 |  | 0 | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01325 | 0 | 0 | OG9-01325 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Paint All Areas --> OG9 | 15 | 15 | 0% | 2023-03-23 08:00 | 2023-04-12 17:00 | 0 | GG PAINT | PAINT | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01330 | 0 | 0 | OG9-01330 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Signs --> OG9 | 2 | 2 | 0% | 2023-04-13 08:00 | 2023-04-14 17:00 | 0 | MLJ | SIGNS | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01235 | 0 | 0 | OG9-01235 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Waterproofing to Parapet --> OG9 | 3 | 3 | 0% | 2022-11-25 08:00 | 2022-11-29 17:00 | 94 | UNSURE | WATERPROOFING | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01280 | 0 | 0 | OG9-01280 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Stucco Soffit --> OG9 | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 75 | CCC | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01317 | 0 | 0 | OG9-01317 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Insulated Metal Panels left out for Access --> OG9 | 5 | 5 | 0% | 2023-01-25 08:00 | 2023-01-31 17:00 | 35 | NAVILLUS | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01092 | 0 | 0 | OG9-01092 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Remaining HW/CW Into OG9 (5' from the building) | 5 | 0 | 100% | 2022-01-04 | 2022-01-06 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01094 | 0 | 0 | OG9-01094 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Remaining Electrical POE Into OG9 | 5 | 0 | 100% | 2021-10-05 | 2021-10-20 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.4 | OG9 | OG9 | 03005 | 0 | 0 | OG9-03005 | Construction | Foundation | Construction.5.4.5.4 | Rough-In Plumbing & Appurtenances - Plumbing Shaft | 10 | 0 | 100% | 2022-09-26 | 2022-10-07 |  | WELKIN | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.4 | OG9 | OG9 | 03010 | 0 | 0 | OG9-03010 | Construction | Foundation | Construction.5.4.5.4 | Install Condensate Pump - Foundation Level | 10 | 0 | 100% | 2022-06-01 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 03105 | 0 | 0 | OG9-03105 | Construction | 1st Floor | Construction.5.4.5.1 | Rough-In Plumbing Piping & Appurtenances - 1st Floor | 15 | 0 | 100% | 2022-04-10 | 2022-04-20 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 03110 | 0 | 0 | OG9-03110 | Construction | 1st Floor | Construction.5.4.5.1 | Rig Fuel Oil Tank & Piping - 1st Floor - N/A | 3 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 03125 | 0 | 0 | OG9-03125 | Construction | 1st Floor | Construction.5.4.5.1 | Install Remaining Piping & Appurtenances - 1st Floor | 10 | 0 | 100% | 2022-06-01 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 03130 | 0 | 0 | OG9-03130 | Construction | 1st Floor | Construction.5.4.5.1 | Install FOT Controls - 1st Floor | 20 | 20 | 0% | 2022-11-25 08:00 | 2022-12-22 17:00 | -12 | MEP | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 03135 | 0 | 0 | OG9-03135 | Construction | 1st Floor | Construction.5.4.5.1 | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | -12 | WELKIN | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 03140 | 0 | 0 | OG9-03140 | Construction | 1st Floor | Construction.5.4.5.1 | Install Plumbing Equipment - 1st Floor | 15 | 0 | 100% | 2022-05-26 | 2022-06-06 |  | 0 | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 03145 | 0 | 0 | OG9-03145 | Construction | 1st Floor | Construction.5.4.5.1 | Mechanical Equipment Start-up & Balance - 1st Floor | 5 | 5 | 0% | 2023-01-03 08:00 | 2023-01-09 17:00 | -12 | WELKIN | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 03150 | 0 | 0 | OG9-03150 | Construction | 1st Floor | Construction.5.4.5.1 | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 0% | 2023-01-10 08:00 | 2023-02-07 17:00 | -12 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG9
In Progress | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 03107 | 0 | 0 | OG9-03107 | Construction | 1st Floor | Construction.5.4.5.1 | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 15 | 2 | 85% | 2022-01-24 | 2022-11-29 10:00 | 11 | WELKIN | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 03142 | 0 | 0 | OG9-03142 | Construction | 1st Floor | Construction.5.4.5.1 | Install Mechanical Equipment - 1st Floor | 20 | 0 | 100% | 2022-08-25 13:00 | 2022-09-16 12:00 |  | WELKIN | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 03205 | 0 | 0 | OG9-03205 | Construction | 2nd Floor | Construction.5.4.5.2 | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 15 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 03225 | 0 | 0 | OG9-03225 | Construction | 2nd Floor | Construction.5.4.5.2 | Install Remaining Piping & Appurtenances - 2nd Floor | 20 | 0 | 100% | 2022-04-04 | 2022-10-07 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 03235 | 0 | 0 | OG9-03235 | Construction | 2nd Floor | Construction.5.4.5.2 | Perform Hydrostatic Testing - 2nd Floor | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 3 | WELKIN | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 03240 | 0 | 0 | OG9-03240 | Construction | 2nd Floor | Construction.5.4.5.2 | Install Plumbing Equipment - 2nd Floor - N/A | 15 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 03245 | 0 | 0 | OG9-03245 | Construction | 2nd Floor | Construction.5.4.5.2 | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 0% | 2022-12-09 08:00 | 2022-12-22 17:00 | -2 | WELKIN | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 03250 | 0 | 0 | OG9-03250 | Construction | 2nd Floor | Construction.5.4.5.2 | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 0% | 2022-12-23 08:00 | 2023-01-24 17:00 | -2 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG9
In Progress | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 03207 | 0 | 0 | OG9-03207 | Construction | 2nd Floor | Construction.5.4.5.2 | Rough-In Mechanical Piping & Appurtenances - 2nd Floor | 15 | 2 | 90% | 2022-03-07 | 2022-11-28 12:00 | 37 | WELKIN | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.2 | OG9 | OG9 | 03242 | 0 | 0 | OG9-03242 | Construction | 2nd Floor | Construction.5.4.5.2 | Install Mechanical Equipment - 2nd Floor | 20 | 0 | 100% | 2022-05-25 | 2022-06-20 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 03405 | 0 | 0 | OG9-03405 | Construction | Roof | Construction.5.4.5.3 | Install Ductwork & Appurtenances - Roof - N/A | 4 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 03410 | 0 | 0 | OG9-03410 | Construction | Roof | Construction.5.4.5.3 | Install & Connect Exhaust Fans - Roof - N/A | 6 | 0 | 100% | 2021-02-01 | 2021-02-01 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.5.3 | OG9 | OG9 | 03415 | 0 | 0 | OG9-03415 | Construction | Roof | Construction.5.4.5.3 | Install Insulation - Roof - N/A | 15 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.6 | OG9 | OG9 | 03505 | 0 | 0 | OG9-03505 | Construction | Testing & Start-Up | Construction.5.4.6 | DOB Mechanical/Plumbing Inspection - OG9 | 4 | 4 | 0% | 2023-02-08 08:00 | 2023-02-13 17:00 | -12 | UNSURE | INSPECTION | INSPECTION | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.6 | OG9 | OG9 | 03510 | 0 | 0 | OG9-03510 | Construction | Testing & Start-Up | Construction.5.4.6 | Perform Start-Up Testing - OG9 | 15 | 15 | 0% | 2023-11-01 08:00 | 2023-11-24 17:00 | -193 | UNSURE | STARTUP | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.6 | OG9 | OG9 | 03515 | 0 | 0 | OG9-03515 | Construction | Testing & Start-Up | Construction.5.4.6 | Start-Up Testing & Commissioning Mechanical/Plumbing - OG9 | 16 | 16 | 0% | 2023-11-27 08:00 | 2023-12-18 17:00 | -154 | UNSURE | STARTUP | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.6 | OG9 | OG9 | 03520 | 0 | 0 | OG9-03520 | Construction | Testing & Start-Up | Construction.5.4.6 | Perform Punch List - Electrical/Mechanical/Plumbing Work - OG9 | 5 | 5 | 0% | 2023-12-19 08:00 | 2023-12-26 17:00 | -154 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.6 | OG9 | OG9 | 03530 | 0 | 0 | OG9-03530 | Construction | Testing & Start-Up | Construction.5.4.6 | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - OG9 | 4 | 4 | 0% | 2023-12-28 08:00 | 2024-01-03 17:00 | -154 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.6 | OG9 | OG9 | 03525 | 0 | 0 | OG9-03525 | Construction | Testing & Start-Up | Construction.5.4.6 | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - OG9 | 1 | 1 | 0% | 2023-12-27 08:00 | 2023-12-27 17:00 | -154 | FSE | INSPECTION | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.3.5.1 | OG3 | OG3 | 01005 | 0 | 0 | OG3-01005 | Construction | Asbestos Abatement | Construction.5.3.5.1 | Asbestos Abatement - gaskets - cellar - OG3 | 3 | 3 | 0% | 2023-12-19 08:00 | 2023-12-21 17:00 | -172 | ATCO | ABESTOS | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.1 | OG3 | OG3 | 01010 | 0 | 0 | OG3-01010 | Construction | Asbestos Abatement | Construction.5.3.5.1 | Asbestos Abatement - wire insulation - cellar --> OG3 | 3 | 0 | 100% | 2021-11-01 08:00 | 2021-11-05 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.1 | OG3 | OG3 | 01015 | 0 | 0 | OG3-01015 | Construction | Asbestos Abatement | Construction.5.3.5.1 | Asbestos Abatement - flooring materials at slab penetrations - cellar --> OG3 | 3 | 0 | 100% | 2022-01-13 08:00 | 2022-01-18 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.1 | OG3 | OG3 | 01020 | 0 | 0 | OG3-01020 | Construction | Asbestos Abatement | Construction.5.3.5.1 | Asbestos Abatement - pipe insulation - cellar --> OG3 | 3 | 0 | 100% | 2021-11-01 08:00 | 2021-11-05 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.1 | OG3 | OG3 | 01025 | 0 | 0 | OG3-01025 | Construction | Asbestos Abatement | Construction.5.3.5.1 | Asbestos Abatement - Window Sills - 1st Floor --> OG3 | 5 | 0 | 100% | 2022-07-11 08:00 | 2022-07-11 17:00 |  | ATCO | ABESTOS | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.5.1 | OG3 | OG3 | 01030 | 0 | 0 | OG3-01030 | Construction | Asbestos Abatement | Construction.5.3.5.1 | Asbestos Abatement - caulk @ windows and areaway vents --> OG3 | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 83 | ATCO | ABESTOS | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.2 | OG3 | OG3 | 01105 | 0 | 0 | OG3-01105 | Construction | Interior Demolition | Construction.5.3.5.2 | Selective Demo (Plaster walls, Doors, windows) - Cellar --> OG3 | 10 | 0 | 100% | 2021-05-12 | 2022-07-01 |  | MLJ | DEMO | DEMO CELLAR WALLS | 02-6005 | 02-6005-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.2 | OG3 | OG3 | 01110 | 0 | 0 | OG3-01110 | Construction | Interior Demolition | Construction.5.3.5.2 | Selective Demo (Doors, windows) - 1st Floor --> OG3 | 5 | 0 | 100% | 2022-06-08 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.2 | OG3 | OG3 | 01115 | 0 | 0 | OG3-01115 | Construction | Interior Demolition | Construction.5.3.5.2 | Selective Demo (Areaway drain, slab, wall) --> OG3 | 10 | 0 | 100% | 2021-06-28 08:00 | 2022-07-01 |  | MLJ | DEMO | DEMO AREAWAY | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.2 | OG3 | OG3 | 01205 | 0 | 0 | OG3-01205 | Construction | Interior Demolition | Construction.5.3.5.2 | Selective Demo (Existing Ramp, railing) - 1st Floor --> OG3 | 5 | 0 | 100% | 2022-09-19 08:00 | 2022-09-20 17:00 |  | MLJ | DEMO | DEMO RAMP | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.2 | OG3 | OG3 | 01210 | 0 | 0 | OG3-01210 | Construction | Interior Demolition | Construction.5.3.5.2 | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> OG3 | 5 | 0 | 100% | 2022-05-09 | 2022-05-13 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.2 | OG3 | OG3 | 01215 | 0 | 0 | OG3-01215 | Construction | Interior Demolition | Construction.5.3.5.2 | Selective Demo - 2nd Floor Apartment for Electrical Room --> OG3 | 5 | 0 | 100% | 2021-10-07 | 2022-01-21 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.4 | OG3 | OG3 | 01310 | 0 | 0 | OG3-01310 | Construction | Interior Renovations | Construction.5.3.5.4 | Make openings in floor for conduit penetrations - 2nd floor apartments --> OG3 | 5 | 0 | 100% | 2022-05-09 | 2022-05-13 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.4 | OG3 | OG3 | 01315 | 0 | 0 | OG3-01315 | Construction | Interior Renovations | Construction.5.3.5.4 | Install beams below floor - 2nd floor apartments --> OG3 | 5 | 0 | 100% | 2022-04-22 | 2022-04-28 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.4 | OG3 | OG3 | 01320 | 0 | 0 | OG3-01320 | Construction | Interior Renovations | Construction.5.3.5.4 | Install FRP around floor openings - 2nd floor apartments --> OG3 | 5 | 0 | 100% | 2022-03-21 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-OG3
In Progress | CI NYCHA Update #22.Construction.5.3.5.4 | OG3 | OG3 | 01325 | 0 | 0 | OG3-01325 | Construction | Interior Renovations | Construction.5.3.5.4 | Frame walls / install door for electrical room - 2nd floor --> OG3 | 3 | 1 | 66% | 2022-04-29 | 2022-11-25 17:00 | 17 | CCC | 0 | 0 | 0 | 0-OG3
In Progress | CI NYCHA Update #22.Construction.5.3.5.4 | OG3 | OG3 | 01330 | 0 | 0 | OG3-01330 | Construction | Interior Renovations | Construction.5.3.5.4 | Install drywall / tape / spackle - electrical room - 2nd floor --> OG3 | 5 | 1 | 80% | 2022-03-07 | 2022-12-09 17:00 | 8 | CCC | 0 | 0 | 0 | 0-OG3
In Progress | CI NYCHA Update #22.Construction.5.3.5.4 | OG3 | OG3 | 01335 | 0 | 0 | OG3-01335 | Construction | Interior Renovations | Construction.5.3.5.4 | Paint walls and seal floor electrical room - 2nd Floor --> OG3 | 10 | 1 | 90% | 2022-05-13 | 2022-12-12 17:00 | 83 | CCC | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.5.4 | OG3 | OG3 | 01340 | 0 | 0 | OG3-01340 | Construction | Interior Renovations | Construction.5.3.5.4 | Install VCT @ electrical room - 2nd Floor --> OG3 | 2 | 2 | 0% | 2022-12-13 08:00 | 2022-12-14 17:00 | 83 | UNSURE | FLOORING | VCT | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.1 | OG3 | OG3 | 01405 | 0 | 0 | OG3-01405 | Construction | East Elevation | Construction.5.3.5.EFPC.1 | Excavate at Curtain Wall for flood protection (East Side) --> OG3 | 8 | 0 | 100% | 2022-05-19 | 2022-05-24 |  | 0 | EXCAVATION | 0 | 31-1000 | 31-1000-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.1 | OG3 | OG3 | 01410 | 0 | 0 | OG3-01410 | Construction | East Elevation | Construction.5.3.5.EFPC.1 | Form concrete footings at Curtain Wall for flood protection (East Side) --> OG3 | 10 | 0 | 100% | 2022-06-07 | 2022-06-07 |  | 0 | FORMWORK | FORMWORK EB | 03-1100 | 03-1100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.1 | OG3 | OG3 | 01415 | 0 | 0 | OG3-01415 | Construction | East Elevation | Construction.5.3.5.EFPC.1 | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> OG3 | 5 | 0 | 100% | 2022-05-24 | 2022-06-02 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.1 | OG3 | OG3 | 01420 | 0 | 0 | OG3-01420 | Construction | East Elevation | Construction.5.3.5.EFPC.1 | Pour concrete footings at Curtain Wall for flood protection (East Side) --> OG3 | 4 | 0 | 100% | 2022-06-07 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.1 | OG3 | OG3 | 01425 | 0 | 0 | OG3-01425 | Construction | East Elevation | Construction.5.3.5.EFPC.1 | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> OG3 | 5 | 0 | 100% | 2022-06-10 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.5.EFPC.1 | OG3 | OG3 | 01430 | 0 | 0 | OG3-01430 | Construction | East Elevation | Construction.5.3.5.EFPC.1 | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG3 | 8 | 8 | 0% | 2022-11-25 08:00 | 2022-12-06 17:00 | 65 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.5.EFPC.1 | OG3 | OG3 | 01435 | 0 | 0 | OG3-01435 | Construction | East Elevation | Construction.5.3.5.EFPC.1 | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG3 | 6 | 6 | 0% | 2022-12-07 08:00 | 2022-12-14 17:00 | 65 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.5.EFPC.1 | OG3 | OG3 | 01440 | 0 | 0 | OG3-01440 | Construction | East Elevation | Construction.5.3.5.EFPC.1 | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG3 | 4 | 4 | 0% | 2022-12-15 08:00 | 2022-12-20 17:00 | 65 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.5.EFPC.1 | OG3 | OG3 | 01445 | 0 | 0 | OG3-01445 | Construction | East Elevation | Construction.5.3.5.EFPC.1 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG3 | 4 | 4 | 0% | 2022-12-21 08:00 | 2022-12-27 17:00 | 66 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.5.EFPC.1 | OG3 | OG3 | 01450 | 0 | 0 | OG3-01450 | Construction | East Elevation | Construction.5.3.5.EFPC.1 | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> OG3 | 4 | 4 | 0% | 2022-12-28 08:00 | 2023-01-03 17:00 | 66 | FAXA | CMU | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.5.EFPC.1 | OG3 | OG3 | 01455 | 0 | 0 | OG3-01455 | Construction | East Elevation | Construction.5.3.5.EFPC.1 | Backfill at Curtain Wall for flood protection (East Side) --> OG3 | 5 | 5 | 0% | 2023-01-04 08:00 | 2023-01-10 17:00 | 66 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.2 | OG3 | OG3 | 01505 | 0 | 0 | OG3-01505 | Construction | South Elevation | Construction.5.3.5.EFPC.2 | Excavate at Curtain Wall for flood protection (South Side) --> OG3 | 7 | 0 | 100% | 2022-05-19 | 2022-05-24 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.2 | OG3 | OG3 | 01510 | 0 | 0 | OG3-01510 | Construction | South Elevation | Construction.5.3.5.EFPC.2 | Form concrete footings at Curtain Wall for flood protection (South Side) --> OG3 | 9 | 0 | 100% | 2022-06-07 | 2022-06-07 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.2 | OG3 | OG3 | 01515 | 0 | 0 | OG3-01515 | Construction | South Elevation | Construction.5.3.5.EFPC.2 | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> OG3 | 4 | 0 | 100% | 2022-05-24 | 2022-06-02 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.2 | OG3 | OG3 | 01520 | 0 | 0 | OG3-01520 | Construction | South Elevation | Construction.5.3.5.EFPC.2 | Pour concrete footings at Curtain Wall for flood protection (South Side) --> OG3 | 3 | 0 | 100% | 2022-06-07 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.2 | OG3 | OG3 | 01525 | 0 | 0 | OG3-01525 | Construction | South Elevation | Construction.5.3.5.EFPC.2 | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> OG3 | 4 | 0 | 100% | 2022-06-10 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.2 | OG3 | OG3 | 01530 | 0 | 0 | OG3-01530 | Construction | South Elevation | Construction.5.3.5.EFPC.2 | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG3 | 7 | 0 | 100% | 2022-09-01 08:00 | 2022-09-05 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.2 | OG3 | OG3 | 01535 | 0 | 0 | OG3-01535 | Construction | South Elevation | Construction.5.3.5.EFPC.2 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG3 | 5 | 0 | 100% | 2022-09-06 | 2022-09-08 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.2 | OG3 | OG3 | 01540 | 0 | 0 | OG3-01540 | Construction | South Elevation | Construction.5.3.5.EFPC.2 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG3 | 3 | 0 | 100% | 2022-09-09 | 2022-09-09 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.2 | OG3 | OG3 | 01545 | 0 | 0 | OG3-01545 | Construction | South Elevation | Construction.5.3.5.EFPC.2 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG3 | 3 | 0 | 100% | 2022-09-12 | 2022-09-14 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.2 | OG3 | OG3 | 01550 | 0 | 0 | OG3-01550 | Construction | South Elevation | Construction.5.3.5.EFPC.2 | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> OG3 | 3 | 0 | 100% | 2022-09-15 | 2022-09-19 |  | FAXA | CMU | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.2 | OG3 | OG3 | 01555 | 0 | 0 | OG3-01555 | Construction | South Elevation | Construction.5.3.5.EFPC.2 | Backfill at Curtain Wall for flood protection (South Side) --> OG3 | 4 | 0 | 100% | 2022-09-20 | 2022-09-22 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.3 | OG3 | OG3 | 01605 | 0 | 0 | OG3-01605 | Construction | North Elevation | Construction.5.3.5.EFPC.3 | Excavate at Curtain Wall for flood protection (North Side) --> OG3 | 7 | 0 | 100% | 2022-05-19 | 2022-05-24 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.3 | OG3 | OG3 | 01610 | 0 | 0 | OG3-01610 | Construction | North Elevation | Construction.5.3.5.EFPC.3 | Form concrete footings at Curtain Wall for flood protection (North Side) --> OG3 | 9 | 0 | 100% | 2022-06-07 | 2022-06-07 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.3 | OG3 | OG3 | 01615 | 0 | 0 | OG3-01615 | Construction | North Elevation | Construction.5.3.5.EFPC.3 | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> OG3 | 4 | 0 | 100% | 2022-05-24 | 2022-06-02 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.3 | OG3 | OG3 | 01620 | 0 | 0 | OG3-01620 | Construction | North Elevation | Construction.5.3.5.EFPC.3 | Pour concrete footings at Curtain Wall for flood protection (North Side) --> OG3 | 3 | 0 | 100% | 2022-06-07 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.3 | OG3 | OG3 | 01625 | 0 | 0 | OG3-01625 | Construction | North Elevation | Construction.5.3.5.EFPC.3 | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> OG3 | 4 | 0 | 100% | 2022-06-10 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.3 | OG3 | OG3 | 01630 | 0 | 0 | OG3-01630 | Construction | North Elevation | Construction.5.3.5.EFPC.3 | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG3 | 7 | 0 | 100% | 2022-09-01 | 2022-09-05 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.3 | OG3 | OG3 | 01635 | 0 | 0 | OG3-01635 | Construction | North Elevation | Construction.5.3.5.EFPC.3 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG3 | 5 | 0 | 100% | 2022-09-06 | 2022-09-08 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.3 | OG3 | OG3 | 01640 | 0 | 0 | OG3-01640 | Construction | North Elevation | Construction.5.3.5.EFPC.3 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG3 | 3 | 0 | 100% | 2022-09-09 | 2022-09-09 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.3 | OG3 | OG3 | 01645 | 0 | 0 | OG3-01645 | Construction | North Elevation | Construction.5.3.5.EFPC.3 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG3 | 3 | 0 | 100% | 2022-09-12 | 2022-09-14 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.3 | OG3 | OG3 | 01650 | 0 | 0 | OG3-01650 | Construction | North Elevation | Construction.5.3.5.EFPC.3 | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> OG3 | 3 | 0 | 100% | 2022-09-15 | 2022-09-19 |  | FAXA | CMU | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.3 | OG3 | OG3 | 01655 | 0 | 0 | OG3-01655 | Construction | North Elevation | Construction.5.3.5.EFPC.3 | Backfill at Curtain Wall for flood protection (North Side) --> OG3 | 4 | 0 | 100% | 2022-09-20 | 2022-09-22 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.4 | OG3 | OG3 | 01705 | 0 | 0 | OG3-01705 | Construction | West Elevation | Construction.5.3.5.EFPC.4 | Excavate at Curtain Wall for flood protection (West Side) --> OG3 | 8 | 0 | 100% | 2022-05-06 | 2022-05-12 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.4 | OG3 | OG3 | 01710 | 0 | 0 | OG3-01710 | Construction | West Elevation | Construction.5.3.5.EFPC.4 | Form concrete footings at Curtain Wall for flood protection (West Side) --> OG3 | 10 | 0 | 100% | 2022-06-07 | 2022-06-07 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.4 | OG3 | OG3 | 01715 | 0 | 0 | OG3-01715 | Construction | West Elevation | Construction.5.3.5.EFPC.4 | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> OG3 | 5 | 0 | 100% | 2022-05-24 | 2022-06-02 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.4 | OG3 | OG3 | 01720 | 0 | 0 | OG3-01720 | Construction | West Elevation | Construction.5.3.5.EFPC.4 | Pour concrete footings at Curtain Wall for flood protection (West Side) --> OG3 | 4 | 0 | 100% | 2022-06-07 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.4 | OG3 | OG3 | 01725 | 0 | 0 | OG3-01725 | Construction | West Elevation | Construction.5.3.5.EFPC.4 | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> OG3 | 5 | 0 | 100% | 2022-06-10 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.4 | OG3 | OG3 | 01730 | 0 | 0 | OG3-01730 | Construction | West Elevation | Construction.5.3.5.EFPC.4 | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG3 | 8 | 0 | 100% | 2022-09-01 | 2022-09-05 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.4 | OG3 | OG3 | 01735 | 0 | 0 | OG3-01735 | Construction | West Elevation | Construction.5.3.5.EFPC.4 | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG3 | 6 | 0 | 100% | 2022-09-06 | 2022-09-08 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.4 | OG3 | OG3 | 01740 | 0 | 0 | OG3-01740 | Construction | West Elevation | Construction.5.3.5.EFPC.4 | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG3 | 4 | 0 | 100% | 2022-09-09 | 2022-09-09 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.4 | OG3 | OG3 | 01745 | 0 | 0 | OG3-01745 | Construction | West Elevation | Construction.5.3.5.EFPC.4 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG3 | 4 | 0 | 100% | 2022-09-12 | 2022-09-14 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.4 | OG3 | OG3 | 01750 | 0 | 0 | OG3-01750 | Construction | West Elevation | Construction.5.3.5.EFPC.4 | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> OG3 | 4 | 0 | 100% | 2022-09-15 | 2022-09-19 |  | FAXA | CMU | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.4 | OG3 | OG3 | 01755 | 0 | 0 | OG3-01755 | Construction | West Elevation | Construction.5.3.5.EFPC.4 | Backfill at Curtain Wall for flood protection (West Side) --> OG3 | 5 | 0 | 100% | 2022-09-20 | 2022-09-22 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.4 | OG3 | OG3 | 01760 | 0 | 0 | OG3-01760 | Construction | West Elevation | Construction.5.3.5.EFPC.4 | Form for slab at Curtain Wall for flood protection (West Side) --> OG3 | 4 | 0 | 100% | 2022-09-26 | 2022-10-05 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.4 | OG3 | OG3 | 01765 | 0 | 0 | OG3-01765 | Construction | West Elevation | Construction.5.3.5.EFPC.4 | Rebar & inserts for slab at Curtain Wall for flood protection (West Side) --> OG3 | 6 | 0 | 100% | 2022-10-06 | 2022-10-13 |  | 0 | REBAR | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.4 | OG3 | OG3 | 01770 | 0 | 0 | OG3-01770 | Construction | West Elevation | Construction.5.3.5.EFPC.4 | Pour slab at Curtain Wall for flood protection (West Side) --> OG3 | 4 | 0 | 100% | 2022-10-14 | 2022-10-14 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.4 | OG3 | OG3 | 01775 | 0 | 0 | OG3-01775 | Construction | West Elevation | Construction.5.3.5.EFPC.4 | Strip Forms for slab at Curtain Wall for flood protection (West Side) --> OG3 | 2 | 0 | 100% | 2022-10-17 | 2022-10-18 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.4 | OG3 | OG3 | 01780 | 0 | 0 | OG3-01780 | Construction | West Elevation | Construction.5.3.5.EFPC.4 | Backfill surounding area at Curtain Wall for flood protection (West Side) --> OG3 | 4 | 0 | 100% | 2022-10-18 | 2022-10-24 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.5 | OG3 | OG3 | 01805 | 0 | 0 | OG3-01805 | Construction | Concrete Shelf Construction | Construction.5.3.5.EFPC.5 | Excavate for concrete shelf around bldg perimeter --> OG3 | 10 | 0 | 100% | 2022-06-07 | 2022-06-07 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.5 | OG3 | OG3 | 01810 | 0 | 0 | OG3-01810 | Construction | Concrete Shelf Construction | Construction.5.3.5.EFPC.5 | Place rebar for concrete shelf around bldg perimeter --> OG3 | 5 | 0 | 100% | 2022-06-07 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.5 | OG3 | OG3 | 01815 | 0 | 0 | OG3-01815 | Construction | Concrete Shelf Construction | Construction.5.3.5.EFPC.5 | Pour concrete shelf around bldg perimeter --> OG3 | 5 | 0 | 100% | 2022-06-10 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.5 | OG3 | OG3 | 01820 | 0 | 0 | OG3-01820 | Construction | Concrete Shelf Construction | Construction.5.3.5.EFPC.5 | Place infill concrete in area ways around bldg perimeter --> OG3 | 5 | 0 | 100% | 2022-08-01 08:00 | 2022-08-05 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.5 | OG3 | OG3 | 01825 | 0 | 0 | OG3-01825 | Construction | Concrete Shelf Construction | Construction.5.3.5.EFPC.5 | Place waterproofing on concrete shelf around bldg perimeter --> OG3 | 10 | 0 | 100% | 2022-08-01 08:00 | 2022-08-05 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.5 | OG3 | OG3 | 01830 | 0 | 0 | OG3-01830 | Construction | Concrete Shelf Construction | Construction.5.3.5.EFPC.5 | Place CMU around bldg perimeter --OG3 | 15 | 0 | 100% | 2022-06-13 | 2022-08-19 17:00 |  | FAXA | CMU | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.5 | OG3 | OG3 | 01835 | 0 | 0 | OG3-01835 | Construction | Concrete Shelf Construction | Construction.5.3.5.EFPC.5 | Place waterproofing on CMU around bldg perimeter --> OG3 | 10 | 0 | 100% | 2022-08-15 08:00 | 2022-08-19 17:00 |  | 0 | WATERPROOFING | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.5.EFPC.5 | OG3 | OG3 | 01840 | 0 | 0 | OG3-01840 | Construction | Concrete Shelf Construction | Construction.5.3.5.EFPC.5 | Place window frames around bldg perimeter --> OG3 | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | 100 | MLJ | CONCRETE SHELF | PLACE WINDOWS | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.5 | OG3 | OG3 | 01845 | 0 | 0 | OG3-01845 | Construction | Concrete Shelf Construction | Construction.5.3.5.EFPC.5 | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> OG3 | 20 | 0 | 100% | 2022-10-28 08:00 | 2022-11-18 17:00 |  | FAXA | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.5.EFPC.5 | OG3 | OG3 | 01850 | 0 | 0 | OG3-01850 | Construction | Concrete Shelf Construction | Construction.5.3.5.EFPC.5 | Backfill around bdg perimeter --> OG3 | 5 | 5 | 0% | 2022-12-09 08:00 | 2022-12-15 17:00 | 100 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.5.EFPC.5 | OG3 | OG3 | 01855 | 0 | 0 | OG3-01855 | Construction | Concrete Shelf Construction | Construction.5.3.5.EFPC.5 | Place frame / stucco / and signs at entrances --> OG3 | 4 | 4 | 0% | 2022-12-16 08:00 | 2022-12-21 17:00 | 100 | CCC | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.5.EFPC.5 | OG3 | OG3 | 01860 | 0 | 0 | OG3-01860 | Construction | Concrete Shelf Construction | Construction.5.3.5.EFPC.5 | Place window floodgates at windows --> OG3 | 5 | 5 | 0% | 2022-12-22 08:00 | 2022-12-29 17:00 | 100 | MLJ | FLOOD PROTECTION | FLOOD WINDOWS | 10-1400 | 10-1400-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.5.EFPC.5 | OG3 | OG3 | 01865 | 0 | 0 | OG3-01865 | Construction | Concrete Shelf Construction | Construction.5.3.5.EFPC.5 | Install signs --> OG3 | 3 | 3 | 0% | 2022-12-30 08:00 | 2023-01-04 17:00 | 100 | MLJ | SIGNS | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.5 | OG3 | OG3 | 01350 | 0 | 0 | OG3-01350 | Construction | Boiler Room Construction | Construction.5.3.5.5 | Drill dowels and place rebar for boiler room concrete walls --> OG3 | 5 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | MLJ | 0 | DRILL & DOWEL | 03-1400 | 03-1400-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.5 | OG3 | OG3 | 01355 | 0 | 0 | OG3-01355 | Construction | Boiler Room Construction | Construction.5.3.5.5 | Form boiler room concrete walls --> OG3 | 5 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.5 | OG3 | OG3 | 01360 | 0 | 0 | OG3-01360 | Construction | Boiler Room Construction | Construction.5.3.5.5 | Pour Concrete boiler room walls --> OG3 | 2 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.5 | OG3 | OG3 | 01365 | 0 | 0 | OG3-01365 | Construction | Boiler Room Construction | Construction.5.3.5.5 | Strip Forms boiler room concrete walls --> OG3 | 3 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.5 | OG3 | OG3 | 01370 | 0 | 0 | OG3-01370 | Construction | Boiler Room Construction | Construction.5.3.5.5 | Place crystaline waterproofing on perimeter walls - cellar --> OG3 | 10 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0 | WATERPROOFING | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.6 | OG3 | OG3 | 01385 | 0 | 0 | OG3-01385 | Construction | Elevator Refurbishment | Construction.5.3.5.6 | Refurbish Elevator 1 --> OG3 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.6 | OG3 | OG3 | 01390 | 0 | 0 | OG3-01390 | Construction | Elevator Refurbishment | Construction.5.3.5.6 | Refurbish Elevator 2 --> OG3 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.6 | OG3 | OG3 | 01380 | 0 | 0 | OG3-01380 | Construction | Elevator Refurbishment | Construction.5.3.5.6 | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.5.7 | OG3 | OG3 | 09005 | 0 | 0 | OG3-09005 | Construction | Civil/Architectural Inspections | Construction.5.3.5.7 | Perform Inspections & Issue Punch List | 5 | 5 | 0% | 2023-12-22 08:00 | 2023-12-29 17:00 | -172 | MLJ | PUNCH LIST | INSPECTION | 99-8200 | 99-8200-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.5.7 | OG3 | OG3 | 09010 | 0 | 0 | OG3-09010 | Construction | Civil/Architectural Inspections | Construction.5.3.5.7 | Perform Punch List | 10 | 10 | 0% | 2024-01-02 08:00 | 2024-01-15 17:00 | -157 | MLJ | PUNCH LIST | 0 | 99-8200 | 99-8200-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.2 | OG3 | OG3 | 01220 | 0 | 0 | OG3-01220 | Construction | Interior Demolition | Construction.5.3.5.2 | Selective Demo (Pumps etc..) - Cellar --> OG3 | 5 | 0 | 100% | 2022-10-10 | 2022-10-12 |  | MLJ | DEMO | DEMO PUMPS | 02-6010 | 02-6010-OG3
Completed | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 03005 | 0 | 0 | OG3-03005 | Construction | Cellar | Construction.5.3.8.1 | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 100% | 2021-05-18 | 2022-02-05 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 03010 | 0 | 0 | OG3-03010 | Construction | Cellar | Construction.5.3.8.1 | Install Condensate Pump - Cellar | 10 | 0 | 100% | 2022-10-13 | 2022-10-18 |  | WELKIN | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 03020 | 0 | 0 | OG3-03020 | Construction | Cellar | Construction.5.3.8.1 | Install Pump Controls - Cellar | 20 | 20 | 0% | 2022-11-25 08:00 | 2022-12-22 17:00 | -17 | MEP | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 03025 | 0 | 0 | OG3-03025 | Construction | Cellar | Construction.5.3.8.1 | Perform Hydrostatic Testing - Cellar | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | -17 | WELKIN | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 03030 | 0 | 0 | OG3-03030 | Construction | Cellar | Construction.5.3.8.1 | Install Plumbing Equipment - Cellar | 15 | 0 | 100% | 2021-11-18 08:00 | 2022-09-01 |  | 0 | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 03035 | 0 | 0 | OG3-03035 | Construction | Cellar | Construction.5.3.8.1 | Pump Equipment Start-up & Balance - Cellar | 10 | 10 | 0% | 2023-01-03 08:00 | 2023-01-17 17:00 | -17 | UNSURE | STARTUP | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 03040 | 0 | 0 | OG3-03040 | Construction | Cellar | Construction.5.3.8.1 | Plumbing/Mechanical Insulation - Cellar | 20 | 20 | 0% | 2023-01-18 08:00 | 2023-02-14 17:00 | -17 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 03015 | 0 | 0 | OG3-03015 | Construction | Cellar | Construction.5.3.8.1 | Install Steam Traps - Cellar | 2 | 0 | 100% | 2022-03-14 | 2022-03-16 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 03007 | 0 | 0 | OG3-03007 | Construction | Cellar | Construction.5.3.8.1 | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 0 | 100% | 2021-12-28 | 2022-03-22 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 03032 | 0 | 0 | OG3-03032 | Construction | Cellar | Construction.5.3.8.1 | Install Mechanical Equipment - Cellar | 20 | 0 | 100% | 2022-01-23 | 2022-03-24 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.8.2 | OG3 | OG3 | 03105 | 0 | 0 | OG3-03105 | Construction | 1st Floor | Construction.5.3.8.2 | Rough-In Plumbing Piping & Appurtenances - 1st Floor - N/A | 10 | 0 | 100% | 2022-03-25 08:00 | 2022-03-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
In Progress | CI NYCHA Update #22.Construction.5.3.8.2 | OG3 | OG3 | 03120 | 0 | 0 | OG3-03120 | Construction | 1st Floor | Construction.5.3.8.2 | Install HVAC Controls - 1st Floor | 20 | 10 | 50% | 2022-08-08 08:00 | 2023-01-17 17:00 | -32 | WELKIN | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.2 | OG3 | OG3 | 03125 | 0 | 0 | OG3-03125 | Construction | 1st Floor | Construction.5.3.8.2 | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 0% | 2023-01-18 08:00 | 2023-01-24 17:00 | -32 | WELKIN | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.2 | OG3 | OG3 | 03130 | 0 | 0 | OG3-03130 | Construction | 1st Floor | Construction.5.3.8.2 | Install Mechanical Louvers - 1st Floor | 15 | 15 | 0% | 2022-12-09 08:00 | 2022-12-30 17:00 | -32 | UNSURE | MECHANICAL LOUVERS | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.2 | OG3 | OG3 | 03135 | 0 | 0 | OG3-03135 | Construction | 1st Floor | Construction.5.3.8.2 | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 0% | 2023-01-25 08:00 | 2023-02-07 17:00 | -32 | WELKIN | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.2 | OG3 | OG3 | 03140 | 0 | 0 | OG3-03140 | Construction | 1st Floor | Construction.5.3.8.2 | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 0% | 2023-02-08 08:00 | 2023-03-08 17:00 | -32 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.2 | OG3 | OG3 | 03115 | 0 | 0 | OG3-03115 | Construction | 1st Floor | Construction.5.3.8.2 | Install Steam Traps - 1st Floor | 1 | 1 | 0% | 2022-12-09 08:00 | 2022-12-09 17:00 | -8 | WELKIN | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.2 | OG3 | OG3 | 03110 | 0 | 0 | OG3-03110 | Construction | 1st Floor | Construction.5.3.8.2 | Install Ductwork and Appurtenances - 1st Floor | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | -32 | WELKIN | DUCTWORK | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.2 | OG3 | OG3 | 03112 | 0 | 0 | OG3-03112 | Construction | 1st Floor | Construction.5.3.8.2 | Install HV & EF Units - 1st Floor | 5 | 5 | 0% | 2022-12-02 08:00 | 2022-12-08 17:00 | -32 | MEP | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.2 | OG3 | OG3 | 03107 | 0 | 0 | OG3-03107 | Construction | 1st Floor | Construction.5.3.8.2 | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | -47 | WELKIN | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 03205 | 0 | 0 | OG3-03205 | Construction | 2nd Floor | Construction.5.3.8.3 | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 10 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 03220 | 0 | 0 | OG3-03220 | Construction | 2nd Floor | Construction.5.3.8.3 | Install HVAC Controls - 2nd Floor | 20 | 20 | 0% | 2023-01-18 08:00 | 2023-02-14 17:00 | -47 | WELKIN | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 03230 | 0 | 0 | OG3-03230 | Construction | 2nd Floor | Construction.5.3.8.3 | Install Mechanical Louvers - 2nd Floor | 15 | 15 | 0% | 2022-12-23 08:00 | 2023-01-17 17:00 | -47 | UNSURE | MECHANICAL LOUVERS | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 03235 | 0 | 0 | OG3-03235 | Construction | 2nd Floor | Construction.5.3.8.3 | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 0% | 2023-02-15 08:00 | 2023-03-01 17:00 | -47 | WELKIN | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 03240 | 0 | 0 | OG3-03240 | Construction | 2nd Floor | Construction.5.3.8.3 | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 0% | 2023-03-02 08:00 | 2023-03-29 17:00 | -47 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 03210 | 0 | 0 | OG3-03210 | Construction | 2nd Floor | Construction.5.3.8.3 | Install Ductwork and Appurtenances - 2nd Floor | 5 | 5 | 0% | 2022-12-09 08:00 | 2022-12-15 17:00 | -47 | WELKIN | DUCTWORK | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.3 | OG3 | OG3 | 03215 | 0 | 0 | OG3-03215 | Construction | 2nd Floor | Construction.5.3.8.3 | Install EF Units - 2nd Floor | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -47 | MEP | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.4 | OG3 | OG3 | 03305 | 0 | 0 | OG3-03305 | Construction | Testing & Start-Up | Construction.5.3.8.4 | DOB Mechanical/Plumbing Inspection - OG3 | 4 | 4 | 0% | 2023-03-30 08:00 | 2023-04-04 17:00 | -47 | UNSURE | INSPECTION | INSPECTION | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.4 | OG3 | OG3 | 03310 | 0 | 0 | OG3-03310 | Construction | Testing & Start-Up | Construction.5.3.8.4 | Perform Start-Up Testing - OG3 | 15 | 15 | 0% | 2023-11-01 08:00 | 2023-11-24 17:00 | -193 | UNSURE | STARTUP | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.4 | OG3 | OG3 | 03315 | 0 | 0 | OG3-03315 | Construction | Testing & Start-Up | Construction.5.3.8.4 | Start-Up Testing Mechanical/Plumbing - OG3 | 16 | 16 | 0% | 2023-11-27 08:00 | 2023-12-18 17:00 | -172 | UNSURE | STARTUP | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.4 | OG3 | OG3 | 03320 | 0 | 0 | OG3-03320 | Construction | Testing & Start-Up | Construction.5.3.8.4 | Perform Punch List - Electrical/Mechanical/Plumbing Work - OG3 | 5 | 5 | 0% | 2023-12-19 08:00 | 2023-12-26 17:00 | -154 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.4 | OG3 | OG3 | 03330 | 0 | 0 | OG3-03330 | Construction | Testing & Start-Up | Construction.5.3.8.4 | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - OG3 | 4 | 4 | 0% | 2023-12-28 08:00 | 2024-01-03 17:00 | -154 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.8.4 | OG3 | OG3 | 03325 | 0 | 0 | OG3-03325 | Construction | Testing & Start-Up | Construction.5.3.8.4 | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - OG3 | 1 | 1 | 0% | 2023-12-27 08:00 | 2023-12-27 17:00 | -154 | FSE | INSPECTION | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.3.8.4 | OG3 | OG3 | 03335 | 0 | 0 | OG3-03335 | Construction | Testing & Start-Up | Construction.5.3.8.4 | Remove Redundant Services - OG3 | 10 | 0 | 100% | 2022-08-01 08:00 | 2022-08-03 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01325 | 0 | 0 | OGW-01325 | Construction | Site Utilities | Construction.5.6.6 | Excavate for Steam & HW OG3--> OG9 | 15 | 0 | 100% | 2021-09-02 08:00 | 2021-09-24 17:00 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01330 | 0 | 0 | OGW-01330 | Construction | Site Utilities | Construction.5.6.6 | Install Steam and HW piping OG3--> OG9 (OTCR) | 20 | 0 | 100% | 2022-01-27 | 2022-08-25 |  | WELKIN | UG PIPE | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01335 | 0 | 0 | OGW-01335 | Construction | Site Utilities | Construction.5.6.6 | Test Steam & HW Piping OG3--> OG9 | 8 | 0 | 100% | 2022-01-04 | 2022-08-31 |  | WELKIN | UG PIPE | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01345 | 0 | 0 | OGW-01345 | Construction | Site Utilities | Construction.5.6.6 | Backfill Steam & HW Piping OG3--> OG9 | 10 | 0 | 100% | 2022-09-14 | 2022-09-16 |  | MLJ | BACKFILL | BACKFILL UTILITY | 31-2200 | 31-2200-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01340 | 0 | 0 | OGW-01340 | Construction | Site Utilities | Construction.5.6.6 | Install Automatic Temperature Control Conduit - OG3--> OG9 | 2 | 0 | 100% | 2022-09-01 08:00 | 2022-09-02 17:00 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01575 | 0 | 0 | OGW-01575 | Construction | Site Utilities | Construction.5.6.6 | Excavate and Install Area Drains AD7 to AD8 to Existing & Piping | 15 | 0 | 100% | 2022-08-22 08:00 | 2022-09-05 |  | MLJ | Excavation | AREA DRAIN | 33-2600 | 33-2600-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01580 | 0 | 0 | OGW-01580 | Construction | Site Utilities | Construction.5.6.6 | Backfill Area Drains AD7 to AD8 TO Existing & Piping | 5 | 0 | 100% | 2022-09-09 08:00 | 2022-09-09 08:00 |  | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01590 | 0 | 0 | OGW-01590 | Construction | Site Utilities | Construction.5.6.6 | Excavate and Install Area Drains AD15 to AD9 to Existing & Piping | 15 | 0 | 100% | 2022-09-12 | 2022-09-16 |  | MLJ | Excavation | AREA DRAIN | 33-2600 | 33-2600-OGW
Completed | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01595 | 0 | 0 | OGW-01595 | Construction | Site Utilities | Construction.5.6.6 | Backfill Area Drains AD15 to AD9 TO Existing & Piping | 5 | 0 | 100% | 2022-09-18 | 2022-09-21 |  | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01650 | 0 | 0 | OGW-01650 | Construction | Site Utilities | Construction.5.6.6 | Excavate and Install Area Drains AD10 to Existing to AD11 to Existing & Piping | 15 | 15 | 0% | 2022-11-25 08:00 | 2022-12-15 17:00 | -70 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01655 | 0 | 0 | OGW-01655 | Construction | Site Utilities | Construction.5.6.6 | Backfill Area Drains AD10 to Existing to AD11 to Existing & Piping | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -20 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01660 | 0 | 0 | OGW-01660 | Construction | Site Utilities | Construction.5.6.6 | Excavate and Install Area Drains AD12 to Existing & Piping | 15 | 15 | 0% | 2022-12-16 08:00 | 2023-01-09 17:00 | -70 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01665 | 0 | 0 | OGW-01665 | Construction | Site Utilities | Construction.5.6.6 | Backfill Area Drains AD12 to Existing & Piping | 5 | 5 | 0% | 2023-01-10 08:00 | 2023-01-17 17:00 | -30 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01670 | 0 | 0 | OGW-01670 | Construction | Site Utilities | Construction.5.6.6 | Excavate and Install Area Drains Cellar Pump to Existing & Piping (inc DIP7) | 15 | 15 | 0% | 2023-01-10 08:00 | 2023-01-31 17:00 | -70 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01675 | 0 | 0 | OGW-01675 | Construction | Site Utilities | Construction.5.6.6 | Backfill Area Drains Cellar Pump to Existing & Piping (inc DIP7) | 5 | 5 | 0% | 2023-09-14 08:00 | 2023-09-20 17:00 | -197 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01680 | 0 | 0 | OGW-01680 | Construction | Site Utilities | Construction.5.6.6 | Excavate and Install Area Drains AD16 to Existing & Piping | 15 | 15 | 0% | 2023-02-01 08:00 | 2023-02-22 17:00 | -70 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01685 | 0 | 0 | OGW-01685 | Construction | Site Utilities | Construction.5.6.6 | Backfill Area Drains AD16 to Existing & Piping | 5 | 5 | 0% | 2023-02-23 08:00 | 2023-03-01 17:00 | -55 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01690 | 0 | 0 | OGW-01690 | Construction | Site Utilities | Construction.5.6.6 | Excavate and Install Area Drains -OG9 POE to Existing & Piping (inc DIP 10) | 15 | 15 | 0% | 2023-02-23 08:00 | 2023-03-15 17:00 | -70 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01695 | 0 | 0 | OGW-01695 | Construction | Site Utilities | Construction.5.6.6 | Backfill Area Drains - OG9 POE to Existing & Piping (inc DIP 10) | 5 | 5 | 0% | 2023-03-16 08:00 | 2023-03-22 17:00 | -70 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.4 | OGW | OGW | 02130 | 0 | 0 | OGW-02130 | Construction | Cable Pulls | Construction.5.6.4 | Pull & Terminate Automatic Temperature Control Cable - OG-9 --> OG-3 | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | -6 | FSE | 0 | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.4 | OGW | OGW | 02135 | 0 | 0 | OGW-02135 | Construction | Cable Pulls | Construction.5.6.4 | Pull & Terminate Automatic Temperature Control Cable - OG-9 --> OG-2 | 5 | 5 | 0% | 2022-12-05 08:00 | 2022-12-09 17:00 | -12 | FSE | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 03005 | 0 | 0 | OG2-03005 | Construction | Cellar | Construction.5.2.8.1 | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 100% | 2021-05-18 | 2022-04-20 |  | 0 | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 03010 | 0 | 0 | OG2-03010 | Construction | Cellar | Construction.5.2.8.1 | Install Condensate Pump - Cellar | 10 | 10 | 0% | 2023-01-03 08:00 | 2023-01-17 17:00 | -57 | WELKIN | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 03020 | 0 | 0 | OG2-03020 | Construction | Cellar | Construction.5.2.8.1 | Install Pump Controls - Cellar | 20 | 20 | 0% | 2022-11-25 08:00 | 2022-12-22 17:00 | -57 | MEP | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 03025 | 0 | 0 | OG2-03025 | Construction | Cellar | Construction.5.2.8.1 | Perform Hydrostatic Testing - Cellar | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | -47 | WELKIN | 0 | 0 | 0 | 0-OG2
In Progress | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 03030 | 0 | 0 | OG2-03030 | Construction | Cellar | Construction.5.2.8.1 | Install Plumbing Equipment - Cellar | 15 | 5 | 66% | 2022-09-01 | 2022-12-01 17:00 | -32 | VITAL | PLUMBING EQUIP | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 03035 | 0 | 0 | OG2-03035 | Construction | Cellar | Construction.5.2.8.1 | Pump Equipment Start-up & Balance - Cellar | 10 | 10 | 0% | 2023-01-18 08:00 | 2023-01-31 17:00 | -57 | UNSURE | STARTUP | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 03040 | 0 | 0 | OG2-03040 | Construction | Cellar | Construction.5.2.8.1 | Plumbing/Mechanical Insulation - Cellar | 20 | 20 | 0% | 2023-02-01 08:00 | 2023-03-01 17:00 | -57 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 03015 | 0 | 0 | OG2-03015 | Construction | Cellar | Construction.5.2.8.1 | Install Steam Traps - Cellar | 2 | 0 | 100% | 2021-07-12 | 2021-07-16 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 03007 | 0 | 0 | OG2-03007 | Construction | Cellar | Construction.5.2.8.1 | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 0 | 100% | 2021-09-20 08:00 | 2021-11-12 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 03032 | 0 | 0 | OG2-03032 | Construction | Cellar | Construction.5.2.8.1 | Install Mechanical Equipment - Cellar | 20 | 0 | 100% | 2021-09-06 | 2021-09-26 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.8.2 | OG2 | OG2 | 03105 | 0 | 0 | OG2-03105 | Construction | 1st Floor | Construction.5.2.8.2 | Rough-In Plumbing Piping & Appurtenances - 1st Floor - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.2 | OG2 | OG2 | 03120 | 0 | 0 | OG2-03120 | Construction | 1st Floor | Construction.5.2.8.2 | Install HVAC Controls - 1st Floor | 20 | 20 | 0% | 2022-12-19 08:00 | 2023-01-18 17:00 | -63 | WELKIN | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.2 | OG2 | OG2 | 03125 | 0 | 0 | OG2-03125 | Construction | 1st Floor | Construction.5.2.8.2 | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 0% | 2023-01-19 08:00 | 2023-01-25 17:00 | -63 | WELKIN | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.2 | OG2 | OG2 | 03130 | 0 | 0 | OG2-03130 | Construction | 1st Floor | Construction.5.2.8.2 | Install Mechanical Louvers - 1st Floor | 15 | 15 | 0% | 2022-11-28 08:00 | 2022-12-16 17:00 | -63 | UNSURE | MECHANICAL LOUVERS | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.2 | OG2 | OG2 | 03135 | 0 | 0 | OG2-03135 | Construction | 1st Floor | Construction.5.2.8.2 | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 0% | 2023-01-26 08:00 | 2023-02-08 17:00 | -63 | WELKIN | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.2 | OG2 | OG2 | 03140 | 0 | 0 | OG2-03140 | Construction | 1st Floor | Construction.5.2.8.2 | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 0% | 2023-02-09 08:00 | 2023-03-09 17:00 | -63 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.8.2 | OG2 | OG2 | 03115 | 0 | 0 | OG2-03115 | Construction | 1st Floor | Construction.5.2.8.2 | Install Steam Traps - 1st Floor | 1 | 0 | 100% | 2022-09-06 08:00 | 2022-09-06 17:00 |  | WELKIN | 0 | 0 | 0 | 0-OG2
In Progress | CI NYCHA Update #22.Construction.5.2.8.2 | OG2 | OG2 | 03110 | 0 | 0 | OG2-03110 | Construction | 1st Floor | Construction.5.2.8.2 | Install Ductwork and Appurtenances - 1st Floor | 5 | 1 | 90% | 2022-09-26 08:00 | 2022-11-25 12:00 | -28 | WELKIN | DUCTWORK | 0 | 0 | 0-OG2
In Progress | CI NYCHA Update #22.Construction.5.2.8.2 | OG2 | OG2 | 03112 | 0 | 0 | OG2-03112 | Construction | 1st Floor | Construction.5.2.8.2 | Install HV & EF Units - 1st Floor | 5 | 1 | 80% | 2022-09-06 08:00 | 2022-11-25 17:00 | -63 | MEP | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.8.2 | OG2 | OG2 | 03107 | 0 | 0 | OG2-03107 | Construction | 1st Floor | Construction.5.2.8.2 | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 0 | 100% | 2022-09-12 08:00 | 2022-09-16 17:00 |  | WELKIN | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 03205 | 0 | 0 | OG2-03205 | Construction | 2nd Floor | Construction.5.2.8.3 | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 10 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 03220 | 0 | 0 | OG2-03220 | Construction | 2nd Floor | Construction.5.2.8.3 | Install HVAC Controls - 2nd Floor | 20 | 20 | 0% | 2023-01-03 08:00 | 2023-01-31 17:00 | -67 | WELKIN | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 03230 | 0 | 0 | OG2-03230 | Construction | 2nd Floor | Construction.5.2.8.3 | Install Mechanical Louvers - 2nd Floor | 15 | 15 | 0% | 2022-11-25 08:00 | 2022-12-15 17:00 | -67 | UNSURE | MECHANICAL LOUVERS | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 03235 | 0 | 0 | OG2-03235 | Construction | 2nd Floor | Construction.5.2.8.3 | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 0% | 2023-02-01 08:00 | 2023-02-14 17:00 | -67 | WELKIN | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 03240 | 0 | 0 | OG2-03240 | Construction | 2nd Floor | Construction.5.2.8.3 | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 0% | 2023-02-15 08:00 | 2023-03-15 17:00 | -67 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 03210 | 0 | 0 | OG2-03210 | Construction | 2nd Floor | Construction.5.2.8.3 | Install Ductwork and Appurtenances - 2nd Floor | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -67 | WELKIN | DUCTWORK | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.3 | OG2 | OG2 | 03215 | 0 | 0 | OG2-03215 | Construction | 2nd Floor | Construction.5.2.8.3 | Install EF Units - 2nd Floor | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | -67 | MEP | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.4 | OG2 | OG2 | 03305 | 0 | 0 | OG2-03305 | Construction | Testing & Start-Up | Construction.5.2.8.4 | DOB Mechanical/Plumbing Inspection - OG2 | 4 | 4 | 0% | 2023-03-16 08:00 | 2023-03-21 17:00 | -67 | UNSURE | INSPECTION | INSPECTION | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.4 | OG2 | OG2 | 03310 | 0 | 0 | OG2-03310 | Construction | Testing & Start-Up | Construction.5.2.8.4 | Perform Start-Up Testing - OG2 | 15 | 15 | 0% | 2023-05-05 08:00 | 2023-05-25 17:00 | -99 | UNSURE | STARTUP | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.4 | OG2 | OG2 | 03315 | 0 | 0 | OG2-03315 | Construction | Testing & Start-Up | Construction.5.2.8.4 | Start-Up Testing & Commissioning Mechanical/Plumbing - OG2 | 16 | 16 | 0% | 2023-05-26 08:00 | 2023-06-19 17:00 | -58 | UNSURE | STARTUP | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.4 | OG2 | OG2 | 03320 | 0 | 0 | OG2-03320 | Construction | Testing & Start-Up | Construction.5.2.8.4 | Perform Punch List - Electrical/Mechanical/Plumbing Work - OG2 | 5 | 5 | 0% | 2023-06-20 08:00 | 2023-06-26 17:00 | -30 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.4 | OG2 | OG2 | 03330 | 0 | 0 | OG2-03330 | Construction | Testing & Start-Up | Construction.5.2.8.4 | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - OG2 | 4 | 4 | 0% | 2023-06-28 08:00 | 2023-07-03 17:00 | -30 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.4 | OG2 | OG2 | 03325 | 0 | 0 | OG2-03325 | Construction | Testing & Start-Up | Construction.5.2.8.4 | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - OG2 | 1 | 1 | 0% | 2023-06-27 08:00 | 2023-06-27 17:00 | -30 | FSE | INSPECTION | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.8.4 | OG2 | OG2 | 03335 | 0 | 0 | OG2-03335 | Construction | Testing & Start-Up | Construction.5.2.8.4 | Remove Redundant Services - OG2 | 10 | 10 | 0% | 2023-06-20 08:00 | 2023-07-03 17:00 | -58 | UNSURE | STARTUP | 0 | 0 | 0-OG2
In Progress | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 02005 | 0 | 0 | OGE-02005 | Construction | Site Utilities | Construction.1.5.6 | Remove, Relocate or Abandon Exisiting Feeder Conduit & Cable | 5 | 3 | 50% | 2021-11-26 | 2022-11-29 12:00 | 28 | FSE | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 02010 | 0 | 0 | OGE-02010 | Construction | Site Utilities | Construction.1.5.6 | Install Manholes & Grounding | 8 | 0 | 100% | 2021-11-24 | 2021-11-24 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.Removals1 | OGE | OGE | 01005 | 0 | 0 | OGE-01005 | Construction | Site Protection & Removals | Construction.1.5.Removals1 | Install Site Fencing - O'Dwyer Gardens - East | 10 | 0 | 100% | 2021-07-26 08:00 | 2021-12-15 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.Removals1 | OGE | OGE | 01015 | 0 | 0 | OGE-01015 | Construction | Site Protection & Removals | Construction.1.5.Removals1 | Install Overhead Protection - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.Removals1 | OGE | OGE | 01020 | 0 | 0 | OGE-01020 | Construction | Site Protection & Removals | Construction.1.5.Removals1 | Install Tree Protection | 5 | 0 | 100% | 2020-11-05 | 2020-11-11 17:00 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.Removals1 | OGE | OGE | 01025 | 0 | 0 | OGE-01025 | Construction | Site Protection & Removals | Construction.1.5.Removals1 | Remove Trees | 2 | 0 | 100% | 2021-01-14 | 2021-01-19 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.Removals1 | OGE | OGE | 01000 | 0 | 0 | OGE-01000 | Construction | Site Protection & Removals | Construction.1.5.Removals1 | Remove Curbs And Existing Fencing | 10 | 0 | 100% | 2021-07-26 08:00 | 2022-02-10 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.Removals1 | OGE | OGE | 01035 | 0 | 0 | OGE-01035 | Construction | Site Protection & Removals | Construction.1.5.Removals1 | Install Erosion Control | 5 | 0 | 100% | 2021-10-30 08:00 | 2022-02-11 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.Removals1 | OGE | OGE | 01010 | 0 | 0 | OGE-01010 | Construction | Site Protection & Removals | Construction.1.5.Removals1 | Set Up Yard and Staging | 10 | 0 | 100% | 2021-08-26 08:00 | 2021-08-26 17:00 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.Removals1 | OGE | OGE | 01045 | 0 | 0 | OGE-01045 | Construction | Site Protection & Removals | Construction.1.5.Removals1 | Clear & Grub | 10 | 0 | 100% | 2021-08-26 08:00 | 2022-02-12 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.Removals1 | OGE | OGE | 01050 | 0 | 0 | OGE-01050 | Construction | Site Protection & Removals | Construction.1.5.Removals1 | Scrape & Store Topsoil | 10 | 0 | 100% | 2022-02-28 | 2022-03-05 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.Removals1 | OGE | OGE | 01055 | 0 | 0 | OGE-01055 | Construction | Site Protection & Removals | Construction.1.5.Removals1 | Soil Testing | 10 | 0 | 100% | 2021-05-18 | 2021-06-08 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.Removals1 | OGE | OGE | 01060 | 0 | 0 | OGE-01060 | Construction | Site Protection & Removals | Construction.1.5.Removals1 | Demo Playgrounds And Misc Site Furniture | 5 | 0 | 100% | 2022-02-08 | 2022-05-01 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.Removals1 | OGE | OGE | 01065 | 0 | 0 | OGE-01065 | Construction | Site Protection & Removals | Construction.1.5.Removals1 | Remove Retaining Walls | 10 | 0 | 100% | 2022-02-09 | 2022-05-01 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.Removals1 | OGE | OGE | 01070 | 0 | 0 | OGE-01070 | Construction | Site Protection & Removals | Construction.1.5.Removals1 | Install Deep Wells For Dewatering - N/R | 10 | 0 | 100% | 2021-05-25 | 2021-05-25 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.Removals1 | OGE | OGE | 01075 | 0 | 0 | OGE-01075 | Construction | Site Protection & Removals | Construction.1.5.Removals1 | Install Piping For Deep Wells - N/R | 5 | 0 | 100% | 2021-05-25 | 2021-05-25 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.Removals1 | OGE | OGE | 01080 | 0 | 0 | OGE-01080 | Construction | Site Protection & Removals | Construction.1.5.Removals1 | Install Discharge Connection For Dewatering - N/R | 10 | 0 | 100% | 2021-05-25 | 2021-05-25 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.Removals1 | OGE | OGE | 01085 | 0 | 0 | OGE-01085 | Construction | Site Protection & Removals | Construction.1.5.Removals1 | Run Electric For Dewatering - N/R | 10 | 0 | 100% | 2021-05-25 | 2021-05-25 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01105 | 0 | 0 | OGE-01105 | Construction | Site Utilities | Construction.1.5.6 | Excavate for CW Pipe - OG10 --> OG6 | 10 | 0 | 100% | 2021-10-11 | 2021-10-13 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01110 | 0 | 0 | OGE-01110 | Construction | Site Utilities | Construction.1.5.6 | Install CW Piping - OG10 --> OG6 | 15 | 0 | 100% | 2022-01-25 | 2022-02-22 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01115 | 0 | 0 | OGE-01115 | Construction | Site Utilities | Construction.1.5.6 | Test CW Piping - OG10 --> OG6 | 10 | 0 | 100% | 2022-02-23 | 2022-03-05 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01120 | 0 | 0 | OGE-01120 | Construction | Site Utilities | Construction.1.5.6 | Backfill CW Piping - OG10 --> OG6 | 5 | 0 | 100% | 2022-05-11 | 2022-05-11 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01150 | 0 | 0 | OGE-01150 | Construction | Site Utilities | Construction.1.5.6 | Excavate for Electric OG6--> OG10 | 10 | 0 | 100% | 2021-10-04 | 2021-10-12 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01155 | 0 | 0 | OGE-01155 | Construction | Site Utilities | Construction.1.5.6 | Install Electrical Conduit OG6--> OG10 | 10 | 0 | 100% | 2021-09-17 08:00 | 2022-04-28 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01160 | 0 | 0 | OGE-01160 | Construction | Site Utilities | Construction.1.5.6 | Encase conduit in concrete OG6--> OG10 | 5 | 0 | 100% | 2021-11-15 08:00 | 2022-04-29 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01165 | 0 | 0 | OGE-01165 | Construction | Site Utilities | Construction.1.5.6 | Backfill Electrical OG6--> OG10 | 5 | 0 | 100% | 2022-01-04 | 2022-05-11 |  | 0 | 0 | 0 | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01405 | 0 | 0 | OGE-01405 | Construction | Site Utilities | Construction.1.5.6 | National Gas to Install Line OG10 --> W33rd Street | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 23 | NATIONAL GRID | GAS INSTALL | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01205 | 0 | 0 | OGE-01205 | Construction | Site Utilities | Construction.1.5.6 | Excavate for Electric OG6--> MH | 3 | 0 | 100% | 2022-03-21 | 2022-04-01 |  | 0 | EXCAVATION | 0 | 33-3100 | 33-3100-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01210 | 0 | 0 | OGE-01210 | Construction | Site Utilities | Construction.1.5.6 | Install Electrical Conduit OG6--> MH | 2 | 0 | 100% | 2022-04-04 | 2022-05-19 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01215 | 0 | 0 | OGE-01215 | Construction | Site Utilities | Construction.1.5.6 | Encase conduit in concrete OG6--> MH | 2 | 0 | 100% | 2022-04-20 | 2022-04-20 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01220 | 0 | 0 | OGE-01220 | Construction | Site Utilities | Construction.1.5.6 | Backfill Electrical OG6 --> MH | 2 | 0 | 100% | 2022-04-21 | 2022-04-22 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01230 | 0 | 0 | OGE-01230 | Construction | Site Utilities | Construction.1.5.6 | Excavate for Electric OG1 -> OG10 | 10 | 0 | 100% | 2021-10-04 | 2021-12-05 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01235 | 0 | 0 | OGE-01235 | Construction | Site Utilities | Construction.1.5.6 | Install Electrical Conduit & MH OG1 -> OG10 | 10 | 0 | 100% | 2021-09-24 08:00 | 2021-12-06 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01240 | 0 | 0 | OGE-01240 | Construction | Site Utilities | Construction.1.5.6 | Encase conduit in concrete OG1 -> OG10 | 3 | 0 | 100% | 2021-10-15 08:00 | 2021-12-10 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01245 | 0 | 0 | OGE-01245 | Construction | Site Utilities | Construction.1.5.6 | Backfill Electrical OG1 -> OG10 | 5 | 0 | 100% | 2021-10-20 08:00 | 2021-12-15 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01255 | 0 | 0 | OGE-01255 | Construction | Site Utilities | Construction.1.5.6 | Excavate for Electric OG1--> MH | 3 | 0 | 100% | 2022-06-24 | 2022-07-22 17:00 |  | MLJ | Excavation | UTILITY EXC | 33-3100 | 33-3100-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01260 | 0 | 0 | OGE-01260 | Construction | Site Utilities | Construction.1.5.6 | Install Electrical Conduit OG1--> MH (Awaiting NYCHA Direction) | 2 | 0 | 100% | 2022-07-15 | 2022-07-29 09:36 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01265 | 0 | 0 | OGE-01265 | Construction | Site Utilities | Construction.1.5.6 | Encase conduit in concrete OG1--> MH | 2 | 0 | 100% | 2022-08-01 | 2022-08-02 |  | MLJ | Concrete | SITE CONCRETE | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01270 | 0 | 0 | OGE-01270 | Construction | Site Utilities | Construction.1.5.6 | Backfill Electrical OG1 --> MH | 2 | 0 | 100% | 2022-08-02 | 2022-08-03 |  | MLJ | BACKFILL | BACKFILL UTILITY | 31-2200 | 31-2200-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01275 | 0 | 0 | OGE-01275 | Construction | Site Utilities | Construction.1.5.6 | Excavate for Steam OG5--> OG3 | 15 | 0 | 100% | 2021-11-30 | 2021-12-20 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01280 | 0 | 0 | OGE-01280 | Construction | Site Utilities | Construction.1.5.6 | Install Steam piping OG5--> SG3 | 20 | 0 | 100% | 2022-03-02 | 2022-04-26 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01285 | 0 | 0 | OGE-01285 | Construction | Site Utilities | Construction.1.5.6 | Test Steam Piping OG5--> SG3 | 8 | 0 | 100% | 2022-04-15 | 2022-05-24 |  | WELKIN | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01290 | 0 | 0 | OGE-01290 | Construction | Site Utilities | Construction.1.5.6 | Backfill Steam Piping OG5--> SG3 | 10 | 0 | 100% | 2022-05-10 | 2022-05-18 |  | 0 | 0 | 0 | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01505 | 0 | 0 | OGE-01505 | Construction | Site Utilities | Construction.1.5.6 | Excavate for water line to drinking fountain OGE --> Water Main W33rd Street | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | 19 | MLJ | EXCAVATION | UTILITY EXC | 33-3100 | 33-3100-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01510 | 0 | 0 | OGE-01510 | Construction | Site Utilities | Construction.1.5.6 | Install water line to drinking fountain OGE --> Water Main W33rd Street | 5 | 5 | 0% | 2022-12-12 08:00 | 2022-12-16 17:00 | 10 | UNSURE | PLAYGROUND | PLUMBING | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01515 | 0 | 0 | OGE-01515 | Construction | Site Utilities | Construction.1.5.6 | Tap water main for drinking fountain water line OGE --> Water Main W33rd Street | 2 | 2 | 0% | 2022-12-19 08:00 | 2022-12-20 17:00 | 10 | UNSURE | PLAYGROUND | PLUMBING | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01520 | 0 | 0 | OGE-01520 | Construction | Site Utilities | Construction.1.5.6 | Backfill water line drinking fountain OGE --> Water Main W33rd Street | 2 | 2 | 0% | 2022-12-21 08:00 | 2022-12-22 17:00 | 10 | MLJ | BACKFILL | BACKFILL SITE | 31-2200 | 31-2200-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01560 | 0 | 0 | OGE-01560 | Construction | Site Utilities | Construction.1.5.6 | Excavate and Install Area Drains AD14>AD13>AD12>AD10 to Existing+ Piping | 15 | 0 | 100% | 2022-08-29 | 2022-09-16 |  | MLJ | Excavation | AREA DRAIN | 33-2600 | 33-2600-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01565 | 0 | 0 | OGE-01565 | Construction | Site Utilities | Construction.1.5.6 | Backfill Area Drains AD14>AD13>AD12>AD10 to Existing+ Piping | 5 | 0 | 100% | 2022-09-19 | 2022-09-22 |  | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGE
Completed | CI NYCHA Update #22.Construction.1.5.Removals1 | OGE | OGE | 01090 | 0 | 0 | OGE-01090 | Construction | Site Protection & Removals | Construction.1.5.Removals1 | Activate Dewatering System | 1 | 0 | 100% | 2022-03-02 | 2022-03-02 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.Removals1 | OGE | OGE | 01095 | 0 | 0 | OGE-01095 | Construction | Site Protection & Removals | Construction.1.5.Removals1 | Maintain Dewatering | 282 | 0 | 100% | 2022-03-02 | 2022-05-02 |  | 0 | dewatering | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01287 | 0 | 0 | OGE-01287 | Construction | Site Utilities | Construction.1.5.6 | Install Automatic Temperature Control Conduit - OG5--> SG3 | 2 | 0 | 100% | 2022-05-19 | 2022-05-19 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.Removals1 | OGE | OGE | 01100 | 0 | 0 | OGE-01100 | Construction | Site Protection & Removals | Construction.1.5.Removals1 | De-Activate Dewatering | 1 | 0 | 100% | 2022-05-02 | 2022-05-02 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01117 | 0 | 0 | OGE-01117 | Construction | Site Utilities | Construction.1.5.6 | Install Automatic Temperature Control Conduit - OG10 --> OG6 | 2 | 0 | 100% | 2022-05-12 | 2022-05-12 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01295 | 0 | 0 | OGE-01295 | Construction | Site Utilities | Construction.1.5.6 | Excavate for Steam & HW OG6--> OG10 | 15 | 0 | 100% | 2021-10-13 | 2021-10-15 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01300 | 0 | 0 | OGE-01300 | Construction | Site Utilities | Construction.1.5.6 | Install Steam and HW piping OG6--> OG10 | 20 | 0 | 100% | 2022-01-04 | 2022-04-08 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01305 | 0 | 0 | OGE-01305 | Construction | Site Utilities | Construction.1.5.6 | Test Steam & HW Piping OG6--> OG10 | 8 | 0 | 100% | 2022-04-11 | 2022-04-11 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01315 | 0 | 0 | OGE-01315 | Construction | Site Utilities | Construction.1.5.6 | Backfill Steam & HW Piping OG6--> OG10 | 10 | 0 | 100% | 2022-05-02 | 2022-05-05 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01310 | 0 | 0 | OGE-01310 | Construction | Site Utilities | Construction.1.5.6 | Install Automatic Temperature Control Conduit - OG6--> OG10 | 2 | 0 | 100% | 2022-05-12 | 2022-05-12 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.4 | OGE | OGE | 01605 | 0 | 0 | OGE-01605 | Construction | Retaining Walls | Construction.1.5.4 | Excavate for retaining wall --> OG Phase 4 | 2 | 0 | 100% | 2022-10-13 | 2022-10-14 |  | MLJ | Excavation | EXC RETAINING | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.4 | OGE | OGE | 01610 | 0 | 0 | OGE-01610 | Construction | Retaining Walls | Construction.1.5.4 | Form Retaining wall footing --> OG Phase 4 | 2 | 0 | 100% | 2022-10-17 | 2022-10-18 |  | MLJ | Formwork | SITE FORMWORK | 03-1600 | 03-1600-OGE
Completed | CI NYCHA Update #22.Construction.1.5.4 | OGE | OGE | 01615 | 0 | 0 | OGE-01615 | Construction | Retaining Walls | Construction.1.5.4 | Rebar Retaining wall footing --> OG Phase 4 | 2 | 0 | 100% | 2022-10-19 | 2022-10-20 |  | 0 | REBAR | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.4 | OGE | OGE | 01620 | 0 | 0 | OGE-01620 | Construction | Retaining Walls | Construction.1.5.4 | Pour Retaining wall footing --> OG Phase 4 | 1 | 0 | 100% | 2022-10-21 | 2022-10-21 |  | MLJ | Concrete | SITE CONCRETE | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.4 | OGE | OGE | 01625 | 0 | 0 | OGE-01625 | Construction | Retaining Walls | Construction.1.5.4 | Strip Retaining wall footing --> OG Phase 4 | 1 | 0 | 100% | 2022-10-24 | 2022-10-24 |  | 0 | Formwork | SITE FORMWORK | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.4 | OGE | OGE | 01630 | 0 | 0 | OGE-01630 | Construction | Retaining Walls | Construction.1.5.4 | Form Retaining wall --> OG Phase 4 | 3 | 0 | 100% | 2022-11-18 | 2022-11-21 |  | MLJ | Formwork | SITE FORMWORK | 03-1600 | 03-1600-OGE
Completed | CI NYCHA Update #22.Construction.1.5.4 | OGE | OGE | 01635 | 0 | 0 | OGE-01635 | Construction | Retaining Walls | Construction.1.5.4 | Rebar Retaining wall --> OG Phase 4 | 3 | 0 | 100% | 2022-11-16 | 2022-11-17 |  | 0 | REBAR | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.4 | OGE | OGE | 01640 | 0 | 0 | OGE-01640 | Construction | Retaining Walls | Construction.1.5.4 | Pour Retaining wall --> OG Phase 4 | 1 | 0 | 100% | 2022-11-22 | 2022-11-22 |  | MLJ | Concrete | SITE CONCRETE | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.4 | OGE | OGE | 01645 | 0 | 0 | OGE-01645 | Construction | Retaining Walls | Construction.1.5.4 | Strip Retaining wall --> OG Phase 4 | 1 | 1 | 0% | 2022-11-25 08:00 | 2022-11-25 17:00 | 29 | MLJ | FORMWORK | SITE FORMWORK | 03-1600 | 03-1600-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.5 | OGE | OGE | 01705 | 0 | 0 | OGE-01705 | Construction | Site Restoration | Construction.1.5.5 | Install Street Curbs --> OG Phase 4 | 15 | 15 | 0% | 2023-03-09 08:00 | 2023-03-29 17:00 | -40 | MLJ | CURBS | 0 | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.5 | OGE | OGE | 01710 | 0 | 0 | OGE-01710 | Construction | Site Restoration | Construction.1.5.5 | Install sidewalks --> OG Phase 4 | 10 | 10 | 0% | 2023-04-13 08:00 | 2023-04-26 17:00 | -40 | JMC | SIDEWALKS | 0 | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.5 | OGE | OGE | 01715 | 0 | 0 | OGE-01715 | Construction | Site Restoration | Construction.1.5.5 | Install curb around play area --> OG Phase 4 | 5 | 5 | 0% | 2023-04-27 08:00 | 2023-05-03 17:00 | -40 | MLJ | CURBS | 0 | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.5 | OGE | OGE | 01720 | 0 | 0 | OGE-01720 | Construction | Site Restoration | Construction.1.5.5 | Install Safety Surface --> OG Phase 4 | 5 | 5 | 0% | 2023-05-04 08:00 | 2023-05-10 17:00 | -40 | UNSURE | PLAYGROUND | SAFETY SURFACE | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.5 | OGE | OGE | 01725 | 0 | 0 | OGE-01725 | Construction | Site Restoration | Construction.1.5.5 | Install site furniture concrete foundations --> OG Phase 4 | 10 | 10 | 0% | 2023-03-30 08:00 | 2023-04-12 17:00 | -40 | MLJ | CONCRETE | SITE CONCRETE | 03-2200 | 03-2200-OGE
In Progress | CI NYCHA Update #22.Construction.1.5.5 | OGE | OGE | 01730 | 0 | 0 | OGE-01730 | Construction | Site Restoration | Construction.1.5.5 | Install integrally colored concrete walkways --> OG Phase 4 | 20 | 18 | 10% | 2022-10-17 | 2022-12-20 17:00 | 57 | JMC | COLORED CONCRETE | 0 | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.5 | OGE | OGE | 01735 | 0 | 0 | OGE-01735 | Construction | Site Restoration | Construction.1.5.5 | Install Play area items --> OG Phase 4 | 5 | 5 | 0% | 2023-05-11 08:00 | 2023-05-17 17:00 | -40 | BRIGHTON | PLAYGROUND | INSTALL | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.5 | OGE | OGE | 01740 | 0 | 0 | OGE-01740 | Construction | Site Restoration | Construction.1.5.5 | Install fence around play area --> OG Phase 4 | 10 | 10 | 0% | 2023-05-18 08:00 | 2023-06-01 17:00 | -40 | MLJ | FENCING | PLAYGROUND | 32-6520 | 32-6520-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.5 | OGE | OGE | 01745 | 0 | 0 | OGE-01745 | Construction | Site Restoration | Construction.1.5.5 | Install Fence at building --> OG10 | 5 | 5 | 0% | 2023-06-02 08:00 | 2023-06-08 17:00 | -40 | ATLAS | SITE RESTORATION | 0 | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.5 | OGE | OGE | 01750 | 0 | 0 | OGE-01750 | Construction | Site Restoration | Construction.1.5.5 | Place Site Furniture --> OG Phase 4 | 10 | 10 | 0% | 2023-06-09 08:00 | 2023-06-22 17:00 | -40 | MLJ | SITE RESTORATION | SITE FURNITURE | 31-2600 | 31-2600-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.5 | OGE | OGE | 01755 | 0 | 0 | OGE-01755 | Construction | Site Restoration | Construction.1.5.5 | Place topsoil --> OG Phase 4 | 3 | 3 | 0% | 2023-09-01 08:00 | 2023-09-05 17:00 | -13 | ASPEN | TOPSOIL | 0 | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.5 | OGE | OGE | 01760 | 0 | 0 | OGE-01760 | Construction | Site Restoration | Construction.1.5.5 | Place trees and plantings --> OG Phase 4 | 5 | 5 | 0% | 2023-09-06 08:00 | 2023-09-12 17:00 | -13 | ASPEN | 0 | 0 | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.5 | OGE | OGE | 01765 | 0 | 0 | OGE-01765 | Construction | Site Restoration | Construction.1.5.5 | Place lawn --> OG Phase 4 | 5 | 5 | 0% | 2023-09-13 08:00 | 2023-09-19 17:00 | -13 | ASPEN | 0 | 0 | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.5 | OGE | OGE | 01770 | 0 | 0 | OGE-01770 | Construction | Site Restoration | Construction.1.5.5 | Demobilize from OG Phase 4 | 5 | 5 | 0% | 2024-01-25 08:00 | 2024-01-31 17:00 | -169 | MLJ | DEMOB | 0 | 99-4000 | 99-4000-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01325 | 0 | 0 | OGE-01325 | Construction | Site Utilities | Construction.1.5.6 | Excavate for Steam OG5--> OG6 | 15 | 0 | 100% | 2022-06-01 | 2022-06-07 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01330 | 0 | 0 | OGE-01330 | Construction | Site Utilities | Construction.1.5.6 | Install Steam and piping OG5--> OG6 | 20 | 0 | 100% | 2022-06-20 | 2022-08-29 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01335 | 0 | 0 | OGE-01335 | Construction | Site Utilities | Construction.1.5.6 | Test Steam & Piping OG5--> OG6 | 8 | 0 | 100% | 2022-08-30 | 2022-08-31 |  | WELKIN | UG PIPE | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01345 | 0 | 0 | OGE-01345 | Construction | Site Utilities | Construction.1.5.6 | Backfill Steam & Piping OG5--> OG6 | 10 | 0 | 100% | 2022-09-06 | 2022-09-09 |  | MLJ | BACKFILL | BACKFILL UTILITY | 31-2200 | 31-2200-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01340 | 0 | 0 | OGE-01340 | Construction | Site Utilities | Construction.1.5.6 | Install Automatic Temperature Control Conduit - OG5--> OG6 | 2 | 0 | 100% | 2022-09-24 08:00 | 2022-09-24 17:00 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01575 | 0 | 0 | OGE-01575 | Construction | Site Utilities | Construction.1.5.6 | Excavate and Install Area Drains - Yard Drain to AD23 + Piping | 15 | 0 | 100% | 2022-08-25 | 2022-08-31 |  | MLJ | Excavation | AREA DRAIN | 33-2600 | 33-2600-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01580 | 0 | 0 | OGE-01580 | Construction | Site Utilities | Construction.1.5.6 | Backfill Area Drains - Yard Drain to AD23 + Piping | 5 | 0 | 100% | 2022-09-01 | 2022-09-05 |  | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01590 | 0 | 0 | OGE-01590 | Construction | Site Utilities | Construction.1.5.6 | Excavate and Install Area Drains - Yard Drain to AD9 + Piping | 15 | 15 | 0% | 2022-11-25 08:00 | 2022-12-15 17:00 | 10 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01595 | 0 | 0 | OGE-01595 | Construction | Site Utilities | Construction.1.5.6 | Backfill Area Drains - Yard Drain to AD9 + Piping | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | 10 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01650 | 0 | 0 | OGE-01650 | Construction | Site Utilities | Construction.1.5.6 | Excavate and Install Area Drains - AD6 > AD9 > AD8 to MH2 & Piping | 15 | 0 | 100% | 2022-09-15 | 2022-10-14 |  | MLJ | Excavation | AREA DRAIN | 33-2600 | 33-2600-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01655 | 0 | 0 | OGE-01655 | Construction | Site Utilities | Construction.1.5.6 | Backfill Area Drains - AD6 > AD9 > AD8 to MH2 & Piping | 5 | 0 | 100% | 2022-10-17 | 2022-10-21 |  | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGE
In Progress | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01660 | 0 | 0 | OGE-01660 | Construction | Site Utilities | Construction.1.5.6 | Excavate and Install Area Drains - Cellar Ramp Pump to Existing & Piping (Incl DIP8 & DIP9) | 15 | 2 | 86% | 2022-08-27 | 2022-11-28 17:00 | 23 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01665 | 0 | 0 | OGE-01665 | Construction | Site Utilities | Construction.1.5.6 | Backfill Area Drains - Cellar Ramp Pump to Existing & Piping (Incl DIP8 & DIP9) | 5 | 5 | 0% | 2022-11-29 08:00 | 2022-12-05 17:00 | 23 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01670 | 0 | 0 | OGE-01670 | Construction | Site Utilities | Construction.1.5.6 | Excavate and Install Area Drains - Yard Drain > AD7 > MH2 > AD18 > AD7 to Existing + Piping | 15 | 0 | 100% | 2022-06-13 | 2022-07-08 |  | MLJ | Excavation | AREA DRAIN | 33-2600 | 33-2600-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01675 | 0 | 0 | OGE-01675 | Construction | Site Utilities | Construction.1.5.6 | Backfill Area Drains - Yard Drain > AD7 > MH2 > AD18 > AD7 to Existing + Piping | 5 | 0 | 100% | 2022-07-10 | 2022-07-15 |  | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01680 | 0 | 0 | OGE-01680 | Construction | Site Utilities | Construction.1.5.6 | Excavate and Install Area Drains - AD23 > MH3 > MH2 & Piping | 15 | 0 | 100% | 2022-06-20 | 2022-08-28 |  | MLJ | Excavation | AREA DRAIN | 33-2600 | 33-2600-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01685 | 0 | 0 | OGE-01685 | Construction | Site Utilities | Construction.1.5.6 | Backfill Area Drains - AD23 > MH3 > MH2 & Piping | 5 | 0 | 100% | 2022-08-29 | 2022-09-05 |  | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01690 | 0 | 0 | OGE-01690 | Construction | Site Utilities | Construction.1.5.6 | Excavate and Install Area Drains - AD15 > AD20 > Existing + Piping | 15 | 15 | 0% | 2022-11-25 08:00 | 2022-12-15 17:00 | -40 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01695 | 0 | 0 | OGE-01695 | Construction | Site Utilities | Construction.1.5.6 | Backfill Area Drains - AD15 > AD20 > Existing + Piping | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -20 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGE
Not Started | CI NYCHA Update #22.Construction.5.2.5.1 | OG2 | OG2 | 01005 | 0 | 0 | OG2-01005 | Construction | Asbestos Abatement | Construction.5.2.5.1 | Asbestos Abatement - gaskets - cellar - OG2 | 3 | 3 | 0% | 2023-07-05 08:00 | 2023-07-07 17:00 | -58 | ATCO | ABESTOS | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.1 | OG2 | OG2 | 01010 | 0 | 0 | OG2-01010 | Construction | Asbestos Abatement | Construction.5.2.5.1 | Asbestos Abatement - wire insulation - cellar --> OG2 | 3 | 0 | 100% | 2021-07-19 08:00 | 2021-08-18 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.1 | OG2 | OG2 | 01015 | 0 | 0 | OG2-01015 | Construction | Asbestos Abatement | Construction.5.2.5.1 | Asbestos Abatement - flooring materials at slab penetrations - cellar --> OG2 | 3 | 0 | 100% | 2022-04-11 08:00 | 2022-04-22 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.1 | OG2 | OG2 | 01020 | 0 | 0 | OG2-01020 | Construction | Asbestos Abatement | Construction.5.2.5.1 | Asbestos Abatement - pipe insulation - cellar --> OG2 | 3 | 0 | 100% | 2021-07-19 08:00 | 2021-08-18 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.1 | OG2 | OG2 | 01025 | 0 | 0 | OG2-01025 | Construction | Asbestos Abatement | Construction.5.2.5.1 | Asbestos Abatement - Window Sills - 1st Floor --> OG2 | 5 | 0 | 100% | 2022-08-29 | 2022-08-29 |  | ATCO | ABESTOS | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.1 | OG2 | OG2 | 01030 | 0 | 0 | OG2-01030 | Construction | Asbestos Abatement | Construction.5.2.5.1 | Asbestos Abatement - caulk @ windows and areaway vents --> OG2 | 5 | 0 | 100% | 2022-09-02 | 2022-09-02 |  | ATCO | ABESTOS | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.2 | OG2 | OG2 | 01105 | 0 | 0 | OG2-01105 | Construction | Interior Demolition | Construction.5.2.5.2 | Selective Demo (Plaster walls, Doors, windows) - Cellar --> OG2 | 10 | 0 | 100% | 2021-05-18 | 2022-07-26 |  | MLJ | DEMO | DEMO CELLAR WALLS | 02-6005 | 02-6005-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.2 | OG2 | OG2 | 01110 | 0 | 0 | OG2-01110 | Construction | Interior Demolition | Construction.5.2.5.2 | Selective Demo (Doors, windows) - 1st Floor --> OG2 | 5 | 0 | 100% | 2022-09-26 | 2022-09-30 |  | MLJ | DEMO | DEMO DOORS WINDOWS | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.2 | OG2 | OG2 | 01115 | 0 | 0 | OG2-01115 | Construction | Interior Demolition | Construction.5.2.5.2 | Selective Demo (Areaway drain, slab, wall) --> OG2 | 10 | 0 | 100% | 2022-08-01 08:00 | 2022-08-05 17:00 |  | MLJ | DEMO | DEMO AREAWAY | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.2 | OG2 | OG2 | 01205 | 0 | 0 | OG2-01205 | Construction | Interior Demolition | Construction.5.2.5.2 | Selective Demo (Existing Ramp, railing) - 1st Floor --> OG2 | 5 | 0 | 100% | 2022-09-01 08:00 | 2022-09-09 17:00 |  | MLJ | DEMO | DEMO RAMP | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.2 | OG2 | OG2 | 01210 | 0 | 0 | OG2-01210 | Construction | Interior Demolition | Construction.5.2.5.2 | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> OG2 - N/A | 5 | 0 | 100% | 2022-03-25 08:00 | 2022-03-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.2 | OG2 | OG2 | 01215 | 0 | 0 | OG2-01215 | Construction | Interior Demolition | Construction.5.2.5.2 | Selective Demo - 2nd Floor Apartment for Electrical Room --> OG2 | 5 | 0 | 100% | 2021-10-08 | 2022-01-20 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.4 | OG2 | OG2 | 01310 | 0 | 0 | OG2-01310 | Construction | Interior Renovations | Construction.5.2.5.4 | Make openings in floor for conduit penetrations - 2nd floor apartments --> OG2 | 5 | 0 | 100% | 2022-05-17 | 2022-05-18 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.4 | OG2 | OG2 | 01315 | 0 | 0 | OG2-01315 | Construction | Interior Renovations | Construction.5.2.5.4 | Install beams below floor - 2nd floor apartments --> OG2 | 5 | 0 | 100% | 2022-04-25 | 2022-04-25 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.4 | OG2 | OG2 | 01320 | 0 | 0 | OG2-01320 | Construction | Interior Renovations | Construction.5.2.5.4 | Install FRP around floor openings - 2nd floor apartments --> OG2 | 5 | 0 | 100% | 2022-04-25 | 2022-05-13 |  | 0 | 0 | 0 | 0 | 0-OG2
In Progress | CI NYCHA Update #22.Construction.5.2.5.4 | OG2 | OG2 | 01325 | 0 | 0 | OG2-01325 | Construction | Interior Renovations | Construction.5.2.5.4 | Frame walls / install door for electrical room - 2nd floor --> OG2 | 3 | 1 | 66% | 2022-03-14 | 2022-11-25 17:00 | -19 | CCC | 0 | 0 | 0 | 0-OG2
In Progress | CI NYCHA Update #22.Construction.5.2.5.4 | OG2 | OG2 | 01330 | 0 | 0 | OG2-01330 | Construction | Interior Renovations | Construction.5.2.5.4 | Install drywall / tape / spackle - electrical room - 2nd floor --> OG2 | 5 | 1 | 80% | 2022-04-27 | 2022-11-25 17:00 | -19 | CCC | 0 | 0 | 0 | 0-OG2
In Progress | CI NYCHA Update #22.Construction.5.2.5.4 | OG2 | OG2 | 01335 | 0 | 0 | OG2-01335 | Construction | Interior Renovations | Construction.5.2.5.4 | Paint walls and seal floor electrical room - 2nd Floor --> OG2 | 10 | 1 | 90% | 2022-05-12 | 2022-11-25 17:00 | 94 | CCC | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.4 | OG2 | OG2 | 01340 | 0 | 0 | OG2-01340 | Construction | Interior Renovations | Construction.5.2.5.4 | Install VCT @ electrical room - 2nd Floor --> OG2 | 2 | 2 | 0% | 2022-12-09 08:00 | 2022-12-12 17:00 | 85 | UNSURE | FLOORING | VCT | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.1 | OG2 | OG2 | 01405 | 0 | 0 | OG2-01405 | Construction | East Elevation | Construction.5.2.5.EFPC.1 | Excavate at Curtain Wall for flood protection (East Side) --> OG2 | 7 | 0 | 100% | 2022-03-16 | 2022-03-23 |  | 0 | EXCAVATION | 0 | 31-1000 | 31-1000-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.1 | OG2 | OG2 | 01410 | 0 | 0 | OG2-01410 | Construction | East Elevation | Construction.5.2.5.EFPC.1 | Form concrete footings at Curtain Wall for flood protection (East Side) --> OG2 | 9 | 0 | 100% | 2022-05-10 | 2022-05-19 |  | 0 | FORMWORK | FORMWORK EB | 03-1100 | 03-1100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.1 | OG2 | OG2 | 01415 | 0 | 0 | OG2-01415 | Construction | East Elevation | Construction.5.2.5.EFPC.1 | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> OG2 | 4 | 0 | 100% | 2022-05-10 | 2022-05-12 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.1 | OG2 | OG2 | 01420 | 0 | 0 | OG2-01420 | Construction | East Elevation | Construction.5.2.5.EFPC.1 | Pour concrete footings at Curtain Wall for flood protection (East Side) --> OG2 | 3 | 0 | 100% | 2022-05-19 | 2022-05-19 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.1 | OG2 | OG2 | 01425 | 0 | 0 | OG2-01425 | Construction | East Elevation | Construction.5.2.5.EFPC.1 | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> OG2 | 4 | 0 | 100% | 2022-05-20 | 2022-05-20 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.1 | OG2 | OG2 | 01430 | 0 | 0 | OG2-01430 | Construction | East Elevation | Construction.5.2.5.EFPC.1 | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG2 | 7 | 0 | 100% | 2022-08-03 | 2022-08-05 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.1 | OG2 | OG2 | 01435 | 0 | 0 | OG2-01435 | Construction | East Elevation | Construction.5.2.5.EFPC.1 | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG2 | 5 | 0 | 100% | 2022-08-08 | 2022-08-10 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.1 | OG2 | OG2 | 01440 | 0 | 0 | OG2-01440 | Construction | East Elevation | Construction.5.2.5.EFPC.1 | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG2 | 3 | 0 | 100% | 2022-08-11 | 2022-08-11 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.1 | OG2 | OG2 | 01445 | 0 | 0 | OG2-01445 | Construction | East Elevation | Construction.5.2.5.EFPC.1 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG2 | 3 | 0 | 100% | 2022-08-12 | 2022-08-15 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.1 | OG2 | OG2 | 01450 | 0 | 0 | OG2-01450 | Construction | East Elevation | Construction.5.2.5.EFPC.1 | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> OG2 | 3 | 0 | 100% | 2022-08-16 | 2022-08-19 |  | FAXA | CMU | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.1 | OG2 | OG2 | 01455 | 0 | 0 | OG2-01455 | Construction | East Elevation | Construction.5.2.5.EFPC.1 | Backfill at Curtain Wall for flood protection (East Side) --> OG2 | 4 | 0 | 100% | 2022-08-22 | 2022-08-24 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.2 | OG2 | OG2 | 01505 | 0 | 0 | OG2-01505 | Construction | South Elevation | Construction.5.2.5.EFPC.2 | Excavate at Curtain Wall for flood protection (South Side) --> OG2 | 8 | 0 | 100% | 2022-03-16 | 2022-03-23 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.2 | OG2 | OG2 | 01510 | 0 | 0 | OG2-01510 | Construction | South Elevation | Construction.5.2.5.EFPC.2 | Form concrete footings at Curtain Wall for flood protection (South Side) --> OG2 | 10 | 0 | 100% | 2022-05-10 | 2022-05-19 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.2 | OG2 | OG2 | 01515 | 0 | 0 | OG2-01515 | Construction | South Elevation | Construction.5.2.5.EFPC.2 | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> OG2 | 5 | 0 | 100% | 2022-05-10 | 2022-05-12 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.2 | OG2 | OG2 | 01520 | 0 | 0 | OG2-01520 | Construction | South Elevation | Construction.5.2.5.EFPC.2 | Pour concrete footings at Curtain Wall for flood protection (South Side) --> OG2 | 4 | 0 | 100% | 2022-05-19 | 2022-05-19 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.2 | OG2 | OG2 | 01525 | 0 | 0 | OG2-01525 | Construction | South Elevation | Construction.5.2.5.EFPC.2 | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> OG2 | 5 | 0 | 100% | 2022-05-20 | 2022-05-20 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.2 | OG2 | OG2 | 01530 | 0 | 0 | OG2-01530 | Construction | South Elevation | Construction.5.2.5.EFPC.2 | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG2 | 8 | 0 | 100% | 2022-08-03 | 2022-08-05 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.2 | OG2 | OG2 | 01535 | 0 | 0 | OG2-01535 | Construction | South Elevation | Construction.5.2.5.EFPC.2 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG2 | 6 | 0 | 100% | 2022-08-08 | 2022-08-10 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.2 | OG2 | OG2 | 01540 | 0 | 0 | OG2-01540 | Construction | South Elevation | Construction.5.2.5.EFPC.2 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG2 | 4 | 0 | 100% | 2022-08-11 | 2022-08-11 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.2 | OG2 | OG2 | 01545 | 0 | 0 | OG2-01545 | Construction | South Elevation | Construction.5.2.5.EFPC.2 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG2 | 4 | 0 | 100% | 2022-08-12 | 2022-08-15 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.2 | OG2 | OG2 | 01550 | 0 | 0 | OG2-01550 | Construction | South Elevation | Construction.5.2.5.EFPC.2 | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> OG2 | 4 | 0 | 100% | 2022-08-16 | 2022-08-19 |  | FAXA | CMU | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.2 | OG2 | OG2 | 01555 | 0 | 0 | OG2-01555 | Construction | South Elevation | Construction.5.2.5.EFPC.2 | Backfill at Curtain Wall for flood protection (South Side) --> OG2 | 5 | 0 | 100% | 2022-08-22 | 2022-08-24 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.3 | OG2 | OG2 | 01605 | 0 | 0 | OG2-01605 | Construction | North Elevation | Construction.5.2.5.EFPC.3 | Excavate at Curtain Wall for flood protection (North Side) --> OG2 | 7 | 0 | 100% | 2022-03-16 | 2022-03-23 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.3 | OG2 | OG2 | 01610 | 0 | 0 | OG2-01610 | Construction | North Elevation | Construction.5.2.5.EFPC.3 | Form concrete footings at Curtain Wall for flood protection (North Side) --> OG2 | 9 | 0 | 100% | 2022-05-10 | 2022-05-19 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.3 | OG2 | OG2 | 01615 | 0 | 0 | OG2-01615 | Construction | North Elevation | Construction.5.2.5.EFPC.3 | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> OG2 | 4 | 0 | 100% | 2022-05-10 | 2022-05-12 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.3 | OG2 | OG2 | 01620 | 0 | 0 | OG2-01620 | Construction | North Elevation | Construction.5.2.5.EFPC.3 | Pour concrete footings at Curtain Wall for flood protection (North Side) --> OG2 | 3 | 0 | 100% | 2022-05-19 | 2022-05-19 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.3 | OG2 | OG2 | 01625 | 0 | 0 | OG2-01625 | Construction | North Elevation | Construction.5.2.5.EFPC.3 | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> OG2 | 4 | 0 | 100% | 2022-05-20 | 2022-05-20 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.3 | OG2 | OG2 | 01630 | 0 | 0 | OG2-01630 | Construction | North Elevation | Construction.5.2.5.EFPC.3 | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG2 | 7 | 0 | 100% | 2022-08-03 | 2022-08-05 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.3 | OG2 | OG2 | 01635 | 0 | 0 | OG2-01635 | Construction | North Elevation | Construction.5.2.5.EFPC.3 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG2 | 5 | 0 | 100% | 2022-08-08 | 2022-08-10 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.3 | OG2 | OG2 | 01640 | 0 | 0 | OG2-01640 | Construction | North Elevation | Construction.5.2.5.EFPC.3 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG2 | 3 | 0 | 100% | 2022-08-11 | 2022-08-11 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.3 | OG2 | OG2 | 01645 | 0 | 0 | OG2-01645 | Construction | North Elevation | Construction.5.2.5.EFPC.3 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG2 | 3 | 0 | 100% | 2022-08-12 | 2022-08-15 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.3 | OG2 | OG2 | 01650 | 0 | 0 | OG2-01650 | Construction | North Elevation | Construction.5.2.5.EFPC.3 | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> OG2 | 3 | 0 | 100% | 2022-08-16 | 2022-08-19 |  | FAXA | CMU | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.3 | OG2 | OG2 | 01655 | 0 | 0 | OG2-01655 | Construction | North Elevation | Construction.5.2.5.EFPC.3 | Backfill at Curtain Wall for flood protection (North Side) --> OG2 | 4 | 0 | 100% | 2022-08-22 | 2022-08-24 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.4 | OG2 | OG2 | 01705 | 0 | 0 | OG2-01705 | Construction | West Elevation | Construction.5.2.5.EFPC.4 | Excavate at Curtain Wall for flood protection (West Side) --> OG2 | 8 | 0 | 100% | 2022-03-16 | 2022-03-23 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.4 | OG2 | OG2 | 01710 | 0 | 0 | OG2-01710 | Construction | West Elevation | Construction.5.2.5.EFPC.4 | Form concrete footings at Curtain Wall for flood protection (West Side) --> OG2 | 10 | 0 | 100% | 2022-05-10 | 2022-05-19 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.4 | OG2 | OG2 | 01715 | 0 | 0 | OG2-01715 | Construction | West Elevation | Construction.5.2.5.EFPC.4 | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> OG2 | 5 | 0 | 100% | 2022-05-10 | 2022-05-12 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.4 | OG2 | OG2 | 01720 | 0 | 0 | OG2-01720 | Construction | West Elevation | Construction.5.2.5.EFPC.4 | Pour concrete footings at Curtain Wall for flood protection (West Side) --> OG2 | 4 | 0 | 100% | 2022-05-19 | 2022-05-19 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.4 | OG2 | OG2 | 01725 | 0 | 0 | OG2-01725 | Construction | West Elevation | Construction.5.2.5.EFPC.4 | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> OG2 | 5 | 0 | 100% | 2022-05-20 | 2022-05-20 |  | 0 | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.EFPC.4 | OG2 | OG2 | 01730 | 0 | 0 | OG2-01730 | Construction | West Elevation | Construction.5.2.5.EFPC.4 | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG2 | 8 | 8 | 0% | 2022-11-25 08:00 | 2022-12-06 17:00 | 49 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.EFPC.4 | OG2 | OG2 | 01735 | 0 | 0 | OG2-01735 | Construction | West Elevation | Construction.5.2.5.EFPC.4 | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG2 | 6 | 6 | 0% | 2022-12-07 08:00 | 2022-12-14 17:00 | 49 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.EFPC.4 | OG2 | OG2 | 01740 | 0 | 0 | OG2-01740 | Construction | West Elevation | Construction.5.2.5.EFPC.4 | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG2 | 4 | 4 | 0% | 2022-12-15 08:00 | 2022-12-20 17:00 | 49 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.EFPC.4 | OG2 | OG2 | 01745 | 0 | 0 | OG2-01745 | Construction | West Elevation | Construction.5.2.5.EFPC.4 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG2 | 4 | 4 | 0% | 2022-12-21 08:00 | 2022-12-27 17:00 | 50 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.EFPC.4 | OG2 | OG2 | 01750 | 0 | 0 | OG2-01750 | Construction | West Elevation | Construction.5.2.5.EFPC.4 | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> OG2 | 4 | 4 | 0% | 2022-12-28 08:00 | 2023-01-03 17:00 | 50 | FAXA | CMU | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.EFPC.4 | OG2 | OG2 | 01755 | 0 | 0 | OG2-01755 | Construction | West Elevation | Construction.5.2.5.EFPC.4 | Backfill at Curtain Wall for flood protection (West Side) --> OG2 | 5 | 5 | 0% | 2023-01-04 08:00 | 2023-01-10 17:00 | 50 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.EFPC.4 | OG2 | OG2 | 01760 | 0 | 0 | OG2-01760 | Construction | West Elevation | Construction.5.2.5.EFPC.4 | Form for slab at Curtain Wall for flood protection (West Side) --> OG2 | 4 | 4 | 0% | 2023-01-11 08:00 | 2023-01-17 17:00 | 50 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.EFPC.4 | OG2 | OG2 | 01765 | 0 | 0 | OG2-01765 | Construction | West Elevation | Construction.5.2.5.EFPC.4 | Rebar & inserts for slab at Curtain Wall for flood protection (West Side) --> OG2 | 6 | 6 | 0% | 2023-01-18 08:00 | 2023-01-25 17:00 | 50 | TONAGE | REBAR | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.EFPC.4 | OG2 | OG2 | 01770 | 0 | 0 | OG2-01770 | Construction | West Elevation | Construction.5.2.5.EFPC.4 | Pour slab at Curtain Wall for flood protection (West Side) --> OG2 | 4 | 4 | 0% | 2023-01-26 08:00 | 2023-01-31 17:00 | 50 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.EFPC.4 | OG2 | OG2 | 01775 | 0 | 0 | OG2-01775 | Construction | West Elevation | Construction.5.2.5.EFPC.4 | Strip Forms for slab at Curtain Wall for flood protection (West Side) --> OG2 | 2 | 2 | 0% | 2023-02-01 08:00 | 2023-02-02 17:00 | 53 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.EFPC.4 | OG2 | OG2 | 01780 | 0 | 0 | OG2-01780 | Construction | West Elevation | Construction.5.2.5.EFPC.4 | Backfill surounding area at Curtain Wall for flood protection (West Side) --> OG2 | 4 | 4 | 0% | 2023-02-08 08:00 | 2023-02-13 17:00 | 50 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.5 | OG2 | OG2 | 01805 | 0 | 0 | OG2-01805 | Construction | Concrete Shelf Construction | Construction.5.2.5.EFPC.5 | Excavate for concrete shelf around bldg perimeter --> OG2 | 10 | 0 | 100% | 2022-05-02 | 2022-05-09 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.5 | OG2 | OG2 | 01810 | 0 | 0 | OG2-01810 | Construction | Concrete Shelf Construction | Construction.5.2.5.EFPC.5 | Place rebar for concrete shelf around bldg perimeter --> OG2 | 5 | 0 | 100% | 2022-05-10 | 2022-05-18 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.5 | OG2 | OG2 | 01815 | 0 | 0 | OG2-01815 | Construction | Concrete Shelf Construction | Construction.5.2.5.EFPC.5 | Pour concrete shelf around bldg perimeter --> OG2 | 5 | 0 | 100% | 2022-05-19 | 2022-05-19 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.5 | OG2 | OG2 | 01820 | 0 | 0 | OG2-01820 | Construction | Concrete Shelf Construction | Construction.5.2.5.EFPC.5 | Place infill concrete in area ways around bldg perimeter --> OG2 | 5 | 0 | 100% | 2022-05-26 | 2022-05-31 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.5 | OG2 | OG2 | 01825 | 0 | 0 | OG2-01825 | Construction | Concrete Shelf Construction | Construction.5.2.5.EFPC.5 | Place waterproofing on concrete shelf around bldg perimeter --> OG2 | 10 | 0 | 100% | 2022-06-01 | 2022-06-06 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.5 | OG2 | OG2 | 01830 | 0 | 0 | OG2-01830 | Construction | Concrete Shelf Construction | Construction.5.2.5.EFPC.5 | Place CMU around bldg perimeter --OG2 | 15 | 0 | 100% | 2022-06-07 | 2022-08-05 17:00 |  | FAXA | CMU | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.5 | OG2 | OG2 | 01835 | 0 | 0 | OG2-01835 | Construction | Concrete Shelf Construction | Construction.5.2.5.EFPC.5 | Place waterproofing on CMU around bldg perimeter --> OG2 (Waterproofing Delay) | 10 | 0 | 100% | 2022-07-11 | 2022-08-25 |  | 0 | WATERPROOFING | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.EFPC.5 | OG2 | OG2 | 01840 | 0 | 0 | OG2-01840 | Construction | Concrete Shelf Construction | Construction.5.2.5.EFPC.5 | Place window frames around bldg perimeter --> OG2 | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | 105 | MLJ | CONCRETE SHELF | PLACE WINDOWS | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.5 | OG2 | OG2 | 01845 | 0 | 0 | OG2-01845 | Construction | Concrete Shelf Construction | Construction.5.2.5.EFPC.5 | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> OG2 | 20 | 0 | 100% | 2022-08-08 | 2022-10-21 |  | FAXA | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.EFPC.5 | OG2 | OG2 | 01850 | 0 | 0 | OG2-01850 | Construction | Concrete Shelf Construction | Construction.5.2.5.EFPC.5 | Backfill around bdg perimeter --> OG2 | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 110 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.EFPC.5 | OG2 | OG2 | 01855 | 0 | 0 | OG2-01855 | Construction | Concrete Shelf Construction | Construction.5.2.5.EFPC.5 | Place frame / stucco / and signs at entrances --> OG2 | 4 | 4 | 0% | 2022-12-09 08:00 | 2022-12-14 17:00 | 105 | CCC | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.EFPC.5 | OG2 | OG2 | 01860 | 0 | 0 | OG2-01860 | Construction | Concrete Shelf Construction | Construction.5.2.5.EFPC.5 | Place window floodgates at windows --> OG2 | 5 | 5 | 0% | 2022-12-15 08:00 | 2022-12-21 17:00 | 105 | MLJ | FLOOD PROTECTION | FLOOD WINDOWS | 10-1400 | 10-1400-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.EFPC.5 | OG2 | OG2 | 01865 | 0 | 0 | OG2-01865 | Construction | Concrete Shelf Construction | Construction.5.2.5.EFPC.5 | Install signs --> OG2 | 3 | 3 | 0% | 2022-12-22 08:00 | 2022-12-27 17:00 | 105 | MLJ | SIGNS | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.5 | OG2 | OG2 | 01350 | 0 | 0 | OG2-01350 | Construction | Boiler Room Construction | Construction.5.2.5.5 | Drill dowels and place rebar for boiler room concrete walls --> OG2 | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | -44 | MLJ | 0 | DRILL & DOWEL | 03-1400 | 03-1400-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.5 | OG2 | OG2 | 01355 | 0 | 0 | OG2-01355 | Construction | Boiler Room Construction | Construction.5.2.5.5 | Form boiler room concrete walls --> OG2 | 5 | 5 | 0% | 2022-12-02 08:00 | 2022-12-08 17:00 | -44 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.5 | OG2 | OG2 | 01360 | 0 | 0 | OG2-01360 | Construction | Boiler Room Construction | Construction.5.2.5.5 | Pour Concrete boiler room walls --> OG2 | 2 | 2 | 0% | 2022-12-09 08:00 | 2022-12-12 17:00 | -44 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.5 | OG2 | OG2 | 01365 | 0 | 0 | OG2-01365 | Construction | Boiler Room Construction | Construction.5.2.5.5 | Strip Forms boiler room concrete walls --> OG2 | 3 | 3 | 0% | 2022-12-13 08:00 | 2022-12-15 17:00 | -42 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.5 | OG2 | OG2 | 01370 | 0 | 0 | OG2-01370 | Construction | Boiler Room Construction | Construction.5.2.5.5 | Place crystaline waterproofing on perimeter walls - cellar --> OG2 - N/A | 10 | 0 | 100% | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0 | WATERPROOFING | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.6 | OG2 | OG2 | 01385 | 0 | 0 | OG2-01385 | Construction | Elevator Refurbishment | Construction.5.2.5.6 | Refurbish Elevator 1 --> OG2 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.6 | OG2 | OG2 | 01390 | 0 | 0 | OG2-01390 | Construction | Elevator Refurbishment | Construction.5.2.5.6 | Refurbish Elevator 2 --> OG2 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.6 | OG2 | OG2 | 01380 | 0 | 0 | OG2-01380 | Construction | Elevator Refurbishment | Construction.5.2.5.6 | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.7 | OG2 | OG2 | 09005 | 0 | 0 | OG2-09005 | Construction | Civil/Architectural Inspections | Construction.5.2.5.7 | Perform Inspections & Issue Punch List | 5 | 5 | 0% | 2023-07-10 08:00 | 2023-07-14 17:00 | -58 | MLJ | PUNCH LIST | INSPECTION | 99-8200 | 99-8200-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.7 | OG2 | OG2 | 09010 | 0 | 0 | OG2-09010 | Construction | Civil/Architectural Inspections | Construction.5.2.5.7 | Perform Punch List | 10 | 10 | 0% | 2023-07-17 08:00 | 2023-07-28 17:00 | -43 | MLJ | PUNCH LIST | 0 | 99-8200 | 99-8200-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.2 | OG2 | OG2 | 01220 | 0 | 0 | OG2-01220 | Construction | Interior Demolition | Construction.5.2.5.2 | Selective Demo (Pumps etc..) - Cellar --> OG2 | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | -57 | MLJ | DEMO | DEMO PUMPS | 02-6010 | 02-6010-OG2
Completed | CI NYCHA Update #22.Procurement.Div. 33 | OGW | 33530 | 0 | 0 | 0 | 33530 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Prepare & Submit Utility Coord. Dwgs - Odwyer Gardens - West | 20 | 0 | 100% | 2021-05-01 08:00 | 2021-06-29 17:00 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Procurement.Div. 33 | OGW | 33535 | 0 | 0 | 0 | 33535 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Review & Approve Utility Coord. Dwgs - Odwyer Gardens - West | 10 | 0 | 100% | 2021-06-30 08:00 | 2021-07-13 17:00 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Procurement.Div. 33 | OGE | 33540 | 0 | 0 | 0 | 33540 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Prepare & Submit Utility Coord. Dwgs - Odwyer Gardens - East | 20 | 0 | 100% | 2021-05-01 08:00 | 2021-06-29 17:00 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Procurement.Div. 33 | OGE | 33545 | 0 | 0 | 0 | 33545 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Review & Approve Utility Coord. Dwgs - Odwyer Gardens - East | 10 | 0 | 100% | 2021-06-30 08:00 | 2021-07-13 17:00 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Procurement.Div. 33 | SGS | 33550 | 0 | 0 | 0 | 33550 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Prepare & Submit Utility Coord. Dwgs - Surfside Gardens South | 20 | 0 | 100% | 2021-07-23 | 2021-07-23 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Procurement.Div. 33 | SGS | 33555 | 0 | 0 | 0 | 33555 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Review & Approve Utility Coord. Dwgs - Surfside Gardens South | 10 | 0 | 100% | 2021-07-24 | 2021-08-11 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Procurement.Div. 33 | S8 | 33560 | 0 | 0 | 0 | 33560 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Prepare & Submit Utility Coord. Dwgs - Site 8 | 20 | 0 | 100% | 2021-07-23 | 2022-05-13 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Procurement.Div. 33 | S8 | 33565 | 0 | 0 | 0 | 33565 | Procurement | Div. 33 - Utilities | Procurement.Div. 33 | Review & Approve Utility Coord. Dwgs - Site 8 | 10 | 0 | 100% | 2022-05-13 08:00 | 2022-05-13 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01350 | 0 | 0 | OGE-01350 | Construction | Site Utilities | Construction.1.5.6 | Excavate for Steam OG1--> OG6 | 15 | 0 | 100% | 2021-10-11 | 2021-10-13 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01355 | 0 | 0 | OGE-01355 | Construction | Site Utilities | Construction.1.5.6 | Install Steam and piping OG1--> OG6 | 20 | 0 | 100% | 2021-11-22 08:00 | 2022-02-22 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01360 | 0 | 0 | OGE-01360 | Construction | Site Utilities | Construction.1.5.6 | Test Steam & Piping OG1--> OG6 | 8 | 0 | 100% | 2022-02-22 | 2022-02-24 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01370 | 0 | 0 | OGE-01370 | Construction | Site Utilities | Construction.1.5.6 | Backfill Steam & Piping OG1--> OG6 | 10 | 0 | 100% | 2022-05-09 | 2022-05-16 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01365 | 0 | 0 | OGE-01365 | Construction | Site Utilities | Construction.1.5.6 | Install Automatic Temperature Control Conduit - OG1--> OG6 | 2 | 0 | 100% | 2022-05-18 | 2022-05-18 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01375 | 0 | 0 | OGE-01375 | Construction | Site Utilities | Construction.1.5.6 | Excavate for HW OG1--> OG10 | 15 | 0 | 100% | 2021-10-11 | 2021-10-13 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01380 | 0 | 0 | OGE-01380 | Construction | Site Utilities | Construction.1.5.6 | Install HW piping OG1--> OG10 | 20 | 0 | 100% | 2022-01-25 08:00 | 2022-02-10 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01385 | 0 | 0 | OGE-01385 | Construction | Site Utilities | Construction.1.5.6 | Test HW Piping OG1--> OG10 | 8 | 0 | 100% | 2022-02-11 | 2022-02-16 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01395 | 0 | 0 | OGE-01395 | Construction | Site Utilities | Construction.1.5.6 | Backfill HW Piping OG1--> OG10 | 10 | 0 | 100% | 2022-05-09 | 2022-05-16 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01390 | 0 | 0 | OGE-01390 | Construction | Site Utilities | Construction.1.5.6 | Install Automatic Temperature Control Conduit - OG1--> OG10 | 2 | 0 | 100% | 2022-05-18 | 2022-05-18 |  | 0 | 0 | 0 | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01700 | 0 | 0 | OGE-01700 | Construction | Site Utilities | Construction.1.5.6 | Excavate and Install Area Drains - AD16 > AD21 > Existing + Piping | 15 | 15 | 0% | 2022-12-16 08:00 | 2023-01-09 17:00 | -40 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01775 | 0 | 0 | OGE-01775 | Construction | Site Utilities | Construction.1.5.6 | Backfill Area Drains - AD16 > AD21 > Existing + Piping | 5 | 5 | 0% | 2023-01-10 08:00 | 2023-01-17 17:00 | -30 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01780 | 0 | 0 | OGE-01780 | Construction | Site Utilities | Construction.1.5.6 | Excavate and Install Area Drains - AD17 > AD22 > Existing + Piping | 15 | 15 | 0% | 2023-01-10 08:00 | 2023-01-31 17:00 | -40 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01785 | 0 | 0 | OGE-01785 | Construction | Site Utilities | Construction.1.5.6 | Backfill Area Drains - AD17 > AD22 > Existing + Piping | 5 | 5 | 0% | 2023-02-01 08:00 | 2023-02-07 17:00 | -40 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGE
Completed | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01790 | 0 | 0 | OGE-01790 | Construction | Site Utilities | Construction.1.5.6 | Excavate and Install Area Drains - AD5 > AD4 > AD3 > Existing + Piping | 15 | 0 | 100% | 2022-11-14 08:00 | 2022-11-18 17:00 |  | MLJ | Excavation | AREA DRAIN | 33-2600 | 33-2600-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01795 | 0 | 0 | OGE-01795 | Construction | Site Utilities | Construction.1.5.6 | Backfill Area Drains - AD5 > AD4 > AD3 > Existing + Piping | 5 | 5 | 0% | 2023-02-08 08:00 | 2023-02-14 17:00 | -40 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01800 | 0 | 0 | OGE-01800 | Construction | Site Utilities | Construction.1.5.6 | Excavate and Install Area Drains - Ramp Pump > AD1 > AD2 > AD16 > AD21 > Existing + Piping | 15 | 15 | 0% | 2022-11-25 08:00 | 2022-12-15 17:00 | -20 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01805 | 0 | 0 | OGE-01805 | Construction | Site Utilities | Construction.1.5.6 | Backfill Area Drains - Ramp Pump > AD1 > AD2 > AD16 > AD21 > Existing + Piping | 5 | 5 | 0% | 2023-02-15 08:00 | 2023-02-22 17:00 | -40 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01810 | 0 | 0 | OGE-01810 | Construction | Site Utilities | Construction.1.5.6 | Excavate and Install Area Drains - AD19 > Existing + Piping | 15 | 15 | 0% | 2022-12-16 08:00 | 2023-01-09 17:00 | -20 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01815 | 0 | 0 | OGE-01815 | Construction | Site Utilities | Construction.1.5.6 | Backfill Area Drains - AD19 > Existing + Piping | 5 | 5 | 0% | 2023-02-23 08:00 | 2023-03-01 17:00 | -40 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01820 | 0 | 0 | OGE-01820 | Construction | Site Utilities | Construction.1.5.6 | Excavate and Install Area Drains - AD1 > AD7 > AD3 > Existing + Piping | 15 | 15 | 0% | 2023-01-10 08:00 | 2023-01-31 17:00 | -20 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.6 | OGE | OGE | 01825 | 0 | 0 | OGE-01825 | Construction | Site Utilities | Construction.1.5.6 | Backfill Area Drains - AD1 > AD7 > AD3 > Existing + Piping | 5 | 5 | 0% | 2023-03-02 08:00 | 2023-03-08 17:00 | -40 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-OGE
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01030 | 0 | 0 | OG10-01030 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Form Plumbing Shafts & Ftgs Below Water Table --> OG10 | 10 | 0 | 100% | 2021-08-23 | 2021-08-26 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01035 | 0 | 0 | OG10-01035 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Rebar Plumbing Shafts & Ftgs Below Water Table --> OG10 | 5 | 0 | 100% | 2021-08-26 08:00 | 2021-08-27 17:00 |  | Tonage | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01040 | 0 | 0 | OG10-01040 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Pour Plumbing Shafts & Ftgs Below Water Table --> OG10 | 2 | 0 | 100% | 2021-08-27 08:00 | 2021-08-27 17:00 |  | MLJ | concrete | NB CONCRETE | 03-1900 | 03-1900-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01045 | 0 | 0 | OG10-01045 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Strip Forms Plumbing Shafts & Ftgs Below Water Table --> OG10 | 5 | 0 | 100% | 2021-08-30 08:00 | 2021-08-31 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01027 | 0 | 0 | OG10-01027 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Waterproof/Insulation Plumbing Shaft ----> OG10 | 5 | 0 | 100% | 2021-08-27 | 2021-08-27 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01020 | 0 | 0 | OG10-01020 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Excavate For Plumbing Shaft & Ftgs/Piers Below Water Table --> OG10 | 10 | 0 | 100% | 2021-07-26 08:00 | 2021-08-03 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01025 | 0 | 0 | OG10-01025 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Prepare Subgrade For Plumbing Shafts & Ftgs / Piers Below Water Table --> OG10 | 3 | 0 | 100% | 2021-08-04 | 2021-08-16 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01055 | 0 | 0 | OG10-01055 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Backfill Plumbing Shaft & Ftgs/Piers --> OG10 | 5 | 0 | 100% | 2021-09-09 | 2021-09-26 |  | 0 | OG10 | 0 | 31-1400 | 31-1400-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01065 | 0 | 0 | OG10-01065 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Excavate For Remaining Ftgs/Pier/Grade Beams --> OG10 | 10 | 0 | 100% | 2021-08-04 | 2021-08-09 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01070 | 0 | 0 | OG10-01070 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Form Remaining Ftgs/Piers/Grade Beams --> OG10 | 10 | 0 | 100% | 2021-08-19 | 2021-09-26 |  | 0 | FORMWORK | FORMWORK NB | 03-1000 | 03-1000-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01075 | 0 | 0 | OG10-01075 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Rebar Remaining Ftgs/Piers/Grade Beams --> OG10 | 10 | 0 | 100% | 2021-09-10 | 2021-09-27 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01080 | 0 | 0 | OG10-01080 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Pour Remaining Ftgs/Piers/Grade Beams --> OG10 | 5 | 0 | 100% | 2021-09-23 08:00 | 2021-09-28 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01085 | 0 | 0 | OG10-01085 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Strip Forms Remaining Ftgs/Piers/Grade Beams --> OG10 | 5 | 0 | 100% | 2021-09-28 | 2021-09-30 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01090 | 0 | 0 | OG10-01090 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Remaining Steam Into OG10 (5' from the building) | 5 | 0 | 100% | 2022-03-28 | 2022-04-06 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01095 | 0 | 0 | OG10-01095 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Backfill Remaining Ftgs/Piers/Grade Beams / Prepare Subgrade --> OG10 | 5 | 0 | 100% | 2021-09-30 | 2021-10-04 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01105 | 0 | 0 | OG10-01105 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Structural Steel Framing - 1st Floor --> OG10 | 10 | 0 | 100% | 2021-12-10 | 2021-12-17 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01110 | 0 | 0 | OG10-01110 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Metal Deck --> OG10 | 2 | 0 | 100% | 2021-12-18 08:00 | 2021-12-24 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01115 | 0 | 0 | OG10-01115 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Form Pour Strip Concrete Stair South Side ---> OG10 | 5 | 0 | 100% | 2021-11-15 08:00 | 2021-11-19 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01120 | 0 | 0 | OG10-01120 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Metal Stairs --> OG10 | 2 | 0 | 100% | 2022-04-04 08:00 | 2022-05-13 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01125 | 0 | 0 | OG10-01125 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Place Insulation Below First Floor --> OG10 | 5 | 0 | 100% | 2021-11-09 08:00 | 2021-11-10 17:00 |  | 0 | 0 | 0 | 07-1100 | 07-1100-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01130 | 0 | 0 | OG10-01130 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Place WWF First Floor Slab --> OG10 | 2 | 0 | 100% | 2021-11-10 08:00 | 2021-11-10 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01135 | 0 | 0 | OG10-01135 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Pour First Floor Slab --> OG10 | 1 | 0 | 100% | 2021-11-15 08:00 | 2021-11-15 17:00 |  | MLJ | concrete | NB CONCRETE | 03-1900 | 03-1900-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01150 | 0 | 0 | OG10-01150 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Form First Floor Concrete Walls First Face And Col Encasements--> OG10 | 3 | 0 | 100% | 2021-11-03 08:00 | 2021-11-12 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01155 | 0 | 0 | OG10-01155 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Rebar First Floor Concrete Walls --> OG10 | 3 | 0 | 100% | 2021-11-15 08:00 | 2021-11-17 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01160 | 0 | 0 | OG10-01160 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Form First Floor Concrete Walls 2Nd Face --> OG10 | 5 | 0 | 100% | 2021-11-18 | 2021-11-23 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01165 | 0 | 0 | OG10-01165 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Form, Rebar & Pour Concrete Pads 1st Floor --> OG10 - N/A | 3 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01170 | 0 | 0 | OG10-01170 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Place WWF 2nd Floor Slab --> OG10 | 2 | 0 | 100% | 2022-02-08 | 2022-02-10 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01175 | 0 | 0 | OG10-01175 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Pour 2nd Floor Slab / First Floor Walls & Col Encasements And 1st Floor Pads --> OG10 | 2 | 0 | 100% | 2022-02-10 | 2022-02-10 |  | MLJ | concrete | NB CONCRETE | 03-1900 | 03-1900-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01180 | 0 | 0 | OG10-01180 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Strip Forms First Floor Walls & Col Encasements And 1st Floor Pads --> OG10 | 3 | 0 | 100% | 2022-02-28 | 2022-03-03 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01185 | 0 | 0 | OG10-01185 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Form Concrete Pads 2nd Floor -->OG10 | 2 | 0 | 100% | 2022-03-28 | 2022-04-01 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01205 | 0 | 0 | OG10-01205 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Place WWF Roof Slab --> OG10 | 2 | 0 | 100% | 2022-02-08 | 2022-02-10 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01210 | 0 | 0 | OG10-01210 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Pour Roof Slab and 2nd Floor Conc Pads -->OG10 | 1 | 0 | 100% | 2022-02-10 | 2022-02-10 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01215 | 0 | 0 | OG10-01215 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Strip Forms Concrete Pads 2nd Floor -->OG10 | 2 | 0 | 100% | 2022-02-08 | 2022-03-03 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01225 | 0 | 0 | OG10-01225 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Spray-On Fireproofing on St Stl --> OG10 | 5 | 0 | 100% | 2022-04-12 | 2022-05-06 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01230 | 0 | 0 | OG10-01230 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Place CMU 1st, 2nd Floors and Roof --> OG10 | 20 | 0 | 100% | 2022-05-09 | 2022-09-22 |  | FAXA | CMU | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01240 | 0 | 0 | OG10-01240 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Stud Framing 1st, 2nd Floors and Roof --> OG10 | 5 | 0 | 100% | 2022-08-10 | 2022-10-14 |  | CCC | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01245 | 0 | 0 | OG10-01245 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Doors --> OG10 | 3 | 3 | 0% | 2023-01-18 08:00 | 2023-01-20 17:00 | 36 | CCC | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01250 | 0 | 0 | OG10-01250 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Cast Stone Panels --> OG10 | 1 | 1 | 0% | 2023-01-23 08:00 | 2023-01-23 17:00 | 36 | JMC | CAST STONE | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01255 | 0 | 0 | OG10-01255 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Insulated Metal Panels/Louvers --> OG10 | 10 | 0 | 100% | 2022-10-14 | 2022-11-16 |  | NAVILLUS | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01260 | 0 | 0 | OG10-01260 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install MEP Roof Penetrations & Drains - OG10 | 1 | 0 | 100% | 2022-08-26 | 2022-08-28 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01265 | 0 | 0 | OG10-01265 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Roofing --> OG10 | 15 | 0 | 100% | 2022-08-08 08:00 | 2022-08-24 17:00 |  | TRIANGLE | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01270 | 0 | 0 | OG10-01270 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Dunnage Gratings --> OG10 | 2 | 0 | 100% | 2022-01-03 10:00 | 2022-01-04 10:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01275 | 0 | 0 | OG10-01275 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Brick Façade & Stone --> OG10 | 20 | 0 | 100% | 2022-09-20 | 2022-10-12 |  | FAXA | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01285 | 0 | 0 | OG10-01285 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Flood Vents And Small Louvers --> OG10 | 3 | 3 | 0% | 2022-11-25 08:00 | 2022-11-29 17:00 | 77 | MLJ | FLOOD PROTECTION | FLOOD VENTS | 08-1700 | 08-1700-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01290 | 0 | 0 | OG10-01290 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Stair And Roof Platform Railings --> OG10 | 5 | 0 | 100% | 2022-10-19 | 2022-10-21 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01295 | 0 | 0 | OG10-01295 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Ladders --> OG10 | 3 | 0 | 100% | 2022-04-15 | 2022-04-18 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01305 | 0 | 0 | OG10-01305 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Sheetrock and Stucco --> OG10 | 10 | 0 | 100% | 2022-02-03 | 2022-02-18 |  | 0 | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01310 | 0 | 0 | OG10-01310 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Ceramic Tile --> OG10 | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | 76 | UNSURE | FLOORING | CERAMIC | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01315 | 0 | 0 | OG10-01315 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Acoustical Ceiling --> OG10 | 2 | 2 | 0% | 2022-11-29 08:00 | 2022-11-30 17:00 | 76 | UNSURE | CEILING | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01320 | 0 | 0 | OG10-01320 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Place Crystaline Waterproofing In Plumbing Shaft --> OG10 | 3 | 0 | 100% | 2022-06-15 08:00 | 2022-06-16 17:00 |  | 0 | WATERPROOFING | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01325 | 0 | 0 | OG10-01325 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Paint All Areas --> OG10 | 15 | 15 | 0% | 2023-04-06 08:00 | 2023-04-26 17:00 | -10 | GG PAINT | PAINT | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01330 | 0 | 0 | OG10-01330 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Signs --> OG10 | 2 | 2 | 0% | 2023-04-27 08:00 | 2023-04-28 17:00 | -10 | MLJ | SIGNS | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01235 | 0 | 0 | OG10-01235 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Waterproofing to Parapet --> OG10 | 3 | 0 | 100% | 2022-08-10 | 2022-08-12 |  | 0 | WATERPROOFING | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01280 | 0 | 0 | OG10-01280 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Stucco Soffit --> OG10 | 5 | 5 | 0% | 2023-01-24 08:00 | 2023-01-30 17:00 | 36 | CCC | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01317 | 0 | 0 | OG10-01317 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Insulated Metal Panels left out for Access --> OG10 | 5 | 0 | 100% | 2022-11-16 | 2022-11-17 |  | NAVILLUS | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01092 | 0 | 0 | OG10-01092 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Remaining HW/CW Into OG10 (5' from the building) | 5 | 0 | 100% | 2021-09-20 | 2021-09-24 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01094 | 0 | 0 | OG10-01094 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Remaining Electrical POE Into OG10 | 5 | 0 | 100% | 2021-09-21 | 2021-10-05 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 03105 | 0 | 0 | OG10-03105 | Construction | 1st Floor | Construction.1.4.5.1 | Rough-In Plumbing Piping & Appurtenances - 1st Floor | 15 | 0 | 100% | 2022-02-03 | 2022-02-18 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 03110 | 0 | 0 | OG10-03110 | Construction | 1st Floor | Construction.1.4.5.1 | Rig Fuel Oil Tank & Piping - 1st Floor - N/A | 3 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 03125 | 0 | 0 | OG10-03125 | Construction | 1st Floor | Construction.1.4.5.1 | Install Remaining Piping & Appurtenances - 1st Floor | 5 | 0 | 100% | 2022-02-15 | 2022-02-18 |  | 0 | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 03130 | 0 | 0 | OG10-03130 | Construction | 1st Floor | Construction.1.4.5.1 | Install FOT Controls - 1st Floor | 20 | 20 | 0% | 2022-11-25 08:00 | 2022-12-22 17:00 | 52 | MEP | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 03135 | 0 | 0 | OG10-03135 | Construction | 1st Floor | Construction.1.4.5.1 | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | 52 | WELKIN | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 03140 | 0 | 0 | OG10-03140 | Construction | 1st Floor | Construction.1.4.5.1 | Install Plumbing Equipment - 1st Floor | 15 | 0 | 100% | 2022-06-06 | 2022-06-24 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 03145 | 0 | 0 | OG10-03145 | Construction | 1st Floor | Construction.1.4.5.1 | Mechanical Equipment Start-up & Balance - 1st Floor - N/A | 5 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 03150 | 0 | 0 | OG10-03150 | Construction | 1st Floor | Construction.1.4.5.1 | Plumbing/Mechanical Insulation - 1st Floor | 10 | 10 | 0% | 2022-12-02 08:00 | 2022-12-15 17:00 | 62 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 03107 | 0 | 0 | OG10-03107 | Construction | 1st Floor | Construction.1.4.5.1 | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 0 | 100% | 2022-06-06 | 2022-06-24 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 03142 | 0 | 0 | OG10-03142 | Construction | 1st Floor | Construction.1.4.5.1 | Install Mechanical Equipment - 1st Floor - N/A | 15 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.4 | OG10 | OG10 | 03005 | 0 | 0 | OG10-03005 | Construction | Foundation | Construction.1.4.5.4 | Rough-In Plumbing & Appurtenances - Plumbing Shaft | 10 | 0 | 100% | 2022-08-15 | 2022-08-23 |  | WELKIN | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.4 | OG10 | OG10 | 03010 | 0 | 0 | OG10-03010 | Construction | Foundation | Construction.1.4.5.4 | Install Condensate Pump - Foundation Level | 10 | 0 | 100% | 2022-08-25 | 2022-08-31 |  | WELKIN | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.2 | OG10 | OG10 | 03205 | 0 | 0 | OG10-03205 | Construction | 2nd Floor | Construction.1.4.5.2 | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 15 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
In Progress | CI NYCHA Update #22.Construction.1.4.5.2 | OG10 | OG10 | 03225 | 0 | 0 | OG10-03225 | Construction | 2nd Floor | Construction.1.4.5.2 | Install Remaining Piping & Appurtenances - 2nd Floor | 20 | 10 | 50% | 2022-10-25 08:00 | 2022-12-08 17:00 | 13 | VITAL | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.2 | OG10 | OG10 | 03235 | 0 | 0 | OG10-03235 | Construction | 2nd Floor | Construction.1.4.5.2 | Perform Hydrostatic Testing - 2nd Floor | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | 3 | WELKIN | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.2 | OG10 | OG10 | 03240 | 0 | 0 | OG10-03240 | Construction | 2nd Floor | Construction.1.4.5.2 | Install Plumbing Equipment - 2nd Floor - N/A | 15 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.2 | OG10 | OG10 | 03245 | 0 | 0 | OG10-03245 | Construction | 2nd Floor | Construction.1.4.5.2 | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 0% | 2023-01-03 08:00 | 2023-01-17 17:00 | 3 | WELKIN | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.2 | OG10 | OG10 | 03250 | 0 | 0 | OG10-03250 | Construction | 2nd Floor | Construction.1.4.5.2 | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 0% | 2023-01-18 08:00 | 2023-02-14 17:00 | 3 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.2 | OG10 | OG10 | 03207 | 0 | 0 | OG10-03207 | Construction | 2nd Floor | Construction.1.4.5.2 | Rough-In Mechanical Piping & Appurtenances - 2nd Floor | 15 | 0 | 100% | 2022-03-28 | 2022-08-08 17:00 |  | WELKIN | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.5.2 | OG10 | OG10 | 03242 | 0 | 0 | OG10-03242 | Construction | 2nd Floor | Construction.1.4.5.2 | Install Mechanical Equipment - 2nd Floor | 20 | 20 | 0% | 2022-11-25 08:00 | 2022-12-22 17:00 | 3 | WELKIN | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 03405 | 0 | 0 | OG10-03405 | Construction | Roof | Construction.1.4.5.3 | Install Ductwork & Appurtenances - Roof - N/A | 4 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 03410 | 0 | 0 | OG10-03410 | Construction | Roof | Construction.1.4.5.3 | Install & Connect Exhaust Fans - Roof - N/A | 6 | 0 | 100% | 2021-02-01 | 2021-02-01 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.5.3 | OG10 | OG10 | 03415 | 0 | 0 | OG10-03415 | Construction | Roof | Construction.1.4.5.3 | Install Insulation - Roof - N/A | 15 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.6 | OG10 | OG10 | 03505 | 0 | 0 | OG10-03505 | Construction | Testing & Start-Up | Construction.1.4.6 | DOB Mechanical/Plumbing Inspection - OG10 | 4 | 4 | 0% | 2023-02-15 08:00 | 2023-02-21 17:00 | 22 | UNSURE | INSPECTION | INSPECTION | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.6 | OG10 | OG10 | 03510 | 0 | 0 | OG10-03510 | Construction | Testing & Start-Up | Construction.1.4.6 | Perform Start-Up Testing - OG10 | 15 | 15 | 0% | 2023-11-27 08:00 | 2023-12-15 17:00 | -169 | UNSURE | STARTUP | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.6 | OG10 | OG10 | 03515 | 0 | 0 | OG10-03515 | Construction | Testing & Start-Up | Construction.1.4.6 | Start-Up Testing & Commissioning Mechanical/Plumbing - OG10 | 16 | 16 | 0% | 2023-12-18 08:00 | 2024-01-10 17:00 | -169 | UNSURE | STARTUP | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.6 | OG10 | OG10 | 03520 | 0 | 0 | OG10-03520 | Construction | Testing & Start-Up | Construction.1.4.6 | Perform Punch List - Electrical/Mechanical/Plumbing Work - OG10 | 5 | 5 | 0% | 2024-01-11 08:00 | 2024-01-17 17:00 | -169 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.6 | OG10 | OG10 | 03530 | 0 | 0 | OG10-03530 | Construction | Testing & Start-Up | Construction.1.4.6 | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - OG10 | 4 | 4 | 0% | 2024-01-19 08:00 | 2024-01-24 17:00 | -169 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.6 | OG10 | OG10 | 03525 | 0 | 0 | OG10-03525 | Construction | Testing & Start-Up | Construction.1.4.6 | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - OG10 | 1 | 1 | 0% | 2024-01-18 08:00 | 2024-01-18 17:00 | -169 | FSE | INSPECTION | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.5.7 | OGE | OGE | 01850 | 0 | 0 | OGE-01850 | Construction | Civil/Architectural Inspections | Construction.1.5.7 | Perform Inspections & Issue Punch List | 5 | 5 | 0% | 2023-05-01 08:00 | 2023-05-05 17:00 | -10 | MLJ | PUNCH LIST | INSPECTION | 99-8200 | 99-8200-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.7 | OGE | OGE | 01855 | 0 | 0 | OGE-01855 | Construction | Civil/Architectural Inspections | Construction.1.5.7 | Perform Punch List | 10 | 10 | 0% | 2023-05-08 08:00 | 2023-05-19 17:00 | 5 | MLJ | PUNCH LIST | 0 | 99-8200 | 99-8200-OGE
Not Started | CI NYCHA Update #22.Construction.1.2.1.1 | OG6 | OG6 | 01005 | 0 | 0 | OG6-01005 | Construction | Asbestos Abatement | Construction.1.2.1.1 | Asbestos Abatement - gaskets - cellar - OG6 | 3 | 3 | 0% | 2024-01-19 08:00 | 2024-01-23 17:00 | -193 | ATCO | ABESTOS | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Construction.1.2.1.1 | OG6 | OG6 | 01010 | 0 | 0 | OG6-01010 | Construction | Asbestos Abatement | Construction.1.2.1.1 | Asbestos Abatement - wire insulation - cellar --> OG6 | 3 | 0 | 100% | 2021-08-23 08:00 | 2021-08-27 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Construction.1.2.1.1 | OG6 | OG6 | 01015 | 0 | 0 | OG6-01015 | Construction | Asbestos Abatement | Construction.1.2.1.1 | Asbestos Abatement - flooring materials at slab penetrations - cellar --> OG6 | 3 | 0 | 100% | 2022-11-14 | 2022-11-17 |  | ATCO | ABESTOS | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Construction.1.2.1.1 | OG6 | OG6 | 01020 | 0 | 0 | OG6-01020 | Construction | Asbestos Abatement | Construction.1.2.1.1 | Asbestos Abatement - pipe insulation - cellar --> OG6 | 3 | 0 | 100% | 2021-08-23 08:00 | 2021-08-27 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Construction.1.2.1.1 | OG6 | OG6 | 01025 | 0 | 0 | OG6-01025 | Construction | Asbestos Abatement | Construction.1.2.1.1 | Asbestos Abatement - Window Sills - 1st Floor --> OG6 | 5 | 0 | 100% | 2022-08-09 08:00 | 2022-08-10 17:00 |  | ATCO | ABESTOS | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Construction.1.2.1.1 | OG6 | OG6 | 01030 | 0 | 0 | OG6-01030 | Construction | Asbestos Abatement | Construction.1.2.1.1 | Asbestos Abatement - caulk @ windows and areaway vents --> OG6 | 5 | 0 | 100% | 2022-11-14 | 2022-11-17 |  | ATCO | ABESTOS | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Construction.1.2.1.2 | OG6 | OG6 | 01105 | 0 | 0 | OG6-01105 | Construction | Interior Demolition | Construction.1.2.1.2 | Selective Demo (Plaster walls, Doors, windows) - Cellar --> OG6 | 10 | 0 | 100% | 2021-05-06 | 2022-08-10 17:00 |  | MLJ | DEMO | DEMO CELLAR WALLS | 02-6005 | 02-6005-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.2 | OG6 | OG6 | 01110 | 0 | 0 | OG6-01110 | Construction | Interior Demolition | Construction.1.2.1.2 | Selective Demo (Doors, windows) - 1st Floor --> OG6 | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | -69 | MLJ | DEMO | DEMO DOORS WINDOWS | 02-6015 | 02-6015-OG6
Completed | CI NYCHA Update #22.Construction.1.2.1.2 | OG6 | OG6 | 01115 | 0 | 0 | OG6-01115 | Construction | Interior Demolition | Construction.1.2.1.2 | Selective Demo (Areaway drain, slab, wall) --> OG6 | 10 | 0 | 100% | 2022-11-15 | 2022-11-19 |  | MLJ | DEMO | DEMO AREAWAY | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.2 | OG6 | OG6 | 01205 | 0 | 0 | OG6-01205 | Construction | Interior Demolition | Construction.1.2.1.2 | Selective Demo (Existing Ramp, railing) - 1st Floor --> OG6 | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | -16 | MLJ | DEMO | DEMO RAMP | 02-6050 | 02-6050-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.2 | OG6 | OG6 | 01210 | 0 | 0 | OG6-01210 | Construction | Interior Demolition | Construction.1.2.1.2 | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> OG6 | 5 | 5 | 0% | 2022-12-02 08:00 | 2022-12-08 17:00 | -16 | MLJ | DEMO | DEMO SLAB OPEN FOR MECH | 02-3000 | 02-3000-OG6
Completed | CI NYCHA Update #22.Construction.1.2.1.2 | OG6 | OG6 | 01215 | 0 | 0 | OG6-01215 | Construction | Interior Demolition | Construction.1.2.1.2 | Selective Demo - 2nd Floor Apartment for Electrical Room --> OG6 | 5 | 0 | 100% | 2021-10-07 | 2022-02-10 |  | 0 | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.4 | OG6 | OG6 | 01310 | 0 | 0 | OG6-01310 | Construction | Interior Renovations | Construction.1.2.1.4 | Make openings in floor for conduit penetrations - 2nd floor apartments --> OG6 | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -74 | MLJ | CORE DRILL | 0 | 02-3000 | 02-3000-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.4 | OG6 | OG6 | 01315 | 0 | 0 | OG6-01315 | Construction | Interior Renovations | Construction.1.2.1.4 | Install beams below floor - 2nd floor apartments --> OG6 | 5 | 5 | 0% | 2022-12-09 08:00 | 2022-12-15 17:00 | -74 | WEIR | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.4 | OG6 | OG6 | 01320 | 0 | 0 | OG6-01320 | Construction | Interior Renovations | Construction.1.2.1.4 | Install FRP around floor openings - 2nd floor apartments --> OG6 | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | -74 | MLJ | 0 | FRP | 03-6000 | 03-6000-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.4 | OG6 | OG6 | 01325 | 0 | 0 | OG6-01325 | Construction | Interior Renovations | Construction.1.2.1.4 | Frame walls / install door for electrical room - 2nd floor --> OG6 | 3 | 3 | 0% | 2023-01-03 08:00 | 2023-01-05 17:00 | -74 | CCC | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.4 | OG6 | OG6 | 01330 | 0 | 0 | OG6-01330 | Construction | Interior Renovations | Construction.1.2.1.4 | Install drywall / tape / spackle - electrical room - 2nd floor --> OG6 | 5 | 5 | 0% | 2023-04-21 08:00 | 2023-04-27 17:00 | -74 | CCC | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.4 | OG6 | OG6 | 01335 | 0 | 0 | OG6-01335 | Construction | Interior Renovations | Construction.1.2.1.4 | Paint walls and seal floor electrical room - 2nd Floor --> OG6 | 10 | 10 | 0% | 2023-05-05 08:00 | 2023-05-18 17:00 | -26 | CCC | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.4 | OG6 | OG6 | 01340 | 0 | 0 | OG6-01340 | Construction | Interior Renovations | Construction.1.2.1.4 | Install VCT @ electrical room - 2nd Floor --> OG6 | 2 | 2 | 0% | 2023-05-19 08:00 | 2023-05-22 17:00 | -26 | UNSURE | FLOORING | VCT | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.1 | OG6 | OG6 | 01405 | 0 | 0 | OG6-01405 | Construction | East Elevation | Construction.1.2.1.EFPC.1 | Excavate at Curtain Wall for flood protection (East Side) --> OG6 | 8 | 8 | 0% | 2022-11-25 08:00 | 2022-12-06 17:00 | -4 | MLJ | EXCAVATION | EB EXC | 31-1000 | 31-1000-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.1 | OG6 | OG6 | 01410 | 0 | 0 | OG6-01410 | Construction | East Elevation | Construction.1.2.1.EFPC.1 | Form concrete footings at Curtain Wall for flood protection (East Side) --> OG6 | 10 | 10 | 0% | 2022-12-07 08:00 | 2022-12-20 17:00 | 33 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.1 | OG6 | OG6 | 01415 | 0 | 0 | OG6-01415 | Construction | East Elevation | Construction.1.2.1.EFPC.1 | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> OG6 | 5 | 5 | 0% | 2022-12-21 08:00 | 2022-12-28 17:00 | 33 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.1 | OG6 | OG6 | 01420 | 0 | 0 | OG6-01420 | Construction | East Elevation | Construction.1.2.1.EFPC.1 | Pour concrete footings at Curtain Wall for flood protection (East Side) --> OG6 | 4 | 4 | 0% | 2022-12-29 08:00 | 2023-01-04 17:00 | 33 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.1 | OG6 | OG6 | 01425 | 0 | 0 | OG6-01425 | Construction | East Elevation | Construction.1.2.1.EFPC.1 | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> OG6 | 5 | 5 | 0% | 2023-01-05 08:00 | 2023-01-11 17:00 | 33 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.1 | OG6 | OG6 | 01430 | 0 | 0 | OG6-01430 | Construction | East Elevation | Construction.1.2.1.EFPC.1 | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG6 | 8 | 8 | 0% | 2023-01-12 08:00 | 2023-01-24 17:00 | 33 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.1 | OG6 | OG6 | 01435 | 0 | 0 | OG6-01435 | Construction | East Elevation | Construction.1.2.1.EFPC.1 | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG6 | 6 | 6 | 0% | 2023-01-25 08:00 | 2023-02-01 17:00 | 33 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.1 | OG6 | OG6 | 01440 | 0 | 0 | OG6-01440 | Construction | East Elevation | Construction.1.2.1.EFPC.1 | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG6 | 4 | 4 | 0% | 2023-02-02 08:00 | 2023-02-07 17:00 | 33 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.1 | OG6 | OG6 | 01445 | 0 | 0 | OG6-01445 | Construction | East Elevation | Construction.1.2.1.EFPC.1 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG6 | 4 | 4 | 0% | 2023-02-08 08:00 | 2023-02-13 17:00 | 34 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.1 | OG6 | OG6 | 01450 | 0 | 0 | OG6-01450 | Construction | East Elevation | Construction.1.2.1.EFPC.1 | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> OG6 | 4 | 4 | 0% | 2023-02-15 08:00 | 2023-02-21 17:00 | 33 | FAXA | CMU | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.1 | OG6 | OG6 | 01455 | 0 | 0 | OG6-01455 | Construction | East Elevation | Construction.1.2.1.EFPC.1 | Backfill at Curtain Wall for flood protection (East Side) --> OG6 | 5 | 5 | 0% | 2023-02-22 08:00 | 2023-02-28 17:00 | 33 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.2 | OG6 | OG6 | 01505 | 0 | 0 | OG6-01505 | Construction | South Elevation | Construction.1.2.1.EFPC.2 | Excavate at Curtain Wall for flood protection (South Side) --> OG6 | 7 | 7 | 0% | 2022-12-07 08:00 | 2022-12-15 17:00 | -4 | MLJ | EXCAVATION | EB EXC | 31-1000 | 31-1000-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.2 | OG6 | OG6 | 01510 | 0 | 0 | OG6-01510 | Construction | South Elevation | Construction.1.2.1.EFPC.2 | Form concrete footings at Curtain Wall for flood protection (South Side) --> OG6 | 9 | 9 | 0% | 2022-12-16 08:00 | 2022-12-29 17:00 | 43 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.2 | OG6 | OG6 | 01515 | 0 | 0 | OG6-01515 | Construction | South Elevation | Construction.1.2.1.EFPC.2 | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> OG6 | 4 | 4 | 0% | 2022-12-30 08:00 | 2023-01-05 17:00 | 43 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.2 | OG6 | OG6 | 01520 | 0 | 0 | OG6-01520 | Construction | South Elevation | Construction.1.2.1.EFPC.2 | Pour concrete footings at Curtain Wall for flood protection (South Side) --> OG6 | 3 | 3 | 0% | 2023-01-06 08:00 | 2023-01-10 17:00 | 43 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.2 | OG6 | OG6 | 01525 | 0 | 0 | OG6-01525 | Construction | South Elevation | Construction.1.2.1.EFPC.2 | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> OG6 | 4 | 4 | 0% | 2023-01-11 08:00 | 2023-01-17 17:00 | 43 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.2 | OG6 | OG6 | 01530 | 0 | 0 | OG6-01530 | Construction | South Elevation | Construction.1.2.1.EFPC.2 | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG6 | 7 | 7 | 0% | 2023-01-18 08:00 | 2023-01-26 17:00 | 43 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.2 | OG6 | OG6 | 01535 | 0 | 0 | OG6-01535 | Construction | South Elevation | Construction.1.2.1.EFPC.2 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG6 | 5 | 5 | 0% | 2023-01-27 08:00 | 2023-02-02 17:00 | 43 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.2 | OG6 | OG6 | 01540 | 0 | 0 | OG6-01540 | Construction | South Elevation | Construction.1.2.1.EFPC.2 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG6 | 3 | 3 | 0% | 2023-02-03 08:00 | 2023-02-07 17:00 | 43 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.2 | OG6 | OG6 | 01545 | 0 | 0 | OG6-01545 | Construction | South Elevation | Construction.1.2.1.EFPC.2 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG6 | 3 | 3 | 0% | 2023-02-08 08:00 | 2023-02-10 17:00 | 45 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.2 | OG6 | OG6 | 01550 | 0 | 0 | OG6-01550 | Construction | South Elevation | Construction.1.2.1.EFPC.2 | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> OG6 | 3 | 3 | 0% | 2023-02-15 08:00 | 2023-02-17 17:00 | 43 | FAXA | CMU | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.2 | OG6 | OG6 | 01555 | 0 | 0 | OG6-01555 | Construction | South Elevation | Construction.1.2.1.EFPC.2 | Backfill at Curtain Wall for flood protection (South Side) --> OG6 | 4 | 4 | 0% | 2023-02-21 08:00 | 2023-02-24 17:00 | 43 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.3 | OG6 | OG6 | 01605 | 0 | 0 | OG6-01605 | Construction | North Elevation | Construction.1.2.1.EFPC.3 | Excavate at Curtain Wall for flood protection (North Side) --> OG6 | 7 | 7 | 0% | 2022-12-16 08:00 | 2022-12-27 17:00 | -4 | MLJ | EXCAVATION | EB EXC | 31-1000 | 31-1000-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.3 | OG6 | OG6 | 01610 | 0 | 0 | OG6-01610 | Construction | North Elevation | Construction.1.2.1.EFPC.3 | Form concrete footings at Curtain Wall for flood protection (North Side) --> OG6 | 9 | 9 | 0% | 2022-12-28 08:00 | 2023-01-10 17:00 | 36 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.3 | OG6 | OG6 | 01615 | 0 | 0 | OG6-01615 | Construction | North Elevation | Construction.1.2.1.EFPC.3 | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> OG6 | 4 | 4 | 0% | 2023-01-11 08:00 | 2023-01-17 17:00 | 36 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.3 | OG6 | OG6 | 01620 | 0 | 0 | OG6-01620 | Construction | North Elevation | Construction.1.2.1.EFPC.3 | Pour concrete footings at Curtain Wall for flood protection (North Side) --> OG6 | 3 | 3 | 0% | 2023-01-18 08:00 | 2023-01-20 17:00 | 36 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.3 | OG6 | OG6 | 01625 | 0 | 0 | OG6-01625 | Construction | North Elevation | Construction.1.2.1.EFPC.3 | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> OG6 | 4 | 4 | 0% | 2023-01-23 08:00 | 2023-01-26 17:00 | 36 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.3 | OG6 | OG6 | 01630 | 0 | 0 | OG6-01630 | Construction | North Elevation | Construction.1.2.1.EFPC.3 | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG6 | 7 | 7 | 0% | 2023-01-27 08:00 | 2023-02-06 17:00 | 36 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.3 | OG6 | OG6 | 01635 | 0 | 0 | OG6-01635 | Construction | North Elevation | Construction.1.2.1.EFPC.3 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG6 | 5 | 5 | 0% | 2023-02-07 08:00 | 2023-02-13 17:00 | 36 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.3 | OG6 | OG6 | 01640 | 0 | 0 | OG6-01640 | Construction | North Elevation | Construction.1.2.1.EFPC.3 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG6 | 3 | 3 | 0% | 2023-02-14 08:00 | 2023-02-16 17:00 | 36 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.3 | OG6 | OG6 | 01645 | 0 | 0 | OG6-01645 | Construction | North Elevation | Construction.1.2.1.EFPC.3 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG6 | 3 | 3 | 0% | 2023-02-17 08:00 | 2023-02-22 17:00 | 38 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.3 | OG6 | OG6 | 01650 | 0 | 0 | OG6-01650 | Construction | North Elevation | Construction.1.2.1.EFPC.3 | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> OG6 | 3 | 3 | 0% | 2023-02-24 08:00 | 2023-02-28 17:00 | 37 | FAXA | CMU | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.3 | OG6 | OG6 | 01655 | 0 | 0 | OG6-01655 | Construction | North Elevation | Construction.1.2.1.EFPC.3 | Backfill at Curtain Wall for flood protection (North Side) --> OG6 | 4 | 4 | 0% | 2023-03-01 08:00 | 2023-03-06 17:00 | 37 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.4 | OG6 | OG6 | 01705 | 0 | 0 | OG6-01705 | Construction | West Elevation | Construction.1.2.1.EFPC.4 | Excavate at Curtain Wall for flood protection (West Side) --> OG6 | 8 | 8 | 0% | 2022-12-28 08:00 | 2023-01-09 17:00 | -4 | MLJ | EXCAVATION | EB EXC | 31-1000 | 31-1000-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.4 | OG6 | OG6 | 01710 | 0 | 0 | OG6-01710 | Construction | West Elevation | Construction.1.2.1.EFPC.4 | Form concrete footings at Curtain Wall for flood protection (West Side) --> OG6 | 10 | 10 | 0% | 2023-01-10 08:00 | 2023-01-24 17:00 | -4 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.4 | OG6 | OG6 | 01715 | 0 | 0 | OG6-01715 | Construction | West Elevation | Construction.1.2.1.EFPC.4 | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> OG6 | 5 | 5 | 0% | 2023-01-25 08:00 | 2023-01-31 17:00 | -4 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.4 | OG6 | OG6 | 01720 | 0 | 0 | OG6-01720 | Construction | West Elevation | Construction.1.2.1.EFPC.4 | Pour concrete footings at Curtain Wall for flood protection (West Side) --> OG6 | 4 | 4 | 0% | 2023-02-01 08:00 | 2023-02-06 17:00 | -4 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.4 | OG6 | OG6 | 01725 | 0 | 0 | OG6-01725 | Construction | West Elevation | Construction.1.2.1.EFPC.4 | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> OG6 | 5 | 5 | 0% | 2023-02-07 08:00 | 2023-02-13 17:00 | -4 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.4 | OG6 | OG6 | 01730 | 0 | 0 | OG6-01730 | Construction | West Elevation | Construction.1.2.1.EFPC.4 | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG6 | 8 | 8 | 0% | 2023-02-14 08:00 | 2023-02-24 17:00 | -4 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.4 | OG6 | OG6 | 01735 | 0 | 0 | OG6-01735 | Construction | West Elevation | Construction.1.2.1.EFPC.4 | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG6 | 6 | 6 | 0% | 2023-02-27 08:00 | 2023-03-06 17:00 | -4 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.4 | OG6 | OG6 | 01740 | 0 | 0 | OG6-01740 | Construction | West Elevation | Construction.1.2.1.EFPC.4 | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG6 | 4 | 4 | 0% | 2023-03-07 08:00 | 2023-03-10 17:00 | -4 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.4 | OG6 | OG6 | 01745 | 0 | 0 | OG6-01745 | Construction | West Elevation | Construction.1.2.1.EFPC.4 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG6 | 4 | 4 | 0% | 2023-03-13 08:00 | 2023-03-16 17:00 | -3 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.4 | OG6 | OG6 | 01750 | 0 | 0 | OG6-01750 | Construction | West Elevation | Construction.1.2.1.EFPC.4 | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> OG6 | 4 | 4 | 0% | 2023-03-20 08:00 | 2023-03-23 17:00 | -4 | FAXA | CMU | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.4 | OG6 | OG6 | 01755 | 0 | 0 | OG6-01755 | Construction | West Elevation | Construction.1.2.1.EFPC.4 | Backfill at Curtain Wall for flood protection (West Side) --> OG6 | 5 | 5 | 0% | 2023-03-24 08:00 | 2023-03-30 17:00 | -4 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.4 | OG6 | OG6 | 01760 | 0 | 0 | OG6-01760 | Construction | West Elevation | Construction.1.2.1.EFPC.4 | Form for slab at Curtain Wall for flood protection (West Side) --> OG6 | 4 | 4 | 0% | 2023-03-31 08:00 | 2023-04-05 17:00 | -4 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.4 | OG6 | OG6 | 01765 | 0 | 0 | OG6-01765 | Construction | West Elevation | Construction.1.2.1.EFPC.4 | Rebar & inserts for slab at Curtain Wall for flood protection (West Side) --> OG6 | 6 | 6 | 0% | 2023-04-06 08:00 | 2023-04-13 17:00 | -4 | TONAGE | REBAR | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.4 | OG6 | OG6 | 01770 | 0 | 0 | OG6-01770 | Construction | West Elevation | Construction.1.2.1.EFPC.4 | Pour slab at Curtain Wall for flood protection (West Side) --> OG6 | 4 | 4 | 0% | 2023-04-14 08:00 | 2023-04-19 17:00 | -4 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.4 | OG6 | OG6 | 01775 | 0 | 0 | OG6-01775 | Construction | West Elevation | Construction.1.2.1.EFPC.4 | Strip Forms for slab at Curtain Wall for flood protection (West Side) --> OG6 | 2 | 2 | 0% | 2023-04-20 08:00 | 2023-04-21 17:00 | -1 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.4 | OG6 | OG6 | 01780 | 0 | 0 | OG6-01780 | Construction | West Elevation | Construction.1.2.1.EFPC.4 | Backfill surounding area at Curtain Wall for flood protection (West Side) --> OG6 | 4 | 4 | 0% | 2023-04-27 08:00 | 2023-05-02 17:00 | -4 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG6
Completed | CI NYCHA Update #22.Construction.1.2.1.EFPC.5 | OG6 | OG6 | 01805 | 0 | 0 | OG6-01805 | Construction | Concrete Shelf Construction | Construction.1.2.1.EFPC.5 | Excavate for concrete shelf around bldg perimeter --> OG6 | 10 | 0 | 100% | 2022-11-01 | 2022-11-07 |  | MLJ | Excavation | EB EXC | 31-1000 | 31-1000-OG6
Completed | CI NYCHA Update #22.Construction.1.2.1.EFPC.5 | OG6 | OG6 | 01810 | 0 | 0 | OG6-01810 | Construction | Concrete Shelf Construction | Construction.1.2.1.EFPC.5 | Place rebar for concrete shelf around bldg perimeter --> OG6 | 5 | 0 | 100% | 2022-11-08 | 2022-11-14 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Completed | CI NYCHA Update #22.Construction.1.2.1.EFPC.5 | OG6 | OG6 | 01815 | 0 | 0 | OG6-01815 | Construction | Concrete Shelf Construction | Construction.1.2.1.EFPC.5 | Pour concrete shelf around bldg perimeter --> OG6 | 5 | 0 | 100% | 2022-11-15 | 2022-11-15 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Completed | CI NYCHA Update #22.Construction.1.2.1.EFPC.5 | OG6 | OG6 | 01820 | 0 | 0 | OG6-01820 | Construction | Concrete Shelf Construction | Construction.1.2.1.EFPC.5 | Place infill concrete in area ways around bldg perimeter --> OG6 | 5 | 0 | 100% | 2022-11-15 | 2022-11-15 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.5 | OG6 | OG6 | 01825 | 0 | 0 | OG6-01825 | Construction | Concrete Shelf Construction | Construction.1.2.1.EFPC.5 | Place waterproofing on concrete shelf around bldg perimeter --> OG6 | 10 | 10 | 0% | 2022-12-02 08:00 | 2022-12-15 17:00 | 35 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.5 | OG6 | OG6 | 01830 | 0 | 0 | OG6-01830 | Construction | Concrete Shelf Construction | Construction.1.2.1.EFPC.5 | Place CMU around bldg perimeter --OG6 | 15 | 15 | 0% | 2022-12-16 08:00 | 2023-01-09 17:00 | 35 | FAXA | CMU | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.5 | OG6 | OG6 | 01835 | 0 | 0 | OG6-01835 | Construction | Concrete Shelf Construction | Construction.1.2.1.EFPC.5 | Place waterproofing on CMU around bldg perimeter --> OG6 | 10 | 10 | 0% | 2023-01-10 08:00 | 2023-01-24 17:00 | 35 | UNSURE | WATERPROOFING | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.5 | OG6 | OG6 | 01840 | 0 | 0 | OG6-01840 | Construction | Concrete Shelf Construction | Construction.1.2.1.EFPC.5 | Place window frames around bldg perimeter --> OG6 | 10 | 10 | 0% | 2023-01-25 08:00 | 2023-02-07 17:00 | 35 | MLJ | CONCRETE SHELF | PLACE WINDOWS | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.5 | OG6 | OG6 | 01845 | 0 | 0 | OG6-01845 | Construction | Concrete Shelf Construction | Construction.1.2.1.EFPC.5 | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> OG6 | 20 | 20 | 0% | 2023-02-08 08:00 | 2023-03-08 17:00 | 35 | FAXA | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.5 | OG6 | OG6 | 01850 | 0 | 0 | OG6-01850 | Construction | Concrete Shelf Construction | Construction.1.2.1.EFPC.5 | Backfill around bdg perimeter --> OG6 | 5 | 5 | 0% | 2023-03-09 08:00 | 2023-03-15 17:00 | 35 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.5 | OG6 | OG6 | 01855 | 0 | 0 | OG6-01855 | Construction | Concrete Shelf Construction | Construction.1.2.1.EFPC.5 | Place frame / stucco / and signs at entrances --> OG6 | 4 | 4 | 0% | 2023-03-16 08:00 | 2023-03-21 17:00 | 35 | CCC | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.5 | OG6 | OG6 | 01860 | 0 | 0 | OG6-01860 | Construction | Concrete Shelf Construction | Construction.1.2.1.EFPC.5 | Place window floodgates at windows --> OG6 | 5 | 5 | 0% | 2023-03-22 08:00 | 2023-03-28 17:00 | 35 | MLJ | FLOOD PROTECTION | FLOOD WINDOWS | 10-1400 | 10-1400-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.5 | OG6 | OG6 | 01865 | 0 | 0 | OG6-01865 | Construction | Concrete Shelf Construction | Construction.1.2.1.EFPC.5 | Install signs --> OG6 | 3 | 3 | 0% | 2023-03-29 08:00 | 2023-03-31 17:00 | 35 | MLJ | SIGNS | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Construction.1.2.1.5 | OG6 | OG6 | 01350 | 0 | 0 | OG6-01350 | Construction | Boiler Room Construction | Construction.1.2.1.5 | Drill dowels and place rebar for boiler room concrete walls --> OG6 | 5 | 0 | 100% | 2022-08-15 | 2022-08-24 |  | MLJ | 0 | DRILL & DOWEL | 03-1400 | 03-1400-OG6
Completed | CI NYCHA Update #22.Construction.1.2.1.5 | OG6 | OG6 | 01355 | 0 | 0 | OG6-01355 | Construction | Boiler Room Construction | Construction.1.2.1.5 | Form boiler room concrete walls --> OG6 | 5 | 0 | 100% | 2022-09-05 | 2022-09-05 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG6
In Progress | CI NYCHA Update #22.Construction.1.2.1.5 | OG6 | OG6 | 01360 | 0 | 0 | OG6-01360 | Construction | Boiler Room Construction | Construction.1.2.1.5 | Pour Concrete boiler room walls --> OG6 | 2 | 1 | 50% | 2022-09-06 | 2022-11-25 17:00 | 91 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.5 | OG6 | OG6 | 01365 | 0 | 0 | OG6-01365 | Construction | Boiler Room Construction | Construction.1.2.1.5 | Strip Forms boiler room concrete walls --> OG6 | 3 | 3 | 0% | 2022-11-28 08:00 | 2022-11-30 17:00 | 93 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG6
Completed | CI NYCHA Update #22.Construction.1.2.1.5 | OG6 | OG6 | 01370 | 0 | 0 | OG6-01370 | Construction | Boiler Room Construction | Construction.1.2.1.5 | Place crystaline waterproofing on perimeter walls - cellar --> OG6 | 10 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0 | WATERPROOFING | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Construction.1.2.1.6 | OG6 | OG6 | 01385 | 0 | 0 | OG6-01385 | Construction | Elevator Refurbishment | Construction.1.2.1.6 | Refurbish Elevator 1 --> OG6 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Construction.1.2.1.6 | OG6 | OG6 | 01390 | 0 | 0 | OG6-01390 | Construction | Elevator Refurbishment | Construction.1.2.1.6 | Refurbish Elevator 2 --> OG6 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Construction.1.2.1.6 | OG6 | OG6 | 01380 | 0 | 0 | OG6-01380 | Construction | Elevator Refurbishment | Construction.1.2.1.6 | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.7 | OG6 | OG6 | 09005 | 0 | 0 | OG6-09005 | Construction | Civil/Architectural Inspections | Construction.1.2.1.7 | Perform Inspections & Issue Punch List | 5 | 5 | 0% | 2024-01-24 08:00 | 2024-01-30 17:00 | -193 | MLJ | PUNCH LIST | INSPECTION | 99-8200 | 99-8200-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.7 | OG6 | OG6 | 09010 | 0 | 0 | OG6-09010 | Construction | Civil/Architectural Inspections | Construction.1.2.1.7 | Perform Punch List | 10 | 10 | 0% | 2024-01-31 08:00 | 2024-02-13 17:00 | -178 | MLJ | PUNCH LIST | 0 | 99-8200 | 99-8200-OG6
Completed | CI NYCHA Update #22.Construction.1.2.1.2 | OG6 | OG6 | 01220 | 0 | 0 | OG6-01220 | Construction | Interior Demolition | Construction.1.2.1.2 | Selective Demo (Pumps etc..) - Cellar --> OG6 | 5 | 0 | 100% | 2022-10-17 | 2022-10-20 |  | MLJ | DEMO | DEMO PUMPS | 02-6010 | 02-6010-OG6
Not Started | CI NYCHA Update #22.Construction.1.3.1.1 | OG1 | OG1 | 01005 | 0 | 0 | OG1-01005 | Construction | Asbestos Abatement | Construction.1.3.1.1 | Asbestos Abatement - gaskets - cellar - OG1 | 3 | 3 | 0% | 2023-12-27 08:00 | 2023-12-29 17:00 | -177 | ATCO | ABESTOS | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.1 | OG1 | OG1 | 01010 | 0 | 0 | OG1-01010 | Construction | Asbestos Abatement | Construction.1.3.1.1 | Asbestos Abatement - wire insulation - cellar --> OG1 | 3 | 0 | 100% | 2021-06-28 08:00 | 2021-07-09 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.1 | OG1 | OG1 | 01015 | 0 | 0 | OG1-01015 | Construction | Asbestos Abatement | Construction.1.3.1.1 | Asbestos Abatement - flooring materials at slab penetrations - cellar --> OG1 | 3 | 0 | 100% | 2022-01-03 08:00 | 2022-01-07 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.1 | OG1 | OG1 | 01020 | 0 | 0 | OG1-01020 | Construction | Asbestos Abatement | Construction.1.3.1.1 | Asbestos Abatement - pipe insulation - cellar --> OG1 | 3 | 0 | 100% | 2021-06-28 08:00 | 2021-07-09 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.1 | OG1 | OG1 | 01025 | 0 | 0 | OG1-01025 | Construction | Asbestos Abatement | Construction.1.3.1.1 | Asbestos Abatement - Window Sills - 1st Floor --> OG1 | 5 | 0 | 100% | 2022-06-27 08:00 | 2022-06-27 17:00 |  | ATCO | ABESTOS | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.1 | OG1 | OG1 | 01030 | 0 | 0 | OG1-01030 | Construction | Asbestos Abatement | Construction.1.3.1.1 | Asbestos Abatement - caulk @ windows and areaway vents --> OG1 | 5 | 0 | 100% | 2022-06-27 08:00 | 2022-06-27 17:00 |  | ATCO | ABESTOS | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.2 | OG1 | OG1 | 01105 | 0 | 0 | OG1-01105 | Construction | Interior Demolition | Construction.1.3.1.2 | Selective Demo (Plaster walls, Doors, windows) - Cellar --> OG1 | 10 | 0 | 100% | 2021-04-25 | 2022-08-25 |  | MLJ | DEMO | DEMO CELLAR WALLS | 02-6005 | 02-6005-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.2 | OG1 | OG1 | 01110 | 0 | 0 | OG1-01110 | Construction | Interior Demolition | Construction.1.3.1.2 | Selective Demo (Doors, windows) - 1st Floor --> OG1 | 5 | 0 | 100% | 2022-06-09 | 2022-06-15 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.2 | OG1 | OG1 | 01115 | 0 | 0 | OG1-01115 | Construction | Interior Demolition | Construction.1.3.1.2 | Selective Demo (Areaway drain, slab, wall) --> OG1 | 10 | 0 | 100% | 2022-08-25 | 2022-08-31 |  | MLJ | DEMO | DEMO AREAWAY | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.2 | OG1 | OG1 | 01205 | 0 | 0 | OG1-01205 | Construction | Interior Demolition | Construction.1.3.1.2 | Selective Demo (Existing Ramp, railing) - 1st Floor --> OG1 | 5 | 0 | 100% | 2022-08-31 | 2022-09-05 |  | MLJ | DEMO | DEMO RAMP | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.2 | OG1 | OG1 | 01210 | 0 | 0 | OG1-01210 | Construction | Interior Demolition | Construction.1.3.1.2 | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> OG1 | 5 | 0 | 100% | 2022-06-08 | 2022-06-15 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.2 | OG1 | OG1 | 01215 | 0 | 0 | OG1-01215 | Construction | Interior Demolition | Construction.1.3.1.2 | Selective Demo - 2nd Floor Apartment for Electrical Room --> OG1 | 5 | 0 | 100% | 2021-10-06 | 2022-01-14 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.4 | OG1 | OG1 | 01310 | 0 | 0 | OG1-01310 | Construction | Interior Renovations | Construction.1.3.1.4 | Make openings in floor for conduit penetrations - 2nd floor apartments --> OG1 | 5 | 0 | 100% | 2022-06-08 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.4 | OG1 | OG1 | 01315 | 0 | 0 | OG1-01315 | Construction | Interior Renovations | Construction.1.3.1.4 | Install beams below floor - 2nd floor apartments --> OG1 | 5 | 0 | 100% | 2022-04-15 | 2022-04-20 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.4 | OG1 | OG1 | 01320 | 0 | 0 | OG1-01320 | Construction | Interior Renovations | Construction.1.3.1.4 | Install FRP around floor openings - 2nd floor apartments --> OG1 | 5 | 0 | 100% | 2022-04-21 | 2022-06-07 |  | 0 | 0 | 0 | 0 | 0-OG1
In Progress | CI NYCHA Update #22.Construction.1.3.1.4 | OG1 | OG1 | 01325 | 0 | 0 | OG1-01325 | Construction | Interior Renovations | Construction.1.3.1.4 | Frame walls / install door for electrical room - 2nd floor --> OG1 | 3 | 1 | 66% | 2022-03-25 | 2022-11-25 17:00 | 89 | CCC | 0 | 0 | 0 | 0-OG1
In Progress | CI NYCHA Update #22.Construction.1.3.1.4 | OG1 | OG1 | 01330 | 0 | 0 | OG1-01330 | Construction | Interior Renovations | Construction.1.3.1.4 | Install drywall / tape / spackle - electrical room - 2nd floor --> OG1 | 5 | 1 | 80% | 2022-05-02 | 2022-12-12 15:24 | 79 | CCC | 0 | 0 | 0 | 0-OG1
In Progress | CI NYCHA Update #22.Construction.1.3.1.4 | OG1 | OG1 | 01335 | 0 | 0 | OG1-01335 | Construction | Interior Renovations | Construction.1.3.1.4 | Paint walls and seal floor electrical room - 2nd Floor --> OG1 | 10 | 1 | 90% | 2022-05-12 | 2023-01-31 17:00 | 50 | CCC | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.4 | OG1 | OG1 | 01340 | 0 | 0 | OG1-01340 | Construction | Interior Renovations | Construction.1.3.1.4 | Install VCT @ electrical room - 2nd Floor --> OG1 | 2 | 2 | 0% | 2023-02-01 08:00 | 2023-02-02 17:00 | 50 | UNSURE | FLOORING | VCT | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.1 | OG1 | OG1 | 01405 | 0 | 0 | OG1-01405 | Construction | East Elevation | Construction.1.3.1.EFPC.1 | Excavate at Curtain Wall for flood protection (East Side) --> OG1 | 8 | 0 | 100% | 2022-04-26 | 2022-05-02 |  | 0 | EXCAVATION | 0 | 31-1000 | 31-1000-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.1 | OG1 | OG1 | 01410 | 0 | 0 | OG1-01410 | Construction | East Elevation | Construction.1.3.1.EFPC.1 | Form concrete footings at Curtain Wall for flood protection (East Side) --> OG1 | 10 | 0 | 100% | 2022-05-20 | 2022-05-25 |  | 0 | FORMWORK | FORMWORK EB | 03-1100 | 03-1100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.1 | OG1 | OG1 | 01415 | 0 | 0 | OG1-01415 | Construction | East Elevation | Construction.1.3.1.EFPC.1 | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> OG1 | 5 | 0 | 100% | 2022-05-06 | 2022-05-18 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.1 | OG1 | OG1 | 01420 | 0 | 0 | OG1-01420 | Construction | East Elevation | Construction.1.3.1.EFPC.1 | Pour concrete footings at Curtain Wall for flood protection (East Side) --> OG1 | 4 | 0 | 100% | 2022-05-24 | 2022-05-24 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.1 | OG1 | OG1 | 01425 | 0 | 0 | OG1-01425 | Construction | East Elevation | Construction.1.3.1.EFPC.1 | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> OG1 | 5 | 0 | 100% | 2022-05-25 | 2022-05-31 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.1 | OG1 | OG1 | 01430 | 0 | 0 | OG1-01430 | Construction | East Elevation | Construction.1.3.1.EFPC.1 | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG1 | 8 | 0 | 100% | 2022-10-07 | 2022-10-11 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.1 | OG1 | OG1 | 01435 | 0 | 0 | OG1-01435 | Construction | East Elevation | Construction.1.3.1.EFPC.1 | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG1 | 6 | 0 | 100% | 2022-10-14 | 2022-10-17 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.1 | OG1 | OG1 | 01440 | 0 | 0 | OG1-01440 | Construction | East Elevation | Construction.1.3.1.EFPC.1 | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG1 | 4 | 0 | 100% | 2022-10-18 | 2022-10-18 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.1 | OG1 | OG1 | 01445 | 0 | 0 | OG1-01445 | Construction | East Elevation | Construction.1.3.1.EFPC.1 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG1 | 4 | 0 | 100% | 2022-10-19 | 2022-10-19 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.1 | OG1 | OG1 | 01450 | 0 | 0 | OG1-01450 | Construction | East Elevation | Construction.1.3.1.EFPC.1 | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> OG1 | 4 | 0 | 100% | 2022-10-20 | 2022-10-25 |  | FAXA | CMU | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.1 | OG1 | OG1 | 01455 | 0 | 0 | OG1-01455 | Construction | East Elevation | Construction.1.3.1.EFPC.1 | Backfill at Curtain Wall for flood protection (East Side) --> OG1 | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 92 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.2 | OG1 | OG1 | 01505 | 0 | 0 | OG1-01505 | Construction | South Elevation | Construction.1.3.1.EFPC.2 | Excavate at Curtain Wall for flood protection (South Side) --> OG1 | 7 | 0 | 100% | 2022-02-16 | 2022-03-01 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.2 | OG1 | OG1 | 01510 | 0 | 0 | OG1-01510 | Construction | South Elevation | Construction.1.3.1.EFPC.2 | Form concrete footings at Curtain Wall for flood protection (South Side) --> OG1 | 9 | 0 | 100% | 2022-02-21 | 2022-03-03 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.2 | OG1 | OG1 | 01515 | 0 | 0 | OG1-01515 | Construction | South Elevation | Construction.1.3.1.EFPC.2 | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> OG1 | 4 | 0 | 100% | 2022-02-22 | 2022-03-06 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.2 | OG1 | OG1 | 01520 | 0 | 0 | OG1-01520 | Construction | South Elevation | Construction.1.3.1.EFPC.2 | Pour concrete footings at Curtain Wall for flood protection (South Side) --> OG1 | 3 | 0 | 100% | 2022-02-24 | 2022-03-10 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.2 | OG1 | OG1 | 01525 | 0 | 0 | OG1-01525 | Construction | South Elevation | Construction.1.3.1.EFPC.2 | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> OG1 | 4 | 0 | 100% | 2022-05-25 | 2022-05-31 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.2 | OG1 | OG1 | 01530 | 0 | 0 | OG1-01530 | Construction | South Elevation | Construction.1.3.1.EFPC.2 | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG1 | 7 | 0 | 100% | 2022-08-25 | 2022-08-31 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.2 | OG1 | OG1 | 01535 | 0 | 0 | OG1-01535 | Construction | South Elevation | Construction.1.3.1.EFPC.2 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG1 | 5 | 0 | 100% | 2022-09-01 | 2022-09-06 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.2 | OG1 | OG1 | 01540 | 0 | 0 | OG1-01540 | Construction | South Elevation | Construction.1.3.1.EFPC.2 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG1 | 3 | 0 | 100% | 2022-09-07 | 2022-09-07 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.2 | OG1 | OG1 | 01545 | 0 | 0 | OG1-01545 | Construction | South Elevation | Construction.1.3.1.EFPC.2 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG1 | 3 | 0 | 100% | 2022-09-08 | 2022-09-09 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.2 | OG1 | OG1 | 01550 | 0 | 0 | OG1-01550 | Construction | South Elevation | Construction.1.3.1.EFPC.2 | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> OG1 | 3 | 0 | 100% | 2022-09-15 | 2022-10-26 |  | FAXA | CMU | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.2 | OG1 | OG1 | 01555 | 0 | 0 | OG1-01555 | Construction | South Elevation | Construction.1.3.1.EFPC.2 | Backfill at Curtain Wall for flood protection (South Side) --> OG1 | 4 | 0 | 100% | 2022-10-27 | 2022-11-02 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.3 | OG1 | OG1 | 01605 | 0 | 0 | OG1-01605 | Construction | North Elevation | Construction.1.3.1.EFPC.3 | Excavate at Curtain Wall for flood protection (North Side) --> OG1 | 7 | 0 | 100% | 2022-05-25 | 2022-06-01 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.3 | OG1 | OG1 | 01610 | 0 | 0 | OG1-01610 | Construction | North Elevation | Construction.1.3.1.EFPC.3 | Form concrete footings at Curtain Wall for flood protection (North Side) --> OG1 | 9 | 0 | 100% | 2022-05-20 | 2022-05-24 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.3 | OG1 | OG1 | 01615 | 0 | 0 | OG1-01615 | Construction | North Elevation | Construction.1.3.1.EFPC.3 | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> OG1 | 4 | 0 | 100% | 2022-05-06 | 2022-05-18 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.3 | OG1 | OG1 | 01620 | 0 | 0 | OG1-01620 | Construction | North Elevation | Construction.1.3.1.EFPC.3 | Pour concrete footings at Curtain Wall for flood protection (North Side) --> OG1 | 3 | 0 | 100% | 2022-05-24 | 2022-05-24 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.3 | OG1 | OG1 | 01625 | 0 | 0 | OG1-01625 | Construction | North Elevation | Construction.1.3.1.EFPC.3 | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> OG1 | 4 | 0 | 100% | 2022-06-01 | 2022-06-03 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.3 | OG1 | OG1 | 01630 | 0 | 0 | OG1-01630 | Construction | North Elevation | Construction.1.3.1.EFPC.3 | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG1 | 7 | 0 | 100% | 2022-08-25 08:00 | 2022-08-31 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.3 | OG1 | OG1 | 01635 | 0 | 0 | OG1-01635 | Construction | North Elevation | Construction.1.3.1.EFPC.3 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG1 | 5 | 0 | 100% | 2022-09-01 | 2022-09-06 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.3 | OG1 | OG1 | 01640 | 0 | 0 | OG1-01640 | Construction | North Elevation | Construction.1.3.1.EFPC.3 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG1 | 3 | 0 | 100% | 2022-09-07 | 2022-09-07 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.3 | OG1 | OG1 | 01645 | 0 | 0 | OG1-01645 | Construction | North Elevation | Construction.1.3.1.EFPC.3 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG1 | 3 | 0 | 100% | 2022-09-08 | 2022-09-09 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.3 | OG1 | OG1 | 01650 | 0 | 0 | OG1-01650 | Construction | North Elevation | Construction.1.3.1.EFPC.3 | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> OG1 | 3 | 0 | 100% | 2022-09-15 | 2022-10-26 |  | FAXA | CMU | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.3 | OG1 | OG1 | 01655 | 0 | 0 | OG1-01655 | Construction | North Elevation | Construction.1.3.1.EFPC.3 | Backfill at Curtain Wall for flood protection (North Side) --> OG1 | 4 | 0 | 100% | 2022-10-27 | 2022-11-02 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.4 | OG1 | OG1 | 01705 | 0 | 0 | OG1-01705 | Construction | West Elevation | Construction.1.3.1.EFPC.4 | Excavate at Curtain Wall for flood protection (West Side) --> OG1 | 8 | 0 | 100% | 2022-11-01 | 2022-11-07 |  | MLJ | Excavation | EB EXC | 31-1000 | 31-1000-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.4 | OG1 | OG1 | 01710 | 0 | 0 | OG1-01710 | Construction | West Elevation | Construction.1.3.1.EFPC.4 | Form concrete footings at Curtain Wall for flood protection (West Side) --> OG1 | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | 42 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.4 | OG1 | OG1 | 01715 | 0 | 0 | OG1-01715 | Construction | West Elevation | Construction.1.3.1.EFPC.4 | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> OG1 | 5 | 5 | 0% | 2022-12-09 08:00 | 2022-12-15 17:00 | 42 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.4 | OG1 | OG1 | 01720 | 0 | 0 | OG1-01720 | Construction | West Elevation | Construction.1.3.1.EFPC.4 | Pour concrete footings at Curtain Wall for flood protection (West Side) --> OG1 | 4 | 4 | 0% | 2022-12-16 08:00 | 2022-12-21 17:00 | 42 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.4 | OG1 | OG1 | 01725 | 0 | 0 | OG1-01725 | Construction | West Elevation | Construction.1.3.1.EFPC.4 | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> OG1 | 5 | 5 | 0% | 2022-12-22 08:00 | 2022-12-29 17:00 | 42 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.4 | OG1 | OG1 | 01730 | 0 | 0 | OG1-01730 | Construction | West Elevation | Construction.1.3.1.EFPC.4 | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG1 | 8 | 8 | 0% | 2022-12-30 08:00 | 2023-01-11 17:00 | 42 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.4 | OG1 | OG1 | 01735 | 0 | 0 | OG1-01735 | Construction | West Elevation | Construction.1.3.1.EFPC.4 | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG1 | 6 | 6 | 0% | 2023-01-12 08:00 | 2023-01-20 17:00 | 42 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.4 | OG1 | OG1 | 01740 | 0 | 0 | OG1-01740 | Construction | West Elevation | Construction.1.3.1.EFPC.4 | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG1 | 4 | 4 | 0% | 2023-01-23 08:00 | 2023-01-26 17:00 | 42 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.4 | OG1 | OG1 | 01745 | 0 | 0 | OG1-01745 | Construction | West Elevation | Construction.1.3.1.EFPC.4 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG1 | 4 | 4 | 0% | 2023-01-27 08:00 | 2023-02-01 17:00 | 43 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.4 | OG1 | OG1 | 01750 | 0 | 0 | OG1-01750 | Construction | West Elevation | Construction.1.3.1.EFPC.4 | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> OG1 | 4 | 4 | 0% | 2023-02-03 08:00 | 2023-02-08 17:00 | 42 | FAXA | CMU | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.4 | OG1 | OG1 | 01755 | 0 | 0 | OG1-01755 | Construction | West Elevation | Construction.1.3.1.EFPC.4 | Backfill at Curtain Wall for flood protection (West Side) --> OG1 | 5 | 5 | 0% | 2023-02-09 08:00 | 2023-02-15 17:00 | 42 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.4 | OG1 | OG1 | 01760 | 0 | 0 | OG1-01760 | Construction | West Elevation | Construction.1.3.1.EFPC.4 | Form for slab at Curtain Wall for flood protection (West Side) --> OG1 | 4 | 4 | 0% | 2023-02-16 08:00 | 2023-02-22 17:00 | 42 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.4 | OG1 | OG1 | 01765 | 0 | 0 | OG1-01765 | Construction | West Elevation | Construction.1.3.1.EFPC.4 | Rebar & inserts for slab at Curtain Wall for flood protection (West Side) --> OG1 | 6 | 6 | 0% | 2023-02-23 08:00 | 2023-03-02 17:00 | 42 | TONAGE | REBAR | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.4 | OG1 | OG1 | 01770 | 0 | 0 | OG1-01770 | Construction | West Elevation | Construction.1.3.1.EFPC.4 | Pour slab at Curtain Wall for flood protection (West Side) --> OG1 | 4 | 4 | 0% | 2023-03-03 08:00 | 2023-03-08 17:00 | 42 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.4 | OG1 | OG1 | 01775 | 0 | 0 | OG1-01775 | Construction | West Elevation | Construction.1.3.1.EFPC.4 | Strip Forms for slab at Curtain Wall for flood protection (West Side) --> OG1 | 2 | 2 | 0% | 2023-03-09 08:00 | 2023-03-10 17:00 | 45 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.4 | OG1 | OG1 | 01780 | 0 | 0 | OG1-01780 | Construction | West Elevation | Construction.1.3.1.EFPC.4 | Backfill surounding area at Curtain Wall for flood protection (West Side) --> OG1 | 4 | 4 | 0% | 2023-03-16 08:00 | 2023-03-21 17:00 | 42 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.5 | OG1 | OG1 | 01805 | 0 | 0 | OG1-01805 | Construction | Concrete Shelf Construction | Construction.1.3.1.EFPC.5 | Excavate for concrete shelf around bldg perimeter --> OG1 | 10 | 0 | 100% | 2022-05-04 | 2022-05-16 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.5 | OG1 | OG1 | 01810 | 0 | 0 | OG1-01810 | Construction | Concrete Shelf Construction | Construction.1.3.1.EFPC.5 | Place rebar for concrete shelf around bldg perimeter --> OG1 | 5 | 0 | 100% | 2022-05-16 | 2022-05-24 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.5 | OG1 | OG1 | 01815 | 0 | 0 | OG1-01815 | Construction | Concrete Shelf Construction | Construction.1.3.1.EFPC.5 | Pour concrete shelf around bldg perimeter --> OG1 | 5 | 0 | 100% | 2022-05-26 | 2022-05-27 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.5 | OG1 | OG1 | 01820 | 0 | 0 | OG1-01820 | Construction | Concrete Shelf Construction | Construction.1.3.1.EFPC.5 | Place infill concrete in area ways around bldg perimeter --> OG1 | 5 | 0 | 100% | 2022-05-27 | 2022-05-27 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.5 | OG1 | OG1 | 01825 | 0 | 0 | OG1-01825 | Construction | Concrete Shelf Construction | Construction.1.3.1.EFPC.5 | Place waterproofing on concrete shelf around bldg perimeter --> OG1 | 10 | 0 | 100% | 2022-06-01 | 2022-06-06 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.5 | OG1 | OG1 | 01830 | 0 | 0 | OG1-01830 | Construction | Concrete Shelf Construction | Construction.1.3.1.EFPC.5 | Place CMU around bldg perimeter --OG1 | 15 | 0 | 100% | 2022-06-14 | 2022-08-05 17:00 |  | FAXA | CMU | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.5 | OG1 | OG1 | 01835 | 0 | 0 | OG1-01835 | Construction | Concrete Shelf Construction | Construction.1.3.1.EFPC.5 | Place waterproofing on CMU around bldg perimeter --> OG1 (Waterproofing Delay) | 10 | 0 | 100% | 2022-08-25 | 2022-09-05 |  | 0 | WATERPROOFING | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.5 | OG1 | OG1 | 01840 | 0 | 0 | OG1-01840 | Construction | Concrete Shelf Construction | Construction.1.3.1.EFPC.5 | Place window frames around bldg perimeter --> OG1 | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | 105 | MLJ | CONCRETE SHELF | PLACE WINDOWS | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.5 | OG1 | OG1 | 01845 | 0 | 0 | OG1-01845 | Construction | Concrete Shelf Construction | Construction.1.3.1.EFPC.5 | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> OG1 | 20 | 0 | 100% | 2022-09-20 | 2022-10-20 |  | FAXA | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.5 | OG1 | OG1 | 01850 | 0 | 0 | OG1-01850 | Construction | Concrete Shelf Construction | Construction.1.3.1.EFPC.5 | Backfill around bdg perimeter --> OG1 | 5 | 0 | 100% | 2022-01-21 | 2022-10-24 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.5 | OG1 | OG1 | 01855 | 0 | 0 | OG1-01855 | Construction | Concrete Shelf Construction | Construction.1.3.1.EFPC.5 | Place frame / stucco / and signs at entrances --> OG1 | 4 | 4 | 0% | 2022-12-09 08:00 | 2022-12-14 17:00 | 105 | CCC | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.5 | OG1 | OG1 | 01860 | 0 | 0 | OG1-01860 | Construction | Concrete Shelf Construction | Construction.1.3.1.EFPC.5 | Place window floodgates at windows --> OG1 | 5 | 5 | 0% | 2022-12-15 08:00 | 2022-12-21 17:00 | 105 | MLJ | FLOOD PROTECTION | FLOOD WINDOWS | 10-1400 | 10-1400-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.5 | OG1 | OG1 | 01865 | 0 | 0 | OG1-01865 | Construction | Concrete Shelf Construction | Construction.1.3.1.EFPC.5 | Install signs --> OG1 | 3 | 3 | 0% | 2022-12-22 08:00 | 2022-12-27 17:00 | 105 | MLJ | SIGNS | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.5 | OG1 | OG1 | 01350 | 0 | 0 | OG1-01350 | Construction | Boiler Room Construction | Construction.1.3.1.5 | Drill dowels and place rebar for boiler room concrete walls --> OG1 | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 22 | MLJ | 0 | DRILL & DOWEL | 03-1400 | 03-1400-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.5 | OG1 | OG1 | 01355 | 0 | 0 | OG1-01355 | Construction | Boiler Room Construction | Construction.1.3.1.5 | Form boiler room concrete walls --> OG1 | 5 | 5 | 0% | 2022-12-02 08:00 | 2022-12-08 17:00 | 22 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.5 | OG1 | OG1 | 01360 | 0 | 0 | OG1-01360 | Construction | Boiler Room Construction | Construction.1.3.1.5 | Pour Concrete boiler room walls --> OG1 | 2 | 2 | 0% | 2022-12-09 08:00 | 2022-12-12 17:00 | 22 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.5 | OG1 | OG1 | 01365 | 0 | 0 | OG1-01365 | Construction | Boiler Room Construction | Construction.1.3.1.5 | Strip Forms boiler room concrete walls --> OG1 | 3 | 3 | 0% | 2022-12-13 08:00 | 2022-12-15 17:00 | 24 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.5 | OG1 | OG1 | 01370 | 0 | 0 | OG1-01370 | Construction | Boiler Room Construction | Construction.1.3.1.5 | Place crystaline waterproofing on perimeter walls - cellar --> OG1 - N/A | 10 | 0 | 100% | 2022-07-25 08:00 | 2022-07-25 17:00 |  | 0 | WATERPROOFING | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.6 | OG1 | OG1 | 01385 | 0 | 0 | OG1-01385 | Construction | Elevator Refurbishment | Construction.1.3.1.6 | Refurbish Elevator 1 --> OG1 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.6 | OG1 | OG1 | 01390 | 0 | 0 | OG1-01390 | Construction | Elevator Refurbishment | Construction.1.3.1.6 | Refurbish Elevator 2 --> OG1 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.6 | OG1 | OG1 | 01380 | 0 | 0 | OG1-01380 | Construction | Elevator Refurbishment | Construction.1.3.1.6 | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.7 | OG1 | OG1 | 09005 | 0 | 0 | OG1-09005 | Construction | Civil/Architectural Inspections | Construction.1.3.1.7 | Perform Inspections & Issue Punch List | 5 | 5 | 0% | 2024-01-02 08:00 | 2024-01-08 17:00 | -177 | MLJ | PUNCH LIST | INSPECTION | 99-8200 | 99-8200-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.7 | OG1 | OG1 | 09010 | 0 | 0 | OG1-09010 | Construction | Civil/Architectural Inspections | Construction.1.3.1.7 | Perform Punch List | 10 | 10 | 0% | 2024-01-09 08:00 | 2024-01-22 17:00 | -162 | MLJ | PUNCH LIST | 0 | 99-8200 | 99-8200-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.2 | OG1 | OG1 | 01220 | 0 | 0 | OG1-01220 | Construction | Interior Demolition | Construction.1.3.1.2 | Selective Demo (Pumps etc..) - Cellar --> OG1 | 5 | 0 | 100% | 2022-07-21 08:00 | 2022-07-26 17:00 |  | MLJ | DEMO | DEMO PUMPS | 02-6010 | 02-6010-OG1
Completed | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 03005 | 0 | 0 | OG6-03005 | Construction | Cellar | Construction.1.2.5.1 | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 100% | 2022-03-28 | 2022-04-15 |  | 0 | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 03010 | 0 | 0 | OG6-03010 | Construction | Cellar | Construction.1.2.5.1 | Install Condensate Pump - Cellar | 10 | 10 | 0% | 2022-11-30 08:00 | 2022-12-13 17:00 | 5 | WELKIN | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 03020 | 0 | 0 | OG6-03020 | Construction | Cellar | Construction.1.2.5.1 | Install Pump Controls - Cellar | 20 | 20 | 0% | 2022-11-30 08:00 | 2022-12-28 17:00 | -5 | MEP | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 03025 | 0 | 0 | OG6-03025 | Construction | Cellar | Construction.1.2.5.1 | Perform Hydrostatic Testing - Cellar | 5 | 5 | 0% | 2022-12-29 08:00 | 2023-01-05 17:00 | -5 | WELKIN | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 03030 | 0 | 0 | OG6-03030 | Construction | Cellar | Construction.1.2.5.1 | Install Plumbing Equipment - Cellar | 15 | 0 | 100% | 2022-09-26 | 2022-10-20 |  | 0 | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 03035 | 0 | 0 | OG6-03035 | Construction | Cellar | Construction.1.2.5.1 | Pump Equipment Start-up & Balance - Cellar | 10 | 10 | 0% | 2023-01-06 08:00 | 2023-01-20 17:00 | -5 | UNSURE | STARTUP | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 03040 | 0 | 0 | OG6-03040 | Construction | Cellar | Construction.1.2.5.1 | Plumbing/Mechanical Insulation - Cellar | 20 | 20 | 0% | 2023-01-23 08:00 | 2023-02-17 17:00 | -5 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 03015 | 0 | 0 | OG6-03015 | Construction | Cellar | Construction.1.2.5.1 | Install Steam Traps - Cellar | 2 | 0 | 100% | 2021-04-26 | 2021-04-28 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
In Progress | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 03007 | 0 | 0 | OG6-03007 | Construction | Cellar | Construction.1.2.5.1 | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 3 | 85% | 2022-04-04 | 2022-11-29 17:00 | -25 | WELKIN | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 03032 | 0 | 0 | OG6-03032 | Construction | Cellar | Construction.1.2.5.1 | Install Mechanical Equipment - Cellar | 20 | 0 | 100% | 2021-10-25 | 2021-12-01 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Construction.1.2.5.2 | OG6 | OG6 | 03105 | 0 | 0 | OG6-03105 | Construction | 1st Floor | Construction.1.2.5.2 | Rough-In Plumbing Piping & Appurtenances - 1st Floor - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG6
In Progress | CI NYCHA Update #22.Construction.1.2.5.2 | OG6 | OG6 | 03120 | 0 | 0 | OG6-03120 | Construction | 1st Floor | Construction.1.2.5.2 | Install HVAC Controls - 1st Floor | 20 | 10 | 50% | 2022-08-15 08:00 | 2023-01-20 17:00 | -20 | WELKIN | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.2 | OG6 | OG6 | 03125 | 0 | 0 | OG6-03125 | Construction | 1st Floor | Construction.1.2.5.2 | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 0% | 2023-01-23 08:00 | 2023-01-27 17:00 | -20 | WELKIN | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.2 | OG6 | OG6 | 03130 | 0 | 0 | OG6-03130 | Construction | 1st Floor | Construction.1.2.5.2 | Install Mechanical Louvers - 1st Floor | 15 | 15 | 0% | 2022-11-30 08:00 | 2022-12-20 17:00 | -20 | UNSURE | MECHANICAL LOUVERS | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.2 | OG6 | OG6 | 03135 | 0 | 0 | OG6-03135 | Construction | 1st Floor | Construction.1.2.5.2 | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 0% | 2023-01-30 08:00 | 2023-02-10 17:00 | -20 | WELKIN | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.2 | OG6 | OG6 | 03140 | 0 | 0 | OG6-03140 | Construction | 1st Floor | Construction.1.2.5.2 | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 0% | 2023-02-13 08:00 | 2023-03-13 17:00 | -20 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Construction.1.2.5.2 | OG6 | OG6 | 03115 | 0 | 0 | OG6-03115 | Construction | 1st Floor | Construction.1.2.5.2 | Install Steam Traps - 1st Floor | 1 | 0 | 100% | 2022-08-22 08:00 | 2022-09-16 08:48 |  | WELKIN | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.2 | OG6 | OG6 | 03110 | 0 | 0 | OG6-03110 | Construction | 1st Floor | Construction.1.2.5.2 | Install Ductwork and Appurtenances - 1st Floor | 5 | 5 | 0% | 2022-12-21 08:00 | 2022-12-28 17:00 | -20 | WELKIN | DUCTWORK | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.2 | OG6 | OG6 | 03112 | 0 | 0 | OG6-03112 | Construction | 1st Floor | Construction.1.2.5.2 | Install HV & EF Units - 1st Floor | 5 | 5 | 0% | 2022-12-29 08:00 | 2023-01-05 17:00 | -20 | MEP | 0 | 0 | 0 | 0-OG6
In Progress | CI NYCHA Update #22.Construction.1.2.5.2 | OG6 | OG6 | 03107 | 0 | 0 | OG6-03107 | Construction | 1st Floor | Construction.1.2.5.2 | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 1 | 95% | 2022-08-08 08:00 | 2022-11-29 17:00 | -25 | WELKIN | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 03205 | 0 | 0 | OG6-03205 | Construction | 2nd Floor | Construction.1.2.5.3 | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 10 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 03220 | 0 | 0 | OG6-03220 | Construction | 2nd Floor | Construction.1.2.5.3 | Install HVAC Controls - 2nd Floor | 20 | 20 | 0% | 2023-01-06 08:00 | 2023-02-03 17:00 | -25 | WELKIN | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 03230 | 0 | 0 | OG6-03230 | Construction | 2nd Floor | Construction.1.2.5.3 | Install Mechanical Louvers - 2nd Floor | 15 | 15 | 0% | 2022-11-30 08:00 | 2022-12-20 17:00 | -25 | UNSURE | MECHANICAL LOUVERS | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 03235 | 0 | 0 | OG6-03235 | Construction | 2nd Floor | Construction.1.2.5.3 | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 0% | 2023-02-06 08:00 | 2023-02-17 17:00 | -25 | WELKIN | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 03240 | 0 | 0 | OG6-03240 | Construction | 2nd Floor | Construction.1.2.5.3 | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 0% | 2023-02-21 08:00 | 2023-03-20 17:00 | -25 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 03210 | 0 | 0 | OG6-03210 | Construction | 2nd Floor | Construction.1.2.5.3 | Install Ductwork and Appurtenances - 2nd Floor | 5 | 5 | 0% | 2022-12-21 08:00 | 2022-12-28 17:00 | -25 | WELKIN | DUCTWORK | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.3 | OG6 | OG6 | 03215 | 0 | 0 | OG6-03215 | Construction | 2nd Floor | Construction.1.2.5.3 | Install EF Units - 2nd Floor | 5 | 5 | 0% | 2022-12-29 08:00 | 2023-01-05 17:00 | -25 | MEP | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.4 | OG6 | OG6 | 03305 | 0 | 0 | OG6-03305 | Construction | Testing & Start-Up | Construction.1.2.5.4 | DOB Mechanical/Plumbing Inspection - OG6 | 4 | 4 | 0% | 2023-03-21 08:00 | 2023-03-24 17:00 | -25 | UNSURE | INSPECTION | INSPECTION | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.4 | OG6 | OG6 | 03310 | 0 | 0 | OG6-03310 | Construction | Testing & Start-Up | Construction.1.2.5.4 | Perform Start-Up Testing - OG6 | 11 | 11 | 0% | 2023-11-27 08:00 | 2023-12-11 17:00 | -193 | UNSURE | STARTUP | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.4 | OG6 | OG6 | 03315 | 0 | 0 | OG6-03315 | Construction | Testing & Start-Up | Construction.1.2.5.4 | Start-Up Testing Mechanical/Plumbing - OG2 | 16 | 16 | 0% | 2023-12-12 08:00 | 2024-01-04 17:00 | -193 | UNSURE | STARTUP | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.4 | OG6 | OG6 | 03320 | 0 | 0 | OG6-03320 | Construction | Testing & Start-Up | Construction.1.2.5.4 | Perform Punch List - Electrical/Mechanical/Plumbing Work - OG2 | 5 | 5 | 0% | 2024-01-05 08:00 | 2024-01-11 17:00 | -165 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.4 | OG6 | OG6 | 03330 | 0 | 0 | OG6-03330 | Construction | Testing & Start-Up | Construction.1.2.5.4 | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - OG2 | 4 | 4 | 0% | 2024-01-15 08:00 | 2024-01-18 17:00 | -165 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.4 | OG6 | OG6 | 03325 | 0 | 0 | OG6-03325 | Construction | Testing & Start-Up | Construction.1.2.5.4 | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - OG2 | 1 | 1 | 0% | 2024-01-12 08:00 | 2024-01-12 17:00 | -165 | FSE | INSPECTION | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.5.4 | OG6 | OG6 | 03335 | 0 | 0 | OG6-03335 | Construction | Testing & Start-Up | Construction.1.2.5.4 | Remove Redundant Services - OG2 | 10 | 10 | 0% | 2024-01-05 08:00 | 2024-01-18 17:00 | -193 | UNSURE | STARTUP | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 03005 | 0 | 0 | OG1-03005 | Construction | Cellar | Construction.1.3.5.1 | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 100% | 2021-09-27 | 2021-12-27 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 03010 | 0 | 0 | OG1-03010 | Construction | Cellar | Construction.1.3.5.1 | Install Condensate Pump - Cellar | 10 | 0 | 100% | 2022-07-27 08:00 | 2022-08-08 17:00 |  | WELKIN | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 03020 | 0 | 0 | OG1-03020 | Construction | Cellar | Construction.1.3.5.1 | Install Pump Controls - Cellar | 20 | 0 | 100% | 2022-08-09 08:00 | 2022-09-09 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 03025 | 0 | 0 | OG1-03025 | Construction | Cellar | Construction.1.3.5.1 | Perform Hydrostatic Testing - Cellar | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | 19 | WELKIN | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 03030 | 0 | 0 | OG1-03030 | Construction | Cellar | Construction.1.3.5.1 | Install Plumbing Equipment - Cellar | 15 | 15 | 0% | 2022-11-25 08:00 | 2022-12-15 17:00 | 19 | VITAL | PLUMBING EQUIP | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 03035 | 0 | 0 | OG1-03035 | Construction | Cellar | Construction.1.3.5.1 | Pump Equipment Start-up & Balance - Cellar | 10 | 10 | 0% | 2022-12-23 08:00 | 2023-01-09 17:00 | 19 | UNSURE | STARTUP | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 03040 | 0 | 0 | OG1-03040 | Construction | Cellar | Construction.1.3.5.1 | Plumbing/Mechanical Insulation - Cellar | 20 | 20 | 0% | 2023-01-10 08:00 | 2023-02-07 17:00 | 19 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 03015 | 0 | 0 | OG1-03015 | Construction | Cellar | Construction.1.3.5.1 | Install Steam Traps - Cellar | 2 | 0 | 100% | 2021-07-26 | 2021-08-26 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 03007 | 0 | 0 | OG1-03007 | Construction | Cellar | Construction.1.3.5.1 | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 0 | 100% | 2021-07-21 | 2021-12-27 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 03032 | 0 | 0 | OG1-03032 | Construction | Cellar | Construction.1.3.5.1 | Install Mechanical Equipment - Cellar | 15 | 0 | 100% | 2021-07-26 08:00 | 2021-12-27 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.5.2 | OG1 | OG1 | 03105 | 0 | 0 | OG1-03105 | Construction | 1st Floor | Construction.1.3.5.2 | Rough-In Plumbing Piping & Appurtenances - 1st Floor - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.2 | OG1 | OG1 | 03120 | 0 | 0 | OG1-03120 | Construction | 1st Floor | Construction.1.3.5.2 | Install HVAC Controls - 1st Floor | 20 | 20 | 0% | 2022-12-19 08:00 | 2023-01-18 17:00 | -2 | WELKIN | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.2 | OG1 | OG1 | 03125 | 0 | 0 | OG1-03125 | Construction | 1st Floor | Construction.1.3.5.2 | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 0% | 2023-01-19 08:00 | 2023-01-25 17:00 | -2 | WELKIN | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.2 | OG1 | OG1 | 03130 | 0 | 0 | OG1-03130 | Construction | 1st Floor | Construction.1.3.5.2 | Install Mechanical Louvers - 1st Floor | 15 | 15 | 0% | 2022-11-28 08:00 | 2022-12-16 17:00 | -2 | UNSURE | MECHANICAL LOUVERS | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.2 | OG1 | OG1 | 03135 | 0 | 0 | OG1-03135 | Construction | 1st Floor | Construction.1.3.5.2 | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 0% | 2023-01-26 08:00 | 2023-02-08 17:00 | -2 | WELKIN | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.2 | OG1 | OG1 | 03140 | 0 | 0 | OG1-03140 | Construction | 1st Floor | Construction.1.3.5.2 | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 0% | 2023-02-09 08:00 | 2023-03-09 17:00 | -2 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.5.2 | OG1 | OG1 | 03115 | 0 | 0 | OG1-03115 | Construction | 1st Floor | Construction.1.3.5.2 | Install Steam Traps - 1st Floor | 1 | 0 | 100% | 2022-07-25 08:00 | 2022-09-23 17:00 |  | WELKIN | 0 | 0 | 0 | 0-OG1
In Progress | CI NYCHA Update #22.Construction.1.3.5.2 | OG1 | OG1 | 03110 | 0 | 0 | OG1-03110 | Construction | 1st Floor | Construction.1.3.5.2 | Install Ductwork and Appurtenances - 1st Floor | 5 | 1 | 80% | 2022-09-20 08:00 | 2022-11-25 17:00 | -2 | WELKIN | DUCTWORK | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.5.2 | OG1 | OG1 | 03112 | 0 | 0 | OG1-03112 | Construction | 1st Floor | Construction.1.3.5.2 | Install HV & EF Units - 1st Floor | 5 | 0 | 100% | 2022-09-19 08:00 | 2022-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.5.2 | OG1 | OG1 | 03107 | 0 | 0 | OG1-03107 | Construction | 1st Floor | Construction.1.3.5.2 | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 0 | 100% | 2021-05-17 | 2021-12-20 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 03205 | 0 | 0 | OG1-03205 | Construction | 2nd Floor | Construction.1.3.5.3 | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 10 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 03220 | 0 | 0 | OG1-03220 | Construction | 2nd Floor | Construction.1.3.5.3 | Install HVAC Controls - 2nd Floor | 20 | 20 | 0% | 2023-01-03 08:00 | 2023-01-31 17:00 | -6 | WELKIN | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 03230 | 0 | 0 | OG1-03230 | Construction | 2nd Floor | Construction.1.3.5.3 | Install Mechanical Louvers - 2nd Floor | 15 | 15 | 0% | 2022-11-25 08:00 | 2022-12-15 17:00 | -6 | UNSURE | MECHANICAL LOUVERS | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 03235 | 0 | 0 | OG1-03235 | Construction | 2nd Floor | Construction.1.3.5.3 | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 0% | 2023-02-01 08:00 | 2023-02-14 17:00 | -6 | WELKIN | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 03240 | 0 | 0 | OG1-03240 | Construction | 2nd Floor | Construction.1.3.5.3 | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 0% | 2023-02-15 08:00 | 2023-03-15 17:00 | -6 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 03210 | 0 | 0 | OG1-03210 | Construction | 2nd Floor | Construction.1.3.5.3 | Install Ductwork and Appurtenances - 2nd Floor | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -6 | WELKIN | DUCTWORK | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.3 | OG1 | OG1 | 03215 | 0 | 0 | OG1-03215 | Construction | 2nd Floor | Construction.1.3.5.3 | Install EF Units - 2nd Floor | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | -6 | MEP | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.4 | OG1 | OG1 | 03305 | 0 | 0 | OG1-03305 | Construction | Testing & Start-Up | Construction.1.3.5.4 | DOB Mechanical/Plumbing Inspection - OG1 | 4 | 4 | 0% | 2023-03-16 08:00 | 2023-03-21 17:00 | -6 | UNSURE | INSPECTION | INSPECTION | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.4 | OG1 | OG1 | 03310 | 0 | 0 | OG1-03310 | Construction | Testing & Start-Up | Construction.1.3.5.4 | Perform Start-Up Testing - OG1 | 11 | 11 | 0% | 2023-11-27 08:00 | 2023-12-11 17:00 | -177 | UNSURE | STARTUP | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.4 | OG1 | OG1 | 03320 | 0 | 0 | OG1-03320 | Construction | Testing & Start-Up | Construction.1.3.5.4 | Perform Punch List - Electrical/Mechanical/Plumbing Work - OG1 | 5 | 5 | 0% | 2023-12-12 08:00 | 2023-12-18 17:00 | -149 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.4 | OG1 | OG1 | 03330 | 0 | 0 | OG1-03330 | Construction | Testing & Start-Up | Construction.1.3.5.4 | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - OG1 | 4 | 4 | 0% | 2023-12-20 08:00 | 2023-12-26 17:00 | -149 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.4 | OG1 | OG1 | 03325 | 0 | 0 | OG1-03325 | Construction | Testing & Start-Up | Construction.1.3.5.4 | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - OG1 | 1 | 1 | 0% | 2023-12-19 08:00 | 2023-12-19 17:00 | -149 | FSE | INSPECTION | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.5.4 | OG1 | OG1 | 03335 | 0 | 0 | OG1-03335 | Construction | Testing & Start-Up | Construction.1.3.5.4 | Remove Redundant Services - OG1 | 10 | 10 | 0% | 2023-12-12 08:00 | 2023-12-26 17:00 | -177 | UNSURE | STARTUP | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 02005 | 0 | 0 | SGS-02005 | Construction | Site Utilities | Construction.4.5.6 | Remove, Relocate or Abandon Exisiting Feeder Conduit & Cable | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | -38 | FSE | 0 | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 02010 | 0 | 0 | SGS-02010 | Construction | Site Utilities | Construction.4.5.6 | Install Manholes & Grounding | 8 | 8 | 0% | 2022-12-02 08:00 | 2022-12-13 17:00 | -38 | FSE | GROUNDING EQUIP | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.Removals1 | SGS | SGS | 01005 | 0 | 0 | SGS-01005 | Construction | Site Protection & Removals | Construction.4.5.Removals1 | Install Site Fencing - Surfside Gardens - South | 10 | 0 | 100% | 2021-04-28 | 2021-05-10 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.Removals1 | SGS | SGS | 01015 | 0 | 0 | SGS-01015 | Construction | Site Protection & Removals | Construction.4.5.Removals1 | Install Overhead Protection - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.Removals1 | SGS | SGS | 01020 | 0 | 0 | SGS-01020 | Construction | Site Protection & Removals | Construction.4.5.Removals1 | Install Tree Protection | 10 | 0 | 100% | 2020-11-04 | 2020-11-11 17:00 |  | 0 | 0 | 0 | 31-1900 | 31-1900-SGS
Completed | CI NYCHA Update #22.Construction.4.5.Removals1 | SGS | SGS | 01025 | 0 | 0 | SGS-01025 | Construction | Site Protection & Removals | Construction.4.5.Removals1 | Remove Trees | 2 | 0 | 100% | 2021-01-14 | 2021-01-19 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.Removals1 | SGS | SGS | 01000 | 0 | 0 | SGS-01000 | Construction | Site Protection & Removals | Construction.4.5.Removals1 | Remove Curbs And Existing Fencing | 10 | 0 | 100% | 2021-07-19 | 2022-02-18 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.Removals1 | SGS | SGS | 01035 | 0 | 0 | SGS-01035 | Construction | Site Protection & Removals | Construction.4.5.Removals1 | Install Erosion Control | 5 | 0 | 100% | 2022-02-10 | 2022-02-18 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.Removals1 | SGS | SGS | 01010 | 0 | 0 | SGS-01010 | Construction | Site Protection & Removals | Construction.4.5.Removals1 | Set Up Yard and Staging | 10 | 0 | 100% | 2020-12-28 | 2021-01-22 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.Removals1 | SGS | SGS | 01045 | 0 | 0 | SGS-01045 | Construction | Site Protection & Removals | Construction.4.5.Removals1 | Clear & Grub | 10 | 0 | 100% | 2021-05-11 | 2022-02-18 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.Removals1 | SGS | SGS | 01050 | 0 | 0 | SGS-01050 | Construction | Site Protection & Removals | Construction.4.5.Removals1 | Scrape & Store Topsoil | 10 | 0 | 100% | 2021-05-11 | 2022-02-18 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.Removals1 | SGS | SGS | 01055 | 0 | 0 | SGS-01055 | Construction | Site Protection & Removals | Construction.4.5.Removals1 | Soil Testing | 10 | 0 | 100% | 2021-05-14 | 2021-06-04 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.Removals1 | SGS | SGS | 01060 | 0 | 0 | SGS-01060 | Construction | Site Protection & Removals | Construction.4.5.Removals1 | Demo Playgrounds And Misc Site Furniture | 5 | 0 | 100% | 2021-07-26 08:00 | 2022-02-18 |  | 0 | 0 | 0 | 02-2000 | 02-2000-SGS
Completed | CI NYCHA Update #22.Construction.4.5.Removals1 | SGS | SGS | 01065 | 0 | 0 | SGS-01065 | Construction | Site Protection & Removals | Construction.4.5.Removals1 | Remove Retaining Walls | 10 | 0 | 100% | 2022-01-10 | 2022-04-22 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.Removals1 | SGS | SGS | 01070 | 0 | 0 | SGS-01070 | Construction | Site Protection & Removals | Construction.4.5.Removals1 | Install Deep Wells For Dewatering - N/A | 10 | 0 | 100% | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.Removals1 | SGS | SGS | 01075 | 0 | 0 | SGS-01075 | Construction | Site Protection & Removals | Construction.4.5.Removals1 | Install Piping For Deep Wells - N/A | 5 | 0 | 100% | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.Removals1 | SGS | SGS | 01080 | 0 | 0 | SGS-01080 | Construction | Site Protection & Removals | Construction.4.5.Removals1 | Install Discharge Connection For Dewatering - N/A | 10 | 0 | 100% | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.Removals1 | SGS | SGS | 01085 | 0 | 0 | SGS-01085 | Construction | Site Protection & Removals | Construction.4.5.Removals1 | Run Electric For Dewatering - N/A | 10 | 0 | 100% | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01150 | 0 | 0 | SGS-01150 | Construction | Site Utilities | Construction.4.5.6 | Excavate for Electric SG7--> SG1 | 10 | 0 | 100% | 2022-05-13 | 2022-05-26 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01155 | 0 | 0 | SGS-01155 | Construction | Site Utilities | Construction.4.5.6 | Install Electrical Conduit SG7--> SG1 | 10 | 0 | 100% | 2022-05-13 | 2022-06-02 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01160 | 0 | 0 | SGS-01160 | Construction | Site Utilities | Construction.4.5.6 | Encase conduit in concrete SG7--> SG1 | 5 | 0 | 100% | 2022-06-03 | 2022-06-06 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01165 | 0 | 0 | SGS-01165 | Construction | Site Utilities | Construction.4.5.6 | Backfill Electrical SG7--> SG1 | 5 | 0 | 100% | 2022-06-02 | 2022-06-06 |  | 0 | 0 | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01405 | 0 | 0 | SGS-01405 | Construction | Site Utilities | Construction.4.5.6 | National Gas Install Line from W31st to SG7 | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 23 | NATIONAL GRID | GAS INSTALL | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01205 | 0 | 0 | SGS-01205 | Construction | Site Utilities | Construction.4.5.6 | Excavate for Electric SG7--> SG2 | 3 | 0 | 100% | 2022-05-13 | 2022-06-27 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01210 | 0 | 0 | SGS-01210 | Construction | Site Utilities | Construction.4.5.6 | Install Electrical Conduit SG7--> SG2 | 2 | 0 | 100% | 2022-05-13 | 2022-06-21 |  | FSE | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01215 | 0 | 0 | SGS-01215 | Construction | Site Utilities | Construction.4.5.6 | Encase conduit in concrete SG7--> SG2 | 2 | 0 | 100% | 2022-06-27 | 2022-06-29 |  | MLJ | Concrete | SITE CONCRETE | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01220 | 0 | 0 | SGS-01220 | Construction | Site Utilities | Construction.4.5.6 | Backfill Electrical SG7--> SG2 | 2 | 0 | 100% | 2022-06-30 | 2022-07-01 |  | MLJ | BACKFILL | BACKFILL UTILITY | 31-2200 | 31-2200-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01230 | 0 | 0 | SGS-01230 | Construction | Site Utilities | Construction.4.5.6 | Excavate for Electric SG7--> SG3 | 10 | 0 | 100% | 2022-05-13 | 2022-06-17 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01235 | 0 | 0 | SGS-01235 | Construction | Site Utilities | Construction.4.5.6 | Install Electrical Conduit & MH SG7--> SG3 | 10 | 0 | 100% | 2022-05-13 | 2022-06-21 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01240 | 0 | 0 | SGS-01240 | Construction | Site Utilities | Construction.4.5.6 | Encase conduit in concrete SG7--> SG3 | 3 | 0 | 100% | 2022-06-22 | 2022-06-22 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01245 | 0 | 0 | SGS-01245 | Construction | Site Utilities | Construction.4.5.6 | Backfill Electrical SG7--> SG3 | 5 | 0 | 100% | 2022-06-23 | 2022-06-23 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01255 | 0 | 0 | SGS-01255 | Construction | Site Utilities | Construction.4.5.6 | Excavate for Electric SG3--> MH | 3 | 0 | 100% | 2022-04-18 | 2022-09-09 |  | MLJ | Excavation | UTILITY EXC | 33-3100 | 33-3100-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01260 | 0 | 0 | SGS-01260 | Construction | Site Utilities | Construction.4.5.6 | Install Electrical Conduit SG3--> MH | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | -2 | FSE | 0 | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01265 | 0 | 0 | SGS-01265 | Construction | Site Utilities | Construction.4.5.6 | Encase conduit in concrete SG3--> MH | 2 | 2 | 0% | 2022-11-29 08:00 | 2022-11-30 17:00 | -2 | MLJ | CONCRETE | SITE CONCRETE | 03-1105 | 03-1105-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01270 | 0 | 0 | SGS-01270 | Construction | Site Utilities | Construction.4.5.6 | Backfill Electrical SG3--> MH | 2 | 2 | 0% | 2022-12-01 08:00 | 2022-12-02 17:00 | -2 | MLJ | BACKFILL | BACKFILL UTILITY | 31-2200 | 31-2200-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01275 | 0 | 0 | SGS-01275 | Construction | Site Utilities | Construction.4.5.6 | Excavate for Steam SG3--> SG2 | 15 | 0 | 100% | 2022-03-25 | 2022-04-08 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01280 | 0 | 0 | SGS-01280 | Construction | Site Utilities | Construction.4.5.6 | Install Steam piping SG3--> SG2 | 20 | 0 | 100% | 2022-04-07 | 2022-06-03 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01285 | 0 | 0 | SGS-01285 | Construction | Site Utilities | Construction.4.5.6 | Test Steam Piping SG3--> SG2 | 8 | 0 | 100% | 2022-06-06 | 2022-06-16 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01290 | 0 | 0 | SGS-01290 | Construction | Site Utilities | Construction.4.5.6 | Backfill Steam Piping SG3--> SG2 | 10 | 0 | 100% | 2022-06-17 | 2022-06-24 |  | 0 | 0 | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01505 | 0 | 0 | SGS-01505 | Construction | Site Utilities | Construction.4.5.6 | Excavate for water line to drinking fountains SGS --> Water Main W32nd Street | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | -7 | MLJ | EXCAVATION | UTILITY EXC | 33-3100 | 33-3100-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01510 | 0 | 0 | SGS-01510 | Construction | Site Utilities | Construction.4.5.6 | Install water line to drinking fountain SGS --> Water Main W32nd Street | 5 | 5 | 0% | 2022-12-12 08:00 | 2022-12-16 17:00 | -16 | UNSURE | PLAYGROUND | PLUMBING | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01515 | 0 | 0 | SGS-01515 | Construction | Site Utilities | Construction.4.5.6 | Tap water main for drinking fountain water line SGS --> Water Main W32nd Street | 2 | 2 | 0% | 2022-12-19 08:00 | 2022-12-20 17:00 | -16 | UNSURE | PLAYGROUND | PLUMBING | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01520 | 0 | 0 | SGS-01520 | Construction | Site Utilities | Construction.4.5.6 | Backfill water line drinking fountain SGS --> Water Main W32nd Street | 2 | 2 | 0% | 2022-12-21 08:00 | 2022-12-22 17:00 | -16 | MLJ | BACKFILL | BACKFILL SITE | 31-2200 | 31-2200-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01560 | 0 | 0 | SGS-01560 | Construction | Site Utilities | Construction.4.5.6 | Excavate and Install Area Drains - Yard Drain to Existing+ Piping incl DIP 3 | 10 | 0 | 100% | 2022-10-21 | 2022-10-28 |  | MLJ | Excavation | AREA DRAIN | 33-2600 | 33-2600-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01565 | 0 | 0 | SGS-01565 | Construction | Site Utilities | Construction.4.5.6 | Backfill Area Drains Yard Drain to Existing+ Piping incl DIP 3 | 5 | 0 | 100% | 2022-10-31 | 2022-11-02 |  | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-SGS
Completed | CI NYCHA Update #22.Construction.4.5.Removals1 | SGS | SGS | 01090 | 0 | 0 | SGS-01090 | Construction | Site Protection & Removals | Construction.4.5.Removals1 | Activate Dewatering System | 1 | 0 | 100% | 2022-01-01 | 2022-01-01 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.Removals1 | SGS | SGS | 01095 | 0 | 0 | SGS-01095 | Construction | Site Protection & Removals | Construction.4.5.Removals1 | Maintain Dewatering | 283 | 0 | 100% | 2022-01-01 | 2022-05-10 |  | 0 | dewatering | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01287 | 0 | 0 | SGS-01287 | Construction | Site Utilities | Construction.4.5.6 | Install Automatic Temperature Control Conduit - SG3--> SG2 | 2 | 0 | 100% | 2022-07-25 08:00 | 2022-07-26 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.Removals1 | SGS | SGS | 01100 | 0 | 0 | SGS-01100 | Construction | Site Protection & Removals | Construction.4.5.Removals1 | De-Activate Dewatering | 1 | 0 | 100% | 2022-05-10 | 2022-05-10 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01295 | 0 | 0 | SGS-01295 | Construction | Site Utilities | Construction.4.5.6 | Excavate for Steam & HW SG3--> SG7 | 15 | 0 | 100% | 2021-12-06 08:00 | 2021-12-16 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01300 | 0 | 0 | SGS-01300 | Construction | Site Utilities | Construction.4.5.6 | Install Steam and HW piping SG3--> SG7 | 20 | 0 | 100% | 2021-12-17 08:00 | 2022-09-14 |  | WELKIN | UG PIPE | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01305 | 0 | 0 | SGS-01305 | Construction | Site Utilities | Construction.4.5.6 | Test Steam & HW Piping SG3--> SG7 | 8 | 0 | 100% | 2022-09-12 | 2022-09-16 |  | WELKIN | UG PIPE | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01315 | 0 | 0 | SGS-01315 | Construction | Site Utilities | Construction.4.5.6 | Backfill Steam & HW Piping SG3--> SG7 | 10 | 0 | 100% | 2022-09-19 | 2022-09-21 |  | MLJ | BACKFILL | BACKFILL UTILITY | 31-2200 | 31-2200-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01310 | 0 | 0 | SGS-01310 | Construction | Site Utilities | Construction.4.5.6 | Install Automatic Temperature Control Conduit - SG3--> SG7 | 2 | 0 | 100% | 2022-09-21 | 2022-09-21 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01325 | 0 | 0 | SGS-01325 | Construction | Site Utilities | Construction.4.5.6 | Excavate for Steam SG3--> SG1 | 15 | 0 | 100% | 2021-11-30 08:00 | 2022-01-25 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01330 | 0 | 0 | SGS-01330 | Construction | Site Utilities | Construction.4.5.6 | Install Steam and piping SG3--> SG1 | 20 | 0 | 100% | 2022-01-26 | 2022-04-08 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01335 | 0 | 0 | SGS-01335 | Construction | Site Utilities | Construction.4.5.6 | Test Steam & Piping SG3--> SG1 | 8 | 0 | 100% | 2022-03-16 | 2022-04-15 17:00 |  | WELKIN | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01345 | 0 | 0 | SGS-01345 | Construction | Site Utilities | Construction.4.5.6 | Backfill Steam & Piping SG3--> SG1 | 10 | 0 | 100% | 2022-04-15 08:00 | 2022-04-15 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01340 | 0 | 0 | SGS-01340 | Construction | Site Utilities | Construction.4.5.6 | Install Automatic Temperature Control Conduit - SG3--> SG1 | 2 | 0 | 100% | 2022-09-21 | 2022-09-21 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01575 | 0 | 0 | SGS-01575 | Construction | Site Utilities | Construction.4.5.6 | Excavate and Install Area Drains - AD8 > AD3 > Existing + Piping incl DIP4 | 10 | 0 | 100% | 2022-11-03 | 2022-11-08 |  | MLJ | Excavation | AREA DRAIN | 33-2600 | 33-2600-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01580 | 0 | 0 | SGS-01580 | Construction | Site Utilities | Construction.4.5.6 | Backfill Area Drains - AD8 > AD3 > Existing + Piping incl DIP4 | 5 | 0 | 100% | 2022-11-08 | 2022-11-10 |  | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01590 | 0 | 0 | SGS-01590 | Construction | Site Utilities | Construction.4.5.6 | Excavate and Install Area Drains - Yard Drain > AD3 > Existing + Piping | 10 | 0 | 100% | 2022-11-03 | 2022-11-08 |  | MLJ | Excavation | AREA DRAIN | 33-2600 | 33-2600-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01595 | 0 | 0 | SGS-01595 | Construction | Site Utilities | Construction.4.5.6 | Backfill Area Drains - Yard Drain > AD3 > Existing + Piping | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | -1 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01650 | 0 | 0 | SGS-01650 | Construction | Site Utilities | Construction.4.5.6 | Excavate and Install Area Drains - AD16 > AD17 & Piping | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | -91 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01655 | 0 | 0 | SGS-01655 | Construction | Site Utilities | Construction.4.5.6 | Backfill Area Drains - AD16 > AD17 & Piping | 5 | 5 | 0% | 2022-12-09 08:00 | 2022-12-15 17:00 | -11 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01660 | 0 | 0 | SGS-01660 | Construction | Site Utilities | Construction.4.5.6 | Excavate and Install Area Drains - AD21 > Trap to Existing & Piping | 10 | 10 | 0% | 2022-12-09 08:00 | 2022-12-22 17:00 | -91 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01665 | 0 | 0 | SGS-01665 | Construction | Site Utilities | Construction.4.5.6 | Backfill Area Drains - AD21 > Trap to Existing & Piping | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | -21 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01670 | 0 | 0 | SGS-01670 | Construction | Site Utilities | Construction.4.5.6 | Excavate and Install Area Drains - AD1 > AD2 > AD4 > Existing + Piping | 10 | 10 | 0% | 2022-12-23 08:00 | 2023-01-09 17:00 | -91 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01675 | 0 | 0 | SGS-01675 | Construction | Site Utilities | Construction.4.5.6 | Backfill Area Drains - AD1 > AD2 > AD4 > Existing + Piping | 5 | 5 | 0% | 2023-01-10 08:00 | 2023-01-17 17:00 | -31 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01680 | 0 | 0 | SGS-01680 | Construction | Site Utilities | Construction.4.5.6 | Excavate and Install Area Drains - AD9 > AD4 > Piping | 10 | 10 | 0% | 2023-01-10 08:00 | 2023-01-24 17:00 | -91 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01685 | 0 | 0 | SGS-01685 | Construction | Site Utilities | Construction.4.5.6 | Backfill Area Drains - AD9 > AD4 > Piping | 5 | 5 | 0% | 2023-01-25 08:00 | 2023-01-31 17:00 | -41 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01690 | 0 | 0 | SGS-01690 | Construction | Site Utilities | Construction.4.5.6 | Excavate and Install Area Drains - AD20 > Existing + Piping | 10 | 10 | 0% | 2023-01-25 08:00 | 2023-02-07 17:00 | -91 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01695 | 0 | 0 | SGS-01695 | Construction | Site Utilities | Construction.4.5.6 | Backfill Area Drains - AD20 > Existing + Piping | 5 | 5 | 0% | 2023-02-08 08:00 | 2023-02-14 17:00 | -51 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01350 | 0 | 0 | SGS-01350 | Construction | Site Utilities | Construction.4.5.6 | Excavate for HW SG7--> SG1 | 15 | 0 | 100% | 2022-01-05 | 2022-01-14 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01355 | 0 | 0 | SGS-01355 | Construction | Site Utilities | Construction.4.5.6 | Install HW and piping SG7--> SG1 | 20 | 0 | 100% | 2022-02-11 | 2022-03-16 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01360 | 0 | 0 | SGS-01360 | Construction | Site Utilities | Construction.4.5.6 | Test HW & Piping SG7--> SG1 | 8 | 0 | 100% | 2022-03-01 | 2022-03-09 |  | WELKIN | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01370 | 0 | 0 | SGS-01370 | Construction | Site Utilities | Construction.4.5.6 | Backfill HW & Piping SG7--> SG1 | 10 | 0 | 100% | 2022-05-02 | 2022-05-05 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01365 | 0 | 0 | SGS-01365 | Construction | Site Utilities | Construction.4.5.6 | Install Automatic Temperature Control Conduit - SG7--> SG1 | 2 | 0 | 100% | 2022-05-25 | 2022-05-27 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01375 | 0 | 0 | SGS-01375 | Construction | Site Utilities | Construction.4.5.6 | Excavate for HW SG7--> SG2 | 15 | 0 | 100% | 2022-02-02 | 2022-05-10 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01380 | 0 | 0 | SGS-01380 | Construction | Site Utilities | Construction.4.5.6 | Install HW piping SG7--> SG2 | 20 | 0 | 100% | 2022-05-10 | 2022-06-09 08:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01385 | 0 | 0 | SGS-01385 | Construction | Site Utilities | Construction.4.5.6 | Test HW Piping SG7--> SG2 | 8 | 0 | 100% | 2022-06-09 | 2022-06-15 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01395 | 0 | 0 | SGS-01395 | Construction | Site Utilities | Construction.4.5.6 | Backfill HW Piping SG7--> SG2 | 10 | 0 | 100% | 2022-06-20 | 2022-06-24 |  | 0 | 0 | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01390 | 0 | 0 | SGS-01390 | Construction | Site Utilities | Construction.4.5.6 | Install Automatic Temperature Control Conduit - SG7--> SG2 | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | 38 | FSE | 0 | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01700 | 0 | 0 | SGS-01700 | Construction | Site Utilities | Construction.4.5.6 | Excavate and Install Area Drains - Yard Drain > AD10 > AD11 > Existing + Piping | 10 | 10 | 0% | 2023-02-08 08:00 | 2023-02-22 17:00 | -91 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01775 | 0 | 0 | SGS-01775 | Construction | Site Utilities | Construction.4.5.6 | Backfill Area Drains - Yard Drain > AD10 > AD11 > Existing + Piping | 5 | 5 | 0% | 2023-02-23 08:00 | 2023-03-01 17:00 | -61 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01780 | 0 | 0 | SGS-01780 | Construction | Site Utilities | Construction.4.5.6 | Excavate and Install Area Drains - AD13 > AD15 > AD14 > AD12 + Piping | 10 | 10 | 0% | 2023-02-23 08:00 | 2023-03-08 17:00 | -91 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01785 | 0 | 0 | SGS-01785 | Construction | Site Utilities | Construction.4.5.6 | Backfill Area Drains - AD13 > AD15 > AD14 > AD12 + Piping | 5 | 5 | 0% | 2023-03-09 08:00 | 2023-03-15 17:00 | -71 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01790 | 0 | 0 | SGS-01790 | Construction | Site Utilities | Construction.4.5.6 | Excavate and Install Area Drains - AD19 > AD18 + Piping | 10 | 10 | 0% | 2023-03-09 08:00 | 2023-03-22 17:00 | -91 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01795 | 0 | 0 | SGS-01795 | Construction | Site Utilities | Construction.4.5.6 | Backfill Area Drains - AD19 > AD18 + Piping | 5 | 5 | 0% | 2023-03-23 08:00 | 2023-03-29 17:00 | -81 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01800 | 0 | 0 | SGS-01800 | Construction | Site Utilities | Construction.4.5.6 | Excavate and Install Area Drains - AD5 > AD6 > AD7 > Existing + Piping | 10 | 10 | 0% | 2023-03-23 08:00 | 2023-04-05 17:00 | -91 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.6 | SGS | SGS | 01805 | 0 | 0 | SGS-01805 | Construction | Site Utilities | Construction.4.5.6 | Backfill Area Drains - AD5 > AD6 > AD7 > Existing + Piping | 5 | 5 | 0% | 2023-04-06 08:00 | 2023-04-12 17:00 | -91 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-SGS
Completed | CI NYCHA Update #22.Construction.4.5.4 | SGS | SGS | 01605 | 0 | 0 | SGS-01605 | Construction | Retaining Walls | Construction.4.5.4 | Excavate for retaining wall --> SGS Phase 5 | 2 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | MLJ | Excavation | EXC RETAINING | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.4 | SGS | SGS | 01610 | 0 | 0 | SGS-01610 | Construction | Retaining Walls | Construction.4.5.4 | Form Retaining wall footing --> SGS Phase 5 | 2 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | MLJ | Formwork | SITE FORMWORK | 03-1600 | 03-1600-SGS
Completed | CI NYCHA Update #22.Construction.4.5.4 | SGS | SGS | 01615 | 0 | 0 | SGS-01615 | Construction | Retaining Walls | Construction.4.5.4 | Rebar Retaining wall footing --> SGS Phase 5 | 2 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0 | REBAR | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.4 | SGS | SGS | 01620 | 0 | 0 | SGS-01620 | Construction | Retaining Walls | Construction.4.5.4 | Pour Retaining wall footing --> SGS Phase 5 | 1 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | MLJ | Concrete | SITE CONCRETE | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.5.4 | SGS | SGS | 01625 | 0 | 0 | SGS-01625 | Construction | Retaining Walls | Construction.4.5.4 | Strip Retaining wall footing --> SGS Phase 5 | 1 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0 | Formwork | SITE FORMWORK | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.4 | SGS | SGS | 01630 | 0 | 0 | SGS-01630 | Construction | Retaining Walls | Construction.4.5.4 | Form Retaining wall --> SGS Phase 5 | 3 | 3 | 0% | 2022-11-25 08:00 | 2022-11-29 17:00 | -7 | MLJ | Formwork | SITE FORMWORK | 03-1600 | 03-1600-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.4 | SGS | SGS | 01635 | 0 | 0 | SGS-01635 | Construction | Retaining Walls | Construction.4.5.4 | Rebar Retaining wall --> SGS Phase 5 | 3 | 3 | 0% | 2022-11-30 08:00 | 2022-12-02 17:00 | -7 | TONAGE | REBAR | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.4 | SGS | SGS | 01640 | 0 | 0 | SGS-01640 | Construction | Retaining Walls | Construction.4.5.4 | Pour Retaining wall --> SGS Phase 5 | 1 | 1 | 0% | 2022-12-05 08:00 | 2022-12-05 17:00 | -7 | MLJ | CONCRETE | SITE CONCRETE | 03-2400 | 03-2400-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.4 | SGS | SGS | 01645 | 0 | 0 | SGS-01645 | Construction | Retaining Walls | Construction.4.5.4 | Strip Retaining wall --> SGS Phase 5 | 1 | 1 | 0% | 2022-12-06 08:00 | 2022-12-06 17:00 | -4 | MLJ | FORMWORK | SITE FORMWORK | 03-1600 | 03-1600-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.5 | SGS | SGS | 01705 | 0 | 0 | SGS-01705 | Construction | Site Restoration | Construction.4.5.5 | Install Street Curbs --> SGS Phase 5 | 15 | 15 | 0% | 2023-07-19 08:00 | 2023-08-08 17:00 | -158 | MLJ | CURBS | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.5 | SGS | SGS | 01710 | 0 | 0 | SGS-01710 | Construction | Site Restoration | Construction.4.5.5 | Install sidewalks --> SGS Phase 5 | 10 | 10 | 0% | 2023-08-23 08:00 | 2023-09-06 17:00 | -158 | JMC | SIDEWALKS | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.5 | SGS | SGS | 01715 | 0 | 0 | SGS-01715 | Construction | Site Restoration | Construction.4.5.5 | Install curb around play area --> SGS Phase 5 | 5 | 5 | 0% | 2023-09-07 08:00 | 2023-09-13 17:00 | -158 | MLJ | CURBS | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.5 | SGS | SGS | 01720 | 0 | 0 | SGS-01720 | Construction | Site Restoration | Construction.4.5.5 | Install Safety Surface --> SGS Phase 5 | 5 | 5 | 0% | 2023-09-14 08:00 | 2023-09-20 17:00 | -158 | UNSURE | PLAYGROUND | SAFETY SURFACE | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.5 | SGS | SGS | 01725 | 0 | 0 | SGS-01725 | Construction | Site Restoration | Construction.4.5.5 | Install site furniture concrete foundations --> SGS Phase 5 | 10 | 10 | 0% | 2023-08-09 08:00 | 2023-08-22 17:00 | -158 | MLJ | CONCRETE | SITE CONCRETE | 03-2200 | 03-2200-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.5 | SGS | SGS | 01730 | 0 | 0 | SGS-01730 | Construction | Site Restoration | Construction.4.5.5 | Install integrally colored concrete walkways --> SGS Phase 5 | 20 | 20 | 0% | 2023-09-21 08:00 | 2023-10-19 17:00 | -158 | JMC | COLORED CONCRETE | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.5 | SGS | SGS | 01735 | 0 | 0 | SGS-01735 | Construction | Site Restoration | Construction.4.5.5 | Install Play area items --> SGS Phase 5 | 5 | 5 | 0% | 2023-10-20 08:00 | 2023-10-26 17:00 | -158 | BRIGHTON | PLAYGROUND | INSTALL | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.5 | SGS | SGS | 01740 | 0 | 0 | SGS-01740 | Construction | Site Restoration | Construction.4.5.5 | Install fence around play area --> SGS Phase 5 | 10 | 10 | 0% | 2023-10-27 08:00 | 2023-11-13 17:00 | -158 | MLJ | FENCING | PLAYGROUND | 32-6520 | 32-6520-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.5 | SGS | SGS | 01745 | 0 | 0 | SGS-01745 | Construction | Site Restoration | Construction.4.5.5 | Install Fence at building --> SG7 | 5 | 5 | 0% | 2023-11-14 08:00 | 2023-11-20 17:00 | -158 | ATLAS | SITE RESTORATION | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.5 | SGS | SGS | 01750 | 0 | 0 | SGS-01750 | Construction | Site Restoration | Construction.4.5.5 | Place Site Furniture --> SGS Phase 5 | 10 | 10 | 0% | 2023-11-21 08:00 | 2023-12-05 17:00 | -158 | MLJ | SITE RESTORATION | SITE FURNITURE | 31-2600 | 31-2600-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.5 | SGS | SGS | 01755 | 0 | 0 | SGS-01755 | Construction | Site Restoration | Construction.4.5.5 | Place topsoil --> SGS Phase 5 | 3 | 3 | 0% | 2024-04-01 08:00 | 2024-04-03 17:00 | -75 | ASPEN | TOPSOIL | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.5 | SGS | SGS | 01760 | 0 | 0 | SGS-01760 | Construction | Site Restoration | Construction.4.5.5 | Place trees and plantings --> SGS Phase 5 | 5 | 5 | 0% | 2024-04-04 08:00 | 2024-04-10 17:00 | -75 | ASPEN | 0 | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.5 | SGS | SGS | 01765 | 0 | 0 | SGS-01765 | Construction | Site Restoration | Construction.4.5.5 | Place lawn --> SGS Phase 5 | 5 | 5 | 0% | 2024-04-11 08:00 | 2024-04-17 17:00 | -75 | ASPEN | 0 | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.5 | SGS | SGS | 01770 | 0 | 0 | SGS-01770 | Construction | Site Restoration | Construction.4.5.5 | Demobilize from SGS Phase 5 | 5 | 5 | 0% | 2024-04-18 08:00 | 2024-04-24 17:00 | -228 | MLJ | DEMOB | 0 | 99-4000 | 99-4000-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.7 | SGS | SGS | 01850 | 0 | 0 | SGS-01850 | Construction | Civil/Architectural Inspections | Construction.4.5.7 | Perform Inspections & Issue Punch List | 5 | 5 | 0% | 2024-04-18 08:00 | 2024-04-24 17:00 | -238 | MLJ | PUNCH LIST | INSPECTION | 99-8200 | 99-8200-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.7 | SGS | SGS | 01855 | 0 | 0 | SGS-01855 | Construction | Civil/Architectural Inspections | Construction.4.5.7 | Perform Punch List | 10 | 10 | 0% | 2024-04-25 08:00 | 2024-05-08 17:00 | -238 | MLJ | PUNCH LIST | 0 | 99-8200 | 99-8200-SGS
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01030 | 0 | 0 | SG7-01030 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Form Plumbing Shafts & Ftgs Below Water Table --> SG7 | 10 | 0 | 100% | 2021-09-10 08:00 | 2021-09-10 17:00 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01035 | 0 | 0 | SG7-01035 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Rebar Plumbing Shafts & Ftgs Below Water Table --> SG7 | 5 | 0 | 100% | 2021-09-10 08:00 | 2021-09-15 17:00 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01040 | 0 | 0 | SG7-01040 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Pour Plumbing Shafts & Ftgs Below Water Table --> SG7 | 2 | 0 | 100% | 2021-09-15 08:00 | 2021-09-15 17:00 |  | MLJ | concrete | NB CONCRETE | 03-1900 | 03-1900-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01045 | 0 | 0 | SG7-01045 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Strip Forms Plumbing Shafts & Ftgs Below Water Table --> SG7 | 5 | 0 | 100% | 2021-10-11 | 2021-10-13 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01025 | 0 | 0 | SG7-01025 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Waterproof/Insulation Plumbing Shaft ----> SG7 | 5 | 0 | 100% | 2021-10-14 | 2021-10-14 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01005 | 0 | 0 | SG7-01005 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Excavate/SOE For Plumbing Shaft & Ftgs/Piers Below Water Table --> SG7 | 10 | 0 | 100% | 2021-07-30 08:00 | 2021-08-24 17:00 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01020 | 0 | 0 | SG7-01020 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Prepare Subgrade For Plumbing Shafts & Ftgs / Piers Below Water Table --> SG7 | 3 | 0 | 100% | 2021-09-27 | 2021-09-30 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01055 | 0 | 0 | SG7-01055 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Backfill Plumbing Shaft & Ftgs/Piers --> SG7 | 5 | 0 | 100% | 2021-10-15 | 2022-05-02 |  | 0 | SG7 | 0 | 31-1400 | 31-1400-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01065 | 0 | 0 | SG7-01065 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Excavate For Remaining Ftgs/Pier/Grade Beams --> SG7 | 10 | 0 | 100% | 2021-08-16 08:00 | 2021-09-10 17:00 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01070 | 0 | 0 | SG7-01070 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Form Remaining Ftgs/Piers/Grade Beams --> SG7 | 10 | 0 | 100% | 2022-01-05 | 2022-05-06 |  | 0 | FORMWORK | FORMWORK NB | 03-1000 | 03-1000-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01075 | 0 | 0 | SG7-01075 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Rebar Remaining Ftgs/Piers/Grade Beams --> SG7 | 10 | 0 | 100% | 2022-01-10 | 2022-05-09 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01080 | 0 | 0 | SG7-01080 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Pour Remaining Ftgs/Piers/Grade Beams --> SG7 | 5 | 0 | 100% | 2022-01-11 | 2022-05-10 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01085 | 0 | 0 | SG7-01085 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Strip Forms Remaining Ftgs/Piers/Grade Beams --> SG7 | 5 | 0 | 100% | 2022-01-12 | 2022-05-12 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01090 | 0 | 0 | SG7-01090 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Remaining Steam Into SG7 (5' from the building) | 5 | 0 | 100% | 2022-05-25 | 2022-06-01 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01095 | 0 | 0 | SG7-01095 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Backfill Remaining Ftgs/Piers/Grade Beams / Prepare Subgrade --> SG7 | 5 | 0 | 100% | 2022-01-14 | 2022-06-09 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01105 | 0 | 0 | SG7-01105 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Structural Steel Framing - 1st Floor --> SG7 | 10 | 0 | 100% | 2022-07-14 | 2022-08-11 17:00 |  | WEIR | STRUCTURAL STEEL | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01110 | 0 | 0 | SG7-01110 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Metal Deck --> SG7 | 2 | 0 | 100% | 2022-08-11 | 2022-08-12 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01115 | 0 | 0 | SG7-01115 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Form Pour Strip Concrete Stair South Side ---> SG7 | 5 | 0 | 100% | 2022-10-25 | 2022-10-31 |  | MLJ | Formwork | NB FORMWORK | 03-1000 | 03-1000-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01120 | 0 | 0 | SG7-01120 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Metal Stairs --> SG7 | 2 | 0 | 100% | 2022-08-15 | 2022-08-24 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01125 | 0 | 0 | SG7-01125 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Place Insulation Below First Floor --> SG7 | 5 | 0 | 100% | 2022-06-14 | 2022-06-15 |  | 0 | 0 | 0 | 07-1100 | 07-1100-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01130 | 0 | 0 | SG7-01130 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Place WWF First Floor Slab --> SG7 | 2 | 0 | 100% | 2022-06-21 | 2022-06-22 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01135 | 0 | 0 | SG7-01135 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Pour First Floor Slab --> SG7 | 1 | 0 | 100% | 2022-06-24 | 2022-06-24 |  | MLJ | concrete | NB CONCRETE | 03-1900 | 03-1900-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01150 | 0 | 0 | SG7-01150 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Form First Floor Concrete Walls First Face And Col Encasements--> SG7 | 3 | 0 | 100% | 2022-05-25 | 2022-05-27 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01155 | 0 | 0 | SG7-01155 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Rebar First Floor Concrete Walls --> SG7 | 3 | 0 | 100% | 2022-05-29 | 2022-05-30 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01160 | 0 | 0 | SG7-01160 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Form First Floor Concrete Walls 2Nd Face --> SG7 | 5 | 0 | 100% | 2022-09-07 | 2022-09-09 |  | MLJ | Formwork | NB FORMWORK | 03-1000 | 03-1000-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01165 | 0 | 0 | SG7-01165 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Form, Rebar & Pour Concrete Pads 1st Floor --> SG7 - N/A | 3 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01170 | 0 | 0 | SG7-01170 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Place WWF 2nd Floor Slab --> SG7 | 2 | 0 | 100% | 2022-09-12 | 2022-09-13 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01175 | 0 | 0 | SG7-01175 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Pour 2nd Floor Slab / First Floor Walls & Col Encasements And 1st Floor Pads --> SG7 | 2 | 0 | 100% | 2022-09-14 | 2022-09-14 |  | MLJ | Concrete | NB CONCRETE | 03-1900 | 03-1900-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01180 | 0 | 0 | SG7-01180 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Strip Forms First Floor Walls & Col Encasements And 1st Floor Pads --> SG7 | 3 | 0 | 100% | 2022-09-16 | 2022-09-16 |  | MLJ | Formwork | NB FORMWORK | 03-1000 | 03-1000-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01185 | 0 | 0 | SG7-01185 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Form Concrete Pads 2nd Floor -->SG7 | 2 | 0 | 100% | 2022-09-07 | 2022-09-09 |  | MLJ | Formwork | NB FORMWORK | 03-1000 | 03-1000-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01205 | 0 | 0 | SG7-01205 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Place WWF Roof Slab --> SG7 | 2 | 0 | 100% | 2022-09-12 | 2022-09-13 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01210 | 0 | 0 | SG7-01210 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Pour Roof Slab and 2nd Floor Conc Pads -->SG7 | 1 | 0 | 100% | 2022-09-14 | 2022-09-14 |  | MLJ | Concrete | NB CONCRETE | 03-1900 | 03-1900-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01215 | 0 | 0 | SG7-01215 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Strip Forms Concrete Pads 2nd Floor -->SG7 | 2 | 0 | 100% | 2022-09-16 | 2022-09-16 |  | MLJ | Formwork | NB FORMWORK | 03-1000 | 03-1000-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01225 | 0 | 0 | SG7-01225 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Spray-On Fireproofing on St Stl --> SG7 | 5 | 0 | 100% | 2022-09-20 | 2022-09-23 |  | SIG | 0 | 0 | 0 | 0-SG7
In Progress | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01230 | 0 | 0 | SG7-01230 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Place CMU 1st, 2nd Floors and Roof --> SG7 | 20 | 5 | 75% | 2022-09-26 08:00 | 2022-12-01 17:00 | -7 | FAXA | CMU | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01240 | 0 | 0 | SG7-01240 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Stud Framing 1st, 2nd Floors and Roof --> SG7 | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | -20 | CCC | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01245 | 0 | 0 | SG7-01245 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Doors --> SG7 | 3 | 3 | 0% | 2023-01-10 08:00 | 2023-01-12 17:00 | -25 | CCC | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01250 | 0 | 0 | SG7-01250 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Cast Stone Panels --> SG7 | 1 | 1 | 0% | 2023-01-13 08:00 | 2023-01-13 17:00 | -25 | JMC | CAST STONE | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01255 | 0 | 0 | SG7-01255 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Insulated Metal Panels/Louvers --> SG7 | 10 | 10 | 0% | 2023-01-17 08:00 | 2023-01-30 17:00 | -25 | NAVILLUS | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01260 | 0 | 0 | SG7-01260 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install MEP Roof Penetrations & Drains - SG7 | 1 | 1 | 0% | 2023-01-31 08:00 | 2023-01-31 17:00 | -25 | MLJ | CORING | ROOF PENETRATIONS | 02-3000 | 02-3000-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01265 | 0 | 0 | SG7-01265 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Roofing --> SG7 | 15 | 15 | 0% | 2023-02-01 08:00 | 2023-02-22 17:00 | -25 | TRIANGLE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01270 | 0 | 0 | SG7-01270 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Dunnage Gratings --> SG7 | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | 20 | E&Y | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01275 | 0 | 0 | SG7-01275 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Brick Façade & Stone --> SG7 | 20 | 20 | 0% | 2022-11-29 08:00 | 2022-12-27 17:00 | 68 | FAXA | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01285 | 0 | 0 | SG7-01285 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Flood Vents And Small Louvers --> SG7 | 3 | 3 | 0% | 2023-02-01 08:00 | 2023-02-03 17:00 | 40 | MLJ | FLOOD PROTECTION | FLOOD VENTS | 08-1700 | 08-1700-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01290 | 0 | 0 | SG7-01290 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Stair And Roof Platform Railings --> SG7 | 5 | 5 | 0% | 2022-12-28 08:00 | 2023-01-04 17:00 | 82 | E&Y | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01295 | 0 | 0 | SG7-01295 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Ladders --> SG7 | 3 | 3 | 0% | 2023-01-05 08:00 | 2023-01-09 17:00 | 82 | E&Y | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01305 | 0 | 0 | SG7-01305 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Sheetrock and Stucco --> SG7 | 10 | 10 | 0% | 2023-03-30 08:00 | 2023-04-12 17:00 | 3 | CCC | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01310 | 0 | 0 | SG7-01310 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Ceramic Tile --> SG7 | 2 | 2 | 0% | 2023-04-13 08:00 | 2023-04-14 17:00 | 3 | UNSURE | FLOORING | CERAMIC | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01315 | 0 | 0 | SG7-01315 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Acoustical Ceiling --> SG7 | 2 | 2 | 0% | 2023-04-17 08:00 | 2023-04-18 17:00 | 3 | UNSURE | CEILING | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01320 | 0 | 0 | SG7-01320 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Place Crystaline Waterproofing In Plumbing Shaft --> SG7 | 3 | 0 | 100% | 2022-11-17 | 2022-11-18 |  | 0 | WATERPROOFING | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01325 | 0 | 0 | SG7-01325 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Paint All Areas --> SG7 | 15 | 15 | 0% | 2023-05-25 08:00 | 2023-06-15 17:00 | -30 | GG PAINT | PAINT | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01330 | 0 | 0 | SG7-01330 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Signs --> SG7 | 2 | 2 | 0% | 2023-06-16 08:00 | 2023-06-19 17:00 | -30 | MLJ | SIGNS | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01235 | 0 | 0 | SG7-01235 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Waterproofing to Parapet --> SG7 | 3 | 3 | 0% | 2022-12-02 08:00 | 2022-12-06 17:00 | 1 | UNSURE | WATERPROOFING | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01280 | 0 | 0 | SG7-01280 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Stucco Soffit --> SG7 | 5 | 5 | 0% | 2022-12-28 08:00 | 2023-01-04 17:00 | 68 | CCC | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01317 | 0 | 0 | SG7-01317 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Insulated Metal Panels left out for Access --> SG7 | 5 | 5 | 0% | 2023-05-18 08:00 | 2023-05-24 17:00 | -30 | NAVILLUS | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01092 | 0 | 0 | SG7-01092 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Remaining HW/CW Into SG7 (5' from the building) | 5 | 0 | 100% | 2022-04-04 | 2022-04-08 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01094 | 0 | 0 | SG7-01094 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Remaining Electrical POE Into SG7 | 5 | 0 | 100% | 2022-06-09 | 2022-06-24 10:00 |  | 0 | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.4 | SG7 | SG7 | 03005 | 0 | 0 | SG7-03005 | Construction | Foundation | Construction.4.4.5.4 | Rough-In Plumbing & Appurtenances - Plumbing Shaft | 10 | 10 | 0% | 2022-12-02 08:00 | 2022-12-15 17:00 | -74 | WELKIN | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.4 | SG7 | SG7 | 03010 | 0 | 0 | SG7-03010 | Construction | Foundation | Construction.4.4.5.4 | Install Condensate Pump - Foundation Level | 10 | 10 | 0% | 2022-12-16 08:00 | 2022-12-30 17:00 | -74 | WELKIN | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 03105 | 0 | 0 | SG7-03105 | Construction | 1st Floor | Construction.4.4.5.1 | Rough-In Plumbing Piping & Appurtenances - 1st Floor | 15 | 15 | 0% | 2023-01-03 08:00 | 2023-01-24 17:00 | -74 | WELKIN | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 03110 | 0 | 0 | SG7-03110 | Construction | 1st Floor | Construction.4.4.5.1 | Rig Fuel Oil Tank & Piping - 1st Floor - N/A | 3 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 03125 | 0 | 0 | SG7-03125 | Construction | 1st Floor | Construction.4.4.5.1 | Install Remaining Piping & Appurtenances - 1st Floor | 10 | 10 | 0% | 2023-01-25 08:00 | 2023-02-07 17:00 | -74 | VITAL | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 03130 | 0 | 0 | SG7-03130 | Construction | 1st Floor | Construction.4.4.5.1 | Install FOT Controls - 1st Floor | 20 | 20 | 0% | 2023-02-08 08:00 | 2023-03-08 17:00 | -64 | MEP | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 03135 | 0 | 0 | SG7-03135 | Construction | 1st Floor | Construction.4.4.5.1 | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 0% | 2023-03-09 08:00 | 2023-03-15 17:00 | -64 | WELKIN | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 03140 | 0 | 0 | SG7-03140 | Construction | 1st Floor | Construction.4.4.5.1 | Install Plumbing Equipment - 1st Floor | 15 | 15 | 0% | 2023-01-25 08:00 | 2023-02-14 17:00 | -49 | VITAL | PLUMBING EQUIP | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 03145 | 0 | 0 | SG7-03145 | Construction | 1st Floor | Construction.4.4.5.1 | Mechanical Equipment Start-up & Balance - 1st Floor - N/A | 5 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 03150 | 0 | 0 | SG7-03150 | Construction | 1st Floor | Construction.4.4.5.1 | Plumbing/Mechanical Insulation - 1st Floor | 10 | 10 | 0% | 2023-02-21 08:00 | 2023-03-06 17:00 | -10 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 03107 | 0 | 0 | SG7-03107 | Construction | 1st Floor | Construction.4.4.5.1 | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 15 | 15 | 0% | 2023-01-03 08:00 | 2023-01-24 17:00 | -74 | WELKIN | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 03142 | 0 | 0 | SG7-03142 | Construction | 1st Floor | Construction.4.4.5.1 | Install Mechanical Equipment - 1st Floor | 5 | 5 | 0% | 2023-01-25 08:00 | 2023-01-31 17:00 | -39 | WELKIN | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 03205 | 0 | 0 | SG7-03205 | Construction | 2nd Floor | Construction.4.4.5.2 | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 15 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 03225 | 0 | 0 | SG7-03225 | Construction | 2nd Floor | Construction.4.4.5.2 | Install Remaining Piping & Appurtenances - 2nd Floor | 20 | 20 | 0% | 2023-03-02 08:00 | 2023-03-29 17:00 | -74 | VITAL | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 03235 | 0 | 0 | SG7-03235 | Construction | 2nd Floor | Construction.4.4.5.2 | Perform Hydrostatic Testing - 2nd Floor | 5 | 5 | 0% | 2023-03-30 08:00 | 2023-04-05 17:00 | -74 | WELKIN | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 03240 | 0 | 0 | SG7-03240 | Construction | 2nd Floor | Construction.4.4.5.2 | Install Plumbing Equipment - 2nd Floor | 15 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 03245 | 0 | 0 | SG7-03245 | Construction | 2nd Floor | Construction.4.4.5.2 | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 0% | 2023-04-06 08:00 | 2023-04-19 17:00 | -62 | WELKIN | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 03250 | 0 | 0 | SG7-03250 | Construction | 2nd Floor | Construction.4.4.5.2 | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 0% | 2023-04-20 08:00 | 2023-05-17 17:00 | -62 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 03207 | 0 | 0 | SG7-03207 | Construction | 2nd Floor | Construction.4.4.5.2 | Rough-In Mechanical Piping & Appurtenances - 2nd Floor | 15 | 15 | 0% | 2023-02-08 08:00 | 2023-03-01 17:00 | -74 | WELKIN | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.2 | SG7 | SG7 | 03242 | 0 | 0 | SG7-03242 | Construction | 2nd Floor | Construction.4.4.5.2 | Install Mechanical Equipment - 2nd Floor | 10 | 10 | 0% | 2023-03-02 08:00 | 2023-03-15 17:00 | -64 | WELKIN | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 03405 | 0 | 0 | SG7-03405 | Construction | Roof | Construction.4.4.5.3 | Install Ductwork & Appurtenances - Roof - N/A | 4 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 03410 | 0 | 0 | SG7-03410 | Construction | Roof | Construction.4.4.5.3 | Install & Connect Exhaust Fans - Roof - N/A | 6 | 0 | 100% | 2021-02-01 | 2021-02-01 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.5.3 | SG7 | SG7 | 03415 | 0 | 0 | SG7-03415 | Construction | Roof | Construction.4.4.5.3 | Install Insulation - Roof - N/A | 15 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.6 | SG7 | SG7 | 03505 | 0 | 0 | SG7-03505 | Construction | Testing & Start-Up | Construction.4.4.5.6 | DOB Mechanical/Plumbing Inspection - SG7 | 4 | 4 | 0% | 2023-05-18 08:00 | 2023-05-23 17:00 | -62 | UNSURE | INSPECTION | INSPECTION | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.6 | SG7 | SG7 | 03510 | 0 | 0 | SG7-03510 | Construction | Testing & Start-Up | Construction.4.4.5.6 | Perform Start-Up Testing - SG7 | 10 | 10 | 0% | 2023-09-20 08:00 | 2023-10-03 17:00 | -109 | UNSURE | STARTUP | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.6 | SG7 | SG7 | 03520 | 0 | 0 | SG7-03520 | Construction | Testing & Start-Up | Construction.4.4.5.6 | Perform Punch List - Electrical/Mechanical/Plumbing Work - SG7 | 5 | 5 | 0% | 2023-10-04 08:00 | 2023-10-10 17:00 | -109 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.6 | SG7 | SG7 | 03530 | 0 | 0 | SG7-03530 | Construction | Testing & Start-Up | Construction.4.4.5.6 | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - SG7 | 4 | 4 | 0% | 2023-10-12 08:00 | 2023-10-18 17:00 | -104 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.6 | SG7 | SG7 | 03525 | 0 | 0 | SG7-03525 | Construction | Testing & Start-Up | Construction.4.4.5.6 | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - SG7 | 1 | 1 | 0% | 2023-10-11 08:00 | 2023-10-11 17:00 | -109 | FSE | INSPECTION | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.7.4.1 | SG1 | SG1 | 01005 | 0 | 0 | SG1-01005 | Construction | Asbestos Abatement | Construction.4.7.4.1 | Asbestos Abatement - gaskets - cellar - SG1 | 3 | 3 | 0% | 2023-10-19 08:00 | 2023-10-23 17:00 | -132 | ATCO | ABESTOS | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.1 | SG1 | SG1 | 01010 | 0 | 0 | SG1-01010 | Construction | Asbestos Abatement | Construction.4.7.4.1 | Asbestos Abatement - wire insulation - cellar --> SG1 | 3 | 0 | 100% | 2021-07-12 08:00 | 2021-07-16 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.1 | SG1 | SG1 | 01015 | 0 | 0 | SG1-01015 | Construction | Asbestos Abatement | Construction.4.7.4.1 | Asbestos Abatement - flooring materials at slab penetrations - cellar --> SG1 - N/A | 3 | 0 | 100% | 2022-03-25 08:00 | 2022-03-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.1 | SG1 | SG1 | 01020 | 0 | 0 | SG1-01020 | Construction | Asbestos Abatement | Construction.4.7.4.1 | Asbestos Abatement - pipe insulation - cellar --> SG1 | 3 | 0 | 100% | 2021-07-12 08:00 | 2021-07-16 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.1 | SG1 | SG1 | 01025 | 0 | 0 | SG1-01025 | Construction | Asbestos Abatement | Construction.4.7.4.1 | Asbestos Abatement - Window Sills - 1st Floor --> SG1 | 5 | 0 | 100% | 2022-09-26 | 2022-09-26 |  | ATCO | ABESTOS | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.1 | SG1 | SG1 | 01030 | 0 | 0 | SG1-01030 | Construction | Asbestos Abatement | Construction.4.7.4.1 | Asbestos Abatement - caulk @ windows and areaway vents --> SG1 | 5 | 0 | 100% | 2022-09-27 | 2022-09-27 |  | ATCO | ABESTOS | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.2 | SG1 | SG1 | 01105 | 0 | 0 | SG1-01105 | Construction | Interior Demolition | Construction.4.7.4.2 | Selective Demo (Plaster walls, Doors, windows) - Cellar --> SG1 | 10 | 0 | 100% | 2021-04-25 | 2022-09-30 |  | MLJ | DEMO | DEMO CELLAR WALLS | 02-6005 | 02-6005-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.2 | SG1 | SG1 | 01110 | 0 | 0 | SG1-01110 | Construction | Interior Demolition | Construction.4.7.4.2 | Selective Demo (Doors, windows) - 1st Floor --> SG1 | 5 | 0 | 100% | 2022-10-03 | 2022-10-07 |  | MLJ | DEMO | DEMO DOORS WINDOWS | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.2 | SG1 | SG1 | 01115 | 0 | 0 | SG1-01115 | Construction | Interior Demolition | Construction.4.7.4.2 | Selective Demo (Areaway drain, slab, wall) --> SG1 | 10 | 0 | 100% | 2022-08-26 | 2022-09-02 |  | MLJ | DEMO | DEMO AREAWAY | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.2 | SG1 | SG1 | 01205 | 0 | 0 | SG1-01205 | Construction | Interior Demolition | Construction.4.7.4.2 | Selective Demo (Existing Ramp, railing) - 1st Floor --> SG1 | 5 | 0 | 100% | 2022-09-02 | 2022-10-04 |  | MLJ | DEMO | DEMO RAMP | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.2 | SG1 | SG1 | 01210 | 0 | 0 | SG1-01210 | Construction | Interior Demolition | Construction.4.7.4.2 | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> SG1 | 5 | 0 | 100% | 2022-05-09 | 2022-05-16 |  | MLJ | DEMO | DEMO SLAB OPEN FOR MECH | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.2 | SG1 | SG1 | 01215 | 0 | 0 | SG1-01215 | Construction | Interior Demolition | Construction.4.7.4.2 | Selective Demo - 2nd Floor Apartment for Electrical Room --> SG1 - N/A | 5 | 0 | 100% | 2021-08-25 08:00 | 2021-08-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.4 | SG1 | SG1 | 01310 | 0 | 0 | SG1-01310 | Construction | Interior Renovations | Construction.4.7.4.4 | Make openings in floor for conduit penetrations - 1st floor apartments --> SG1 - N/A | 5 | 0 | 100% | 2021-08-25 08:00 | 2021-08-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.4 | SG1 | SG1 | 01315 | 0 | 0 | SG1-01315 | Construction | Interior Renovations | Construction.4.7.4.4 | Install beams below floor - 1st floor apartments --> SG1 - N/A | 5 | 0 | 100% | 2021-08-25 08:00 | 2021-08-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.4 | SG1 | SG1 | 01320 | 0 | 0 | SG1-01320 | Construction | Interior Renovations | Construction.4.7.4.4 | Install FRP around floor openings - 1st floor apartments --> SG1 - N/A | 5 | 0 | 100% | 2021-08-25 08:00 | 2021-08-25 17:00 |  | 0 | FRP | 0 | 03-6000 | 03-6000-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.4 | SG1 | SG1 | 01325 | 0 | 0 | SG1-01325 | Construction | Interior Renovations | Construction.4.7.4.4 | Frame walls / install door for electrical room - 1st floor --> SG1 - N/A | 3 | 0 | 100% | 2021-08-25 08:00 | 2021-08-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.4 | SG1 | SG1 | 01330 | 0 | 0 | SG1-01330 | Construction | Interior Renovations | Construction.4.7.4.4 | Install drywall / tape / spackle - electrical room - 1st floor --> SG1 - N/A | 5 | 0 | 100% | 2021-08-25 08:00 | 2021-08-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.4 | SG1 | SG1 | 01335 | 0 | 0 | SG1-01335 | Construction | Interior Renovations | Construction.4.7.4.4 | Paint walls and seal floor electrical room - 1st Floor --> SG1 - N/A | 10 | 0 | 100% | 2021-08-25 08:00 | 2021-08-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.4 | SG1 | SG1 | 01340 | 0 | 0 | SG1-01340 | Construction | Interior Renovations | Construction.4.7.4.4 | Install VCT @ electrical room - 1st Floor --> SG1 - N/A | 2 | 0 | 100% | 2021-08-25 08:00 | 2021-08-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.1 | SG1 | SG1 | 01405 | 0 | 0 | SG1-01405 | Construction | East Elevation | Construction.4.7.4.EFPC.1 | Excavate at Curtain Wall for flood protection (East Side) --> SG1 | 8 | 0 | 100% | 2022-07-21 08:00 | 2022-08-04 17:00 |  | MLJ | Excavation | EB EXC | 31-1000 | 31-1000-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.1 | SG1 | SG1 | 01410 | 0 | 0 | SG1-01410 | Construction | East Elevation | Construction.4.7.4.EFPC.1 | Form concrete footings at Curtain Wall for flood protection (East Side) --> SG1 | 10 | 0 | 100% | 2022-09-26 | 2022-10-07 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.1 | SG1 | SG1 | 01415 | 0 | 0 | SG1-01415 | Construction | East Elevation | Construction.4.7.4.EFPC.1 | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> SG1 | 5 | 0 | 100% | 2022-10-10 | 2022-10-14 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.1 | SG1 | SG1 | 01420 | 0 | 0 | SG1-01420 | Construction | East Elevation | Construction.4.7.4.EFPC.1 | Pour concrete footings at Curtain Wall for flood protection (East Side) --> SG1 | 4 | 0 | 100% | 2022-10-18 | 2022-10-18 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.1 | SG1 | SG1 | 01425 | 0 | 0 | SG1-01425 | Construction | East Elevation | Construction.4.7.4.EFPC.1 | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> SG1 | 5 | 0 | 100% | 2022-10-19 | 2022-11-02 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.1 | SG1 | SG1 | 01430 | 0 | 0 | SG1-01430 | Construction | East Elevation | Construction.4.7.4.EFPC.1 | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG1 | 8 | 0 | 100% | 2022-11-14 | 2022-11-17 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.1 | SG1 | SG1 | 01435 | 0 | 0 | SG1-01435 | Construction | East Elevation | Construction.4.7.4.EFPC.1 | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG1 | 6 | 0 | 100% | 2022-11-14 | 2022-11-16 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.1 | SG1 | SG1 | 01440 | 0 | 0 | SG1-01440 | Construction | East Elevation | Construction.4.7.4.EFPC.1 | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG1 | 4 | 0 | 100% | 2022-11-18 | 2022-11-18 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.1 | SG1 | SG1 | 01445 | 0 | 0 | SG1-01445 | Construction | East Elevation | Construction.4.7.4.EFPC.1 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG1 | 4 | 0 | 100% | 2022-11-21 | 2022-11-22 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.1 | SG1 | SG1 | 01450 | 0 | 0 | SG1-01450 | Construction | East Elevation | Construction.4.7.4.EFPC.1 | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> SG1 | 4 | 4 | 0% | 2022-12-02 08:00 | 2022-12-07 17:00 | -34 | FAXA | CMU | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.1 | SG1 | SG1 | 01455 | 0 | 0 | SG1-01455 | Construction | East Elevation | Construction.4.7.4.EFPC.1 | Backfill at Curtain Wall for flood protection (East Side) --> SG1 | 5 | 5 | 0% | 2022-12-08 08:00 | 2022-12-14 17:00 | -34 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.1 | SG1 | SG1 | 01460 | 0 | 0 | SG1-01460 | Construction | East Elevation | Construction.4.7.4.EFPC.1 | Form for slab at Curtain Wall for flood protection (East Side) --> SG1 | 4 | 4 | 0% | 2022-12-15 08:00 | 2022-12-20 17:00 | -34 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.1 | SG1 | SG1 | 01465 | 0 | 0 | SG1-01465 | Construction | East Elevation | Construction.4.7.4.EFPC.1 | Rebar & inserts for slab at Curtain Wall for flood protection (East Side) --> SG1 | 6 | 6 | 0% | 2022-12-21 08:00 | 2022-12-29 17:00 | -34 | TONAGE | REBAR | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.1 | SG1 | SG1 | 01470 | 0 | 0 | SG1-01470 | Construction | East Elevation | Construction.4.7.4.EFPC.1 | Pour slab at Curtain Wall for flood protection (East Side) --> SG1 | 4 | 4 | 0% | 2022-12-30 08:00 | 2023-01-05 17:00 | -34 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.1 | SG1 | SG1 | 01475 | 0 | 0 | SG1-01475 | Construction | East Elevation | Construction.4.7.4.EFPC.1 | Strip Forms for slab at Curtain Wall for flood protection (East Side) --> SG1 | 2 | 2 | 0% | 2023-01-06 08:00 | 2023-01-09 17:00 | -31 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.1 | SG1 | SG1 | 01480 | 0 | 0 | SG1-01480 | Construction | East Elevation | Construction.4.7.4.EFPC.1 | Backfill surounding area at Curtain Wall for flood protection (East Side) --> SG1 | 4 | 4 | 0% | 2023-01-13 08:00 | 2023-01-19 17:00 | -34 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.2 | SG1 | SG1 | 01505 | 0 | 0 | SG1-01505 | Construction | South Elevation | Construction.4.7.4.EFPC.2 | Excavate at Curtain Wall for flood protection (South Side) --> SG1 | 7 | 0 | 100% | 2022-10-25 08:00 | 2022-10-26 |  | MLJ | Excavation | EB EXC | 31-1000 | 31-1000-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.2 | SG1 | SG1 | 01510 | 0 | 0 | SG1-01510 | Construction | South Elevation | Construction.4.7.4.EFPC.2 | Form concrete footings at Curtain Wall for flood protection (South Side) --> SG1 | 9 | 0 | 100% | 2022-11-14 | 2022-11-17 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.2 | SG1 | SG1 | 01515 | 0 | 0 | SG1-01515 | Construction | South Elevation | Construction.4.7.4.EFPC.2 | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> SG1 | 4 | 0 | 100% | 2022-11-14 | 2022-11-16 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.2 | SG1 | SG1 | 01520 | 0 | 0 | SG1-01520 | Construction | South Elevation | Construction.4.7.4.EFPC.2 | Pour concrete footings at Curtain Wall for flood protection (South Side) --> SG1 | 3 | 0 | 100% | 2022-11-18 | 2022-11-18 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.2 | SG1 | SG1 | 01525 | 0 | 0 | SG1-01525 | Construction | South Elevation | Construction.4.7.4.EFPC.2 | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> SG1 | 4 | 0 | 100% | 2022-11-19 08:00 | 2022-11-24 17:00 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.2 | SG1 | SG1 | 01530 | 0 | 0 | SG1-01530 | Construction | South Elevation | Construction.4.7.4.EFPC.2 | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG1 | 7 | 0 | 100% | 2022-11-14 | 2022-11-17 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.2 | SG1 | SG1 | 01535 | 0 | 0 | SG1-01535 | Construction | South Elevation | Construction.4.7.4.EFPC.2 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG1 | 5 | 0 | 100% | 2022-11-14 | 2022-11-16 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.2 | SG1 | SG1 | 01540 | 0 | 0 | SG1-01540 | Construction | South Elevation | Construction.4.7.4.EFPC.2 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG1 | 3 | 0 | 100% | 2022-11-18 | 2022-11-18 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.2 | SG1 | SG1 | 01545 | 0 | 0 | SG1-01545 | Construction | South Elevation | Construction.4.7.4.EFPC.2 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG1 | 3 | 0 | 100% | 2022-11-21 | 2022-11-22 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.2 | SG1 | SG1 | 01550 | 0 | 0 | SG1-01550 | Construction | South Elevation | Construction.4.7.4.EFPC.2 | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> SG1 | 3 | 3 | 0% | 2022-11-25 08:00 | 2022-11-29 17:00 | -3 | FAXA | CMU | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.2 | SG1 | SG1 | 01555 | 0 | 0 | SG1-01555 | Construction | South Elevation | Construction.4.7.4.EFPC.2 | Backfill at Curtain Wall for flood protection (South Side) --> SG1 | 4 | 4 | 0% | 2022-11-30 08:00 | 2022-12-05 17:00 | -3 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.3 | SG1 | SG1 | 01605 | 0 | 0 | SG1-01605 | Construction | North Elevation | Construction.4.7.4.EFPC.3 | Excavate at Curtain Wall for flood protection (North Side) --> SG1 | 7 | 0 | 100% | 2022-08-25 | 2022-08-28 |  | MLJ | Excavation | EB EXC | 31-1000 | 31-1000-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.3 | SG1 | SG1 | 01610 | 0 | 0 | SG1-01610 | Construction | North Elevation | Construction.4.7.4.EFPC.3 | Form concrete footings at Curtain Wall for flood protection (North Side) --> SG1 | 9 | 0 | 100% | 2022-08-28 | 2022-09-02 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.3 | SG1 | SG1 | 01615 | 0 | 0 | SG1-01615 | Construction | North Elevation | Construction.4.7.4.EFPC.3 | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> SG1 | 4 | 0 | 100% | 2022-09-05 | 2022-09-06 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.3 | SG1 | SG1 | 01620 | 0 | 0 | SG1-01620 | Construction | North Elevation | Construction.4.7.4.EFPC.3 | Pour concrete footings at Curtain Wall for flood protection (North Side) --> SG1 | 3 | 0 | 100% | 2022-09-07 | 2022-09-07 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.3 | SG1 | SG1 | 01625 | 0 | 0 | SG1-01625 | Construction | North Elevation | Construction.4.7.4.EFPC.3 | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> SG1 | 4 | 0 | 100% | 2022-09-08 | 2022-09-09 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.3 | SG1 | SG1 | 01630 | 0 | 0 | SG1-01630 | Construction | North Elevation | Construction.4.7.4.EFPC.3 | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG1 | 7 | 0 | 100% | 2022-09-12 | 2022-09-13 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.3 | SG1 | SG1 | 01635 | 0 | 0 | SG1-01635 | Construction | North Elevation | Construction.4.7.4.EFPC.3 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG1 | 5 | 0 | 100% | 2022-09-14 | 2022-09-15 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.3 | SG1 | SG1 | 01640 | 0 | 0 | SG1-01640 | Construction | North Elevation | Construction.4.7.4.EFPC.3 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG1 | 3 | 0 | 100% | 2022-09-16 | 2022-09-16 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.3 | SG1 | SG1 | 01645 | 0 | 0 | SG1-01645 | Construction | North Elevation | Construction.4.7.4.EFPC.3 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG1 | 3 | 0 | 100% | 2022-09-26 08:00 | 2022-09-28 17:00 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.3 | SG1 | SG1 | 01650 | 0 | 0 | SG1-01650 | Construction | North Elevation | Construction.4.7.4.EFPC.3 | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> SG1 | 3 | 0 | 100% | 2022-09-29 08:00 | 2022-10-03 17:00 |  | FAXA | CMU | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.3 | SG1 | SG1 | 01655 | 0 | 0 | SG1-01655 | Construction | North Elevation | Construction.4.7.4.EFPC.3 | Backfill at Curtain Wall for flood protection (North Side) --> SG1 | 4 | 0 | 100% | 2022-10-04 08:00 | 2022-10-07 17:00 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.4 | SG1 | SG1 | 01705 | 0 | 0 | SG1-01705 | Construction | West Elevation | Construction.4.7.4.EFPC.4 | Excavate at Curtain Wall for flood protection (West Side) --> SG1 | 8 | 0 | 100% | 2022-09-26 08:00 | 2022-10-05 17:00 |  | MLJ | Excavation | EB EXC | 31-1000 | 31-1000-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.4 | SG1 | SG1 | 01710 | 0 | 0 | SG1-01710 | Construction | West Elevation | Construction.4.7.4.EFPC.4 | Form concrete footings at Curtain Wall for flood protection (West Side) --> SG1 | 10 | 0 | 100% | 2022-10-06 08:00 | 2022-10-18 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.4 | SG1 | SG1 | 01715 | 0 | 0 | SG1-01715 | Construction | West Elevation | Construction.4.7.4.EFPC.4 | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> SG1 | 5 | 0 | 100% | 2022-10-19 | 2022-10-21 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.4 | SG1 | SG1 | 01720 | 0 | 0 | SG1-01720 | Construction | West Elevation | Construction.4.7.4.EFPC.4 | Pour concrete footings at Curtain Wall for flood protection (West Side) --> SG1 | 4 | 0 | 100% | 2022-10-24 | 2022-10-24 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.4 | SG1 | SG1 | 01725 | 0 | 0 | SG1-01725 | Construction | West Elevation | Construction.4.7.4.EFPC.4 | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> SG1 | 5 | 0 | 100% | 2022-10-25 | 2022-10-28 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.4 | SG1 | SG1 | 01730 | 0 | 0 | SG1-01730 | Construction | West Elevation | Construction.4.7.4.EFPC.4 | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG1 | 8 | 0 | 100% | 2022-11-14 | 2022-11-17 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.4 | SG1 | SG1 | 01735 | 0 | 0 | SG1-01735 | Construction | West Elevation | Construction.4.7.4.EFPC.4 | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG1 | 6 | 0 | 100% | 2022-11-14 | 2022-11-16 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.4 | SG1 | SG1 | 01740 | 0 | 0 | SG1-01740 | Construction | West Elevation | Construction.4.7.4.EFPC.4 | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG1 | 4 | 0 | 100% | 2022-11-18 | 2022-11-18 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.4 | SG1 | SG1 | 01745 | 0 | 0 | SG1-01745 | Construction | West Elevation | Construction.4.7.4.EFPC.4 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG1 | 4 | 0 | 100% | 2022-11-21 | 2022-11-22 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.4 | SG1 | SG1 | 01750 | 0 | 0 | SG1-01750 | Construction | West Elevation | Construction.4.7.4.EFPC.4 | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> SG1 | 4 | 4 | 0% | 2022-11-25 08:00 | 2022-11-30 17:00 | -29 | FAXA | CMU | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.4 | SG1 | SG1 | 01755 | 0 | 0 | SG1-01755 | Construction | West Elevation | Construction.4.7.4.EFPC.4 | Backfill at Curtain Wall for flood protection (West Side) --> SG1 | 5 | 5 | 0% | 2022-12-01 08:00 | 2022-12-07 17:00 | -29 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.4 | SG1 | SG1 | 01760 | 0 | 0 | SG1-01760 | Construction | West Elevation | Construction.4.7.4.EFPC.4 | Form for slab at Curtain Wall for flood protection (West Side) --> SG1 | 4 | 4 | 0% | 2022-12-08 08:00 | 2022-12-13 17:00 | -29 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.4 | SG1 | SG1 | 01765 | 0 | 0 | SG1-01765 | Construction | West Elevation | Construction.4.7.4.EFPC.4 | Rebar & inserts for slab at Curtain Wall for flood protection (West Side) --> SG1 | 6 | 6 | 0% | 2022-12-14 08:00 | 2022-12-21 17:00 | -29 | TONAGE | REBAR | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.4 | SG1 | SG1 | 01770 | 0 | 0 | SG1-01770 | Construction | West Elevation | Construction.4.7.4.EFPC.4 | Pour slab at Curtain Wall for flood protection (West Side) --> SG1 | 4 | 4 | 0% | 2022-12-22 08:00 | 2022-12-28 17:00 | -29 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.4 | SG1 | SG1 | 01775 | 0 | 0 | SG1-01775 | Construction | West Elevation | Construction.4.7.4.EFPC.4 | Strip Forms for slab at Curtain Wall for flood protection (West Side) --> SG1 | 2 | 2 | 0% | 2022-12-29 08:00 | 2022-12-30 17:00 | -26 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.4 | SG1 | SG1 | 01780 | 0 | 0 | SG1-01780 | Construction | West Elevation | Construction.4.7.4.EFPC.4 | Backfill surounding area at Curtain Wall for flood protection (West Side) --> SG1 | 4 | 4 | 0% | 2023-01-05 08:00 | 2023-01-10 17:00 | -28 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.5 | SG1 | SG1 | 01805 | 0 | 0 | SG1-01805 | Construction | Concrete Shelf Construction | Construction.4.7.4.EFPC.5 | Excavate for concrete shelf around bldg perimeter --> SG1 | 10 | 0 | 100% | 2022-08-25 | 2022-08-28 |  | MLJ | Excavation | EB EXC | 31-1000 | 31-1000-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.5 | SG1 | SG1 | 01810 | 0 | 0 | SG1-01810 | Construction | Concrete Shelf Construction | Construction.4.7.4.EFPC.5 | Place rebar for concrete shelf around bldg perimeter --> SG1 | 5 | 0 | 100% | 2022-08-28 | 2022-09-02 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.5 | SG1 | SG1 | 01815 | 0 | 0 | SG1-01815 | Construction | Concrete Shelf Construction | Construction.4.7.4.EFPC.5 | Pour concrete shelf around bldg perimeter --> SG1 | 5 | 0 | 100% | 2022-09-05 | 2022-09-06 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.5 | SG1 | SG1 | 01820 | 0 | 0 | SG1-01820 | Construction | Concrete Shelf Construction | Construction.4.7.4.EFPC.5 | Place infill concrete in area ways around bldg perimeter --> SG1 | 5 | 0 | 100% | 2022-09-26 08:00 | 2022-09-29 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.5 | SG1 | SG1 | 01825 | 0 | 0 | SG1-01825 | Construction | Concrete Shelf Construction | Construction.4.7.4.EFPC.5 | Place waterproofing on concrete shelf around bldg perimeter --> SG1 | 10 | 0 | 100% | 2022-09-30 | 2022-10-04 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.5 | SG1 | SG1 | 01830 | 0 | 0 | SG1-01830 | Construction | Concrete Shelf Construction | Construction.4.7.4.EFPC.5 | Place CMU around bldg perimeter --SG1 | 15 | 0 | 100% | 2022-10-05 | 2022-10-21 |  | FAXA | CMU | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.5 | SG1 | SG1 | 01835 | 0 | 0 | SG1-01835 | Construction | Concrete Shelf Construction | Construction.4.7.4.EFPC.5 | Place waterproofing on CMU around bldg perimeter --> SG1 | 10 | 0 | 100% | 2022-10-24 | 2022-11-07 |  | 0 | WATERPROOFING | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.5 | SG1 | SG1 | 01840 | 0 | 0 | SG1-01840 | Construction | Concrete Shelf Construction | Construction.4.7.4.EFPC.5 | Place window frames around bldg perimeter --> SG1 | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | -16 | MLJ | CONCRETE SHELF | PLACE WINDOWS | 0 | 0-SG1
In Progress | CI NYCHA Update #22.Construction.4.7.4.EFPC.5 | SG1 | SG1 | 01845 | 0 | 0 | SG1-01845 | Construction | Concrete Shelf Construction | Construction.4.7.4.EFPC.5 | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> SG1 | 20 | 5 | 75% | 2022-10-26 | 2022-12-15 17:00 | -16 | FAXA | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.5 | SG1 | SG1 | 01850 | 0 | 0 | SG1-01850 | Construction | Concrete Shelf Construction | Construction.4.7.4.EFPC.5 | Backfill around bdg perimeter --> SG1 | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -16 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.5 | SG1 | SG1 | 01855 | 0 | 0 | SG1-01855 | Construction | Concrete Shelf Construction | Construction.4.7.4.EFPC.5 | Place frame / stucco / and signs at entrances --> SG1 | 4 | 4 | 0% | 2022-12-23 08:00 | 2022-12-29 17:00 | 90 | CCC | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.5 | SG1 | SG1 | 01860 | 0 | 0 | SG1-01860 | Construction | Concrete Shelf Construction | Construction.4.7.4.EFPC.5 | Place window floodgates at windows --> SG1 | 5 | 5 | 0% | 2022-12-30 08:00 | 2023-01-06 17:00 | 90 | MLJ | FLOOD PROTECTION | FLOOD WINDOWS | 10-1400 | 10-1400-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.5 | SG1 | SG1 | 01865 | 0 | 0 | SG1-01865 | Construction | Concrete Shelf Construction | Construction.4.7.4.EFPC.5 | Install signs --> SG1 | 3 | 3 | 0% | 2023-01-09 08:00 | 2023-01-11 17:00 | 90 | MLJ | SIGNS | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.5 | SG1 | SG1 | 01350 | 0 | 0 | SG1-01350 | Construction | Boiler Room Construction | Construction.4.7.4.5 | Drill dowels and place rebar for boiler room concrete walls --> SG1 | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 75 | MLJ | 0 | DRILL & DOWEL | 03-1400 | 03-1400-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.5 | SG1 | SG1 | 01355 | 0 | 0 | SG1-01355 | Construction | Boiler Room Construction | Construction.4.7.4.5 | Form boiler room concrete walls --> SG1 | 5 | 5 | 0% | 2022-12-02 08:00 | 2022-12-08 17:00 | 80 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.5 | SG1 | SG1 | 01360 | 0 | 0 | SG1-01360 | Construction | Boiler Room Construction | Construction.4.7.4.5 | Pour Concrete boiler room walls --> SG1 | 2 | 2 | 0% | 2022-12-09 08:00 | 2022-12-12 17:00 | 80 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.5 | SG1 | SG1 | 01365 | 0 | 0 | SG1-01365 | Construction | Boiler Room Construction | Construction.4.7.4.5 | Strip Forms boiler room concrete walls --> SG1 | 3 | 3 | 0% | 2022-12-13 08:00 | 2022-12-15 17:00 | 82 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.5 | SG1 | SG1 | 01370 | 0 | 0 | SG1-01370 | Construction | Boiler Room Construction | Construction.4.7.4.5 | Place crystaline waterproofing on perimeter walls - cellar --> SG1 | 10 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0 | WATERPROOFING | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.6 | SG1 | SG1 | 01385 | 0 | 0 | SG1-01385 | Construction | Elevator Refurbishment | Construction.4.7.4.6 | Refurbish Elevator 1 --> SG1 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.6 | SG1 | SG1 | 01390 | 0 | 0 | SG1-01390 | Construction | Elevator Refurbishment | Construction.4.7.4.6 | Refurbish Elevator 2 --> SG1 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.6 | SG1 | SG1 | 01380 | 0 | 0 | SG1-01380 | Construction | Elevator Refurbishment | Construction.4.7.4.6 | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.7 | SG1 | SG1 | 09005 | 0 | 0 | SG1-09005 | Construction | Civil/Architectural Inspections | Construction.4.7.4.7 | Perform Inspections & Issue Punch List | 5 | 5 | 0% | 2023-10-24 08:00 | 2023-10-30 17:00 | -132 | MLJ | PUNCH LIST | INSPECTION | 99-8200 | 99-8200-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.7 | SG1 | SG1 | 09010 | 0 | 0 | SG1-09010 | Construction | Civil/Architectural Inspections | Construction.4.7.4.7 | Perform Punch List | 10 | 10 | 0% | 2023-10-31 08:00 | 2023-11-15 17:00 | -117 | MLJ | PUNCH LIST | 0 | 99-8200 | 99-8200-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.2 | SG1 | SG1 | 01220 | 0 | 0 | SG1-01220 | Construction | Interior Demolition | Construction.4.7.4.2 | Selective Demo (Pumps etc..) - Cellar --> SG1 | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 11 | MLJ | DEMO | DEMO PUMPS | 02-6010 | 02-6010-SG1
Not Started | CI NYCHA Update #22.Construction.4.3.5.1 | SG3 | SG3 | 01005 | 0 | 0 | SG3-01005 | Construction | Asbestos Abatement | Construction.4.3.5.1 | Asbestos Abatement - gaskets - cellar - SG3 | 3 | 3 | 0% | 2023-10-25 08:00 | 2023-10-27 17:00 | -136 | ATCO | ABESTOS | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.1 | SG3 | SG3 | 01010 | 0 | 0 | SG3-01010 | Construction | Asbestos Abatement | Construction.4.3.5.1 | Asbestos Abatement - wire insulation - cellar --> SG3 | 3 | 0 | 100% | 2021-11-08 08:00 | 2021-11-12 17:00 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.1 | SG3 | SG3 | 01015 | 0 | 0 | SG3-01015 | Construction | Asbestos Abatement | Construction.4.3.5.1 | Asbestos Abatement - flooring materials at slab penetrations - cellar --> SG3 | 3 | 0 | 100% | 2022-06-27 08:00 | 2022-06-28 17:00 |  | ATCO | ABESTOS | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.1 | SG3 | SG3 | 01020 | 0 | 0 | SG3-01020 | Construction | Asbestos Abatement | Construction.4.3.5.1 | Asbestos Abatement - pipe insulation - cellar --> SG3 | 3 | 0 | 100% | 2021-11-08 08:00 | 2021-11-12 17:00 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.1 | SG3 | SG3 | 01025 | 0 | 0 | SG3-01025 | Construction | Asbestos Abatement | Construction.4.3.5.1 | Asbestos Abatement - Window Sills - 1st Floor --> SG3 | 5 | 0 | 100% | 2022-10-01 | 2022-10-01 |  | ATCO | ABESTOS | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.1 | SG3 | SG3 | 01030 | 0 | 0 | SG3-01030 | Construction | Asbestos Abatement | Construction.4.3.5.1 | Asbestos Abatement - caulk @ windows and areaway vents --> SG3 | 5 | 0 | 100% | 2022-10-02 | 2022-10-02 |  | ATCO | ABESTOS | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.2 | SG3 | SG3 | 01105 | 0 | 0 | SG3-01105 | Construction | Interior Demolition | Construction.4.3.5.2 | Selective Demo (Plaster walls, Doors, windows) - Cellar --> SG3 | 10 | 0 | 100% | 2021-05-06 | 2022-08-01 |  | MLJ | DEMO | DEMO CELLAR WALLS | 02-6005 | 02-6005-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.2 | SG3 | SG3 | 01110 | 0 | 0 | SG3-01110 | Construction | Interior Demolition | Construction.4.3.5.2 | Selective Demo (Doors, windows) - 1st Floor --> SG3 | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | -36 | MLJ | DEMO | DEMO DOORS WINDOWS | 02-6015 | 02-6015-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.2 | SG3 | SG3 | 01115 | 0 | 0 | SG3-01115 | Construction | Interior Demolition | Construction.4.3.5.2 | Selective Demo (Areaway drain, slab, wall) --> SG3 | 10 | 0 | 100% | 2022-09-26 08:00 | 2022-10-07 17:00 |  | MLJ | DEMO | DEMO AREAWAY | 0 | 0-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.2 | SG3 | SG3 | 01205 | 0 | 0 | SG3-01205 | Construction | Interior Demolition | Construction.4.3.5.2 | Selective Demo (Existing Ramp, railing) - 1st Floor --> SG3 | 5 | 0 | 100% | 2022-10-17 08:00 | 2022-10-21 17:00 |  | MLJ | DEMO | DEMO RAMP | 0 | 0-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.2 | SG3 | SG3 | 01210 | 0 | 0 | SG3-01210 | Construction | Interior Demolition | Construction.4.3.5.2 | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> SG3 | 5 | 0 | 100% | 2022-10-18 08:00 | 2022-10-21 |  | MLJ | DEMO | DEMO SLAB OPEN FOR MECH | 02-3000 | 02-3000-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.2 | SG3 | SG3 | 01215 | 0 | 0 | SG3-01215 | Construction | Interior Demolition | Construction.4.3.5.2 | Selective Demo - 2nd Floor Apartment for Electrical Room --> SG3 | 5 | 0 | 100% | 2022-01-27 08:00 | 2022-02-02 17:00 |  | MLJ | DEMO | DEMO 2ND FLOOR | 02-6060 | 02-6060-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.4 | SG3 | SG3 | 01310 | 0 | 0 | SG3-01310 | Construction | Interior Renovations | Construction.4.3.5.4 | Make openings in floor for conduit penetrations - 2nd floor apartments --> SG3 | 5 | 0 | 100% | 2022-10-17 | 2022-10-21 |  | MLJ | CORE DRILL | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.4 | SG3 | SG3 | 01315 | 0 | 0 | SG3-01315 | Construction | Interior Renovations | Construction.4.3.5.4 | Install beams below floor - 2nd floor apartments --> SG3 | 5 | 0 | 100% | 2022-09-30 | 2022-10-21 |  | WEIR | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.4 | SG3 | SG3 | 01320 | 0 | 0 | SG3-01320 | Construction | Interior Renovations | Construction.4.3.5.4 | Install FRP around floor openings - 2nd floor apartments --> SG3 | 5 | 0 | 100% | 2022-08-15 08:00 | 2022-08-24 17:00 |  | MLJ | 0 | FRP | 03-6000 | 03-6000-SG3
In Progress | CI NYCHA Update #22.Construction.4.3.5.4 | SG3 | SG3 | 01325 | 0 | 0 | SG3-01325 | Construction | Interior Renovations | Construction.4.3.5.4 | Frame walls / install door for electrical room - 2nd floor --> SG3 | 3 | 1 | 66% | 2022-05-04 | 2022-11-25 17:00 | -2 | CCC | 0 | 0 | 0 | 0-SG3
In Progress | CI NYCHA Update #22.Construction.4.3.5.4 | SG3 | SG3 | 01330 | 0 | 0 | SG3-01330 | Construction | Interior Renovations | Construction.4.3.5.4 | Install drywall / tape / spackle - electrical room - 2nd floor --> SG3 | 5 | 1 | 80% | 2022-06-21 | 2022-11-25 17:00 | 84 | CCC | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.4 | SG3 | SG3 | 01335 | 0 | 0 | SG3-01335 | Construction | Interior Renovations | Construction.4.3.5.4 | Paint walls and seal floor electrical room - 2nd Floor --> SG3 | 10 | 10 | 0% | 2022-11-28 08:00 | 2022-12-09 17:00 | 84 | CCC | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.4 | SG3 | SG3 | 01340 | 0 | 0 | SG3-01340 | Construction | Interior Renovations | Construction.4.3.5.4 | Install VCT @ electrical room - 2nd Floor --> SG3 | 2 | 2 | 0% | 2022-12-12 08:00 | 2022-12-13 17:00 | 84 | UNSURE | FLOORING | VCT | 0 | 0-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.EFPC.1 | SG3 | SG3 | 01405 | 0 | 0 | SG3-01405 | Construction | East Elevation | Construction.4.3.5.EFPC.1 | Excavate at Curtain Wall for flood protection (East Side) --> SG3 | 8 | 0 | 100% | 2022-08-25 | 2022-08-28 |  | MLJ | Excavation | EB EXC | 31-1000 | 31-1000-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.EFPC.1 | SG3 | SG3 | 01410 | 0 | 0 | SG3-01410 | Construction | East Elevation | Construction.4.3.5.EFPC.1 | Form concrete footings at Curtain Wall for flood protection (East Side) --> SG3 | 10 | 0 | 100% | 2022-08-28 | 2022-09-02 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.EFPC.1 | SG3 | SG3 | 01415 | 0 | 0 | SG3-01415 | Construction | East Elevation | Construction.4.3.5.EFPC.1 | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> SG3 | 5 | 0 | 100% | 2022-09-05 | 2022-09-06 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.EFPC.1 | SG3 | SG3 | 01420 | 0 | 0 | SG3-01420 | Construction | East Elevation | Construction.4.3.5.EFPC.1 | Pour concrete footings at Curtain Wall for flood protection (East Side) --> SG3 | 4 | 0 | 100% | 2022-09-07 | 2022-09-07 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.1 | SG3 | SG3 | 01425 | 0 | 0 | SG3-01425 | Construction | East Elevation | Construction.4.3.5.EFPC.1 | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> SG3 | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | -57 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.1 | SG3 | SG3 | 01430 | 0 | 0 | SG3-01430 | Construction | East Elevation | Construction.4.3.5.EFPC.1 | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG3 | 8 | 8 | 0% | 2022-12-02 08:00 | 2022-12-13 17:00 | -57 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.1 | SG3 | SG3 | 01435 | 0 | 0 | SG3-01435 | Construction | East Elevation | Construction.4.3.5.EFPC.1 | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG3 | 6 | 6 | 0% | 2022-12-14 08:00 | 2022-12-21 17:00 | -57 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.1 | SG3 | SG3 | 01440 | 0 | 0 | SG3-01440 | Construction | East Elevation | Construction.4.3.5.EFPC.1 | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG3 | 4 | 4 | 0% | 2022-12-22 08:00 | 2022-12-28 17:00 | -57 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.1 | SG3 | SG3 | 01445 | 0 | 0 | SG3-01445 | Construction | East Elevation | Construction.4.3.5.EFPC.1 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG3 | 4 | 4 | 0% | 2022-12-29 08:00 | 2023-01-04 17:00 | -56 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.1 | SG3 | SG3 | 01450 | 0 | 0 | SG3-01450 | Construction | East Elevation | Construction.4.3.5.EFPC.1 | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> SG3 | 4 | 4 | 0% | 2023-01-05 08:00 | 2023-01-10 17:00 | -56 | FAXA | CMU | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.1 | SG3 | SG3 | 01455 | 0 | 0 | SG3-01455 | Construction | East Elevation | Construction.4.3.5.EFPC.1 | Backfill at Curtain Wall for flood protection (East Side) --> SG3 | 5 | 5 | 0% | 2023-01-11 08:00 | 2023-01-18 17:00 | -56 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.1 | SG3 | SG3 | 01460 | 0 | 0 | SG3-01460 | Construction | East Elevation | Construction.4.3.5.EFPC.1 | Form for slab at Curtain Wall for flood protection (East Side) --> SG3 | 4 | 4 | 0% | 2023-01-19 08:00 | 2023-01-24 17:00 | -56 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.1 | SG3 | SG3 | 01465 | 0 | 0 | SG3-01465 | Construction | East Elevation | Construction.4.3.5.EFPC.1 | Rebar & inserts for slab at Curtain Wall for flood protection (East Side) --> SG3 | 6 | 6 | 0% | 2023-01-25 08:00 | 2023-02-01 17:00 | -56 | TONAGE | REBAR | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.1 | SG3 | SG3 | 01470 | 0 | 0 | SG3-01470 | Construction | East Elevation | Construction.4.3.5.EFPC.1 | Pour slab at Curtain Wall for flood protection (East Side) --> SG3 | 4 | 4 | 0% | 2023-02-02 08:00 | 2023-02-07 17:00 | -56 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.1 | SG3 | SG3 | 01475 | 0 | 0 | SG3-01475 | Construction | East Elevation | Construction.4.3.5.EFPC.1 | Strip Forms for slab at Curtain Wall for flood protection (East Side) --> SG3 | 2 | 2 | 0% | 2023-02-08 08:00 | 2023-02-09 17:00 | -53 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.1 | SG3 | SG3 | 01480 | 0 | 0 | SG3-01480 | Construction | East Elevation | Construction.4.3.5.EFPC.1 | Backfill surounding area at Curtain Wall for flood protection (East Side) --> SG3 | 4 | 4 | 0% | 2023-02-15 08:00 | 2023-02-21 17:00 | -56 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.2 | SG3 | SG3 | 01505 | 0 | 0 | SG3-01505 | Construction | South Elevation | Construction.4.3.5.EFPC.2 | Excavate at Curtain Wall for flood protection (South Side) --> SG3 | 8 | 8 | 0% | 2022-11-25 08:00 | 2022-12-06 17:00 | -84 | MLJ | EXCAVATION | EB EXC | 31-1000 | 31-1000-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.2 | SG3 | SG3 | 01510 | 0 | 0 | SG3-01510 | Construction | South Elevation | Construction.4.3.5.EFPC.2 | Form concrete footings at Curtain Wall for flood protection (South Side) --> SG3 | 10 | 10 | 0% | 2022-12-07 08:00 | 2022-12-20 17:00 | -84 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.2 | SG3 | SG3 | 01515 | 0 | 0 | SG3-01515 | Construction | South Elevation | Construction.4.3.5.EFPC.2 | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> SG3 | 5 | 5 | 0% | 2022-12-21 08:00 | 2022-12-28 17:00 | -84 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.2 | SG3 | SG3 | 01520 | 0 | 0 | SG3-01520 | Construction | South Elevation | Construction.4.3.5.EFPC.2 | Pour concrete footings at Curtain Wall for flood protection (South Side) --> SG3 | 4 | 4 | 0% | 2022-12-29 08:00 | 2023-01-04 17:00 | -84 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.2 | SG3 | SG3 | 01525 | 0 | 0 | SG3-01525 | Construction | South Elevation | Construction.4.3.5.EFPC.2 | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> SG3 | 5 | 5 | 0% | 2023-01-05 08:00 | 2023-01-11 17:00 | -84 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.2 | SG3 | SG3 | 01530 | 0 | 0 | SG3-01530 | Construction | South Elevation | Construction.4.3.5.EFPC.2 | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG3 | 8 | 8 | 0% | 2023-01-12 08:00 | 2023-01-24 17:00 | -84 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.2 | SG3 | SG3 | 01535 | 0 | 0 | SG3-01535 | Construction | South Elevation | Construction.4.3.5.EFPC.2 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG3 | 6 | 6 | 0% | 2023-01-25 08:00 | 2023-02-01 17:00 | -84 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.2 | SG3 | SG3 | 01540 | 0 | 0 | SG3-01540 | Construction | South Elevation | Construction.4.3.5.EFPC.2 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG3 | 4 | 4 | 0% | 2023-02-02 08:00 | 2023-02-07 17:00 | -84 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.2 | SG3 | SG3 | 01545 | 0 | 0 | SG3-01545 | Construction | South Elevation | Construction.4.3.5.EFPC.2 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG3 | 4 | 4 | 0% | 2023-02-08 08:00 | 2023-02-13 17:00 | -83 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.2 | SG3 | SG3 | 01550 | 0 | 0 | SG3-01550 | Construction | South Elevation | Construction.4.3.5.EFPC.2 | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> SG3 | 4 | 4 | 0% | 2023-02-15 08:00 | 2023-02-21 17:00 | -84 | FAXA | CMU | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.2 | SG3 | SG3 | 01555 | 0 | 0 | SG3-01555 | Construction | South Elevation | Construction.4.3.5.EFPC.2 | Backfill at Curtain Wall for flood protection (South Side) --> SG3 | 5 | 5 | 0% | 2023-02-22 08:00 | 2023-02-28 17:00 | -84 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.2 | SG3 | SG3 | 01560 | 0 | 0 | SG3-01560 | Construction | South Elevation | Construction.4.3.5.EFPC.2 | Form for slab at Curtain Wall for flood protection (South Side) --> SG3 | 4 | 4 | 0% | 2023-03-01 08:00 | 2023-03-06 17:00 | -84 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.2 | SG3 | SG3 | 01565 | 0 | 0 | SG3-01565 | Construction | South Elevation | Construction.4.3.5.EFPC.2 | Rebar & inserts for slab at Curtain Wall for flood protection (South Side) --> SG3 | 6 | 6 | 0% | 2023-03-07 08:00 | 2023-03-14 17:00 | -84 | TONAGE | REBAR | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.2 | SG3 | SG3 | 01570 | 0 | 0 | SG3-01570 | Construction | South Elevation | Construction.4.3.5.EFPC.2 | Pour slab at Curtain Wall for flood protection (South Side) --> SG3 | 4 | 4 | 0% | 2023-03-15 08:00 | 2023-03-20 17:00 | -84 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.2 | SG3 | SG3 | 01575 | 0 | 0 | SG3-01575 | Construction | South Elevation | Construction.4.3.5.EFPC.2 | Strip Forms for slab at Curtain Wall for flood protection (South Side) --> SG3 | 2 | 2 | 0% | 2023-03-21 08:00 | 2023-03-22 17:00 | -81 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.2 | SG3 | SG3 | 01580 | 0 | 0 | SG3-01580 | Construction | South Elevation | Construction.4.3.5.EFPC.2 | Backfill surounding area at Curtain Wall for flood protection (South Side) --> SG3 | 4 | 4 | 0% | 2023-03-28 08:00 | 2023-03-31 17:00 | -84 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.EFPC.3 | SG3 | SG3 | 01605 | 0 | 0 | SG3-01605 | Construction | North Elevation | Construction.4.3.5.EFPC.3 | Excavate at Curtain Wall for flood protection (North Side) --> SG3 | 8 | 0 | 100% | 2022-09-26 08:00 | 2022-10-05 17:00 |  | MLJ | Excavation | EB EXC | 31-1000 | 31-1000-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.EFPC.3 | SG3 | SG3 | 01610 | 0 | 0 | SG3-01610 | Construction | North Elevation | Construction.4.3.5.EFPC.3 | Form concrete footings at Curtain Wall for flood protection (North Side) --> SG3 | 10 | 0 | 100% | 2022-10-06 08:00 | 2022-10-20 17:00 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
In Progress | CI NYCHA Update #22.Construction.4.3.5.EFPC.3 | SG3 | SG3 | 01615 | 0 | 0 | SG3-01615 | Construction | North Elevation | Construction.4.3.5.EFPC.3 | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> SG3 | 5 | 4 | 20% | 2022-10-21 08:00 | 2022-11-30 17:00 | -40 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.3 | SG3 | SG3 | 01620 | 0 | 0 | SG3-01620 | Construction | North Elevation | Construction.4.3.5.EFPC.3 | Pour concrete footings at Curtain Wall for flood protection (North Side) --> SG3 | 4 | 4 | 0% | 2022-12-01 08:00 | 2022-12-06 17:00 | -40 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.3 | SG3 | SG3 | 01625 | 0 | 0 | SG3-01625 | Construction | North Elevation | Construction.4.3.5.EFPC.3 | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> SG3 | 5 | 5 | 0% | 2022-12-07 08:00 | 2022-12-13 17:00 | -40 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.3 | SG3 | SG3 | 01630 | 0 | 0 | SG3-01630 | Construction | North Elevation | Construction.4.3.5.EFPC.3 | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG3 | 8 | 8 | 0% | 2022-12-14 08:00 | 2022-12-23 17:00 | -40 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.3 | SG3 | SG3 | 01635 | 0 | 0 | SG3-01635 | Construction | North Elevation | Construction.4.3.5.EFPC.3 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG3 | 6 | 6 | 0% | 2022-12-27 08:00 | 2023-01-04 17:00 | -40 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.3 | SG3 | SG3 | 01640 | 0 | 0 | SG3-01640 | Construction | North Elevation | Construction.4.3.5.EFPC.3 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG3 | 4 | 4 | 0% | 2023-01-05 08:00 | 2023-01-10 17:00 | -40 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.3 | SG3 | SG3 | 01645 | 0 | 0 | SG3-01645 | Construction | North Elevation | Construction.4.3.5.EFPC.3 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG3 | 4 | 4 | 0% | 2023-01-11 08:00 | 2023-01-17 17:00 | -40 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.3 | SG3 | SG3 | 01650 | 0 | 0 | SG3-01650 | Construction | North Elevation | Construction.4.3.5.EFPC.3 | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> SG3 | 4 | 4 | 0% | 2023-01-18 08:00 | 2023-01-23 17:00 | -40 | FAXA | CMU | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.3 | SG3 | SG3 | 01655 | 0 | 0 | SG3-01655 | Construction | North Elevation | Construction.4.3.5.EFPC.3 | Backfill at Curtain Wall for flood protection (North Side) --> SG3 | 5 | 5 | 0% | 2023-01-24 08:00 | 2023-01-30 17:00 | -40 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.4 | SG3 | SG3 | 01705 | 0 | 0 | SG3-01705 | Construction | West Elevation | Construction.4.3.5.EFPC.4 | Excavate at Curtain Wall for flood protection (West Side) --> SG3 | 8 | 8 | 0% | 2023-03-23 08:00 | 2023-04-03 17:00 | -157 | MLJ | EXCAVATION | EB EXC | 31-1000 | 31-1000-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.4 | SG3 | SG3 | 01710 | 0 | 0 | SG3-01710 | Construction | West Elevation | Construction.4.3.5.EFPC.4 | Form concrete footings at Curtain Wall for flood protection (West Side) --> SG3 | 10 | 10 | 0% | 2023-04-04 08:00 | 2023-04-17 17:00 | -157 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.4 | SG3 | SG3 | 01715 | 0 | 0 | SG3-01715 | Construction | West Elevation | Construction.4.3.5.EFPC.4 | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> SG3 | 5 | 5 | 0% | 2023-04-18 08:00 | 2023-04-24 17:00 | -157 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.4 | SG3 | SG3 | 01720 | 0 | 0 | SG3-01720 | Construction | West Elevation | Construction.4.3.5.EFPC.4 | Pour concrete footings at Curtain Wall for flood protection (West Side) --> SG3 | 4 | 4 | 0% | 2023-04-25 08:00 | 2023-04-28 17:00 | -157 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.4 | SG3 | SG3 | 01725 | 0 | 0 | SG3-01725 | Construction | West Elevation | Construction.4.3.5.EFPC.4 | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> SG3 | 5 | 5 | 0% | 2023-05-01 08:00 | 2023-05-05 17:00 | -157 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.4 | SG3 | SG3 | 01730 | 0 | 0 | SG3-01730 | Construction | West Elevation | Construction.4.3.5.EFPC.4 | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG3 | 8 | 8 | 0% | 2023-05-08 08:00 | 2023-05-17 17:00 | -157 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.4 | SG3 | SG3 | 01735 | 0 | 0 | SG3-01735 | Construction | West Elevation | Construction.4.3.5.EFPC.4 | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG3 | 6 | 6 | 0% | 2023-05-18 08:00 | 2023-05-25 17:00 | -157 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.4 | SG3 | SG3 | 01740 | 0 | 0 | SG3-01740 | Construction | West Elevation | Construction.4.3.5.EFPC.4 | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG3 | 4 | 4 | 0% | 2023-05-26 08:00 | 2023-06-01 17:00 | -157 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.4 | SG3 | SG3 | 01745 | 0 | 0 | SG3-01745 | Construction | West Elevation | Construction.4.3.5.EFPC.4 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG3 | 4 | 4 | 0% | 2023-06-02 08:00 | 2023-06-07 17:00 | -148 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.4 | SG3 | SG3 | 01750 | 0 | 0 | SG3-01750 | Construction | West Elevation | Construction.4.3.5.EFPC.4 | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> SG3 | 4 | 4 | 0% | 2023-06-02 08:00 | 2023-06-07 17:00 | -157 | FAXA | CMU | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.4 | SG3 | SG3 | 01755 | 0 | 0 | SG3-01755 | Construction | West Elevation | Construction.4.3.5.EFPC.4 | Backfill at Curtain Wall for flood protection (West Side) --> SG3 | 5 | 5 | 0% | 2023-06-08 08:00 | 2023-06-14 17:00 | -157 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.4 | SG3 | SG3 | 01760 | 0 | 0 | SG3-01760 | Construction | West Elevation | Construction.4.3.5.EFPC.4 | Form for slab at Curtain Wall for flood protection (West Side) --> SG3 | 4 | 4 | 0% | 2023-06-15 08:00 | 2023-06-20 17:00 | -157 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.4 | SG3 | SG3 | 01765 | 0 | 0 | SG3-01765 | Construction | West Elevation | Construction.4.3.5.EFPC.4 | Rebar & inserts for slab at Curtain Wall for flood protection (West Side) --> SG3 | 6 | 6 | 0% | 2023-06-21 08:00 | 2023-06-28 17:00 | -157 | TONAGE | REBAR | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.4 | SG3 | SG3 | 01770 | 0 | 0 | SG3-01770 | Construction | West Elevation | Construction.4.3.5.EFPC.4 | Pour slab at Curtain Wall for flood protection (West Side) --> SG3 | 4 | 4 | 0% | 2023-06-29 08:00 | 2023-07-05 17:00 | -157 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.4 | SG3 | SG3 | 01775 | 0 | 0 | SG3-01775 | Construction | West Elevation | Construction.4.3.5.EFPC.4 | Strip Forms for slab at Curtain Wall for flood protection (West Side) --> SG3 | 2 | 2 | 0% | 2023-07-06 08:00 | 2023-07-07 17:00 | -155 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.4 | SG3 | SG3 | 01780 | 0 | 0 | SG3-01780 | Construction | West Elevation | Construction.4.3.5.EFPC.4 | Backfill surounding area at Curtain Wall for flood protection (West Side) --> SG3 | 4 | 4 | 0% | 2023-07-13 08:00 | 2023-07-18 17:00 | -158 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.EFPC.5 | SG3 | SG3 | 01805 | 0 | 0 | SG3-01805 | Construction | Concrete Shelf Construction | Construction.4.3.5.EFPC.5 | Excavate for concrete shelf around bldg perimeter --> SG3 | 10 | 0 | 100% | 2022-08-11 08:00 | 2022-08-24 17:00 |  | MLJ | Excavation | EB EXC | 31-1000 | 31-1000-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.EFPC.5 | SG3 | SG3 | 01810 | 0 | 0 | SG3-01810 | Construction | Concrete Shelf Construction | Construction.4.3.5.EFPC.5 | Place rebar for concrete shelf around bldg perimeter --> SG3 | 5 | 0 | 100% | 2022-09-09 08:00 | 2022-09-23 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.EFPC.5 | SG3 | SG3 | 01815 | 0 | 0 | SG3-01815 | Construction | Concrete Shelf Construction | Construction.4.3.5.EFPC.5 | Pour concrete shelf around bldg perimeter --> SG3 | 5 | 0 | 100% | 2022-09-26 08:00 | 2022-09-30 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.EFPC.5 | SG3 | SG3 | 01820 | 0 | 0 | SG3-01820 | Construction | Concrete Shelf Construction | Construction.4.3.5.EFPC.5 | Place infill concrete in area ways around bldg perimeter --> SG3 | 5 | 0 | 100% | 2022-10-03 08:00 | 2022-10-07 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.EFPC.5 | SG3 | SG3 | 01825 | 0 | 0 | SG3-01825 | Construction | Concrete Shelf Construction | Construction.4.3.5.EFPC.5 | Place waterproofing on concrete shelf around bldg perimeter --> SG3 | 10 | 0 | 100% | 2022-10-10 08:00 | 2022-10-18 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
In Progress | CI NYCHA Update #22.Construction.4.3.5.EFPC.5 | SG3 | SG3 | 01830 | 0 | 0 | SG3-01830 | Construction | Concrete Shelf Construction | Construction.4.3.5.EFPC.5 | Place CMU around bldg perimeter --SG3 | 15 | 10 | 33% | 2022-10-19 | 2023-04-19 17:00 | -141 | FAXA | CMU | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.5 | SG3 | SG3 | 01835 | 0 | 0 | SG3-01835 | Construction | Concrete Shelf Construction | Construction.4.3.5.EFPC.5 | Place waterproofing on CMU around bldg perimeter --> SG3 | 10 | 10 | 0% | 2023-04-20 08:00 | 2023-05-03 17:00 | -141 | DSTAR | WATERPROOFING | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.5 | SG3 | SG3 | 01840 | 0 | 0 | SG3-01840 | Construction | Concrete Shelf Construction | Construction.4.3.5.EFPC.5 | Place window frames around bldg perimeter --> SG3 | 10 | 10 | 0% | 2023-05-04 08:00 | 2023-05-17 17:00 | -141 | MLJ | CONCRETE SHELF | PLACE WINDOWS | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.5 | SG3 | SG3 | 01845 | 0 | 0 | SG3-01845 | Construction | Concrete Shelf Construction | Construction.4.3.5.EFPC.5 | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> SG3 | 20 | 20 | 0% | 2023-05-18 08:00 | 2023-06-15 17:00 | -141 | FAXA | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.5 | SG3 | SG3 | 01850 | 0 | 0 | SG3-01850 | Construction | Concrete Shelf Construction | Construction.4.3.5.EFPC.5 | Backfill around bdg perimeter --> SG3 | 5 | 5 | 0% | 2023-06-16 08:00 | 2023-06-22 17:00 | -141 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.5 | SG3 | SG3 | 01855 | 0 | 0 | SG3-01855 | Construction | Concrete Shelf Construction | Construction.4.3.5.EFPC.5 | Place frame / stucco / and signs at entrances --> SG3 | 4 | 4 | 0% | 2023-06-23 08:00 | 2023-06-28 17:00 | -35 | CCC | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.5 | SG3 | SG3 | 01860 | 0 | 0 | SG3-01860 | Construction | Concrete Shelf Construction | Construction.4.3.5.EFPC.5 | Place window floodgates at windows --> SG3 | 5 | 5 | 0% | 2023-06-29 08:00 | 2023-07-06 17:00 | -35 | MLJ | FLOOD PROTECTION | FLOOD WINDOWS | 10-1400 | 10-1400-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.5 | SG3 | SG3 | 01865 | 0 | 0 | SG3-01865 | Construction | Concrete Shelf Construction | Construction.4.3.5.EFPC.5 | Install signs --> SG3 | 3 | 3 | 0% | 2023-07-07 08:00 | 2023-07-11 17:00 | -35 | MLJ | SIGNS | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.5 | SG3 | SG3 | 01350 | 0 | 0 | SG3-01350 | Construction | Boiler Room Construction | Construction.4.3.5.5 | Drill dowels and place rebar for boiler room concrete walls --> SG3 | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 80 | MLJ | 0 | DRILL & DOWEL | 03-1400 | 03-1400-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.5 | SG3 | SG3 | 01355 | 0 | 0 | SG3-01355 | Construction | Boiler Room Construction | Construction.4.3.5.5 | Form boiler room concrete walls --> SG3 | 5 | 5 | 0% | 2022-12-02 08:00 | 2022-12-08 17:00 | 80 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.5 | SG3 | SG3 | 01360 | 0 | 0 | SG3-01360 | Construction | Boiler Room Construction | Construction.4.3.5.5 | Pour Concrete boiler room walls --> SG3 | 2 | 2 | 0% | 2022-12-09 08:00 | 2022-12-12 17:00 | 80 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.5 | SG3 | SG3 | 01365 | 0 | 0 | SG3-01365 | Construction | Boiler Room Construction | Construction.4.3.5.5 | Strip Forms boiler room concrete walls --> SG3 | 3 | 3 | 0% | 2022-12-13 08:00 | 2022-12-15 17:00 | 82 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.5 | SG3 | SG3 | 01370 | 0 | 0 | SG3-01370 | Construction | Boiler Room Construction | Construction.4.3.5.5 | Place crystaline waterproofing on perimeter walls - cellar --> SG3 - N/R, Bulletin 5 | 10 | 0 | 100% | 2022-07-01 | 2022-07-01 17:00 |  | 0 | WATERPROOFING | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.6 | SG3 | SG3 | 01385 | 0 | 0 | SG3-01385 | Construction | Elevator Refurbishment | Construction.4.3.5.6 | Refurbish Elevator 1 --> SG3 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.6 | SG3 | SG3 | 01390 | 0 | 0 | SG3-01390 | Construction | Elevator Refurbishment | Construction.4.3.5.6 | Refurbish Elevator 2 --> SG3 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.6 | SG3 | SG3 | 01380 | 0 | 0 | SG3-01380 | Construction | Elevator Refurbishment | Construction.4.3.5.6 | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.7 | SG3 | SG3 | 09005 | 0 | 0 | SG3-09005 | Construction | Civil/Architectural Inspections | Construction.4.3.5.7 | Perform Inspections & Issue Punch List | 5 | 5 | 0% | 2023-10-30 08:00 | 2023-11-03 17:00 | -136 | MLJ | PUNCH LIST | INSPECTION | 99-8200 | 99-8200-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.7 | SG3 | SG3 | 09010 | 0 | 0 | SG3-09010 | Construction | Civil/Architectural Inspections | Construction.4.3.5.7 | Perform Punch List | 10 | 10 | 0% | 2023-11-06 08:00 | 2023-11-21 17:00 | -121 | MLJ | PUNCH LIST | 0 | 99-8200 | 99-8200-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.2 | SG3 | SG3 | 01220 | 0 | 0 | SG3-01220 | Construction | Interior Demolition | Construction.4.3.5.2 | Selective Demo (Pumps etc..) - Cellar --> SG3 | 5 | 5 | 0% | 2022-12-02 08:00 | 2022-12-08 17:00 | 32 | MLJ | DEMO | DEMO PUMPS | 02-6010 | 02-6010-SG3
Not Started | CI NYCHA Update #22.Construction.4.2.1.1 | SG2 | SG2 | 01005 | 0 | 0 | SG2-01005 | Construction | Asbestos Abatement | Construction.4.2.1.1 | Asbestos Abatement - gaskets - cellar - SG2 | 3 | 3 | 0% | 2023-10-19 08:00 | 2023-10-23 17:00 | -132 | ATCO | ABESTOS | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.1 | SG2 | SG2 | 01010 | 0 | 0 | SG2-01010 | Construction | Asbestos Abatement | Construction.4.2.1.1 | Asbestos Abatement - wire insulation - cellar --> SG2 | 3 | 0 | 100% | 2022-02-28 08:00 | 2022-03-04 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.1 | SG2 | SG2 | 01015 | 0 | 0 | SG2-01015 | Construction | Asbestos Abatement | Construction.4.2.1.1 | Asbestos Abatement - flooring materials at slab penetrations - cellar --> SG2 - N/A | 3 | 0 | 100% | 2022-03-25 08:00 | 2022-03-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.1 | SG2 | SG2 | 01020 | 0 | 0 | SG2-01020 | Construction | Asbestos Abatement | Construction.4.2.1.1 | Asbestos Abatement - pipe insulation - cellar --> SG2 | 3 | 0 | 100% | 2022-02-28 08:00 | 2022-03-04 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.1 | SG2 | SG2 | 01025 | 0 | 0 | SG2-01025 | Construction | Asbestos Abatement | Construction.4.2.1.1 | Asbestos Abatement - Window Sills - 1st Floor --> SG2 | 5 | 0 | 100% | 2022-04-27 08:00 | 2022-04-28 17:00 |  | ATCO | ABESTOS | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.1 | SG2 | SG2 | 01030 | 0 | 0 | SG2-01030 | Construction | Asbestos Abatement | Construction.4.2.1.1 | Asbestos Abatement - caulk @ windows and areaway vents --> SG2 | 5 | 0 | 100% | 2022-04-27 08:00 | 2022-04-28 17:00 |  | ATCO | ABESTOS | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.2 | SG2 | SG2 | 01105 | 0 | 0 | SG2-01105 | Construction | Interior Demolition | Construction.4.2.1.2 | Selective Demo (Plaster walls, Doors, windows) - Cellar --> SG2 | 10 | 0 | 100% | 2021-05-18 | 2022-08-05 17:00 |  | MLJ | DEMO | DEMO CELLAR WALLS | 02-6005 | 02-6005-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.2 | SG2 | SG2 | 01110 | 0 | 0 | SG2-01110 | Construction | Interior Demolition | Construction.4.2.1.2 | Selective Demo (Doors, windows) - 1st Floor --> SG2 | 5 | 0 | 100% | 2022-09-26 08:00 | 2022-09-30 17:00 |  | MLJ | DEMO | DEMO DOORS WINDOWS | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.2 | SG2 | SG2 | 01115 | 0 | 0 | SG2-01115 | Construction | Interior Demolition | Construction.4.2.1.2 | Selective Demo (Areaway drain, slab, wall) --> SG2 | 10 | 0 | 100% | 2022-08-01 | 2022-08-05 |  | MLJ | DEMO | DEMO AREAWAY | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.2 | SG2 | SG2 | 01205 | 0 | 0 | SG2-01205 | Construction | Interior Demolition | Construction.4.2.1.2 | Selective Demo (Existing Ramp, railing) - 1st Floor --> SG2 | 5 | 0 | 100% | 2022-09-26 08:00 | 2022-09-30 17:00 |  | MLJ | DEMO | DEMO RAMP | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.2 | SG2 | SG2 | 01210 | 0 | 0 | SG2-01210 | Construction | Interior Demolition | Construction.4.2.1.2 | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> SG2 | 5 | 0 | 100% | 2022-10-03 08:00 | 2022-10-07 17:00 |  | MLJ | DEMO | DEMO SLAB OPEN FOR MECH | 02-3000 | 02-3000-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.2 | SG2 | SG2 | 01215 | 0 | 0 | SG2-01215 | Construction | Interior Demolition | Construction.4.2.1.2 | Selective Demo - 2nd Floor Apartment for Electrical Room --> SG2 - N/A | 5 | 0 | 100% | 2022-01-27 | 2022-05-02 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.4 | SG2 | SG2 | 01310 | 0 | 0 | SG2-01310 | Construction | Interior Renovations | Construction.4.2.1.4 | Make openings in floor for conduit penetrations - 1st floor apartments --> SG2 - N/A | 5 | 0 | 100% | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.4 | SG2 | SG2 | 01315 | 0 | 0 | SG2-01315 | Construction | Interior Renovations | Construction.4.2.1.4 | Install beams below floor - 1st floor apartments --> SG2 - N/A | 5 | 0 | 100% | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.4 | SG2 | SG2 | 01320 | 0 | 0 | SG2-01320 | Construction | Interior Renovations | Construction.4.2.1.4 | Install FRP around floor openings - 1st floor apartments --> SG2 - N/A | 5 | 0 | 100% | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0 | FRP | 0 | 03-6000 | 03-6000-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.4 | SG2 | SG2 | 01325 | 0 | 0 | SG2-01325 | Construction | Interior Renovations | Construction.4.2.1.4 | Frame walls / install door for electrical room - 1st floor --> SG2 - N/A | 3 | 0 | 100% | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.4 | SG2 | SG2 | 01330 | 0 | 0 | SG2-01330 | Construction | Interior Renovations | Construction.4.2.1.4 | Install drywall / tape / spackle - electrical room - 1st floor --> SG2 - N/A | 5 | 0 | 100% | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.4 | SG2 | SG2 | 01335 | 0 | 0 | SG2-01335 | Construction | Interior Renovations | Construction.4.2.1.4 | Paint walls and seal floor electrical room - 1st Floor --> SG2 - N/A | 10 | 0 | 100% | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.4 | SG2 | SG2 | 01340 | 0 | 0 | SG2-01340 | Construction | Interior Renovations | Construction.4.2.1.4 | Install VCT @ electrical room - 1st Floor --> SG2 - N/A | 2 | 0 | 100% | 2022-04-25 08:00 | 2022-04-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.1 | SG2 | SG2 | 01405 | 0 | 0 | SG2-01405 | Construction | East Elevation | Construction.4.2.1.EFPC.1 | Excavate at Curtain Wall for flood protection (East Side) --> SG2 | 8 | 0 | 100% | 2022-08-05 | 2022-08-19 17:00 |  | MLJ | Excavation | EB EXC | 31-1000 | 31-1000-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.1 | SG2 | SG2 | 01410 | 0 | 0 | SG2-01410 | Construction | East Elevation | Construction.4.2.1.EFPC.1 | Form concrete footings at Curtain Wall for flood protection (East Side) --> SG2 | 10 | 0 | 100% | 2022-10-03 | 2022-10-07 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.1 | SG2 | SG2 | 01415 | 0 | 0 | SG2-01415 | Construction | East Elevation | Construction.4.2.1.EFPC.1 | Rebar concrete footings at Curtain Wall for flood protection (East Side) --> SG2 | 5 | 0 | 100% | 2022-10-10 08:00 | 2022-10-14 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.1 | SG2 | SG2 | 01420 | 0 | 0 | SG2-01420 | Construction | East Elevation | Construction.4.2.1.EFPC.1 | Pour concrete footings at Curtain Wall for flood protection (East Side) --> SG2 | 4 | 0 | 100% | 2022-10-19 | 2022-10-19 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.1 | SG2 | SG2 | 01425 | 0 | 0 | SG2-01425 | Construction | East Elevation | Construction.4.2.1.EFPC.1 | Strip Forms concrete footings at Curtain Wall for flood protection (East Side) --> SG2 | 5 | 0 | 100% | 2022-10-25 | 2022-10-31 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.1 | SG2 | SG2 | 01430 | 0 | 0 | SG2-01430 | Construction | East Elevation | Construction.4.2.1.EFPC.1 | Form concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG2 | 8 | 8 | 0% | 2022-11-25 08:00 | 2022-12-06 17:00 | -50 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.1 | SG2 | SG2 | 01435 | 0 | 0 | SG2-01435 | Construction | East Elevation | Construction.4.2.1.EFPC.1 | Rebar concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG2 | 6 | 6 | 0% | 2022-12-07 08:00 | 2022-12-14 17:00 | -50 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.1 | SG2 | SG2 | 01440 | 0 | 0 | SG2-01440 | Construction | East Elevation | Construction.4.2.1.EFPC.1 | Pour concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG2 | 4 | 4 | 0% | 2022-12-15 08:00 | 2022-12-20 17:00 | -50 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.1 | SG2 | SG2 | 01445 | 0 | 0 | SG2-01445 | Construction | East Elevation | Construction.4.2.1.EFPC.1 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG2 | 4 | 4 | 0% | 2022-12-21 08:00 | 2022-12-27 17:00 | -49 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.1 | SG2 | SG2 | 01450 | 0 | 0 | SG2-01450 | Construction | East Elevation | Construction.4.2.1.EFPC.1 | Place CMU wall and grout fill at Curtain Wall for flood protection (East Side) --> SG2 | 4 | 4 | 0% | 2022-12-28 08:00 | 2023-01-03 17:00 | -49 | FAXA | CMU | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.1 | SG2 | SG2 | 01455 | 0 | 0 | SG2-01455 | Construction | East Elevation | Construction.4.2.1.EFPC.1 | Backfill at Curtain Wall for flood protection (East Side) --> SG2 | 5 | 5 | 0% | 2023-01-04 08:00 | 2023-01-10 17:00 | -49 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.1 | SG2 | SG2 | 01460 | 0 | 0 | SG2-01460 | Construction | East Elevation | Construction.4.2.1.EFPC.1 | Form for slab at Curtain Wall for flood protection (East Side) --> SG2 | 4 | 4 | 0% | 2023-01-11 08:00 | 2023-01-17 17:00 | -49 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.1 | SG2 | SG2 | 01465 | 0 | 0 | SG2-01465 | Construction | East Elevation | Construction.4.2.1.EFPC.1 | Rebar & inserts for slab at Curtain Wall for flood protection (East Side) --> SG2 | 6 | 6 | 0% | 2023-01-18 08:00 | 2023-01-25 17:00 | -49 | TONAGE | REBAR | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.1 | SG2 | SG2 | 01470 | 0 | 0 | SG2-01470 | Construction | East Elevation | Construction.4.2.1.EFPC.1 | Pour slab at Curtain Wall for flood protection (East Side) --> SG2 | 4 | 4 | 0% | 2023-01-26 08:00 | 2023-01-31 17:00 | -49 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.1 | SG2 | SG2 | 01475 | 0 | 0 | SG2-01475 | Construction | East Elevation | Construction.4.2.1.EFPC.1 | Strip Forms for slab at Curtain Wall for flood protection (East Side) --> SG2 | 2 | 2 | 0% | 2023-02-01 08:00 | 2023-02-02 17:00 | -47 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.1 | SG2 | SG2 | 01480 | 0 | 0 | SG2-01480 | Construction | East Elevation | Construction.4.2.1.EFPC.1 | Backfill surounding area at Curtain Wall for flood protection (East Side) --> SG2 | 4 | 4 | 0% | 2023-02-08 08:00 | 2023-02-13 17:00 | -50 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.2 | SG2 | SG2 | 01505 | 0 | 0 | SG2-01505 | Construction | South Elevation | Construction.4.2.1.EFPC.2 | Excavate at Curtain Wall for flood protection (South Side) --> SG2 | 7 | 0 | 100% | 2022-08-22 | 2022-08-24 |  | MLJ | Excavation | EB EXC | 31-1000 | 31-1000-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.2 | SG2 | SG2 | 01510 | 0 | 0 | SG2-01510 | Construction | South Elevation | Construction.4.2.1.EFPC.2 | Form concrete footings at Curtain Wall for flood protection (South Side) --> SG2 | 9 | 0 | 100% | 2022-08-25 | 2022-08-28 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.2 | SG2 | SG2 | 01515 | 0 | 0 | SG2-01515 | Construction | South Elevation | Construction.4.2.1.EFPC.2 | Rebar concrete footings at Curtain Wall for flood protection (South Side) --> SG2 | 4 | 0 | 100% | 2022-08-28 | 2022-09-02 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.2 | SG2 | SG2 | 01520 | 0 | 0 | SG2-01520 | Construction | South Elevation | Construction.4.2.1.EFPC.2 | Pour concrete footings at Curtain Wall for flood protection (South Side) --> SG2 | 3 | 0 | 100% | 2022-09-05 | 2022-09-06 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.2 | SG2 | SG2 | 01525 | 0 | 0 | SG2-01525 | Construction | South Elevation | Construction.4.2.1.EFPC.2 | Strip Forms concrete footings at Curtain Wall for flood protection (South Side) --> SG2 | 4 | 0 | 100% | 2022-09-07 | 2022-09-07 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.2 | SG2 | SG2 | 01530 | 0 | 0 | SG2-01530 | Construction | South Elevation | Construction.4.2.1.EFPC.2 | Form concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG2 | 7 | 0 | 100% | 2022-09-08 | 2022-09-09 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.2 | SG2 | SG2 | 01535 | 0 | 0 | SG2-01535 | Construction | South Elevation | Construction.4.2.1.EFPC.2 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG2 | 5 | 0 | 100% | 2022-09-12 | 2022-09-13 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.2 | SG2 | SG2 | 01540 | 0 | 0 | SG2-01540 | Construction | South Elevation | Construction.4.2.1.EFPC.2 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG2 | 3 | 0 | 100% | 2022-09-14 | 2022-09-15 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.2 | SG2 | SG2 | 01545 | 0 | 0 | SG2-01545 | Construction | South Elevation | Construction.4.2.1.EFPC.2 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG2 | 3 | 0 | 100% | 2022-09-16 | 2022-09-16 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.2 | SG2 | SG2 | 01550 | 0 | 0 | SG2-01550 | Construction | South Elevation | Construction.4.2.1.EFPC.2 | Place CMU wall and grout fill at Curtain Wall for flood protection (South Side) --> SG2 | 3 | 3 | 0% | 2022-11-25 08:00 | 2022-11-29 17:00 | -3 | FAXA | CMU | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.2 | SG2 | SG2 | 01555 | 0 | 0 | SG2-01555 | Construction | South Elevation | Construction.4.2.1.EFPC.2 | Backfill at Curtain Wall for flood protection (South Side) --> SG2 | 4 | 4 | 0% | 2022-11-30 08:00 | 2022-12-05 17:00 | -3 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.3 | SG2 | SG2 | 01605 | 0 | 0 | SG2-01605 | Construction | North Elevation | Construction.4.2.1.EFPC.3 | Excavate at Curtain Wall for flood protection (North Side) --> SG2 | 7 | 0 | 100% | 2022-08-22 | 2022-08-24 |  | MLJ | Excavation | EB EXC | 31-1000 | 31-1000-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.3 | SG2 | SG2 | 01610 | 0 | 0 | SG2-01610 | Construction | North Elevation | Construction.4.2.1.EFPC.3 | Form concrete footings at Curtain Wall for flood protection (North Side) --> SG2 | 9 | 0 | 100% | 2022-08-25 | 2022-08-28 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.3 | SG2 | SG2 | 01615 | 0 | 0 | SG2-01615 | Construction | North Elevation | Construction.4.2.1.EFPC.3 | Rebar concrete footings at Curtain Wall for flood protection (North Side) --> SG2 | 4 | 0 | 100% | 2022-08-28 | 2022-09-02 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.3 | SG2 | SG2 | 01620 | 0 | 0 | SG2-01620 | Construction | North Elevation | Construction.4.2.1.EFPC.3 | Pour concrete footings at Curtain Wall for flood protection (North Side) --> SG2 | 3 | 0 | 100% | 2022-09-05 | 2022-09-06 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.3 | SG2 | SG2 | 01625 | 0 | 0 | SG2-01625 | Construction | North Elevation | Construction.4.2.1.EFPC.3 | Strip Forms concrete footings at Curtain Wall for flood protection (North Side) --> SG2 | 4 | 0 | 100% | 2022-09-07 | 2022-09-07 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.3 | SG2 | SG2 | 01630 | 0 | 0 | SG2-01630 | Construction | North Elevation | Construction.4.2.1.EFPC.3 | Form concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG2 | 7 | 0 | 100% | 2022-09-08 | 2022-09-09 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.3 | SG2 | SG2 | 01635 | 0 | 0 | SG2-01635 | Construction | North Elevation | Construction.4.2.1.EFPC.3 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG2 | 5 | 0 | 100% | 2022-09-12 | 2022-09-13 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.3 | SG2 | SG2 | 01640 | 0 | 0 | SG2-01640 | Construction | North Elevation | Construction.4.2.1.EFPC.3 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG2 | 3 | 0 | 100% | 2022-09-14 | 2022-09-15 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.3 | SG2 | SG2 | 01645 | 0 | 0 | SG2-01645 | Construction | North Elevation | Construction.4.2.1.EFPC.3 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG2 | 3 | 0 | 100% | 2022-09-16 | 2022-09-16 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.3 | SG2 | SG2 | 01650 | 0 | 0 | SG2-01650 | Construction | North Elevation | Construction.4.2.1.EFPC.3 | Place CMU wall and grout fill at Curtain Wall for flood protection (North Side) --> SG2 | 3 | 0 | 100% | 2022-09-26 08:00 | 2022-10-03 |  | FAXA | CMU | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.3 | SG2 | SG2 | 01655 | 0 | 0 | SG2-01655 | Construction | North Elevation | Construction.4.2.1.EFPC.3 | Backfill at Curtain Wall for flood protection (North Side) --> SG2 | 4 | 0 | 100% | 2022-10-04 | 2022-10-07 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.4 | SG2 | SG2 | 01705 | 0 | 0 | SG2-01705 | Construction | West Elevation | Construction.4.2.1.EFPC.4 | Excavate at Curtain Wall for flood protection (West Side) --> SG2 | 8 | 0 | 100% | 2022-10-10 | 2022-10-14 |  | MLJ | Excavation | EB EXC | 31-1000 | 31-1000-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.4 | SG2 | SG2 | 01710 | 0 | 0 | SG2-01710 | Construction | West Elevation | Construction.4.2.1.EFPC.4 | Form concrete footings at Curtain Wall for flood protection (West Side) --> SG2 | 10 | 0 | 100% | 2022-10-17 | 2022-10-21 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.4 | SG2 | SG2 | 01715 | 0 | 0 | SG2-01715 | Construction | West Elevation | Construction.4.2.1.EFPC.4 | Rebar concrete footings at Curtain Wall for flood protection (West Side) --> SG2 | 5 | 0 | 100% | 2022-10-24 | 2022-10-26 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.4 | SG2 | SG2 | 01720 | 0 | 0 | SG2-01720 | Construction | West Elevation | Construction.4.2.1.EFPC.4 | Pour concrete footings at Curtain Wall for flood protection (West Side) --> SG2 | 4 | 0 | 100% | 2022-10-27 | 2022-10-27 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.4 | SG2 | SG2 | 01725 | 0 | 0 | SG2-01725 | Construction | West Elevation | Construction.4.2.1.EFPC.4 | Strip Forms concrete footings at Curtain Wall for flood protection (West Side) --> SG2 | 5 | 0 | 100% | 2022-10-28 | 2022-10-28 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.4 | SG2 | SG2 | 01730 | 0 | 0 | SG2-01730 | Construction | West Elevation | Construction.4.2.1.EFPC.4 | Form concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG2 | 8 | 0 | 100% | 2022-10-31 | 2022-11-01 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.4 | SG2 | SG2 | 01735 | 0 | 0 | SG2-01735 | Construction | West Elevation | Construction.4.2.1.EFPC.4 | Rebar concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG2 | 6 | 0 | 100% | 2022-11-02 | 2022-11-03 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.4 | SG2 | SG2 | 01740 | 0 | 0 | SG2-01740 | Construction | West Elevation | Construction.4.2.1.EFPC.4 | Pour concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG2 | 4 | 0 | 100% | 2022-11-04 | 2022-11-04 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.4 | SG2 | SG2 | 01745 | 0 | 0 | SG2-01745 | Construction | West Elevation | Construction.4.2.1.EFPC.4 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG2 | 4 | 0 | 100% | 2022-11-07 | 2022-11-08 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.4 | SG2 | SG2 | 01750 | 0 | 0 | SG2-01750 | Construction | West Elevation | Construction.4.2.1.EFPC.4 | Place CMU wall and grout fill at Curtain Wall for flood protection (West Side) --> SG2 | 4 | 0 | 100% | 2022-11-09 | 2022-11-18 |  | FAXA | CMU | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.4 | SG2 | SG2 | 01755 | 0 | 0 | SG2-01755 | Construction | West Elevation | Construction.4.2.1.EFPC.4 | Backfill at Curtain Wall for flood protection (West Side) --> SG2 | 5 | 0 | 100% | 2022-11-09 | 2022-11-09 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.4 | SG2 | SG2 | 01760 | 0 | 0 | SG2-01760 | Construction | West Elevation | Construction.4.2.1.EFPC.4 | Form for slab at Curtain Wall for flood protection (West Side) --> SG2 | 4 | 0 | 100% | 2022-10-31 | 2022-11-01 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.4 | SG2 | SG2 | 01765 | 0 | 0 | SG2-01765 | Construction | West Elevation | Construction.4.2.1.EFPC.4 | Rebar & inserts for slab at Curtain Wall for flood protection (West Side) --> SG2 | 6 | 0 | 100% | 2022-11-02 | 2022-11-03 |  | 0 | REBAR | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.4 | SG2 | SG2 | 01770 | 0 | 0 | SG2-01770 | Construction | West Elevation | Construction.4.2.1.EFPC.4 | Pour slab at Curtain Wall for flood protection (West Side) --> SG2 | 4 | 0 | 100% | 2022-11-04 | 2022-11-04 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.4 | SG2 | SG2 | 01775 | 0 | 0 | SG2-01775 | Construction | West Elevation | Construction.4.2.1.EFPC.4 | Strip Forms for slab at Curtain Wall for flood protection (West Side) --> SG2 | 2 | 0 | 100% | 2022-11-07 | 2022-11-08 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.4 | SG2 | SG2 | 01780 | 0 | 0 | SG2-01780 | Construction | West Elevation | Construction.4.2.1.EFPC.4 | Backfill surounding area at Curtain Wall for flood protection (West Side) --> SG2 | 4 | 0 | 100% | 2022-11-09 | 2022-11-09 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.5 | SG2 | SG2 | 01805 | 0 | 0 | SG2-01805 | Construction | Concrete Shelf Construction | Construction.4.2.1.EFPC.5 | Excavate for concrete shelf around bldg perimeter --> SG2 | 10 | 0 | 100% | 2022-08-03 08:00 | 2022-08-10 17:00 |  | MLJ | Excavation | EB EXC | 31-1000 | 31-1000-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.5 | SG2 | SG2 | 01810 | 0 | 0 | SG2-01810 | Construction | Concrete Shelf Construction | Construction.4.2.1.EFPC.5 | Place rebar for concrete shelf around bldg perimeter --> SG2 | 5 | 0 | 100% | 2022-05-18 08:00 | 2022-08-23 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.5 | SG2 | SG2 | 01815 | 0 | 0 | SG2-01815 | Construction | Concrete Shelf Construction | Construction.4.2.1.EFPC.5 | Pour concrete shelf around bldg perimeter --> SG2 | 5 | 0 | 100% | 2022-08-24 08:00 | 2022-08-24 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.5 | SG2 | SG2 | 01820 | 0 | 0 | SG2-01820 | Construction | Concrete Shelf Construction | Construction.4.2.1.EFPC.5 | Place infill concrete in area ways around bldg perimeter --> SG2 | 5 | 0 | 100% | 2022-08-24 08:00 | 2022-08-24 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.5 | SG2 | SG2 | 01825 | 0 | 0 | SG2-01825 | Construction | Concrete Shelf Construction | Construction.4.2.1.EFPC.5 | Place waterproofing on concrete shelf around bldg perimeter --> SG2 | 10 | 0 | 100% | 2022-09-26 08:00 | 2022-10-07 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.5 | SG2 | SG2 | 01830 | 0 | 0 | SG2-01830 | Construction | Concrete Shelf Construction | Construction.4.2.1.EFPC.5 | Place CMU around bldg perimeter --SG2 | 15 | 0 | 100% | 2022-10-03 | 2022-10-24 |  | FAXA | CMU | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.5 | SG2 | SG2 | 01835 | 0 | 0 | SG2-01835 | Construction | Concrete Shelf Construction | Construction.4.2.1.EFPC.5 | Place waterproofing on CMU around bldg perimeter --> SG2 | 10 | 0 | 100% | 2022-10-25 | 2022-11-08 |  | 0 | WATERPROOFING | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.5 | SG2 | SG2 | 01840 | 0 | 0 | SG2-01840 | Construction | Concrete Shelf Construction | Construction.4.2.1.EFPC.5 | Place window frames around bldg perimeter --> SG2 | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | -13 | MLJ | CONCRETE SHELF | PLACE WINDOWS | 0 | 0-SG2
In Progress | CI NYCHA Update #22.Construction.4.2.1.EFPC.5 | SG2 | SG2 | 01845 | 0 | 0 | SG2-01845 | Construction | Concrete Shelf Construction | Construction.4.2.1.EFPC.5 | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> SG2 | 20 | 2 | 90% | 2022-11-01 | 2022-12-12 17:00 | -13 | FAXA | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.5 | SG2 | SG2 | 01850 | 0 | 0 | SG2-01850 | Construction | Concrete Shelf Construction | Construction.4.2.1.EFPC.5 | Backfill around bdg perimeter --> SG2 | 5 | 5 | 0% | 2022-12-13 08:00 | 2022-12-19 17:00 | -13 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.5 | SG2 | SG2 | 01855 | 0 | 0 | SG2-01855 | Construction | Concrete Shelf Construction | Construction.4.2.1.EFPC.5 | Place frame / stucco / and signs at entrances --> SG2 | 4 | 4 | 0% | 2022-12-20 08:00 | 2022-12-23 17:00 | 93 | CCC | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.5 | SG2 | SG2 | 01860 | 0 | 0 | SG2-01860 | Construction | Concrete Shelf Construction | Construction.4.2.1.EFPC.5 | Place window floodgates at windows --> SG2 | 5 | 5 | 0% | 2022-12-27 08:00 | 2023-01-03 17:00 | 93 | MLJ | FLOOD PROTECTION | FLOOD WINDOWS | 10-1400 | 10-1400-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.5 | SG2 | SG2 | 01865 | 0 | 0 | SG2-01865 | Construction | Concrete Shelf Construction | Construction.4.2.1.EFPC.5 | Install signs --> SG2 | 3 | 3 | 0% | 2023-01-04 08:00 | 2023-01-06 17:00 | 93 | MLJ | SIGNS | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.5 | SG2 | SG2 | 01350 | 0 | 0 | SG2-01350 | Construction | Boiler Room Construction | Construction.4.2.1.5 | Drill dowels and place rebar for boiler room concrete walls --> SG2 | 5 | 5 | 0% | 2022-12-02 08:00 | 2022-12-08 17:00 | 75 | MLJ | 0 | DRILL & DOWEL | 03-1400 | 03-1400-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.5 | SG2 | SG2 | 01355 | 0 | 0 | SG2-01355 | Construction | Boiler Room Construction | Construction.4.2.1.5 | Form boiler room concrete walls --> SG2 | 5 | 5 | 0% | 2022-12-09 08:00 | 2022-12-15 17:00 | 75 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.5 | SG2 | SG2 | 01360 | 0 | 0 | SG2-01360 | Construction | Boiler Room Construction | Construction.4.2.1.5 | Pour Concrete boiler room walls --> SG2 | 2 | 2 | 0% | 2022-12-16 08:00 | 2022-12-19 17:00 | 75 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.5 | SG2 | SG2 | 01365 | 0 | 0 | SG2-01365 | Construction | Boiler Room Construction | Construction.4.2.1.5 | Strip Forms boiler room concrete walls --> SG2 | 3 | 3 | 0% | 2022-12-20 08:00 | 2022-12-22 17:00 | 77 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.5 | SG2 | SG2 | 01370 | 0 | 0 | SG2-01370 | Construction | Boiler Room Construction | Construction.4.2.1.5 | Place crystaline waterproofing on perimeter walls - cellar --> SG2 - N/R, Bulletin 5 | 10 | 0 | 100% | 2022-07-01 08:00 | 2022-07-01 17:00 |  | 0 | WATERPROOFING | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.6 | SG2 | SG2 | 01385 | 0 | 0 | SG2-01385 | Construction | Elevator Refurbishment | Construction.4.2.1.6 | Refurbish Elevator 1 --> SG2 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.6 | SG2 | SG2 | 01390 | 0 | 0 | SG2-01390 | Construction | Elevator Refurbishment | Construction.4.2.1.6 | Refurbish Elevator 2 --> SG2 (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.6 | SG2 | SG2 | 01380 | 0 | 0 | SG2-01380 | Construction | Elevator Refurbishment | Construction.4.2.1.6 | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.7 | SG2 | SG2 | 09005 | 0 | 0 | SG2-09005 | Construction | Civil/Architectural Inspections | Construction.4.2.1.7 | Perform Inspections & Issue Punch List | 5 | 5 | 0% | 2023-10-24 08:00 | 2023-10-30 17:00 | -132 | MLJ | PUNCH LIST | INSPECTION | 99-8200 | 99-8200-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.7 | SG2 | SG2 | 09010 | 0 | 0 | SG2-09010 | Construction | Civil/Architectural Inspections | Construction.4.2.1.7 | Perform Punch List | 10 | 10 | 0% | 2023-10-31 08:00 | 2023-11-15 17:00 | -117 | MLJ | PUNCH LIST | 0 | 99-8200 | 99-8200-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.2 | SG2 | SG2 | 01220 | 0 | 0 | SG2-01220 | Construction | Interior Demolition | Construction.4.2.1.2 | Selective Demo (Pumps etc..) - Cellar --> SG2 | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | 25 | MLJ | DEMO | DEMO PUMPS | 02-6010 | 02-6010-SG2
Completed | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 03005 | 0 | 0 | SG3-03005 | Construction | Cellar | Construction.4.3.8.1 | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 100% | 2022-03-10 | 2022-04-11 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 03010 | 0 | 0 | SG3-03010 | Construction | Cellar | Construction.4.3.8.1 | Install Condensate Pump - Cellar | 10 | 0 | 100% | 2022-07-25 08:00 | 2022-08-01 17:00 |  | WELKIN | 0 | 0 | 0 | 0-SG3
In Progress | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 03020 | 0 | 0 | SG3-03020 | Construction | Cellar | Construction.4.3.8.1 | Install Pump Controls - Cellar | 20 | 5 | 75% | 2022-07-27 08:00 | 2022-12-01 17:00 | 11 | MEP | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 03025 | 0 | 0 | SG3-03025 | Construction | Cellar | Construction.4.3.8.1 | Perform Hydrostatic Testing - Cellar | 5 | 5 | 0% | 2023-04-06 08:00 | 2023-04-12 17:00 | -74 | WELKIN | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 03030 | 0 | 0 | SG3-03030 | Construction | Cellar | Construction.4.3.8.1 | Install Plumbing Equipment - Cellar | 15 | 0 | 100% | 2022-07-27 08:00 | 2022-10-03 |  | 0 | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 03035 | 0 | 0 | SG3-03035 | Construction | Cellar | Construction.4.3.8.1 | Pump Equipment Start-up & Balance - Cellar | 10 | 10 | 0% | 2023-04-13 08:00 | 2023-04-26 17:00 | -63 | UNSURE | STARTUP | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 03040 | 0 | 0 | SG3-03040 | Construction | Cellar | Construction.4.3.8.1 | Plumbing/Mechanical Insulation - Cellar | 20 | 20 | 0% | 2023-04-27 08:00 | 2023-05-24 17:00 | -63 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 03015 | 0 | 0 | SG3-03015 | Construction | Cellar | Construction.4.3.8.1 | Install Steam Traps - Cellar | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | 14 | WELKIN | 0 | 0 | 0 | 0-SG3
In Progress | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 03007 | 0 | 0 | SG3-03007 | Construction | Cellar | Construction.4.3.8.1 | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 8 | 60% | 2022-09-26 08:00 | 2022-12-06 17:00 | -32 | WELKIN | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 03032 | 0 | 0 | SG3-03032 | Construction | Cellar | Construction.4.3.8.1 | Install Mechanical Equipment - Cellar | 20 | 20 | 0% | 2022-12-07 08:00 | 2023-01-05 17:00 | -12 | WELKIN | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Construction.4.3.8.2 | SG3 | SG3 | 03105 | 0 | 0 | SG3-03105 | Construction | 1st Floor | Construction.4.3.8.2 | Rough-In Plumbing Piping & Appurtenances - 1st Floor - N/A | 10 | 0 | 100% | 2022-03-25 08:00 | 2022-03-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.2 | SG3 | SG3 | 03120 | 0 | 0 | SG3-03120 | Construction | 1st Floor | Construction.4.3.8.2 | Install HVAC Controls - 1st Floor | 20 | 20 | 0% | 2023-01-13 08:00 | 2023-02-10 17:00 | -32 | WELKIN | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.2 | SG3 | SG3 | 03125 | 0 | 0 | SG3-03125 | Construction | 1st Floor | Construction.4.3.8.2 | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 0% | 2023-04-13 08:00 | 2023-04-19 17:00 | -74 | WELKIN | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.2 | SG3 | SG3 | 03130 | 0 | 0 | SG3-03130 | Construction | 1st Floor | Construction.4.3.8.2 | Install Mechanical Louvers - 1st Floor | 15 | 15 | 0% | 2022-12-21 08:00 | 2023-01-12 17:00 | -32 | UNSURE | MECHANICAL LOUVERS | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.2 | SG3 | SG3 | 03135 | 0 | 0 | SG3-03135 | Construction | 1st Floor | Construction.4.3.8.2 | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 0% | 2023-04-20 08:00 | 2023-05-03 17:00 | -68 | WELKIN | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.2 | SG3 | SG3 | 03140 | 0 | 0 | SG3-03140 | Construction | 1st Floor | Construction.4.3.8.2 | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 0% | 2023-05-04 08:00 | 2023-06-01 17:00 | -68 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.2 | SG3 | SG3 | 03115 | 0 | 0 | SG3-03115 | Construction | 1st Floor | Construction.4.3.8.2 | Install Steam Traps - 1st Floor | 1 | 1 | 0% | 2022-12-21 08:00 | 2022-12-21 17:00 | 2 | WELKIN | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.2 | SG3 | SG3 | 03110 | 0 | 0 | SG3-03110 | Construction | 1st Floor | Construction.4.3.8.2 | Install Ductwork and Appurtenances - 1st Floor | 5 | 5 | 0% | 2022-12-07 08:00 | 2022-12-13 17:00 | -32 | WELKIN | DUCTWORK | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.2 | SG3 | SG3 | 03112 | 0 | 0 | SG3-03112 | Construction | 1st Floor | Construction.4.3.8.2 | Install HV & EF Units - 1st Floor | 5 | 5 | 0% | 2022-12-14 08:00 | 2022-12-20 17:00 | -32 | MEP | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.2 | SG3 | SG3 | 03107 | 0 | 0 | SG3-03107 | Construction | 1st Floor | Construction.4.3.8.2 | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 10 | 0% | 2022-12-07 08:00 | 2022-12-20 17:00 | -31 | WELKIN | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 03205 | 0 | 0 | SG3-03205 | Construction | 2nd Floor | Construction.4.3.8.3 | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 10 | 0 | 100% | 2021-07-26 | 2021-07-26 17:00 |  | 0 | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 03220 | 0 | 0 | SG3-03220 | Construction | 2nd Floor | Construction.4.3.8.3 | Install HVAC Controls - 2nd Floor | 20 | 20 | 0% | 2023-01-30 08:00 | 2023-02-27 17:00 | -31 | WELKIN | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 03230 | 0 | 0 | SG3-03230 | Construction | 2nd Floor | Construction.4.3.8.3 | Install Mechanical Louvers - 2nd Floor | 15 | 15 | 0% | 2022-12-21 08:00 | 2023-01-12 17:00 | -31 | UNSURE | MECHANICAL LOUVERS | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 03235 | 0 | 0 | SG3-03235 | Construction | 2nd Floor | Construction.4.3.8.3 | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 0% | 2023-02-28 08:00 | 2023-03-13 17:00 | -31 | WELKIN | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 03240 | 0 | 0 | SG3-03240 | Construction | 2nd Floor | Construction.4.3.8.3 | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 0% | 2023-03-14 08:00 | 2023-04-10 17:00 | -31 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 03210 | 0 | 0 | SG3-03210 | Construction | 2nd Floor | Construction.4.3.8.3 | Install Ductwork and Appurtenances - 2nd Floor | 5 | 5 | 0% | 2023-01-13 08:00 | 2023-01-20 17:00 | -31 | WELKIN | DUCTWORK | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.3 | SG3 | SG3 | 03215 | 0 | 0 | SG3-03215 | Construction | 2nd Floor | Construction.4.3.8.3 | Install EF Units - 2nd Floor | 5 | 5 | 0% | 2023-01-23 08:00 | 2023-01-27 17:00 | -31 | MEP | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.4 | SG3 | SG3 | 03305 | 0 | 0 | SG3-03305 | Construction | Testing & Start-Up | Construction.4.3.8.4 | DOB Mechanical/Plumbing Inspection - SG3 | 4 | 4 | 0% | 2023-06-02 08:00 | 2023-06-07 17:00 | -68 | UNSURE | INSPECTION | INSPECTION | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.4 | SG3 | SG3 | 03310 | 0 | 0 | SG3-03310 | Construction | Testing & Start-Up | Construction.4.3.8.4 | Perform Start-Up Testing - SG3 | 10 | 10 | 0% | 2023-09-26 08:00 | 2023-10-09 17:00 | -136 | UNSURE | STARTUP | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.4 | SG3 | SG3 | 03320 | 0 | 0 | SG3-03320 | Construction | Testing & Start-Up | Construction.4.3.8.4 | Perform Punch List - Electrical/Mechanical/Plumbing Work - SG3 | 5 | 5 | 0% | 2023-10-10 08:00 | 2023-10-17 17:00 | -112 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.4 | SG3 | SG3 | 03330 | 0 | 0 | SG3-03330 | Construction | Testing & Start-Up | Construction.4.3.8.4 | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - SG3 | 4 | 4 | 0% | 2023-10-19 08:00 | 2023-10-24 17:00 | -108 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.4 | SG3 | SG3 | 03325 | 0 | 0 | SG3-03325 | Construction | Testing & Start-Up | Construction.4.3.8.4 | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - SG3 | 1 | 1 | 0% | 2023-10-18 08:00 | 2023-10-18 17:00 | -112 | FSE | INSPECTION | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.8.4 | SG3 | SG3 | 03335 | 0 | 0 | SG3-03335 | Construction | Testing & Start-Up | Construction.4.3.8.4 | Remove Redundant Services - SG3 | 10 | 10 | 0% | 2023-10-10 08:00 | 2023-10-24 17:00 | -136 | UNSURE | STARTUP | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.4.7.8.3 | SG1 | SG1 | 03305 | 0 | 0 | SG1-03305 | Construction | Testing & Start-Up | Construction.4.7.8.3 | DOB Mechanical/Plumbing Inspection - SG1 | 4 | 4 | 0% | 2023-06-16 08:00 | 2023-06-21 17:00 | -74 | UNSURE | INSPECTION | INSPECTION | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.3 | SG1 | SG1 | 03310 | 0 | 0 | SG1-03310 | Construction | Testing & Start-Up | Construction.4.7.8.3 | Perform Start-Up Testing - SG1 | 10 | 10 | 0% | 2023-09-20 08:00 | 2023-10-03 17:00 | -132 | UNSURE | STARTUP | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.3 | SG1 | SG1 | 03320 | 0 | 0 | SG1-03320 | Construction | Testing & Start-Up | Construction.4.7.8.3 | Perform Punch List - Electrical/Mechanical/Plumbing Work - SG1 | 5 | 5 | 0% | 2023-10-04 08:00 | 2023-10-10 17:00 | -107 | FSE | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.3 | SG1 | SG1 | 03330 | 0 | 0 | SG1-03330 | Construction | Testing & Start-Up | Construction.4.7.8.3 | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - SG1 | 4 | 4 | 0% | 2023-10-20 08:00 | 2023-10-25 17:00 | -109 | FSE | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.3 | SG1 | SG1 | 03325 | 0 | 0 | SG1-03325 | Construction | Testing & Start-Up | Construction.4.7.8.3 | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - SG1 | 1 | 1 | 0% | 2023-10-19 08:00 | 2023-10-19 17:00 | -112 | FSE | INSPECTION | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.3 | SG1 | SG1 | 03335 | 0 | 0 | SG1-03335 | Construction | Testing & Start-Up | Construction.4.7.8.3 | Remove Redundant Services - SG1 | 10 | 10 | 0% | 2023-10-04 08:00 | 2023-10-18 17:00 | -132 | UNSURE | STARTUP | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.8.2 | SG1 | SG1 | 03105 | 0 | 0 | SG1-03105 | Construction | 1st Floor | Construction.4.7.8.2 | Rough-In Plumbing Piping & Appurtenances - 1st Floor N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.8.2 | SG1 | SG1 | 03120 | 0 | 0 | SG1-03120 | Construction | 1st Floor | Construction.4.7.8.2 | Install HVAC Controls - 1st Floor | 20 | 0 | 100% | 2022-06-10 | 2022-06-24 |  | 0 | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.2 | SG1 | SG1 | 03125 | 0 | 0 | SG1-03125 | Construction | 1st Floor | Construction.4.7.8.2 | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 0% | 2023-04-27 08:00 | 2023-05-03 17:00 | -74 | WELKIN | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.8.2 | SG1 | SG1 | 03130 | 0 | 0 | SG1-03130 | Construction | 1st Floor | Construction.4.7.8.2 | Install Mechanical Louvers - 1st Floor | 15 | 0 | 100% | 2022-06-20 | 2022-06-24 |  | 0 | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.2 | SG1 | SG1 | 03135 | 0 | 0 | SG1-03135 | Construction | 1st Floor | Construction.4.7.8.2 | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 0% | 2023-05-04 08:00 | 2023-05-17 17:00 | -74 | WELKIN | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.2 | SG1 | SG1 | 03140 | 0 | 0 | SG1-03140 | Construction | 1st Floor | Construction.4.7.8.2 | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 0% | 2023-05-18 08:00 | 2023-06-15 17:00 | -74 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.8.2 | SG1 | SG1 | 03115 | 0 | 0 | SG1-03115 | Construction | 1st Floor | Construction.4.7.8.2 | Install Steam Traps - 1st Floor | 1 | 0 | 100% | 2022-05-27 | 2022-06-03 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.8.2 | SG1 | SG1 | 03110 | 0 | 0 | SG1-03110 | Construction | 1st Floor | Construction.4.7.8.2 | Install Ductwork and Appurtenances - 1st Floor | 5 | 0 | 100% | 2022-05-25 | 2022-06-24 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.8.2 | SG1 | SG1 | 03112 | 0 | 0 | SG1-03112 | Construction | 1st Floor | Construction.4.7.8.2 | Install HV & EF Units - 1st Floor | 5 | 0 | 100% | 2022-05-19 | 2022-05-20 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.8.2 | SG1 | SG1 | 03107 | 0 | 0 | SG1-03107 | Construction | 1st Floor | Construction.4.7.8.2 | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 0 | 100% | 2022-05-25 | 2022-06-24 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 03005 | 0 | 0 | SG1-03005 | Construction | Cellar | Construction.4.7.8.1 | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 100% | 2022-03-10 | 2022-04-11 |  | 0 | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 03010 | 0 | 0 | SG1-03010 | Construction | Cellar | Construction.4.7.8.1 | Install Condensate Pump - Cellar | 10 | 10 | 0% | 2022-12-02 08:00 | 2022-12-15 17:00 | 11 | WELKIN | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 03020 | 0 | 0 | SG1-03020 | Construction | Cellar | Construction.4.7.8.1 | Install Pump Controls - Cellar | 20 | 0 | 100% | 2022-10-25 | 2022-11-18 |  | 0 | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 03025 | 0 | 0 | SG1-03025 | Construction | Cellar | Construction.4.7.8.1 | Perform Hydrostatic Testing - Cellar | 5 | 5 | 0% | 2023-04-20 08:00 | 2023-04-26 17:00 | -74 | WELKIN | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 03030 | 0 | 0 | SG1-03030 | Construction | Cellar | Construction.4.7.8.1 | Install Plumbing Equipment - Cellar | 15 | 0 | 100% | 2022-10-25 | 2022-11-18 |  | 0 | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 03035 | 0 | 0 | SG1-03035 | Construction | Cellar | Construction.4.7.8.1 | Pump Equipment Start-up & Balance - Cellar | 10 | 10 | 0% | 2023-04-27 08:00 | 2023-05-10 17:00 | -69 | UNSURE | STARTUP | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 03040 | 0 | 0 | SG1-03040 | Construction | Cellar | Construction.4.7.8.1 | Plumbing/Mechanical Insulation - Cellar | 20 | 20 | 0% | 2023-05-11 08:00 | 2023-06-08 17:00 | -69 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 03015 | 0 | 0 | SG1-03015 | Construction | Cellar | Construction.4.7.8.1 | Install Steam Traps - Cellar | 2 | 0 | 100% | 2022-08-22 08:00 | 2022-09-02 08:48 |  | WELKIN | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 03007 | 0 | 0 | SG1-03007 | Construction | Cellar | Construction.4.7.8.1 | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 0 | 100% | 2021-07-26 | 2021-12-20 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 03032 | 0 | 0 | SG1-03032 | Construction | Cellar | Construction.4.7.8.1 | Install Mechanical Equipment - Cellar | 20 | 0 | 100% | 2021-07-26 08:00 | 2021-12-20 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 03005 | 0 | 0 | SG2-03005 | Construction | Cellar | Construction.4.2.4.1 | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 100% | 2022-01-31 | 2022-02-18 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 03010 | 0 | 0 | SG2-03010 | Construction | Cellar | Construction.4.2.4.1 | Install Condensate Pump - Cellar | 10 | 0 | 100% | 2022-07-27 08:00 | 2022-08-05 17:00 |  | WELKIN | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 03020 | 0 | 0 | SG2-03020 | Construction | Cellar | Construction.4.2.4.1 | Install Pump Controls - Cellar | 20 | 20 | 0% | 2022-11-25 08:00 | 2022-12-22 17:00 | 15 | MEP | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 03025 | 0 | 0 | SG2-03025 | Construction | Cellar | Construction.4.2.4.1 | Perform Hydrostatic Testing - Cellar | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | 15 | WELKIN | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 03030 | 0 | 0 | SG2-03030 | Construction | Cellar | Construction.4.2.4.1 | Install Plumbing Equipment - Cellar | 15 | 0 | 100% | 2022-10-27 | 2022-11-18 |  | 0 | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 03035 | 0 | 0 | SG2-03035 | Construction | Cellar | Construction.4.2.4.1 | Pump Equipment Start-up & Balance - Cellar | 10 | 10 | 0% | 2023-01-03 08:00 | 2023-01-17 17:00 | 15 | UNSURE | STARTUP | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 03040 | 0 | 0 | SG2-03040 | Construction | Cellar | Construction.4.2.4.1 | Plumbing/Mechanical Insulation - Cellar | 20 | 20 | 0% | 2023-01-18 08:00 | 2023-02-14 17:00 | 15 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 03015 | 0 | 0 | SG2-03015 | Construction | Cellar | Construction.4.2.4.1 | Install Steam Traps - Cellar | 2 | 0 | 100% | 2021-09-07 | 2021-12-20 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 03007 | 0 | 0 | SG2-03007 | Construction | Cellar | Construction.4.2.4.1 | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 0 | 100% | 2021-09-07 | 2021-12-20 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 03032 | 0 | 0 | SG2-03032 | Construction | Cellar | Construction.4.2.4.1 | Install Mechanical Equipment - Cellar | 20 | 0 | 100% | 2021-09-07 | 2021-12-20 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.4.2 | SG2 | SG2 | 03105 | 0 | 0 | SG2-03105 | Construction | 1st Floor | Construction.4.2.4.2 | Rough-In Plumbing Piping & Appurtenances - 1st Floor - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-SG2
In Progress | CI NYCHA Update #22.Construction.4.2.4.2 | SG2 | SG2 | 03120 | 0 | 0 | SG2-03120 | Construction | 1st Floor | Construction.4.2.4.2 | Install HVAC Controls - 1st Floor | 20 | 10 | 50% | 2022-08-08 08:00 | 2022-12-08 17:00 | 30 | WELKIN | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.2 | SG2 | SG2 | 03125 | 0 | 0 | SG2-03125 | Construction | 1st Floor | Construction.4.2.4.2 | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | 25 | WELKIN | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.2 | SG2 | SG2 | 03130 | 0 | 0 | SG2-03130 | Construction | 1st Floor | Construction.4.2.4.2 | Install Mechanical Louvers - 1st Floor | 15 | 15 | 0% | 2022-11-25 08:00 | 2022-12-15 17:00 | 25 | UNSURE | MECHANICAL LOUVERS | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.2 | SG2 | SG2 | 03135 | 0 | 0 | SG2-03135 | Construction | 1st Floor | Construction.4.2.4.2 | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 0% | 2022-12-23 08:00 | 2023-01-09 17:00 | 25 | WELKIN | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.2 | SG2 | SG2 | 03140 | 0 | 0 | SG2-03140 | Construction | 1st Floor | Construction.4.2.4.2 | Plumbing/Mechanical Insulation - 1st Floor | 15 | 15 | 0% | 2023-01-10 08:00 | 2023-01-31 17:00 | 25 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.4.2 | SG2 | SG2 | 03115 | 0 | 0 | SG2-03115 | Construction | 1st Floor | Construction.4.2.4.2 | Install Steam Traps - 1st Floor | 1 | 0 | 100% | 2022-09-20 08:00 | 2022-09-23 08:24 |  | WELKIN | 0 | 0 | 0 | 0-SG2
In Progress | CI NYCHA Update #22.Construction.4.2.4.2 | SG2 | SG2 | 03110 | 0 | 0 | SG2-03110 | Construction | 1st Floor | Construction.4.2.4.2 | Install Ductwork and Appurtenances - 1st Floor | 5 | 1 | 90% | 2022-08-25 08:00 | 2022-12-15 17:00 | 25 | WELKIN | DUCTWORK | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.4.2 | SG2 | SG2 | 03112 | 0 | 0 | SG2-03112 | Construction | 1st Floor | Construction.4.2.4.2 | Install HV & EF Units - 1st Floor | 5 | 0 | 100% | 2022-08-25 08:00 | 2022-09-02 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.4.2.4.2 | SG2 | SG2 | 03107 | 0 | 0 | SG2-03107 | Construction | 1st Floor | Construction.4.2.4.2 | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 0 | 100% | 2022-07-25 08:00 | 2022-07-29 17:00 |  | WELKIN | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.3 | SG2 | SG2 | 03305 | 0 | 0 | SG2-03305 | Construction | Testing & Start-Up | Construction.4.2.4.3 | DOB Mechanical/Plumbing Inspection - SG2 | 4 | 4 | 0% | 2023-06-22 08:00 | 2023-06-27 17:00 | -74 | UNSURE | INSPECTION | INSPECTION | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.3 | SG2 | SG2 | 03310 | 0 | 0 | SG2-03310 | Construction | Testing & Start-Up | Construction.4.2.4.3 | Perform Start-Up Testing - SG2 | 10 | 10 | 0% | 2023-09-20 08:00 | 2023-10-03 17:00 | -132 | UNSURE | STARTUP | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.3 | SG2 | SG2 | 03320 | 0 | 0 | SG2-03320 | Construction | Testing & Start-Up | Construction.4.2.4.3 | Perform Punch List - Electrical/Mechanical/Plumbing Work - SG2 | 5 | 5 | 0% | 2023-10-04 08:00 | 2023-10-10 17:00 | -106 | FSE | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.3 | SG2 | SG2 | 03330 | 0 | 0 | SG2-03330 | Construction | Testing & Start-Up | Construction.4.2.4.3 | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - SG2 | 4 | 4 | 0% | 2023-10-23 08:00 | 2023-10-26 17:00 | -110 | FSE | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.3 | SG2 | SG2 | 03325 | 0 | 0 | SG2-03325 | Construction | Testing & Start-Up | Construction.4.2.4.3 | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - SG2 | 1 | 1 | 0% | 2023-10-20 08:00 | 2023-10-20 17:00 | -112 | FSE | INSPECTION | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.4.3 | SG2 | SG2 | 03335 | 0 | 0 | SG2-03335 | Construction | Testing & Start-Up | Construction.4.2.4.3 | Remove Redundant Services - SG2 | 10 | 10 | 0% | 2023-10-04 08:00 | 2023-10-18 17:00 | -132 | UNSURE | STARTUP | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.8.3.Removals1 | S8 | S8 | 01005 | 0 | 0 | S8-01005 | Construction | Site Protection & Removals | Construction.8.3.Removals1 | Install Site Fencing - Site 8 | 10 | 0 | 100% | 2021-07-12 08:00 | 2021-10-15 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.Removals1 | S8 | S8 | 01015 | 0 | 0 | S8-01015 | Construction | Site Protection & Removals | Construction.8.3.Removals1 | Install Overhead Protection - N/A | 10 | 0 | 100% | 2022-02-25 | 2022-02-25 |  | 0 | 0 | 0 | 01-6300 | 01-6300-S8
Completed | CI NYCHA Update #22.Construction.8.3.Removals1 | S8 | S8 | 01020 | 0 | 0 | S8-01020 | Construction | Site Protection & Removals | Construction.8.3.Removals1 | Install Tree Protection | 10 | 0 | 100% | 2020-11-06 | 2020-11-11 17:00 |  | 0 | 0 | 0 | 31-1900 | 31-1900-S8
Completed | CI NYCHA Update #22.Construction.8.3.Removals1 | S8 | S8 | 01025 | 0 | 0 | S8-01025 | Construction | Site Protection & Removals | Construction.8.3.Removals1 | Remove Trees | 2 | 0 | 100% | 2021-05-10 | 2022-05-10 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.Removals1 | S8 | S8 | 01000 | 0 | 0 | S8-01000 | Construction | Site Protection & Removals | Construction.8.3.Removals1 | Remove Curbs And Existing Fencing | 10 | 0 | 100% | 2021-05-10 | 2022-05-10 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.Removals1 | S8 | S8 | 01035 | 0 | 0 | S8-01035 | Construction | Site Protection & Removals | Construction.8.3.Removals1 | Install Erosion Control | 5 | 0 | 100% | 2022-03-01 | 2022-05-10 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.Removals1 | S8 | S8 | 01010 | 0 | 0 | S8-01010 | Construction | Site Protection & Removals | Construction.8.3.Removals1 | Set Up Yard and Staging | 10 | 0 | 100% | 2021-01-10 | 2021-02-26 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.Removals1 | S8 | S8 | 01045 | 0 | 0 | S8-01045 | Construction | Site Protection & Removals | Construction.8.3.Removals1 | Clear & Grub | 10 | 0 | 100% | 2021-07-26 08:00 | 2022-05-10 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.Removals1 | S8 | S8 | 01050 | 0 | 0 | S8-01050 | Construction | Site Protection & Removals | Construction.8.3.Removals1 | Scrape & Store Topsoil | 10 | 0 | 100% | 2021-10-20 | 2022-05-10 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.Removals1 | S8 | S8 | 01055 | 0 | 0 | S8-01055 | Construction | Site Protection & Removals | Construction.8.3.Removals1 | Soil Testing | 10 | 0 | 100% | 2021-05-14 | 2021-06-04 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.Removals1 | S8 | S8 | 01060 | 0 | 0 | S8-01060 | Construction | Site Protection & Removals | Construction.8.3.Removals1 | Demo Playgrounds And Misc Site Furniture | 5 | 0 | 100% | 2021-07-16 08:00 | 2022-05-10 |  | 0 | 0 | 0 | 02-2000 | 02-2000-S8
Completed | CI NYCHA Update #22.Construction.8.3.Removals1 | S8 | S8 | 01065 | 0 | 0 | S8-01065 | Construction | Site Protection & Removals | Construction.8.3.Removals1 | Remove Retaining Walls | 10 | 0 | 100% | 2022-04-26 | 2022-05-10 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.Removals1 | S8 | S8 | 01070 | 0 | 0 | S8-01070 | Construction | Site Protection & Removals | Construction.8.3.Removals1 | Install Deep Wells For Dewatering | 2 | 0 | 100% | 2022-03-25 | 2022-03-25 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.Removals1 | S8 | S8 | 01075 | 0 | 0 | S8-01075 | Construction | Site Protection & Removals | Construction.8.3.Removals1 | Install Piping For Deep Wells - N/A | 5 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.Removals1 | S8 | S8 | 01080 | 0 | 0 | S8-01080 | Construction | Site Protection & Removals | Construction.8.3.Removals1 | Install Discharge Connection For Dewatering - N/A | 10 | 0 | 100% | 2022-03-25 08:00 | 2022-03-25 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.Removals1 | S8 | S8 | 01085 | 0 | 0 | S8-01085 | Construction | Site Protection & Removals | Construction.8.3.Removals1 | Run Electric For Dewatering - N/A | 10 | 0 | 100% | 2022-03-25 08:00 | 2022-03-25 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01150 | 0 | 0 | S8-01150 | Construction | Site Utilities | Construction.8.3.6 | Excavate for Electric S8.2--> S8.1 (South) | 10 | 0 | 100% | 2022-06-14 | 2022-10-21 |  | MLJ | Excavation | UTILITY EXC | 33-3100 | 33-3100-S8
Completed | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01155 | 0 | 0 | S8-01155 | Construction | Site Utilities | Construction.8.3.6 | Install Electrical Conduit S8.2--> S8.1 (South) | 5 | 0 | 100% | 2022-06-07 | 2022-11-15 |  | FSE | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01160 | 0 | 0 | S8-01160 | Construction | Site Utilities | Construction.8.3.6 | Encase conduit in concrete S8.2--> S8.1 (South) | 5 | 0 | 100% | 2022-11-03 | 2022-11-03 |  | MLJ | Concrete | SITE CONCRETE | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01165 | 0 | 0 | S8-01165 | Construction | Site Utilities | Construction.8.3.6 | Backfill Electrical S8.2--> S8.1 (South) | 5 | 0 | 100% | 2022-11-03 | 2022-11-04 |  | MLJ | BACKFILL | BACKFILL UTILITY | 31-2200 | 31-2200-S8
Not Started | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01405 | 0 | 0 | S8-01405 | Construction | Site Utilities | Construction.8.3.6 | Gas Line Installation - W36th Street to S8-2 (by National Gas) | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | -35 | NATIONAL GRID | GAS INSTALL | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01205 | 0 | 0 | S8-01205 | Construction | Site Utilities | Construction.8.3.6 | Excavate for Electric S8.2--> S8.1 (North) | 3 | 0 | 100% | 2022-04-10 | 2022-06-06 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01210 | 0 | 0 | S8-01210 | Construction | Site Utilities | Construction.8.3.6 | Install Electrical Conduit S8.2--> S8.1 (North) | 5 | 0 | 100% | 2022-04-05 08:00 | 2022-06-01 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01215 | 0 | 0 | S8-01215 | Construction | Site Utilities | Construction.8.3.6 | Encase conduit in concrete S8.2--> S8.1 (North) | 2 | 0 | 100% | 2022-06-10 | 2022-06-10 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01220 | 0 | 0 | S8-01220 | Construction | Site Utilities | Construction.8.3.6 | Backfill Electrical S8.2--> S8.1 (North) | 2 | 0 | 100% | 2022-06-13 | 2022-06-13 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01255 | 0 | 0 | S8-01255 | Construction | Site Utilities | Construction.8.3.6 | Excavate for Electric S8.2--> MH | 3 | 0 | 100% | 2022-06-06 | 2022-08-05 17:00 |  | MLJ | Excavation | UTILITY EXC | 33-3100 | 33-3100-S8
Completed | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01260 | 0 | 0 | S8-01260 | Construction | Site Utilities | Construction.8.3.6 | Install Electrical Conduit S8.2--> MH | 5 | 0 | 100% | 2022-06-07 | 2022-08-09 |  | FSE | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01265 | 0 | 0 | S8-01265 | Construction | Site Utilities | Construction.8.3.6 | Encase conduit in concrete S8.2--> MH | 2 | 0 | 100% | 2022-08-10 | 2022-08-10 |  | MLJ | Concrete | SITE CONCRETE | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01270 | 0 | 0 | S8-01270 | Construction | Site Utilities | Construction.8.3.6 | Backfill Electric S8.2--> MH | 2 | 0 | 100% | 2022-08-11 | 2022-08-11 |  | MLJ | BACKFILL | BACKFILL UTILITY | 31-2200 | 31-2200-S8
Not Started | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01505 | 0 | 0 | S8-01505 | Construction | Site Utilities | Construction.8.3.6 | Excavate for water line - S8 Fountain & Playground --> Water Main Surf Avenue | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | -43 | MLJ | EXCAVATION | PLAYGROUND | 11-6010 | 11-6010-S8
Not Started | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01510 | 0 | 0 | S8-01510 | Construction | Site Utilities | Construction.8.3.6 | Install water line - S8 Fountain & Playground --> Water Main Surf Avenue | 5 | 5 | 0% | 2022-12-12 08:00 | 2022-12-16 17:00 | -1 | UNSURE | PLAYGROUND | PLUMBING | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01515 | 0 | 0 | S8-01515 | Construction | Site Utilities | Construction.8.3.6 | Tap water main for S8 Fountain & Playground --> Water Main Surf Avenue | 2 | 2 | 0% | 2022-12-19 08:00 | 2022-12-20 17:00 | -1 | UNSURE | PLAYGROUND | PLUMBING | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01520 | 0 | 0 | S8-01520 | Construction | Site Utilities | Construction.8.3.6 | Backfill water line - S8 Fountain & Playground --> Water Main Surf Avenue | 2 | 2 | 0% | 2022-12-21 08:00 | 2022-12-22 17:00 | -1 | MLJ | BACKFILL | BACKFILL UTILITY | 31-2200 | 31-2200-S8
Not Started | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01560 | 0 | 0 | S8-01560 | Construction | Site Utilities | Construction.8.3.6 | Excavate and Install Area Drains AD10> Existing+ Piping | 15 | 15 | 0% | 2023-01-11 08:00 | 2023-02-01 17:00 | -27 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-S8
Not Started | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01565 | 0 | 0 | S8-01565 | Construction | Site Utilities | Construction.8.3.6 | Backfill Area Drains AD10> Existing+ Piping | 5 | 5 | 0% | 2023-02-02 08:00 | 2023-02-08 17:00 | -27 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-S8
Completed | CI NYCHA Update #22.Construction.8.3.Removals1 | S8 | S8 | 01090 | 0 | 0 | S8-01090 | Construction | Site Protection & Removals | Construction.8.3.Removals1 | Activate Dewatering System | 1 | 0 | 100% | 2022-05-11 | 2022-05-11 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.Removals1 | S8 | S8 | 01095 | 0 | 0 | S8-01095 | Construction | Site Protection & Removals | Construction.8.3.Removals1 | Maintain Dewatering | 255 | 0 | 100% | 2022-05-11 | 2022-07-15 15:00 |  | 0 | dewatering | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.Removals1 | S8 | S8 | 01100 | 0 | 0 | S8-01100 | Construction | Site Protection & Removals | Construction.8.3.Removals1 | De-Activate Dewatering | 1 | 0 | 100% | 2022-07-15 15:00 | 2022-07-15 15:00 |  | 0 | 0 | 0 | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01650 | 0 | 0 | S8-01650 | Construction | Site Utilities | Construction.8.3.6 | Excavate and Install Area Drains - AD6 > AD8 > AD9 to Existing & Piping | 15 | 15 | 0% | 2022-11-29 08:00 | 2022-12-19 17:00 | -43 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-S8
Not Started | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01655 | 0 | 0 | S8-01655 | Construction | Site Utilities | Construction.8.3.6 | Backfill Area Drains - AD6 > AD8 > AD9 to Existing & Piping | 5 | 5 | 0% | 2022-12-20 08:00 | 2022-12-27 17:00 | 2 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-S8
Not Started | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01660 | 0 | 0 | S8-01660 | Construction | Site Utilities | Construction.8.3.6 | Excavate and Install Area Drains - AD5 > Existing + Piping | 15 | 15 | 0% | 2022-12-20 08:00 | 2023-01-11 17:00 | -43 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-S8
Not Started | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01665 | 0 | 0 | S8-01665 | Construction | Site Utilities | Construction.8.3.6 | Backfill Area Drains - AD5 > Existing + Piping | 5 | 5 | 0% | 2023-01-12 08:00 | 2023-01-19 17:00 | -13 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-S8
Not Started | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01670 | 0 | 0 | S8-01670 | Construction | Site Utilities | Construction.8.3.6 | Excavate and Install Area Drains - Yard Drain > Existing + Piping | 15 | 15 | 0% | 2023-01-12 08:00 | 2023-02-02 17:00 | -43 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-S8
Not Started | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01675 | 0 | 0 | S8-01675 | Construction | Site Utilities | Construction.8.3.6 | Backfill Area Drains - Yard Drain > Existing + Piping | 5 | 5 | 0% | 2023-02-03 08:00 | 2023-02-09 17:00 | -28 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-S8
Not Started | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01680 | 0 | 0 | S8-01680 | Construction | Site Utilities | Construction.8.3.6 | Excavate and Install Area Drains - AD1 > AD2 > Existing + Piping | 15 | 15 | 0% | 2023-02-03 08:00 | 2023-02-24 17:00 | -43 | MLJ | EXCAVATION | AREA DRAIN | 33-2600 | 33-2600-S8
Not Started | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01685 | 0 | 0 | S8-01685 | Construction | Site Utilities | Construction.8.3.6 | Backfill Area Drains - AD1 > AD2 > Existing + Piping | 5 | 5 | 0% | 2023-02-27 08:00 | 2023-03-03 17:00 | -43 | MLJ | BACKFILL | BACKFILL AD | 33-2600 | 33-2600-S8
Completed | CI NYCHA Update #22.Construction.8.3.4 | S8 | S8 | 01605 | 0 | 0 | S8-01605 | Construction | Retaining Walls | Construction.8.3.4 | Excavate for retaining wall --> S8 Phase 6 | 2 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | MLJ | Excavation | EXC RETAINING | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.4 | S8 | S8 | 01610 | 0 | 0 | S8-01610 | Construction | Retaining Walls | Construction.8.3.4 | Form Retaining wall footing --> S8 Phase 6 | 2 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | MLJ | Formwork | SITE FORMWORK | 03-1600 | 03-1600-S8
Completed | CI NYCHA Update #22.Construction.8.3.4 | S8 | S8 | 01615 | 0 | 0 | S8-01615 | Construction | Retaining Walls | Construction.8.3.4 | Rebar Retaining wall footing --> S8 Phase 6 | 2 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0 | REBAR | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.4 | S8 | S8 | 01620 | 0 | 0 | S8-01620 | Construction | Retaining Walls | Construction.8.3.4 | Pour Retaining wall footing --> S8 Phase 6 | 1 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | MLJ | Concrete | SITE CONCRETE | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.4 | S8 | S8 | 01625 | 0 | 0 | S8-01625 | Construction | Retaining Walls | Construction.8.3.4 | Strip Retaining wall footing --> S8 Phase 6 | 1 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0 | Formwork | SITE FORMWORK | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.4 | S8 | S8 | 01630 | 0 | 0 | S8-01630 | Construction | Retaining Walls | Construction.8.3.4 | Form Retaining wall -->S8 Phase 6 | 3 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | MLJ | Formwork | SITE FORMWORK | 03-1600 | 03-1600-S8
Completed | CI NYCHA Update #22.Construction.8.3.4 | S8 | S8 | 01635 | 0 | 0 | S8-01635 | Construction | Retaining Walls | Construction.8.3.4 | Rebar Retaining wall --> S8 Phase 6 | 3 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0 | REBAR | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.4 | S8 | S8 | 01640 | 0 | 0 | S8-01640 | Construction | Retaining Walls | Construction.8.3.4 | Pour Retaining wall --> S8 Phase 6 | 1 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | MLJ | Concrete | SITE CONCRETE | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.4 | S8 | S8 | 01645 | 0 | 0 | S8-01645 | Construction | Retaining Walls | Construction.8.3.4 | Strip Retaining wall --> S8 Phase 6 | 1 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | 0 | Formwork | SITE FORMWORK | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.5 | S8 | S8 | 01705 | 0 | 0 | S8-01705 | Construction | Site Restoration | Construction.8.3.5 | Install Street Curbs --> S8 Phase 6 | 15 | 15 | 0% | 2023-10-19 08:00 | 2023-11-09 17:00 | -202 | MLJ | CURBS | 0 | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.5 | S8 | S8 | 01710 | 0 | 0 | S8-01710 | Construction | Site Restoration | Construction.8.3.5 | Install sidewalks --> S8 Phase 6 | 10 | 10 | 0% | 2023-11-28 08:00 | 2023-12-11 17:00 | -159 | JMC | SIDEWALKS | 0 | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.5 | S8 | S8 | 01715 | 0 | 0 | S8-01715 | Construction | Site Restoration | Construction.8.3.5 | Install curb around play area --> S8 Phase 6 | 5 | 5 | 0% | 2023-03-06 08:00 | 2023-03-10 17:00 | -23 | MLJ | CURBS | 0 | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.5 | S8 | S8 | 01720 | 0 | 0 | S8-01720 | Construction | Site Restoration | Construction.8.3.5 | Install Safety Surface --> S8 Phase 6 | 5 | 5 | 0% | 2023-11-28 08:00 | 2023-12-04 17:00 | -202 | UNSURE | PLAYGROUND | SAFETY SURFACE | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.5 | S8 | S8 | 01725 | 0 | 0 | S8-01725 | Construction | Site Restoration | Construction.8.3.5 | Install site furniture concrete foundations --> S8 Phase 6 | 10 | 10 | 0% | 2023-11-13 08:00 | 2023-11-27 17:00 | -202 | MLJ | CONCRETE | SITE CONCRETE | 03-2200 | 03-2200-S8
Not Started | CI NYCHA Update #22.Construction.8.3.5 | S8 | S8 | 01730 | 0 | 0 | S8-01730 | Construction | Site Restoration | Construction.8.3.5 | Install integrally colored concrete walkways --> S8 Phase 6 | 15 | 15 | 0% | 2023-12-05 08:00 | 2023-12-26 17:00 | -202 | JMC | COLORED CONCRETE | 0 | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.5 | S8 | S8 | 01735 | 0 | 0 | S8-01735 | Construction | Site Restoration | Construction.8.3.5 | Install Play area items --> S8 Phase 6 | 5 | 5 | 0% | 2023-12-27 08:00 | 2024-01-03 17:00 | -202 | BRIGHTON | PLAYGROUND | INSTALL | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.5 | S8 | S8 | 01740 | 0 | 0 | S8-01740 | Construction | Site Restoration | Construction.8.3.5 | Install fence around play area --> S8 Phase 6 | 10 | 10 | 0% | 2024-01-04 08:00 | 2024-01-17 17:00 | -202 | MLJ | FENCING | PLAYGROUND | 32-6520 | 32-6520-S8
Not Started | CI NYCHA Update #22.Construction.8.3.5 | S8 | S8 | 01745 | 0 | 0 | S8-01745 | Construction | Site Restoration | Construction.8.3.5 | Install Fence at building --> S8 | 5 | 5 | 0% | 2024-01-18 08:00 | 2024-01-24 17:00 | -202 | ATLAS | SITE RESTORATION | 0 | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.5 | S8 | S8 | 01750 | 0 | 0 | S8-01750 | Construction | Site Restoration | Construction.8.3.5 | Place Site Furniture --> S8 Phase 6 | 10 | 10 | 0% | 2024-01-25 08:00 | 2024-02-07 17:00 | -202 | MLJ | SITE RESTORATION | SITE FURNITURE | 31-2600 | 31-2600-S8
Not Started | CI NYCHA Update #22.Construction.8.3.5 | S8 | S8 | 01755 | 0 | 0 | S8-01755 | Construction | Site Restoration | Construction.8.3.5 | Place topsoil --> S8 Phase 6 | 3 | 3 | 0% | 2024-04-01 08:00 | 2024-04-03 17:00 | -75 | ASPEN | TOPSOIL | 0 | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.5 | S8 | S8 | 01760 | 0 | 0 | S8-01760 | Construction | Site Restoration | Construction.8.3.5 | Place trees and plantings --> S8 Phase 6 | 5 | 5 | 0% | 2024-04-04 08:00 | 2024-04-10 17:00 | -75 | ASPEN | 0 | 0 | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.5 | S8 | S8 | 01765 | 0 | 0 | S8-01765 | Construction | Site Restoration | Construction.8.3.5 | Place lawn --> SGS Phase 5 | 5 | 5 | 0% | 2024-04-11 08:00 | 2024-04-17 17:00 | -75 | ASPEN | 0 | 0 | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.5 | S8 | S8 | 01770 | 0 | 0 | S8-01770 | Construction | Site Restoration | Construction.8.3.5 | Demobilize from SGS Phase 6 | 5 | 5 | 0% | 2024-04-18 08:00 | 2024-04-24 17:00 | -228 | MLJ | DEMOB | 0 | 99-4000 | 99-4000-S8
Not Started | CI NYCHA Update #22.Construction.8.3.7 | S8 | S8 | 01850 | 0 | 0 | S8-01850 | Construction | Civil/Architectural Inspections | Construction.8.3.7 | Perform Inspections & Issue Punch List | 5 | 5 | 0% | 2024-04-18 08:00 | 2024-04-24 17:00 | -238 | MLJ | PUNCH LIST | INSPECTION | 99-8200 | 99-8200-S8
Not Started | CI NYCHA Update #22.Construction.8.3.7 | S8 | S8 | 01855 | 0 | 0 | S8-01855 | Construction | Civil/Architectural Inspections | Construction.8.3.7 | Perform Punch List | 10 | 10 | 0% | 2024-04-25 08:00 | 2024-05-08 17:00 | -238 | MLJ | PUNCH LIST | 0 | 99-8200 | 99-8200-S8
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01030 | 0 | 0 | S8A-01030 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Form Plumbing Shafts & Ftgs Below Water Table --> S8 (Addition) | 10 | 0 | 100% | 2022-05-16 | 2022-05-16 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01035 | 0 | 0 | S8A-01035 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Rebar Plumbing Shafts & Ftgs Below Water Table --> S8 (Addition) | 5 | 0 | 100% | 2022-05-16 | 2022-05-17 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01040 | 0 | 0 | S8A-01040 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Pour Plumbing Shafts & Ftgs Below Water Table --> S8 (Addition) | 2 | 0 | 100% | 2022-05-18 | 2022-05-18 |  | MLJ | concrete | NB CONCRETE | 03-1900 | 03-1900-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01045 | 0 | 0 | S8A-01045 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Strip Forms Plumbing Shafts & Ftgs Below Water Table --> S8 (Addition) | 5 | 0 | 100% | 2022-05-18 | 2022-05-18 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01025 | 0 | 0 | S8A-01025 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Waterproof/Insulation Plumbing Shaft ----> S8 (Addition) | 5 | 0 | 100% | 2022-05-18 | 2022-05-18 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01005 | 0 | 0 | S8A-01005 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Excavate/SOE For Plumbing Shaft & Ftgs/Piers Below Water Table --> S8 (Addition) | 10 | 0 | 100% | 2022-04-29 | 2022-05-11 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01020 | 0 | 0 | S8A-01020 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Prepare Subgrade For Plumbing Shafts & Ftgs / Piers Below Water Table --> S8 (Addition) | 3 | 0 | 100% | 2022-05-12 | 2022-05-13 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01055 | 0 | 0 | S8A-01055 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Backfill Plumbing Shaft & Ftgs/Piers --> S8 (Addition) | 5 | 0 | 100% | 2022-05-16 | 2022-05-16 |  | 0 | S82 | 0 | 31-1400 | 31-1400-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01065 | 0 | 0 | S8A-01065 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Excavate For Remaining Ftgs/Pier/Grade Beams --> S8 (Addition) | 10 | 0 | 100% | 2022-05-16 | 2022-05-20 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01070 | 0 | 0 | S8A-01070 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Form Remaining Ftgs/Piers/Grade Beams --> S8 (Addition) | 10 | 0 | 100% | 2022-06-01 | 2022-06-08 |  | 0 | FORMWORK | FORMWORK NB | 03-1000 | 03-1000-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01075 | 0 | 0 | S8A-01075 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Rebar Remaining Ftgs/Piers/Grade Beams --> S8 (Addition) | 10 | 0 | 100% | 2022-05-25 | 2022-06-07 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01080 | 0 | 0 | S8A-01080 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Pour Remaining Ftgs/Piers/Grade Beams --> S8 (Addition) | 5 | 0 | 100% | 2022-06-02 | 2022-06-08 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01085 | 0 | 0 | S8A-01085 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Strip Forms Remaining Ftgs/Piers/Grade Beams --> S8 (Addition) | 5 | 0 | 100% | 2022-07-18 | 2022-07-20 |  | MLJ | Formwork | NB FORMWORK | 03-1000 | 03-1000-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01090 | 0 | 0 | S8A-01090 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Remaining Steam Into S8 (Addition) (5' from the building) | 5 | 0 | 100% | 2022-09-01 | 2022-09-01 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01095 | 0 | 0 | S8A-01095 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Backfill Remaining Ftgs/Piers/Grade Beams / Prepare Subgrade --> S8 (Addition) | 5 | 0 | 100% | 2022-06-28 | 2022-07-05 |  | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01105 | 0 | 0 | S8A-01105 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Structural Steel Framing - 1st Floor --> S8 (Addition) | 10 | 0 | 100% | 2022-07-26 08:00 | 2022-08-22 17:00 |  | WEIR | STRUCTURAL STEEL | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01110 | 0 | 0 | S8A-01110 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Metal Deck --> S8 (Addition) | 2 | 0 | 100% | 2022-08-22 08:00 | 2022-08-24 17:00 |  | 0 | 0 | 0 | 0 | 0-S8A
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01115 | 0 | 0 | S8A-01115 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Form Pour Strip Concrete Stair South Side ---> S8 (Addition) | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 85 | MLJ | Formwork | NB FORMWORK | 03-1000 | 03-1000-S82
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01120 | 0 | 0 | S8A-01120 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Metal Stairs --> S8 (Addition) | 2 | 2 | 0% | 2022-12-09 08:00 | 2022-12-12 17:00 | 85 | E&Y | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01125 | 0 | 0 | S8A-01125 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Place Insulation Below First Floor --> S8 (Addition) | 5 | 0 | 100% | 2022-07-07 | 2022-08-08 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01130 | 0 | 0 | S8A-01130 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Place WWF First Floor Slab --> S8 (Addition) | 2 | 0 | 100% | 2022-07-11 08:00 | 2022-07-14 17:00 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01135 | 0 | 0 | S8A-01135 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Pour First Floor Slab --> S8 (Addition) | 1 | 0 | 100% | 2022-07-15 08:00 | 2022-07-15 17:00 |  | MLJ | Concrete | NB CONCRETE | 03-1900 | 03-1900-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01150 | 0 | 0 | S8A-01150 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Form First Floor Concrete Walls First Face And Col Encasements--> S8 (Addition) | 3 | 0 | 100% | 2022-09-05 | 2022-09-06 |  | MLJ | Formwork | NB FORMWORK | 03-1000 | 03-1000-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01155 | 0 | 0 | S8A-01155 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Rebar First Floor Concrete Walls --> S8 (Addition) | 3 | 0 | 100% | 2022-09-01 | 2022-09-02 |  | MLJ | Concrete | NB CONCRETE | 03-1900 | 03-1900-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01160 | 0 | 0 | S8A-01160 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Form First Floor Concrete Walls 2Nd Face --> S8 (Addition) | 5 | 0 | 100% | 2022-09-21 | 2022-09-22 |  | MLJ | Formwork | NB FORMWORK | 03-1000 | 03-1000-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01165 | 0 | 0 | S8A-01165 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Form, Rebar & Pour Concrete Pads 1st Floor --> S8 (Addition) - N/A | 3 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01170 | 0 | 0 | S8A-01170 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Place WWF 2nd Floor Slab --> S8 (Addition) | 2 | 0 | 100% | 2022-09-21 | 2022-09-22 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01175 | 0 | 0 | S8A-01175 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Pour 2nd Floor Slab / First Floor Walls & Col Encasements And 1st Floor Pads --> S8 (Addition) | 2 | 0 | 100% | 2022-09-27 | 2022-09-27 17:00 |  | MLJ | Concrete | NB CONCRETE | 03-1900 | 03-1900-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01180 | 0 | 0 | S8A-01180 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Strip Forms First Floor Walls & Col Encasements And 1st Floor Pads --> S8 (Addition) | 3 | 0 | 100% | 2022-09-29 | 2022-10-04 |  | MLJ | Formwork | NB FORMWORK | 03-1000 | 03-1000-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01185 | 0 | 0 | S8A-01185 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Form Concrete Pads 2nd Floor -->S8 (Addition) | 2 | 0 | 100% | 2022-09-26 | 2022-09-26 |  | MLJ | Formwork | NB FORMWORK | 03-1000 | 03-1000-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01205 | 0 | 0 | S8A-01205 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Place WWF Roof Slab --> S8 (Addition) | 2 | 0 | 100% | 2022-09-19 | 2022-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01210 | 0 | 0 | S8A-01210 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Pour Roof Slab and 2nd Floor Conc Pads -->S8 (Addition) | 1 | 0 | 100% | 2022-09-27 | 2022-09-27 |  | MLJ | Concrete | NB CONCRETE | 03-1900 | 03-1900-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01215 | 0 | 0 | S8A-01215 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Strip Forms Concrete Pads 2nd Floor -->S8 (Addition) | 2 | 0 | 100% | 2022-10-03 | 2022-10-05 |  | MLJ | Formwork | NB FORMWORK | 03-1000 | 03-1000-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01225 | 0 | 0 | S8A-01225 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Spray-On Fireproofing on St Stl --> S8 (Addition) | 5 | 0 | 100% | 2022-10-10 | 2022-11-02 |  | SIG | 0 | 0 | 0 | 0-S8A
In Progress | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01230 | 0 | 0 | S8A-01230 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Place CMU 1st, 2nd Floors and Roof --> S8 (Addition) | 20 | 15 | 25% | 2022-11-01 | 2022-12-15 17:00 | -49 | FAXA | CMU | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01240 | 0 | 0 | S8A-01240 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Stud Framing 1st, 2nd Floors and Roof --> S8 (Addition) | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | 55 | CCC | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01245 | 0 | 0 | S8A-01245 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Doors --> S8 (Addition) | 3 | 3 | 0% | 2023-01-10 08:00 | 2023-01-12 17:00 | 50 | CCC | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01250 | 0 | 0 | S8A-01250 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Cast Stone Panels --> S8 (Addition) | 1 | 1 | 0% | 2023-01-13 08:00 | 2023-01-13 17:00 | 50 | JMC | CAST STONE | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01255 | 0 | 0 | S8A-01255 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Insulated Metal Panels/Louvers --> S8 (Addition) | 10 | 10 | 0% | 2023-01-17 08:00 | 2023-01-30 17:00 | 50 | NAVILLUS | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01260 | 0 | 0 | S8A-01260 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install MEP Roof Penetrations & Drains - S8 (Addition) | 1 | 1 | 0% | 2023-01-31 08:00 | 2023-01-31 17:00 | 50 | MLJ | CORING | ROOF PENETRATIONS | 02-3000 | 02-3000-S82
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01265 | 0 | 0 | S8A-01265 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Roofing --> S8 (Addition) | 15 | 15 | 0% | 2023-02-01 08:00 | 2023-02-22 17:00 | 52 | TRIANGLE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01270 | 0 | 0 | S8A-01270 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Dunnage Gratings --> S8 (Addition) | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | 24 | E&Y | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01275 | 0 | 0 | S8A-01275 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Brick Façade & Stone --> S8 (Addition) | 20 | 20 | 0% | 2022-11-29 08:00 | 2022-12-27 17:00 | 68 | FAXA | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01285 | 0 | 0 | S8A-01285 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Flood Vents And Small Louvers --> S8 (Addition) | 3 | 3 | 0% | 2023-02-01 08:00 | 2023-02-03 17:00 | 50 | MLJ | FLOOD PROTECTION | FLOOD VENTS | 08-1700 | 08-1700-S82
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01290 | 0 | 0 | S8A-01290 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Stair And Roof Platform Railings --> S8 (Addition) | 5 | 5 | 0% | 2022-12-28 08:00 | 2023-01-04 17:00 | 75 | E&Y | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01295 | 0 | 0 | S8A-01295 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Ladders --> S8 (Addition) | 3 | 3 | 0% | 2023-01-05 08:00 | 2023-01-09 17:00 | 82 | E&Y | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01305 | 0 | 0 | S8A-01305 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Sheetrock and Stucco --> S8 (Addition) | 10 | 10 | 0% | 2023-04-20 08:00 | 2023-05-03 17:00 | -2 | CCC | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01310 | 0 | 0 | S8A-01310 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Ceramic Tile --> S8 (Addition) | 2 | 2 | 0% | 2023-05-04 08:00 | 2023-05-05 17:00 | -2 | UNSURE | FLOORING | CERAMIC | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01315 | 0 | 0 | S8A-01315 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Acoustical Ceiling --> S8 (Addition) | 2 | 2 | 0% | 2023-05-08 08:00 | 2023-05-09 17:00 | -2 | UNSURE | CEILING | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01320 | 0 | 0 | S8A-01320 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Place Crystaline Waterproofing In Plumbing Shaft --> S8 (Addition) | 3 | 3 | 0% | 2022-11-25 08:00 | 2022-11-29 17:00 | 92 | DSTAR | WATERPROOFING | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01325 | 0 | 0 | S8A-01325 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Paint All Areas --> S8 (Addition) | 15 | 15 | 0% | 2023-06-16 08:00 | 2023-07-07 17:00 | -45 | GG PAINT | PAINT | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01330 | 0 | 0 | S8A-01330 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Signs --> S8 (Addition) | 2 | 2 | 0% | 2023-07-10 08:00 | 2023-07-11 17:00 | -45 | MLJ | SIGNS | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01235 | 0 | 0 | S8A-01235 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Waterproofing to Parapet --> S8 (Addition) | 3 | 3 | 0% | 2022-12-16 08:00 | 2022-12-20 17:00 | 66 | UNSURE | WATERPROOFING | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01280 | 0 | 0 | S8A-01280 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Stucco Soffit --> S8 (Addition) | 5 | 5 | 0% | 2022-12-28 08:00 | 2023-01-04 17:00 | 68 | CCC | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01317 | 0 | 0 | S8A-01317 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Insulated Metal Panels left out for Access --> S8 (Addition) | 5 | 5 | 0% | 2023-06-09 08:00 | 2023-06-15 17:00 | -45 | NAVILLUS | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01092 | 0 | 0 | S8A-01092 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Remaining HW/CW Into S8 (Addition) (5' from the building) | 5 | 0 | 100% | 2022-08-25 08:00 | 2022-08-30 17:00 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01094 | 0 | 0 | S8A-01094 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Remaining Electrical POE Into S8 (Addition) | 5 | 0 | 100% | 2022-06-01 | 2022-06-15 |  | 0 | 0 | 0 | 0 | 0-S8A
Not Started | CI NYCHA Update #22.Construction.8.1.5.1 | S81 | S8E | 01005 | 0 | 0 | S8E-01005 | Construction | Asbestos Abatement | Construction.8.1.5.1 | Asbestos Abatement - gaskets - cellar - S8 (Existing) | 3 | 3 | 0% | 2023-08-10 08:00 | 2023-08-14 17:00 | -84 | ATCO | ABESTOS | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.1 | S81 | S8E | 01010 | 0 | 0 | S8E-01010 | Construction | Asbestos Abatement | Construction.8.1.5.1 | Asbestos Abatement - wire insulation - cellar --> S8 (Existing) | 3 | 3 | 0% | 2022-11-25 08:00 | 2022-11-29 17:00 | -30 | ATCO | ABESTOS | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.1 | S81 | S8E | 01015 | 0 | 0 | S8E-01015 | Construction | Asbestos Abatement | Construction.8.1.5.1 | Asbestos Abatement - flooring materials at slab penetrations - cellar --> S8 (Existing) | 3 | 3 | 0% | 2022-11-30 08:00 | 2022-12-02 17:00 | -30 | ATCO | ABESTOS | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.1 | S81 | S8E | 01020 | 0 | 0 | S8E-01020 | Construction | Asbestos Abatement | Construction.8.1.5.1 | Asbestos Abatement - pipe insulation - cellar --> S8 (Existing) | 3 | 3 | 0% | 2022-12-05 08:00 | 2022-12-07 17:00 | -30 | ATCO | ABESTOS | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Construction.8.1.5.1 | S8E | S8E | 01025 | 0 | 0 | S8E-01025 | Construction | Asbestos Abatement | Construction.8.1.5.1 | Asbestos Abatement - Window Sills - 1st Floor --> S8 (Existing) | 5 | 0 | 100% | 2022-04-20 | 2022-04-22 |  | 0 | 0 | 0 | 0 | 0-S8E
Not Started | CI NYCHA Update #22.Construction.8.1.5.1 | S81 | S8E | 01030 | 0 | 0 | S8E-01030 | Construction | Asbestos Abatement | Construction.8.1.5.1 | Asbestos Abatement - caulk @ windows and areaway vents --> S8 (Existing) | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | -24 | ATCO | ABESTOS | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.2 | S81 | S8E | 01105 | 0 | 0 | S8E-01105 | Construction | Interior Demolition | Construction.8.1.5.2 | Selective Demo (Plaster walls, Doors, windows) - Cellar --> S8 (Existing) | 10 | 10 | 0% | 2022-12-08 08:00 | 2022-12-21 17:00 | -30 | MLJ | DEMO | DEMO CELLAR WALLS | 02-6005 | 02-6005-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.2 | S81 | S8E | 01110 | 0 | 0 | S8E-01110 | Construction | Interior Demolition | Construction.8.1.5.2 | Selective Demo (Doors, windows) - 1st Floor --> S8 (Existing) | 5 | 5 | 0% | 2022-12-22 08:00 | 2022-12-29 17:00 | -30 | MLJ | DEMO | DEMO DOORS WINDOWS | 02-6015 | 02-6015-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.2 | S81 | S8E | 01115 | 0 | 0 | S8E-01115 | Construction | Interior Demolition | Construction.8.1.5.2 | Selective Demo (Areaway drain, slab, wall) --> S8 (Existing) | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | -2 | MLJ | DEMO | DEMO AREAWAY | 02-6025 | 02-6025-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.2 | S81 | S8E | 01205 | 0 | 0 | S8E-01205 | Construction | Interior Demolition | Construction.8.1.5.2 | Selective Demo (Existing Ramp, railing) - 1st Floor --> S8 (Existing) | 5 | 5 | 0% | 2022-12-09 08:00 | 2022-12-15 17:00 | -2 | MLJ | DEMO | DEMO RAMP | 02-6050 | 02-6050-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.2 | S81 | S8E | 01210 | 0 | 0 | S8E-01210 | Construction | Interior Demolition | Construction.8.1.5.2 | Selective Demo - Slab openings for mechanical - Cellar & 1st Floor --> S8 (Existing) | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -2 | MLJ | DEMO | DEMO SLAB OPEN FOR MECH | 02-3000 | 02-3000-S81
Completed | CI NYCHA Update #22.Construction.8.1.5.2 | S8E | S8E | 01215 | 0 | 0 | S8E-01215 | Construction | Interior Demolition | Construction.8.1.5.2 | Selective Demo - 2nd Floor Apartment for Electrical Room --> S8 (Existing) - N/A | 5 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-S8E
Not Started | CI NYCHA Update #22.Construction.8.1.5.4 | S81 | S8E | 01310 | 0 | 0 | S8E-01310 | Construction | Interior Renovations | Construction.8.1.5.4 | Make openings in floor for conduit penetrations - 1st floor apartments --> S8 (Existing) | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 12 | MLJ | CORE DRILL | 0 | 02-3000 | 02-3000-S81
Completed | CI NYCHA Update #22.Construction.8.1.5.4 | S8E | S8E | 01315 | 0 | 0 | S8E-01315 | Construction | Interior Renovations | Construction.8.1.5.4 | Install beams below floor - 1st floor apartments --> S8 (Existing) | 5 | 0 | 100% | 2022-09-01 08:00 | 2022-09-01 17:00 |  | WEIR | 0 | 0 | 0 | 0-S8E
Not Started | CI NYCHA Update #22.Construction.8.1.5.4 | S81 | S8E | 01320 | 0 | 0 | S8E-01320 | Construction | Interior Renovations | Construction.8.1.5.4 | Install FRP around floor openings - 1st floor apartments --> S8 (Existing) | 5 | 5 | 0% | 2022-12-02 08:00 | 2022-12-08 17:00 | 12 | MLJ | 0 | FRP | 03-6000 | 03-6000-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.4 | S81 | S8E | 01325 | 0 | 0 | S8E-01325 | Construction | Interior Renovations | Construction.8.1.5.4 | Frame walls / install door for electrical room - 1st floor --> S8 (Existing) | 3 | 3 | 0% | 2022-12-09 08:00 | 2022-12-13 17:00 | 12 | CCC | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.4 | S81 | S8E | 01330 | 0 | 0 | S8E-01330 | Construction | Interior Renovations | Construction.8.1.5.4 | Install drywall / tape / spackle - electrical room - 1st floor --> S8 (Existing) | 5 | 5 | 0% | 2023-04-03 08:00 | 2023-04-07 17:00 | -10 | CCC | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.4 | S81 | S8E | 01335 | 0 | 0 | S8E-01335 | Construction | Interior Renovations | Construction.8.1.5.4 | Paint walls and seal floor electrical room - 1st Floor --> S8 (Existing) | 10 | 10 | 0% | 2023-04-17 08:00 | 2023-04-28 17:00 | -12 | CCC | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.4 | S81 | S8E | 01340 | 0 | 0 | S8E-01340 | Construction | Interior Renovations | Construction.8.1.5.4 | Install VCT @ electrical room - 1st Floor --> S8 (Existing) | 2 | 2 | 0% | 2023-05-01 08:00 | 2023-05-02 17:00 | -12 | UNSURE | FLOORING | VCT | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.1 | S81 | S8E | 01405 | 0 | 0 | S8E-01405 | Construction | North Wing - North Elevation | Construction.8.1.5.EFPC.1 | Excavate at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 9 | 9 | 0% | 2022-11-25 08:00 | 2022-12-07 17:00 | -90 | MLJ | EXCAVATION | EB EXC | 31-1000 | 31-1000-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.1 | S81 | S8E | 01410 | 0 | 0 | S8E-01410 | Construction | North Wing - North Elevation | Construction.8.1.5.EFPC.1 | Form concrete footings at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 12 | 12 | 0% | 2022-12-08 08:00 | 2022-12-23 17:00 | -90 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.1 | S81 | S8E | 01415 | 0 | 0 | S8E-01415 | Construction | North Wing - North Elevation | Construction.8.1.5.EFPC.1 | Rebar concrete footings at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 7 | 7 | 0% | 2022-12-27 08:00 | 2023-01-05 17:00 | -90 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.1 | S81 | S8E | 01420 | 0 | 0 | S8E-01420 | Construction | North Wing - North Elevation | Construction.8.1.5.EFPC.1 | Pour concrete footings at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 6 | 6 | 0% | 2023-01-06 08:00 | 2023-01-13 17:00 | -90 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.1 | S81 | S8E | 01425 | 0 | 0 | S8E-01425 | Construction | North Wing - North Elevation | Construction.8.1.5.EFPC.1 | Strip Forms concrete footings at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 7 | 7 | 0% | 2023-01-17 08:00 | 2023-01-25 17:00 | -90 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.1 | S81 | S8E | 01430 | 0 | 0 | S8E-01430 | Construction | North Wing - North Elevation | Construction.8.1.5.EFPC.1 | Form concrete walls & shelf at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 10 | 10 | 0% | 2023-01-26 08:00 | 2023-02-08 17:00 | -90 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.1 | S81 | S8E | 01435 | 0 | 0 | S8E-01435 | Construction | North Wing - North Elevation | Construction.8.1.5.EFPC.1 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 8 | 8 | 0% | 2023-02-09 08:00 | 2023-02-21 17:00 | -90 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.1 | S81 | S8E | 01440 | 0 | 0 | S8E-01440 | Construction | North Wing - North Elevation | Construction.8.1.5.EFPC.1 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 6 | 6 | 0% | 2023-02-22 08:00 | 2023-03-01 17:00 | -90 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.1 | S81 | S8E | 01445 | 0 | 0 | S8E-01445 | Construction | North Wing - North Elevation | Construction.8.1.5.EFPC.1 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 6 | 6 | 0% | 2023-03-02 08:00 | 2023-03-09 17:00 | -90 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.1 | S81 | S8E | 01450 | 0 | 0 | S8E-01450 | Construction | North Wing - North Elevation | Construction.8.1.5.EFPC.1 | Place CMU wall and grout fill at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 6 | 6 | 0% | 2023-03-10 08:00 | 2023-03-17 17:00 | -90 | FAXA | CMU | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.1 | S81 | S8E | 01455 | 0 | 0 | S8E-01455 | Construction | North Wing - North Elevation | Construction.8.1.5.EFPC.1 | Backfill at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 7 | 7 | 0% | 2023-03-20 08:00 | 2023-03-28 17:00 | -90 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.1 | S81 | S8E | 01460 | 0 | 0 | S8E-01460 | Construction | North Wing - North Elevation | Construction.8.1.5.EFPC.1 | Form for slab at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 6 | 6 | 0% | 2023-03-29 08:00 | 2023-04-05 17:00 | -90 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.1 | S81 | S8E | 01465 | 0 | 0 | S8E-01465 | Construction | North Wing - North Elevation | Construction.8.1.5.EFPC.1 | Rebar & inserts for slab at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 8 | 8 | 0% | 2023-04-06 08:00 | 2023-04-17 17:00 | -90 | TONAGE | REBAR | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.1 | S81 | S8E | 01470 | 0 | 0 | S8E-01470 | Construction | North Wing - North Elevation | Construction.8.1.5.EFPC.1 | Pour slab at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 6 | 6 | 0% | 2023-04-18 08:00 | 2023-04-25 17:00 | -90 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.1 | S81 | S8E | 01475 | 0 | 0 | S8E-01475 | Construction | North Wing - North Elevation | Construction.8.1.5.EFPC.1 | Strip Forms for slab at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 4 | 4 | 0% | 2023-04-26 08:00 | 2023-05-01 17:00 | -90 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.1 | S81 | S8E | 01480 | 0 | 0 | S8E-01480 | Construction | North Wing - North Elevation | Construction.8.1.5.EFPC.1 | Backfill surounding area at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 6 | 6 | 0% | 2023-10-10 08:00 | 2023-10-18 17:00 | -202 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.2 | S81 | S8E | 01505 | 0 | 0 | S8E-01505 | Construction | South Wing - East Elevation | Construction.8.1.5.EFPC.2 | Excavate at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 9 | 9 | 0% | 2022-11-25 08:00 | 2022-12-07 17:00 | -91 | MLJ | EXCAVATION | EB EXC | 31-1000 | 31-1000-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.2 | S81 | S8E | 01510 | 0 | 0 | S8E-01510 | Construction | South Wing - East Elevation | Construction.8.1.5.EFPC.2 | Form concrete footings at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 12 | 12 | 0% | 2022-12-08 08:00 | 2022-12-23 17:00 | -91 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.2 | S81 | S8E | 01515 | 0 | 0 | S8E-01515 | Construction | South Wing - East Elevation | Construction.8.1.5.EFPC.2 | Rebar concrete footings at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 7 | 7 | 0% | 2022-12-27 08:00 | 2023-01-05 17:00 | -91 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.2 | S81 | S8E | 01520 | 0 | 0 | S8E-01520 | Construction | South Wing - East Elevation | Construction.8.1.5.EFPC.2 | Pour concrete footings at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 6 | 6 | 0% | 2023-01-06 08:00 | 2023-01-13 17:00 | -91 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.2 | S81 | S8E | 01525 | 0 | 0 | S8E-01525 | Construction | South Wing - East Elevation | Construction.8.1.5.EFPC.2 | Strip Forms concrete footings at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 7 | 7 | 0% | 2023-01-17 08:00 | 2023-01-25 17:00 | -91 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.2 | S81 | S8E | 01530 | 0 | 0 | S8E-01530 | Construction | South Wing - East Elevation | Construction.8.1.5.EFPC.2 | Form concrete walls & shelf at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 10 | 10 | 0% | 2023-01-26 08:00 | 2023-02-08 17:00 | -91 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.2 | S81 | S8E | 01535 | 0 | 0 | S8E-01535 | Construction | South Wing - East Elevation | Construction.8.1.5.EFPC.2 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 8 | 8 | 0% | 2023-02-09 08:00 | 2023-02-21 17:00 | -91 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.2 | S81 | S8E | 01540 | 0 | 0 | S8E-01540 | Construction | South Wing - East Elevation | Construction.8.1.5.EFPC.2 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 6 | 6 | 0% | 2023-02-22 08:00 | 2023-03-01 17:00 | -91 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.2 | S81 | S8E | 01545 | 0 | 0 | S8E-01545 | Construction | South Wing - East Elevation | Construction.8.1.5.EFPC.2 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 6 | 6 | 0% | 2023-03-02 08:00 | 2023-03-09 17:00 | -91 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.2 | S81 | S8E | 01550 | 0 | 0 | S8E-01550 | Construction | South Wing - East Elevation | Construction.8.1.5.EFPC.2 | Place CMU wall and grout fill at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 6 | 6 | 0% | 2023-03-10 08:00 | 2023-03-17 17:00 | -91 | FAXA | CMU | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.2 | S81 | S8E | 01555 | 0 | 0 | S8E-01555 | Construction | South Wing - East Elevation | Construction.8.1.5.EFPC.2 | Backfill at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 7 | 7 | 0% | 2023-03-20 08:00 | 2023-03-28 17:00 | -91 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.2 | S81 | S8E | 01560 | 0 | 0 | S8E-01560 | Construction | South Wing - East Elevation | Construction.8.1.5.EFPC.2 | Form for slab at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 6 | 6 | 0% | 2023-03-29 08:00 | 2023-04-05 17:00 | -91 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.2 | S81 | S8E | 01565 | 0 | 0 | S8E-01565 | Construction | South Wing - East Elevation | Construction.8.1.5.EFPC.2 | Rebar & inserts for slab at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 8 | 8 | 0% | 2023-04-06 08:00 | 2023-04-17 17:00 | -91 | TONAGE | REBAR | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.2 | S81 | S8E | 01570 | 0 | 0 | S8E-01570 | Construction | South Wing - East Elevation | Construction.8.1.5.EFPC.2 | Pour slab at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 6 | 6 | 0% | 2023-04-18 08:00 | 2023-04-25 17:00 | -91 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.2 | S81 | S8E | 01575 | 0 | 0 | S8E-01575 | Construction | South Wing - East Elevation | Construction.8.1.5.EFPC.2 | Strip Forms for slab at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 4 | 4 | 0% | 2023-04-26 08:00 | 2023-05-01 17:00 | -90 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.2 | S81 | S8E | 01580 | 0 | 0 | S8E-01580 | Construction | South Wing - East Elevation | Construction.8.1.5.EFPC.2 | Backfill surounding area at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 6 | 6 | 0% | 2023-05-03 08:00 | 2023-05-10 17:00 | -91 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-S81
Completed | CI NYCHA Update #22.Construction.8.1.5.EFPC.3 | S8E | S8E | 01605 | 0 | 0 | S8E-01605 | Construction | South Wing - West Elevation | Construction.8.1.5.EFPC.3 | Excavate at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 9 | 0 | 100% | 2022-11-14 | 2022-11-16 |  | MLJ | Excavation | EB EXC | 31-1000 | 31-1000-S8E
Completed | CI NYCHA Update #22.Construction.8.1.5.EFPC.3 | S8E | S8E | 01610 | 0 | 0 | S8E-01610 | Construction | South Wing - West Elevation | Construction.8.1.5.EFPC.3 | Form concrete footings at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 12 | 0 | 100% | 2022-11-16 | 2022-11-18 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S8E
Completed | CI NYCHA Update #22.Construction.8.1.5.EFPC.3 | S8E | S8E | 01615 | 0 | 0 | S8E-01615 | Construction | South Wing - West Elevation | Construction.8.1.5.EFPC.3 | Rebar concrete footings at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 7 | 0 | 100% | 2022-11-16 | 2022-11-18 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S8E
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.3 | S81 | S8E | 01620 | 0 | 0 | S8E-01620 | Construction | South Wing - West Elevation | Construction.8.1.5.EFPC.3 | Pour concrete footings at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 6 | 6 | 0% | 2022-11-25 08:00 | 2022-12-02 17:00 | -32 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.3 | S81 | S8E | 01625 | 0 | 0 | S8E-01625 | Construction | South Wing - West Elevation | Construction.8.1.5.EFPC.3 | Strip Forms concrete footings at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 7 | 7 | 0% | 2022-12-05 08:00 | 2022-12-13 17:00 | -32 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.3 | S81 | S8E | 01630 | 0 | 0 | S8E-01630 | Construction | South Wing - West Elevation | Construction.8.1.5.EFPC.3 | Form concrete walls & shelf at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 10 | 10 | 0% | 2022-12-14 08:00 | 2022-12-28 17:00 | -32 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.3 | S81 | S8E | 01635 | 0 | 0 | S8E-01635 | Construction | South Wing - West Elevation | Construction.8.1.5.EFPC.3 | Rebar concrete walls & shelf at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 8 | 8 | 0% | 2022-12-29 08:00 | 2023-01-10 17:00 | -32 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.3 | S81 | S8E | 01640 | 0 | 0 | S8E-01640 | Construction | South Wing - West Elevation | Construction.8.1.5.EFPC.3 | Pour concrete walls & shelf at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 6 | 6 | 0% | 2023-01-11 08:00 | 2023-01-19 17:00 | -32 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.3 | S81 | S8E | 01645 | 0 | 0 | S8E-01645 | Construction | South Wing - West Elevation | Construction.8.1.5.EFPC.3 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 6 | 6 | 0% | 2023-01-20 08:00 | 2023-01-27 17:00 | -32 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.3 | S81 | S8E | 01650 | 0 | 0 | S8E-01650 | Construction | South Wing - West Elevation | Construction.8.1.5.EFPC.3 | Place CMU wall and grout fill at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 6 | 6 | 0% | 2023-01-30 08:00 | 2023-02-06 17:00 | -32 | FAXA | CMU | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.3 | S81 | S8E | 01655 | 0 | 0 | S8E-01655 | Construction | South Wing - West Elevation | Construction.8.1.5.EFPC.3 | Backfill at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 7 | 7 | 0% | 2023-02-07 08:00 | 2023-02-15 17:00 | -32 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-S81
Completed | CI NYCHA Update #22.Construction.8.1.5.EFPC.4 | S8E | S8E | 01705 | 0 | 0 | S8E-01705 | Construction | North Wing - South Elevation | Construction.8.1.5.EFPC.4 | Excavate at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 9 | 0 | 100% | 2022-11-14 | 2022-11-16 |  | MLJ | Excavation | EB EXC | 31-1000 | 31-1000-S8E
Completed | CI NYCHA Update #22.Construction.8.1.5.EFPC.4 | S8E | S8E | 01710 | 0 | 0 | S8E-01710 | Construction | North Wing - South Elevation | Construction.8.1.5.EFPC.4 | Form concrete footings at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 11 | 0 | 100% | 2022-11-16 | 2022-11-18 |  | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S8E
Completed | CI NYCHA Update #22.Construction.8.1.5.EFPC.4 | S8E | S8E | 01715 | 0 | 0 | S8E-01715 | Construction | North Wing - South Elevation | Construction.8.1.5.EFPC.4 | Rebar concrete footings at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 6 | 0 | 100% | 2022-11-16 | 2022-11-18 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S8E
In Progress | CI NYCHA Update #22.Construction.8.1.5.EFPC.4 | S81 | S8E | 01720 | 0 | 0 | S8E-01720 | Construction | North Wing - South Elevation | Construction.8.1.5.EFPC.4 | Pour concrete footings at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 5 | 3 | 40% | 2022-11-23 08:00 | 2022-11-29 17:00 | -97 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.4 | S81 | S8E | 01725 | 0 | 0 | S8E-01725 | Construction | North Wing - South Elevation | Construction.8.1.5.EFPC.4 | Strip Forms concrete footings at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 6 | 6 | 0% | 2022-11-30 08:00 | 2022-12-07 17:00 | -97 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.4 | S81 | S8E | 01730 | 0 | 0 | S8E-01730 | Construction | North Wing - South Elevation | Construction.8.1.5.EFPC.4 | Form concrete walls & shelf at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 9 | 9 | 0% | 2022-12-08 08:00 | 2022-12-20 17:00 | -97 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.4 | S81 | S8E | 01735 | 0 | 0 | S8E-01735 | Construction | North Wing - South Elevation | Construction.8.1.5.EFPC.4 | Rebar concrete walls & shelf at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 7 | 7 | 0% | 2022-12-21 08:00 | 2022-12-30 17:00 | -97 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.4 | S81 | S8E | 01740 | 0 | 0 | S8E-01740 | Construction | North Wing - South Elevation | Construction.8.1.5.EFPC.4 | Pour concrete walls & shelf at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 5 | 5 | 0% | 2023-01-03 08:00 | 2023-01-09 17:00 | -97 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.4 | S81 | S8E | 01745 | 0 | 0 | S8E-01745 | Construction | North Wing - South Elevation | Construction.8.1.5.EFPC.4 | Strip Forms concrete walls & shelf at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 5 | 5 | 0% | 2023-01-10 08:00 | 2023-01-17 17:00 | -97 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.4 | S81 | S8E | 01750 | 0 | 0 | S8E-01750 | Construction | North Wing - South Elevation | Construction.8.1.5.EFPC.4 | Place CMU wall and grout fill at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 5 | 5 | 0% | 2023-01-18 08:00 | 2023-01-24 17:00 | -97 | FAXA | CMU | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.4 | S81 | S8E | 01755 | 0 | 0 | S8E-01755 | Construction | North Wing - South Elevation | Construction.8.1.5.EFPC.4 | Backfill at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 6 | 6 | 0% | 2023-01-25 08:00 | 2023-02-01 17:00 | -97 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.5 | S81 | S8E | 01805 | 0 | 0 | S8E-01805 | Construction | Concrete Shelf Construction | Construction.8.1.5.EFPC.5 | Excavate for concrete shelf around bldg perimeter --> S8 (Existing) | 10 | 10 | 0% | 2023-01-26 08:00 | 2023-02-08 17:00 | -97 | MLJ | EXCAVATION | EB EXC | 31-1000 | 31-1000-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.5 | S81 | S8E | 01810 | 0 | 0 | S8E-01810 | Construction | Concrete Shelf Construction | Construction.8.1.5.EFPC.5 | Place rebar for concrete shelf around bldg perimeter --> S8 (Existing) | 5 | 5 | 0% | 2023-02-09 08:00 | 2023-02-15 17:00 | -97 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.5 | S81 | S8E | 01815 | 0 | 0 | S8E-01815 | Construction | Concrete Shelf Construction | Construction.8.1.5.EFPC.5 | Pour concrete shelf around bldg perimeter --> S8 (Existing) | 5 | 5 | 0% | 2023-02-16 08:00 | 2023-02-23 17:00 | -97 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.5 | S81 | S8E | 01820 | 0 | 0 | S8E-01820 | Construction | Concrete Shelf Construction | Construction.8.1.5.EFPC.5 | Place infill concrete in area ways around bldg perimeter --> S8 (Existing) | 5 | 5 | 0% | 2023-02-24 08:00 | 2023-03-02 17:00 | -97 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.5 | S81 | S8E | 01825 | 0 | 0 | S8E-01825 | Construction | Concrete Shelf Construction | Construction.8.1.5.EFPC.5 | Place waterproofing on concrete shelf around bldg perimeter --> S8 (Existing) | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | -41 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.5 | S81 | S8E | 01830 | 0 | 0 | S8E-01830 | Construction | Concrete Shelf Construction | Construction.8.1.5.EFPC.5 | Place CMU around bldg perimeter --S8 (Existing) | 15 | 15 | 0% | 2023-03-03 08:00 | 2023-03-23 17:00 | -97 | FAXA | CMU | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.5 | S81 | S8E | 01835 | 0 | 0 | S8E-01835 | Construction | Concrete Shelf Construction | Construction.8.1.5.EFPC.5 | Place waterproofing on CMU around bldg perimeter --> S8 (Existing) | 10 | 10 | 0% | 2023-03-24 08:00 | 2023-04-06 17:00 | -97 | UNSURE | WATERPROOFING | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.5 | S81 | S8E | 01840 | 0 | 0 | S8E-01840 | Construction | Concrete Shelf Construction | Construction.8.1.5.EFPC.5 | Place window frames around bldg perimeter --> S8 (Existing) | 10 | 10 | 0% | 2023-04-07 08:00 | 2023-04-20 17:00 | -97 | MLJ | CONCRETE SHELF | PLACE WINDOWS | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.5 | S81 | S8E | 01845 | 0 | 0 | S8E-01845 | Construction | Concrete Shelf Construction | Construction.8.1.5.EFPC.5 | Place insulation, brick, cavity fill, capstone/window sill around bldg perimeter --> S8 (Existing) | 15 | 15 | 0% | 2023-04-21 08:00 | 2023-05-11 17:00 | -97 | FAXA | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.5 | S81 | S8E | 01850 | 0 | 0 | S8E-01850 | Construction | Concrete Shelf Construction | Construction.8.1.5.EFPC.5 | Backfill around bdg perimeter --> S8 (Existing) | 5 | 5 | 0% | 2023-05-12 08:00 | 2023-05-18 17:00 | -97 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.5 | S81 | S8E | 01855 | 0 | 0 | S8E-01855 | Construction | Concrete Shelf Construction | Construction.8.1.5.EFPC.5 | Place frame / stucco / and signs at entrances --> S8 (Existing) | 4 | 4 | 0% | 2023-05-19 08:00 | 2023-05-24 17:00 | -11 | CCC | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.5 | S81 | S8E | 01860 | 0 | 0 | S8E-01860 | Construction | Concrete Shelf Construction | Construction.8.1.5.EFPC.5 | Place window floodgates at windows --> S8 (Existing) | 5 | 5 | 0% | 2023-05-25 08:00 | 2023-06-01 17:00 | -11 | MLJ | FLOOD PROTECTION | FLOOD WINDOWS | 10-1400 | 10-1400-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.5 | S81 | S8E | 01865 | 0 | 0 | S8E-01865 | Construction | Concrete Shelf Construction | Construction.8.1.5.EFPC.5 | Install signs --> S8 (Existing) | 3 | 3 | 0% | 2023-06-02 08:00 | 2023-06-06 17:00 | -11 | MLJ | SIGNS | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.5 | S81 | S8E | 01350 | 0 | 0 | S8E-01350 | Construction | Boiler Room Construction | Construction.8.1.5.5 | Drill dowels and place rebar for boiler room concrete walls --> S8 (Existing) | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 80 | MLJ | 0 | DRILL & DOWEL | 03-1400 | 03-1400-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.5 | S81 | S8E | 01355 | 0 | 0 | S8E-01355 | Construction | Boiler Room Construction | Construction.8.1.5.5 | Form boiler room concrete walls --> S8 (Existing) | 5 | 5 | 0% | 2022-12-02 08:00 | 2022-12-08 17:00 | 80 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.5 | S81 | S8E | 01360 | 0 | 0 | S8E-01360 | Construction | Boiler Room Construction | Construction.8.1.5.5 | Pour Concrete boiler room walls --> S8 (Existing) | 2 | 2 | 0% | 2022-12-09 08:00 | 2022-12-12 17:00 | 80 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.5 | S81 | S8E | 01365 | 0 | 0 | S8E-01365 | Construction | Boiler Room Construction | Construction.8.1.5.5 | Strip Forms boiler room concrete walls --> S8 (Existing) | 3 | 3 | 0% | 2022-12-13 08:00 | 2022-12-15 17:00 | 82 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.5 | S81 | S8E | 01370 | 0 | 0 | S8E-01370 | Construction | Boiler Room Construction | Construction.8.1.5.5 | Place crystaline waterproofing on perimeter walls - cellar --> S8 (Existing) | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | -40 | DSTAR | WATERPROOFING | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Construction.8.1.5.6 | S8E | S8E | 01385 | 0 | 0 | S8E-01385 | Construction | Elevator Refurbishment | Construction.8.1.5.6 | Refurbish Elevator 1 --> S8 (Existing) (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-S8E
Completed | CI NYCHA Update #22.Construction.8.1.5.6 | S8E | S8E | 01390 | 0 | 0 | S8E-01390 | Construction | Elevator Refurbishment | Construction.8.1.5.6 | Refurbish Elevator 2 --> S8 (Existing) (Omitted PCOCO 69) | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-S8E
Completed | CI NYCHA Update #22.Construction.8.1.5.6 | S8E | S8E | 01380 | 0 | 0 | S8E-01380 | Construction | Elevator Refurbishment | Construction.8.1.5.6 | Obtain Shutdown for Elevators (Omitted PCOCO 69) | 3 | 0 | 100% | 2021-11-25 08:00 | 2021-11-25 17:00 |  | 0 | 0 | 0 | 0 | 0-S8E
Not Started | CI NYCHA Update #22.Construction.8.1.5.7 | S81 | S8E | 09005 | 0 | 0 | S8E-09005 | Construction | Civil/Architectural Inspections | Construction.8.1.5.7 | Perform Inspections & Issue Punch List | 5 | 5 | 0% | 2023-10-19 08:00 | 2023-10-25 17:00 | -129 | MLJ | PUNCH LIST | INSPECTION | 99-8200 | 99-8200-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.7 | S81 | S8E | 09010 | 0 | 0 | S8E-09010 | Construction | Civil/Architectural Inspections | Construction.8.1.5.7 | Perform Punch List | 10 | 10 | 0% | 2023-10-26 08:00 | 2023-11-09 17:00 | -114 | MLJ | PUNCH LIST | 0 | 99-8200 | 99-8200-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.2 | S81 | S8E | 01220 | 0 | 0 | S8E-01220 | Construction | Interior Demolition | Construction.8.1.5.2 | Selective Demo (Pumps etc..) - Cellar --> S8 (Existing) | 5 | 5 | 0% | 2023-02-08 08:00 | 2023-02-14 17:00 | -32 | MLJ | DEMO | DEMO PUMPS | 02-6010 | 02-6010-S81
Completed | CI NYCHA Update #22.Construction.8.1.8.1 | S8E | S8E | 03005 | 0 | 0 | S8E-03005 | Construction | Cellar | Construction.8.1.8.1 | Rough-In Plumbing Piping & Appurtenances - Cellar | 20 | 0 | 100% | 2022-11-01 | 2022-11-18 |  | WELKIN | 0 | 0 | 0 | 0-S8E
Not Started | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 03010 | 0 | 0 | S8E-03010 | Construction | Cellar | Construction.8.1.8.1 | Install Condensate Pump - Cellar | 10 | 10 | 0% | 2023-02-15 08:00 | 2023-03-01 17:00 | -32 | WELKIN | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 03020 | 0 | 0 | S8E-03020 | Construction | Cellar | Construction.8.1.8.1 | Install Pump Controls - Cellar | 20 | 20 | 0% | 2023-01-10 08:00 | 2023-02-07 17:00 | -32 | MEP | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 03025 | 0 | 0 | S8E-03025 | Construction | Cellar | Construction.8.1.8.1 | Perform Hydrostatic Testing - Cellar | 5 | 5 | 0% | 2023-03-06 08:00 | 2023-03-10 17:00 | -32 | WELKIN | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 03030 | 0 | 0 | S8E-03030 | Construction | Cellar | Construction.8.1.8.1 | Install Plumbing Equipment - Cellar | 15 | 15 | 0% | 2022-11-25 08:00 | 2022-12-15 17:00 | 20 | VITAL | PLUMBING EQUIP | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 03035 | 0 | 0 | S8E-03035 | Construction | Cellar | Construction.8.1.8.1 | Pump Equipment Start-up & Balance - Cellar | 10 | 10 | 0% | 2023-03-13 08:00 | 2023-03-24 17:00 | -32 | UNSURE | STARTUP | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 03040 | 0 | 0 | S8E-03040 | Construction | Cellar | Construction.8.1.8.1 | Plumbing/Mechanical Insulation - Cellar | 20 | 20 | 0% | 2023-03-27 08:00 | 2023-04-21 17:00 | -32 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 03015 | 0 | 0 | S8E-03015 | Construction | Cellar | Construction.8.1.8.1 | Install Steam Traps - Cellar | 2 | 2 | 0% | 2023-03-02 08:00 | 2023-03-03 17:00 | -32 | WELKIN | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 03007 | 0 | 0 | S8E-03007 | Construction | Cellar | Construction.8.1.8.1 | Rough-In Mechanical Piping & Appurtenances - Cellar | 20 | 20 | 0% | 2022-12-09 08:00 | 2023-01-09 17:00 | -40 | WELKIN | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 03032 | 0 | 0 | S8E-03032 | Construction | Cellar | Construction.8.1.8.1 | Install Mechanical Equipment - Cellar | 20 | 20 | 0% | 2023-01-10 08:00 | 2023-02-07 17:00 | -15 | WELKIN | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.2 | S81 | S8E | 03105 | 0 | 0 | S8E-03105 | Construction | 1st Floor | Construction.8.1.8.2 | Rough-In Plumbing Piping & Appurtenances - 1st Floor | 10 | 10 | 0% | 2023-01-10 08:00 | 2023-01-24 17:00 | -6 | WELKIN | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.2 | S81 | S8E | 03120 | 0 | 0 | S8E-03120 | Construction | 1st Floor | Construction.8.1.8.2 | Install HVAC Controls - 1st Floor | 20 | 20 | 0% | 2023-02-15 08:00 | 2023-03-15 17:00 | -40 | WELKIN | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.2 | S81 | S8E | 03125 | 0 | 0 | S8E-03125 | Construction | 1st Floor | Construction.8.1.8.2 | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 0% | 2023-03-16 08:00 | 2023-03-22 17:00 | -40 | WELKIN | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.2 | S81 | S8E | 03130 | 0 | 0 | S8E-03130 | Construction | 1st Floor | Construction.8.1.8.2 | Install Mechanical Louvers - 1st Floor | 15 | 15 | 0% | 2023-01-25 08:00 | 2023-02-14 17:00 | -40 | UNSURE | MECHANICAL LOUVERS | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.2 | S81 | S8E | 03135 | 0 | 0 | S8E-03135 | Construction | 1st Floor | Construction.8.1.8.2 | Mechanical Equipment Start-up & Balance - 1st Floor | 10 | 10 | 0% | 2023-03-23 08:00 | 2023-04-05 17:00 | -40 | WELKIN | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.2 | S81 | S8E | 03140 | 0 | 0 | S8E-03140 | Construction | 1st Floor | Construction.8.1.8.2 | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 0% | 2023-04-06 08:00 | 2023-05-03 17:00 | -40 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.2 | S81 | S8E | 03115 | 0 | 0 | S8E-03115 | Construction | 1st Floor | Construction.8.1.8.2 | Install Steam Traps - 1st Floor | 1 | 1 | 0% | 2023-01-25 08:00 | 2023-01-25 17:00 | -6 | WELKIN | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.2 | S81 | S8E | 03110 | 0 | 0 | S8E-03110 | Construction | 1st Floor | Construction.8.1.8.2 | Install Ductwork and Appurtenances - 1st Floor | 5 | 5 | 0% | 2023-01-10 08:00 | 2023-01-17 17:00 | -40 | WELKIN | DUCTWORK | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.2 | S81 | S8E | 03112 | 0 | 0 | S8E-03112 | Construction | 1st Floor | Construction.8.1.8.2 | Install HV & EF Units - 1st Floor | 5 | 5 | 0% | 2023-01-18 08:00 | 2023-01-24 17:00 | -40 | MEP | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.2 | S81 | S8E | 03107 | 0 | 0 | S8E-03107 | Construction | 1st Floor | Construction.8.1.8.2 | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 10 | 10 | 0% | 2023-01-10 08:00 | 2023-01-24 17:00 | -6 | WELKIN | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.2.5.1 | S82 | S8A | 03105 | 0 | 0 | S8A-03105 | Construction | 1st Floor | Construction.8.2.5.1 | Rough-In Plumbing Piping & Appurtenances - 1st Floor | 15 | 15 | 0% | 2023-01-03 08:00 | 2023-01-24 17:00 | -69 | WELKIN | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Construction.8.2.5.1 | S8A | S8A | 03110 | 0 | 0 | S8A-03110 | Construction | 1st Floor | Construction.8.2.5.1 | Rig Fuel Oil Tank & Piping - 1st Floor - N/A | 3 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-S8A
Not Started | CI NYCHA Update #22.Construction.8.2.5.1 | S82 | S8A | 03125 | 0 | 0 | S8A-03125 | Construction | 1st Floor | Construction.8.2.5.1 | Install Remaining Piping & Appurtenances - 1st Floor | 10 | 10 | 0% | 2023-02-15 08:00 | 2023-03-01 17:00 | -69 | VITAL | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.1 | S82 | S8A | 03130 | 0 | 0 | S8A-03130 | Construction | 1st Floor | Construction.8.2.5.1 | Install FOT Controls - 1st Floor | 20 | 20 | 0% | 2023-03-02 08:00 | 2023-03-29 17:00 | -49 | MEP | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.1 | S82 | S8A | 03135 | 0 | 0 | S8A-03135 | Construction | 1st Floor | Construction.8.2.5.1 | Perform Hydrostatic Testing - 1st Floor | 5 | 5 | 0% | 2023-03-30 08:00 | 2023-04-05 17:00 | -49 | WELKIN | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.1 | S82 | S8A | 03140 | 0 | 0 | S8A-03140 | Construction | 1st Floor | Construction.8.2.5.1 | Install Plumbing Equipment - 1st Floor | 15 | 15 | 0% | 2023-02-15 08:00 | 2023-03-08 17:00 | -34 | VITAL | PLUMBING EQUIP | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.1 | S82 | S8A | 03145 | 0 | 0 | S8A-03145 | Construction | 1st Floor | Construction.8.2.5.1 | Mechanical Equipment Start-up & Balance - 1st Floor | 5 | 5 | 0% | 2023-04-06 08:00 | 2023-04-12 17:00 | -49 | WELKIN | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.1 | S82 | S8A | 03150 | 0 | 0 | S8A-03150 | Construction | 1st Floor | Construction.8.2.5.1 | Plumbing/Mechanical Insulation - 1st Floor | 20 | 20 | 0% | 2023-04-13 08:00 | 2023-05-10 17:00 | -49 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.1 | S82 | S8A | 03107 | 0 | 0 | S8A-03107 | Construction | 1st Floor | Construction.8.2.5.1 | Rough-In Mechanical Piping & Appurtenances - 1st Floor | 15 | 15 | 0% | 2023-01-25 08:00 | 2023-02-14 17:00 | -69 | WELKIN | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.1 | S82 | S8A | 03142 | 0 | 0 | S8A-03142 | Construction | 1st Floor | Construction.8.2.5.1 | Install Mechanical Equipment - 1st Floor | 15 | 15 | 0% | 2023-02-15 08:00 | 2023-03-08 17:00 | -36 | WELKIN | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.4 | S82 | S8A | 03005 | 0 | 0 | S8A-03005 | Construction | Foundation | Construction.8.2.5.4 | Rough-In Plumbing & Appurtenances - Plumbing Shaft | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | -49 | WELKIN | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.4 | S82 | S8A | 03010 | 0 | 0 | S8A-03010 | Construction | Foundation | Construction.8.2.5.4 | Install Condensate Pump - Foundation Level | 10 | 10 | 0% | 2023-01-03 08:00 | 2023-01-17 17:00 | -49 | WELKIN | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Construction.8.2.5.2 | S8A | S8A | 03205 | 0 | 0 | S8A-03205 | Construction | 2nd Floor | Construction.8.2.5.2 | Rough-In Plumbing Piping & Appurtenances - 2nd Floor - N/A | 15 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-S8A
Not Started | CI NYCHA Update #22.Construction.8.2.5.2 | S82 | S8A | 03225 | 0 | 0 | S8A-03225 | Construction | 2nd Floor | Construction.8.2.5.2 | Install Remaining Piping & Appurtenances - 2nd Floor | 20 | 20 | 0% | 2023-03-23 08:00 | 2023-04-19 17:00 | -69 | VITAL | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.2 | S82 | S8A | 03235 | 0 | 0 | S8A-03235 | Construction | 2nd Floor | Construction.8.2.5.2 | Perform Hydrostatic Testing - 2nd Floor | 5 | 5 | 0% | 2023-04-20 08:00 | 2023-04-26 17:00 | -69 | WELKIN | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Construction.8.2.5.2 | S8A | S8A | 03240 | 0 | 0 | S8A-03240 | Construction | 2nd Floor | Construction.8.2.5.2 | Install Plumbing Equipment - 2nd Floor - N/A | 15 | 0 | 100% | 2021-08-02 08:00 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-S8A
Not Started | CI NYCHA Update #22.Construction.8.2.5.2 | S82 | S8A | 03245 | 0 | 0 | S8A-03245 | Construction | 2nd Floor | Construction.8.2.5.2 | Mechanical Equipment Start-up & Balance - 2nd Floor | 10 | 10 | 0% | 2023-04-27 08:00 | 2023-05-10 17:00 | -69 | WELKIN | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.2 | S82 | S8A | 03250 | 0 | 0 | S8A-03250 | Construction | 2nd Floor | Construction.8.2.5.2 | Plumbing/Mechanical Insulation - 2nd Floor | 20 | 20 | 0% | 2023-05-11 08:00 | 2023-06-08 17:00 | -69 | WELKIN/TRISTAN | INSULATION | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.2 | S82 | S8A | 03207 | 0 | 0 | S8A-03207 | Construction | 2nd Floor | Construction.8.2.5.2 | Rough-In Mechanical Piping & Appurtenances - 2nd Floor | 15 | 15 | 0% | 2023-03-02 08:00 | 2023-03-22 17:00 | -69 | WELKIN | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.2 | S82 | S8A | 03242 | 0 | 0 | S8A-03242 | Construction | 2nd Floor | Construction.8.2.5.2 | Install Mechanical Equipment - 2nd Floor | 5 | 5 | 0% | 2023-03-23 08:00 | 2023-03-29 17:00 | -54 | WELKIN | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Construction.8.2.5.3 | S8A | S8A | 03405 | 0 | 0 | S8A-03405 | Construction | Roof | Construction.8.2.5.3 | Install Ductwork & Appurtenances - Roof - N/A | 4 | 0 | 100% | 2021-02-01 | 2021-02-01 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Construction.8.2.5.3 | S8A | S8A | 03410 | 0 | 0 | S8A-03410 | Construction | Roof | Construction.8.2.5.3 | Install & Connect Exhaust Fans - Roof - N/A | 6 | 0 | 100% | 2021-02-01 | 2021-02-01 |  | 0 | 0 | 0 | 0 | 0-S8A
Not Started | CI NYCHA Update #22.Construction.8.2.5.3 | S82 | S8A | 03415 | 0 | 0 | S8A-03415 | Construction | Roof | Construction.8.2.5.3 | Install Insulation - Roof | 15 | 15 | 0% | 2022-11-25 08:00 | 2022-12-15 17:00 | 51 | TRIANGLE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.6 | S82 | S8A | 03505 | 0 | 0 | S8A-03505 | Construction | Testing & Start-Up | Construction.8.2.5.6 | DOB Mechanical/Plumbing Inspection - S8A | 4 | 4 | 0% | 2023-06-09 08:00 | 2023-06-14 17:00 | -69 | UNSURE | INSPECTION | INSPECTION | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.6 | S82 | S8A | 03510 | 0 | 0 | S8A-03510 | Construction | Testing & Start-Up | Construction.8.2.5.6 | Perform Start-Up Testing - S8A | 10 | 10 | 0% | 2023-07-19 08:00 | 2023-08-01 17:00 | -61 | UNSURE | STARTUP | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.6 | S82 | S8A | 03520 | 0 | 0 | S8A-03520 | Construction | Testing & Start-Up | Construction.8.2.5.6 | Perform Punch List - Electrical/Mechanical/Plumbing Work - S8A | 5 | 5 | 0% | 2023-08-02 08:00 | 2023-08-08 17:00 | -61 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.6 | S82 | S8A | 03530 | 0 | 0 | S8A-03530 | Construction | Testing & Start-Up | Construction.8.2.5.6 | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - S8A | 4 | 4 | 0% | 2023-10-24 08:00 | 2023-10-27 17:00 | -111 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.6 | S82 | S8A | 03525 | 0 | 0 | S8A-03525 | Construction | Testing & Start-Up | Construction.8.2.5.6 | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - S8A | 1 | 1 | 0% | 2023-10-23 08:00 | 2023-10-23 17:00 | -112 | FSE | INSPECTION | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.1.8.3 | S81 | S8E | 03305 | 0 | 0 | S8E-03305 | Construction | Testing & Start-Up | Construction.8.1.8.3 | DOB Mechanical/Plumbing Inspection - S8E | 4 | 4 | 0% | 2023-06-22 08:00 | 2023-06-27 17:00 | -74 | UNSURE | INSPECTION | INSPECTION | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.3 | S81 | S8E | 03310 | 0 | 0 | S8E-03310 | Construction | Testing & Start-Up | Construction.8.1.8.3 | Perform Start-Up Testing - S8E | 10 | 10 | 0% | 2023-07-13 08:00 | 2023-07-26 17:00 | -84 | UNSURE | STARTUP | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.3 | S81 | S8E | 03320 | 0 | 0 | S8E-03320 | Construction | Testing & Start-Up | Construction.8.1.8.3 | Perform Punch List - Electrical/Mechanical/Plumbing Work - S8E | 5 | 5 | 0% | 2023-07-27 08:00 | 2023-08-02 17:00 | -56 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.3 | S81 | S8E | 03330 | 0 | 0 | S8E-03330 | Construction | Testing & Start-Up | Construction.8.1.8.3 | Perform Training/Deliver Spare Parts - Electrical/Mechanical/Plumbing Work - S8E | 4 | 4 | 0% | 2023-10-25 08:00 | 2023-10-30 17:00 | -112 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.3 | S81 | S8E | 03325 | 0 | 0 | S8E-03325 | Construction | Testing & Start-Up | Construction.8.1.8.3 | Final Inspection/Accept Electrical/Mechanical/Plumbing Work - S8E | 1 | 1 | 0% | 2023-10-24 08:00 | 2023-10-24 17:00 | -112 | FSE | INSPECTION | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.8.1.8.3 | S81 | S8E | 03335 | 0 | 0 | S8E-03335 | Construction | Testing & Start-Up | Construction.8.1.8.3 | Remove Redundant Services - S8E | 10 | 10 | 0% | 2023-07-27 08:00 | 2023-08-09 17:00 | -84 | UNSURE | STARTUP | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05010 | 0 | 0 | PERMIT-05010 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Demolition Permit | 20 | 0 | 100% | 2021-03-17 | 2021-10-06 |  | 0 | 0 | 0 | 0 | 0-0
Not Started | CI NYCHA Update #22.Milestones | NA | M905 | 0 | 0 | 0 | M905 | Milestones | Milestones | Milestones | Project Close-out (Including obtaining COC) | 90 | 90 | 0% | 2024-05-09 08:00 | 2024-08-06 17:00 | -348 | MLJ | MILESTONE | 0 | NA | NA-NA
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01013 | 0 | 0 | OG10-01013 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Asbestos Abatement at OG-7 (Garden Shed) | 5 | 0 | 100% | 2021-03-05 | 2021-03-05 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01015 | 0 | 0 | OG10-01015 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Demo OG-7 (Garden Shed) Structure | 3 | 0 | 100% | 2021-12-02 08:00 | 2021-12-02 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01018 | 0 | 0 | OG10-01018 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Demo OG-7 Footings | 2 | 0 | 100% | 2021-12-03 | 2021-12-04 |  | 0 | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01410 | 0 | 0 | OGP1-01410 | Construction | Site Utilities | Construction.3.5.4 | National Gas to Install Line - OG8 --> W33rd Street | 5 | 5 | 0% | 2022-12-02 08:00 | 2022-12-08 17:00 | -17 | NATIONAL GRID | GAS INSTALL | 0 | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.3.5.4 | OGP1 | OGP1 | 01415 | 0 | 0 | OGP1-01415 | Construction | Site Utilities | Construction.3.5.4 | Backfill Gas line - OG8 --> W33rd Street | 5 | 5 | 0% | 2022-12-09 08:00 | 2022-12-15 17:00 | 9 | MLJ | BACKFILL | BACKFILL UTILITY | 31-2200 | 31-2200-OGP1
Completed | CI NYCHA Update #22.Construction.2.2.5.2 | SG4 | SG4 | 01220 | 0 | 0 | SG4-01220 | Construction | Interior Demolition | Construction.2.2.5.2 | Selective Demo (pumps etc..) - Cellar --> SG4 | 5 | 0 | 100% | 2022-06-06 | 2022-06-10 |  | 0 | 0 | 0 | 02-6010 | 02-6010-SG4
Completed | CI NYCHA Update #22.Procurement.Div 1.GENRAL | 0 | 01575 | 0 | 0 | 0 | 01575 | Procurement | General | Procurement.Div 1.GENRAL | Prepare & Submit Construction Work Plan | 20 | 0 | 100% | 2020-10-01 | 2020-11-11 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.GENRAL | 0 | 01580 | 0 | 0 | 0 | 01580 | Procurement | General | Procurement.Div 1.GENRAL | Review & Approve Construction Work Plan | 10 | 0 | 100% | 2020-11-12 | 2020-12-15 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01850 | 0 | 0 | 0 | 01850 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Prepare & Submit Arborist Subcontractor | 5 | 0 | 100% | 2020-09-01 | 2020-09-23 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01855 | 0 | 0 | 0 | 01855 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Review & Approve Arborist Subcontractor | 10 | 0 | 100% | 2020-09-24 | 2020-10-14 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Construction.2.5.4 | SGN | SGN | 01521 | 0 | 0 | SGN-01521 | Construction | Retaining Walls | Construction.2.5.4 | Cure Retaining wall footing --> SGN | 7 | 0 | 100% | 2022-08-17 08:00 | 2022-08-23 17:00 |  | MLJ | CONCRETE | SITE CONCRETE | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.5.4 | SGN | SGN | 01541 | 0 | 0 | SGN-01541 | Construction | Retaining Walls | Construction.2.5.4 | Cure Retaining wall --> SGN | 7 | 0 | 100% | 2022-08-26 08:00 | 2022-09-02 17:00 |  | MLJ | CONCRETE | SITE CONCRETE | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01041 | 0 | 0 | SG6-01041 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Cure Plumbing Shafts & Ftgs Below Water Table --> SG6 | 7 | 0 | 100% | 2021-04-30 | 2021-05-07 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01081 | 0 | 0 | SG6-01081 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Cure Remaining Ftgs/Piers/Grade Beams --> SG6 | 7 | 0 | 100% | 2021-07-13 | 2021-07-20 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01116 | 0 | 0 | SG6-01116 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Cure Concrete Stair South Side ---> SG6 | 7 | 0 | 100% | 2021-12-11 08:00 | 2021-12-17 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01140 | 0 | 0 | SG6-01140 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Cure First Floor Slab --> SG6 | 7 | 0 | 100% | 2021-07-13 08:00 | 2021-07-20 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01176 | 0 | 0 | SG6-01176 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Cure 2nd Floor Slab / First Floor Walls & Col Encasements --> SG6 | 7 | 0 | 100% | 2021-10-13 | 2021-10-20 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01211 | 0 | 0 | SG6-01211 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Cure Roof Slab and 2nd Floor Conc Pads -->SG6 | 7 | 0 | 100% | 2021-12-04 08:00 | 2021-12-10 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.2.5.5 | SG4 | SG4 | 01361 | 0 | 0 | SG4-01361 | Construction | Boiler Room Construction | Construction.2.2.5.5 | Cure Concrete boiler room walls --> SG4 | 7 | 0 | 100% | 2021-05-14 | 2021-05-21 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.1 | SG4 | SG4 | 01421 | 0 | 0 | SG4-01421 | Construction | East Elevation | Construction.2.2.5.EFPC.1 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> SG4 | 7 | 0 | 100% | 2022-02-25 08:00 | 2022-03-03 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.1 | SG4 | SG4 | 01441 | 0 | 0 | SG4-01441 | Construction | East Elevation | Construction.2.2.5.EFPC.1 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG4 | 7 | 0 | 100% | 2022-03-22 08:00 | 2022-03-28 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.1 | SG4 | SG4 | 01471 | 0 | 0 | SG4-01471 | Construction | East Elevation | Construction.2.2.5.EFPC.1 | Cure slab at Curtain Wall for flood protection (East Side) --> SG4 | 7 | 0 | 100% | 2022-08-12 08:00 | 2022-08-18 17:00 |  | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.2 | SG4 | SG4 | 01521 | 0 | 0 | SG4-01521 | Construction | South Elevation | Construction.2.2.5.EFPC.2 | Cure concrete footings at Curtain Wall for flood protection (South Side) --> SG4 | 7 | 0 | 100% | 2022-02-25 08:00 | 2022-03-03 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.2 | SG4 | SG4 | 01541 | 0 | 0 | SG4-01541 | Construction | South Elevation | Construction.2.2.5.EFPC.2 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG4 | 7 | 0 | 100% | 2022-03-22 08:00 | 2022-03-28 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.2 | SG4 | SG4 | 01571 | 0 | 0 | SG4-01571 | Construction | South Elevation | Construction.2.2.5.EFPC.2 | Cure slab at Curtain Wall for flood protection (South Side) --> SG4 | 7 | 0 | 100% | 2022-03-22 08:00 | 2022-03-28 17:00 |  | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.3 | SG4 | SG4 | 01621 | 0 | 0 | SG4-01621 | Construction | North Elevation | Construction.2.2.5.EFPC.3 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> SG4 | 7 | 0 | 100% | 2022-04-16 08:00 | 2022-04-22 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.3 | SG4 | SG4 | 01641 | 0 | 0 | SG4-01641 | Construction | North Elevation | Construction.2.2.5.EFPC.3 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG4 | 7 | 0 | 100% | 2022-05-02 08:00 | 2022-05-08 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.5.EFPC.3 | SG4 | SG4 | 01671 | 0 | 0 | SG4-01671 | Construction | North Elevation | Construction.2.2.5.EFPC.3 | Cure slab at Curtain Wall for flood protection (North Side) --> SG4 | 7 | 7 | 0% | 2022-12-15 08:00 | 2022-12-21 17:00 | 109 | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.4 | SG4 | SG4 | 01721 | 0 | 0 | SG4-01721 | Construction | West Elevation | Construction.2.2.5.EFPC.4 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> SG4 | 7 | 0 | 100% | 2022-02-25 08:00 | 2022-03-03 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.4 | SG4 | SG4 | 01741 | 0 | 0 | SG4-01741 | Construction | West Elevation | Construction.2.2.5.EFPC.4 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG4 | 7 | 0 | 100% | 2022-03-22 08:00 | 2022-03-28 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.5.EFPC.4 | SG4 | SG4 | 01771 | 0 | 0 | SG4-01771 | Construction | West Elevation | Construction.2.2.5.EFPC.4 | Cure slab at Curtain Wall for flood protection (West Side) --> SG4 | 7 | 7 | 0% | 2022-12-09 08:00 | 2022-12-15 17:00 | 115 | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-SG4
Completed | CI NYCHA Update #22.Construction.2.2.5.EFPC.5 | SG4 | SG4 | 01816 | 0 | 0 | SG4-01816 | Construction | Concrete Shelf Construction | Construction.2.2.5.EFPC.5 | Cure concrete shelf around bldg perimeter --> SG4 | 7 | 0 | 100% | 2022-03-22 08:00 | 2022-03-28 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG4
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.1 | SG5 | SG5 | 01421 | 0 | 0 | SG5-01421 | Construction | East Elevation | Construction.2.3.5.EFPC.1 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> SG5 | 7 | 0 | 100% | 2022-02-22 08:00 | 2022-03-01 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.1 | SG5 | SG5 | 01441 | 0 | 0 | SG5-01441 | Construction | East Elevation | Construction.2.3.5.EFPC.1 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG5 | 7 | 0 | 100% | 2022-08-12 | 2022-08-18 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.1 | SG5 | SG5 | 01471 | 0 | 0 | SG5-01471 | Construction | East Elevation | Construction.2.3.5.EFPC.1 | Cure slab at Curtain Wall for flood protection (East Side) --> SG5 | 7 | 0 | 100% | 2022-09-10 08:00 | 2022-09-16 17:00 |  | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.2 | SG5 | SG5 | 01521 | 0 | 0 | SG5-01521 | Construction | South Elevation | Construction.2.3.5.EFPC.2 | Cure concrete footings at Curtain Wall for flood protection (South Side) --> SG5 | 7 | 0 | 100% | 2022-08-01 08:00 | 2022-08-08 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.2 | SG5 | SG5 | 01541 | 0 | 0 | SG5-01541 | Construction | South Elevation | Construction.2.3.5.EFPC.2 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG5 | 7 | 0 | 100% | 2022-08-02 08:00 | 2022-08-08 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.2 | SG5 | SG5 | 01571 | 0 | 0 | SG5-01571 | Construction | South Elevation | Construction.2.3.5.EFPC.2 | Cure slab at Curtain Wall for flood protection (South Side) --> SG5 | 7 | 7 | 0% | 2022-12-15 08:00 | 2022-12-21 17:00 | 103 | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.3 | SG5 | SG5 | 01621 | 0 | 0 | SG5-01621 | Construction | North Elevation | Construction.2.3.5.EFPC.3 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> SG5 | 7 | 0 | 100% | 2022-02-22 08:00 | 2022-02-28 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.3 | SG5 | SG5 | 01641 | 0 | 0 | SG5-01641 | Construction | North Elevation | Construction.2.3.5.EFPC.3 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG5 | 7 | 7 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 89 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.3 | SG5 | SG5 | 01671 | 0 | 0 | SG5-01671 | Construction | North Elevation | Construction.2.3.5.EFPC.3 | Cure slab at Curtain Wall for flood protection (North Side) --> SG5 | 7 | 7 | 0% | 2023-01-06 08:00 | 2023-01-12 17:00 | 87 | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.4 | SG5 | SG5 | 01721 | 0 | 0 | SG5-01721 | Construction | West Elevation | Construction.2.3.5.EFPC.4 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> SG5 | 7 | 0 | 100% | 2022-03-22 08:00 | 2022-03-29 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.4 | SG5 | SG5 | 01741 | 0 | 0 | SG5-01741 | Construction | West Elevation | Construction.2.3.5.EFPC.4 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG5 | 7 | 0 | 100% | 2022-08-12 08:00 | 2022-08-19 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.4 | SG5 | SG5 | 01771 | 0 | 0 | SG5-01771 | Construction | West Elevation | Construction.2.3.5.EFPC.4 | Cure slab at Curtain Wall for flood protection (West Side) --> SG5 | 7 | 0 | 100% | 2022-09-10 08:00 | 2022-09-16 17:00 |  | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.EFPC.5 | SG5 | SG5 | 01817 | 0 | 0 | SG5-01817 | Construction | Concrete Shelf Construction | Construction.2.3.5.EFPC.5 | Cure concrete shelf around bldg perimeter --> SG5 | 7 | 0 | 100% | 2022-03-22 08:00 | 2022-03-29 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG5
Completed | CI NYCHA Update #22.Construction.3.5.1 | OGP1 | OGP1 | 01621 | 0 | 0 | OGP1-01621 | Construction | Retaining Walls | Construction.3.5.1 | Cure Retaining wall footing --> OG Phase 2A | 7 | 0 | 100% | 2022-07-26 08:00 | 2022-08-02 17:00 |  | MLJ | CONCRETE | SITE CONCRETE | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.5.1 | OGP1 | OGP1 | 01641 | 0 | 0 | OGP1-01641 | Construction | Retaining Walls | Construction.3.5.1 | Cure Retaining wall --> OG Phase 2A | 7 | 0 | 100% | 2022-07-26 08:00 | 2022-08-02 17:00 |  | MLJ | CONCRETE | SITE CONCRETE | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01041 | 0 | 0 | OG8-01041 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Cure Plumbing Shafts & Ftgs Below Water Table --> OG8 | 7 | 0 | 100% | 2021-08-10 | 2021-08-17 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01081 | 0 | 0 | OG8-01081 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Cure Remaining Ftgs/Piers/Grade Beams --> OG8 | 7 | 0 | 100% | 2021-12-08 08:00 | 2021-12-09 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01116 | 0 | 0 | OG8-01116 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Cure Concrete Stair South Side ---> OG8 | 7 | 0 | 100% | 2022-03-05 08:00 | 2022-03-12 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01136 | 0 | 0 | OG8-01136 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Cure First Floor Slab --> OG8 | 7 | 0 | 100% | 2022-03-08 08:00 | 2022-03-15 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01176 | 0 | 0 | OG8-01176 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Cure 2nd Floor Slab / First Floor Walls & Col Encasements --> OG8 | 7 | 0 | 100% | 2022-04-06 08:00 | 2022-04-12 17:00 |  | MLJ | CONCRETE | NB CONCRETE | 03-1900 | 03-1900-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01211 | 0 | 0 | OG8-01211 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Cure Roof Slab and 2nd Floor Conc Pads -->OG8 | 7 | 0 | 100% | 2022-05-10 | 2022-05-10 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.6.5.5 | OG4 | OG4 | 01361 | 0 | 0 | OG4-01361 | Construction | Boiler Room Construction | Construction.3.6.5.5 | Cure Concrete boiler room walls --> OG4 | 7 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.1 | OG4 | OG4 | 01421 | 0 | 0 | OG4-01421 | Construction | East Elevation | Construction.3.6.5.EFPC.1 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> OG4 | 7 | 0 | 100% | 2022-06-22 08:00 | 2022-06-28 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.1 | OG4 | OG4 | 01441 | 0 | 0 | OG4-01441 | Construction | East Elevation | Construction.3.6.5.EFPC.1 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG4 | 7 | 0 | 100% | 2022-06-22 08:00 | 2022-06-28 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.2 | OG4 | OG4 | 01521 | 0 | 0 | OG4-01521 | Construction | South Elevation | Construction.3.6.5.EFPC.2 | Cure concrete footings at Curtain Wall for flood protection (South Side) --> OG4 | 7 | 0 | 100% | 2022-06-22 08:00 | 2022-06-28 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.5.EFPC.2 | OG4 | OG4 | 01541 | 0 | 0 | OG4-01541 | Construction | South Elevation | Construction.3.6.5.EFPC.2 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG4 | 7 | 7 | 0% | 2022-12-01 08:00 | 2022-12-07 17:00 | 95 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.3 | OG4 | OG4 | 01621 | 0 | 0 | OG4-01621 | Construction | North Elevation | Construction.3.6.5.EFPC.3 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> OG4 | 7 | 0 | 100% | 2022-06-22 08:00 | 2022-06-28 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.3 | OG4 | OG4 | 01641 | 0 | 0 | OG4-01641 | Construction | North Elevation | Construction.3.6.5.EFPC.3 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG4 | 7 | 0 | 100% | 2022-10-15 08:00 | 2022-10-21 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.4 | OG4 | OG4 | 01721 | 0 | 0 | OG4-01721 | Construction | West Elevation | Construction.3.6.5.EFPC.4 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> OG4 | 7 | 0 | 100% | 2022-06-22 08:00 | 2022-06-28 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.4 | OG4 | OG4 | 01741 | 0 | 0 | OG4-01741 | Construction | West Elevation | Construction.3.6.5.EFPC.4 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG4 | 7 | 0 | 100% | 2022-10-15 08:00 | 2022-10-21 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG4
Completed | CI NYCHA Update #22.Construction.3.6.5.EFPC.5 | OG4 | OG4 | 01816 | 0 | 0 | OG4-01816 | Construction | Concrete Shelf Construction | Construction.3.6.5.EFPC.5 | Cure concrete shelf around bldg perimeter --> OG4 | 7 | 0 | 100% | 2022-06-22 08:00 | 2022-06-29 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG4
Not Started | CI NYCHA Update #22.Construction.3.3.5.5 | OG5 | OG5 | 01361 | 0 | 0 | OG5-01361 | Construction | Boiler Room Construction | Construction.3.3.5.5 | Cure Concrete boiler room walls --> OG5 | 7 | 7 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 136 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.1 | OG5 | OG5 | 01421 | 0 | 0 | OG5-01421 | Construction | East Elevation | Construction.3.3.5.EFPC.1 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> OG5 | 7 | 0 | 100% | 2022-06-11 08:00 | 2022-06-17 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.1 | OG5 | OG5 | 01441 | 0 | 0 | OG5-01441 | Construction | East Elevation | Construction.3.3.5.EFPC.1 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG5 | 7 | 0 | 100% | 2022-10-11 08:00 | 2022-10-17 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.2 | OG5 | OG5 | 01521 | 0 | 0 | OG5-01521 | Construction | South Elevation | Construction.3.3.5.EFPC.2 | Cure concrete footings at Curtain Wall for flood protection (South Side) --> OG5 | 7 | 0 | 100% | 2022-06-11 08:00 | 2022-06-17 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.2 | OG5 | OG5 | 01541 | 0 | 0 | OG5-01541 | Construction | South Elevation | Construction.3.3.5.EFPC.2 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG5 | 7 | 0 | 100% | 2022-06-25 08:00 | 2022-07-01 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.2 | OG5 | OG5 | 01571 | 0 | 0 | OG5-01571 | Construction | South Elevation | Construction.3.3.5.EFPC.2 | Cure slab at Curtain Wall for flood protection (South Side) --> OG5 | 7 | 0 | 100% | 2022-08-23 08:00 | 2022-08-29 17:00 |  | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.3 | OG5 | OG5 | 01621 | 0 | 0 | OG5-01621 | Construction | North Elevation | Construction.3.3.5.EFPC.3 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> OG5 | 7 | 0 | 100% | 2022-06-09 08:00 | 2022-06-15 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.3 | OG5 | OG5 | 01641 | 0 | 0 | OG5-01641 | Construction | North Elevation | Construction.3.3.5.EFPC.3 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG5 | 7 | 0 | 100% | 2022-08-09 08:00 | 2022-08-15 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.4 | OG5 | OG5 | 01721 | 0 | 0 | OG5-01721 | Construction | West Elevation | Construction.3.3.5.EFPC.4 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> OG5 | 7 | 0 | 100% | 2022-06-09 08:00 | 2022-06-15 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG5
Not Started | CI NYCHA Update #22.Construction.3.3.5.EFPC.4 | OG5 | OG5 | 01741 | 0 | 0 | OG5-01741 | Construction | West Elevation | Construction.3.3.5.EFPC.4 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG5 | 7 | 7 | 0% | 2022-12-07 08:00 | 2022-12-13 17:00 | 125 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG5
Completed | CI NYCHA Update #22.Construction.3.3.5.EFPC.5 | OG5 | OG5 | 01816 | 0 | 0 | OG5-01816 | Construction | Concrete Shelf Construction | Construction.3.3.5.EFPC.5 | Cure concrete shelf around bldg perimeter --> OG5 | 7 | 0 | 100% | 2022-06-11 08:00 | 2022-06-17 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG5
Completed | CI NYCHA Update #22.Construction.5.6.1 | OGW | OGW | 01621 | 0 | 0 | OGW-01621 | Construction | Retaining Walls | Construction.5.6.1 | Cure Retaining wall footing --> OG Phase 3A | 7 | 0 | 100% | 2022-09-22 08:00 | 2022-09-24 17:00 |  | MLJ | CONCRETE | SITE CONCRETE | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.1 | OGW | OGW | 01641 | 0 | 0 | OGW-01641 | Construction | Retaining Walls | Construction.5.6.1 | Cure Retaining wall --> OG Phase 3A | 7 | 7 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 7 | MLJ | CONCRETE | SITE CONCRETE | 03-2400 | 03-2400-OGW
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01041 | 0 | 0 | OG9-01041 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Cure Plumbing Shafts & Ftgs Below Water Table --> OG9 | 7 | 0 | 100% | 2021-09-17 08:00 | 2021-09-24 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01081 | 0 | 0 | OG9-01081 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Cure Remaining Ftgs/Piers/Grade Beams --> OG9 | 7 | 0 | 100% | 2021-11-03 08:00 | 2021-11-09 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01116 | 0 | 0 | OG9-01116 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Cure Concrete Stair South Side ---> OG9 | 7 | 0 | 100% | 2021-12-20 08:00 | 2021-12-27 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01136 | 0 | 0 | OG9-01136 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Cure First Floor Slab --> OG9 | 7 | 0 | 100% | 2021-12-27 08:00 | 2022-01-07 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01176 | 0 | 0 | OG9-01176 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Cure 2nd Floor Slab / First Floor Walls & Col Encasements --> OG9 | 7 | 0 | 100% | 2022-02-07 08:00 | 2022-02-14 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01211 | 0 | 0 | OG9-01211 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Cure Roof Slab and 2nd Floor Conc Pads -->OG9 | 7 | 0 | 100% | 2022-02-02 08:00 | 2022-02-09 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.5.3.5.5 | OG3 | OG3 | 01361 | 0 | 0 | OG3-01361 | Construction | Boiler Room Construction | Construction.5.3.5.5 | Cure Concrete boiler room walls --> OG3 | 7 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.1 | OG3 | OG3 | 01421 | 0 | 0 | OG3-01421 | Construction | East Elevation | Construction.5.3.5.EFPC.1 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> OG3 | 7 | 0 | 100% | 2022-06-11 08:00 | 2022-06-17 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Not Started | CI NYCHA Update #22.Construction.5.3.5.EFPC.1 | OG3 | OG3 | 01441 | 0 | 0 | OG3-01441 | Construction | East Elevation | Construction.5.3.5.EFPC.1 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG3 | 7 | 7 | 0% | 2022-12-21 08:00 | 2022-12-27 17:00 | 97 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.2 | OG3 | OG3 | 01521 | 0 | 0 | OG3-01521 | Construction | South Elevation | Construction.5.3.5.EFPC.2 | Cure concrete footings at Curtain Wall for flood protection (South Side) --> OG3 | 7 | 0 | 100% | 2022-06-11 08:00 | 2022-06-17 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.2 | OG3 | OG3 | 01541 | 0 | 0 | OG3-01541 | Construction | South Elevation | Construction.5.3.5.EFPC.2 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG3 | 7 | 0 | 100% | 2022-09-10 08:00 | 2022-09-16 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.3 | OG3 | OG3 | 01621 | 0 | 0 | OG3-01621 | Construction | North Elevation | Construction.5.3.5.EFPC.3 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> OG3 | 7 | 0 | 100% | 2022-06-11 08:00 | 2022-06-17 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.3 | OG3 | OG3 | 01641 | 0 | 0 | OG3-01641 | Construction | North Elevation | Construction.5.3.5.EFPC.3 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG3 | 7 | 0 | 100% | 2022-09-10 08:00 | 2022-09-16 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.4 | OG3 | OG3 | 01721 | 0 | 0 | OG3-01721 | Construction | West Elevation | Construction.5.3.5.EFPC.4 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> OG3 | 7 | 0 | 100% | 2022-06-11 08:00 | 2022-06-17 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.4 | OG3 | OG3 | 01741 | 0 | 0 | OG3-01741 | Construction | West Elevation | Construction.5.3.5.EFPC.4 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG3 | 7 | 0 | 100% | 2022-09-10 08:00 | 2022-09-16 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.4 | OG3 | OG3 | 01771 | 0 | 0 | OG3-01771 | Construction | West Elevation | Construction.5.3.5.EFPC.4 | Cure slab at Curtain Wall for flood protection (West Side) --> OG3 | 7 | 0 | 100% | 2022-10-14 08:00 | 2022-10-21 17:00 |  | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-OG3
Completed | CI NYCHA Update #22.Construction.5.3.5.EFPC.5 | OG3 | OG3 | 01816 | 0 | 0 | OG3-01816 | Construction | Concrete Shelf Construction | Construction.5.3.5.EFPC.5 | Cure concrete shelf around bldg perimeter --> OG3 | 7 | 0 | 100% | 2022-06-11 08:00 | 2022-06-17 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG3
Not Started | CI NYCHA Update #22.Construction.5.2.5.5 | OG2 | OG2 | 01361 | 0 | 0 | OG2-01361 | Construction | Boiler Room Construction | Construction.5.2.5.5 | Cure Concrete boiler room walls --> OG2 | 7 | 7 | 0% | 2022-12-13 08:00 | 2022-12-19 17:00 | -68 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.1 | OG2 | OG2 | 01421 | 0 | 0 | OG2-01421 | Construction | East Elevation | Construction.5.2.5.EFPC.1 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> OG2 | 7 | 0 | 100% | 2022-05-20 08:00 | 2022-05-26 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.1 | OG2 | OG2 | 01441 | 0 | 0 | OG2-01441 | Construction | East Elevation | Construction.5.2.5.EFPC.1 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG2 | 7 | 0 | 100% | 2022-08-12 08:00 | 2022-08-18 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.2 | OG2 | OG2 | 01521 | 0 | 0 | OG2-01521 | Construction | South Elevation | Construction.5.2.5.EFPC.2 | Cure concrete footings at Curtain Wall for flood protection (South Side) --> OG2 | 7 | 0 | 100% | 2022-05-20 08:00 | 2022-05-26 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.2 | OG2 | OG2 | 01541 | 0 | 0 | OG2-01541 | Construction | South Elevation | Construction.5.2.5.EFPC.2 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG2 | 7 | 0 | 100% | 2022-08-12 08:00 | 2022-08-17 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.3 | OG2 | OG2 | 01621 | 0 | 0 | OG2-01621 | Construction | North Elevation | Construction.5.2.5.EFPC.3 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> OG2 | 7 | 0 | 100% | 2022-05-20 08:00 | 2022-05-26 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.3 | OG2 | OG2 | 01641 | 0 | 0 | OG2-01641 | Construction | North Elevation | Construction.5.2.5.EFPC.3 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG2 | 7 | 0 | 100% | 2022-08-12 08:00 | 2022-08-18 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.4 | OG2 | OG2 | 01721 | 0 | 0 | OG2-01721 | Construction | West Elevation | Construction.5.2.5.EFPC.4 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> OG2 | 7 | 0 | 100% | 2022-05-20 08:00 | 2022-05-26 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.EFPC.4 | OG2 | OG2 | 01741 | 0 | 0 | OG2-01741 | Construction | West Elevation | Construction.5.2.5.EFPC.4 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG2 | 7 | 7 | 0% | 2022-12-21 08:00 | 2022-12-27 17:00 | 75 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG2
Not Started | CI NYCHA Update #22.Construction.5.2.5.EFPC.4 | OG2 | OG2 | 01771 | 0 | 0 | OG2-01771 | Construction | West Elevation | Construction.5.2.5.EFPC.4 | Cure slab at Curtain Wall for flood protection (West Side) --> OG2 | 7 | 7 | 0% | 2023-02-01 08:00 | 2023-02-07 17:00 | 71 | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-OG2
Completed | CI NYCHA Update #22.Construction.5.2.5.EFPC.5 | OG2 | OG2 | 01816 | 0 | 0 | OG2-01816 | Construction | Concrete Shelf Construction | Construction.5.2.5.EFPC.5 | Cure concrete shelf around bldg perimeter --> OG2 | 7 | 0 | 100% | 2022-05-20 08:00 | 2022-05-26 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG2
Completed | CI NYCHA Update #22.Construction.1.5.4 | OGE | OGE | 01621 | 0 | 0 | OGE-01621 | Construction | Retaining Walls | Construction.1.5.4 | Cure Retaining wall footing --> OG Phase 4 | 7 | 0 | 100% | 2022-10-21 08:00 | 2022-10-24 17:00 |  | MLJ | CONCRETE | SITE CONCRETE | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.4 | OGE | OGE | 01641 | 0 | 0 | OGE-01641 | Construction | Retaining Walls | Construction.1.5.4 | Cure Retaining wall --> OG Phase 4 | 7 | 7 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 39 | MLJ | CONCRETE | SITE CONCRETE | 03-2400 | 03-2400-OGE
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01041 | 0 | 0 | OG10-01041 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Cure Plumbing Shafts & Ftgs Below Water Table --> OG10 | 7 | 0 | 100% | 2021-08-28 08:00 | 2021-09-04 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01081 | 0 | 0 | OG10-01081 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Cure Remaining Ftgs/Piers/Grade Beams --> OG10 | 7 | 0 | 100% | 2021-09-28 08:00 | 2021-10-05 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01116 | 0 | 0 | OG10-01116 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Cure Concrete Stair South Side ---> OG10 | 7 | 0 | 100% | 2021-11-15 08:00 | 2021-11-19 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01136 | 0 | 0 | OG10-01136 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Cure First Floor Slab --> OG10 | 7 | 0 | 100% | 2021-11-16 08:00 | 2021-11-23 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01176 | 0 | 0 | OG10-01176 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Cure 2nd Floor Slab / First Floor Walls & Col Encasements And 1st Floor Pads --> OG10 | 7 | 0 | 100% | 2022-02-11 08:00 | 2022-02-18 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01211 | 0 | 0 | OG10-01211 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Cure Roof Slab and 2nd Floor Conc Pads -->OG10 | 7 | 0 | 100% | 2022-02-11 08:00 | 2022-02-18 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.2.1.5 | OG6 | OG6 | 01361 | 0 | 0 | OG6-01361 | Construction | Boiler Room Construction | Construction.1.2.1.5 | Cure Concrete boiler room walls --> OG6 | 7 | 7 | 0% | 2022-11-26 08:00 | 2022-12-02 17:00 | 135 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.1 | OG6 | OG6 | 01421 | 0 | 0 | OG6-01421 | Construction | East Elevation | Construction.1.2.1.EFPC.1 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> OG6 | 7 | 7 | 0% | 2023-01-05 08:00 | 2023-01-11 17:00 | 69 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.1 | OG6 | OG6 | 01441 | 0 | 0 | OG6-01441 | Construction | East Elevation | Construction.1.2.1.EFPC.1 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG6 | 7 | 7 | 0% | 2023-02-08 08:00 | 2023-02-14 17:00 | 48 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.2 | OG6 | OG6 | 01521 | 0 | 0 | OG6-01521 | Construction | South Elevation | Construction.1.2.1.EFPC.2 | Cure concrete footings at Curtain Wall for flood protection (South Side) --> OG6 | 7 | 7 | 0% | 2023-01-11 08:00 | 2023-01-17 17:00 | 78 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.2 | OG6 | OG6 | 01541 | 0 | 0 | OG6-01541 | Construction | South Elevation | Construction.1.2.1.EFPC.2 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG6 | 7 | 7 | 0% | 2023-02-08 08:00 | 2023-02-14 17:00 | 62 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.3 | OG6 | OG6 | 01621 | 0 | 0 | OG6-01621 | Construction | North Elevation | Construction.1.2.1.EFPC.3 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> OG6 | 7 | 7 | 0% | 2023-01-21 08:00 | 2023-01-27 17:00 | 68 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.3 | OG6 | OG6 | 01641 | 0 | 0 | OG6-01641 | Construction | North Elevation | Construction.1.2.1.EFPC.3 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG6 | 7 | 7 | 0% | 2023-02-17 08:00 | 2023-02-23 17:00 | 53 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.4 | OG6 | OG6 | 01721 | 0 | 0 | OG6-01721 | Construction | West Elevation | Construction.1.2.1.EFPC.4 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> OG6 | 7 | 7 | 0% | 2023-02-07 08:00 | 2023-02-13 17:00 | 15 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.4 | OG6 | OG6 | 01741 | 0 | 0 | OG6-01741 | Construction | West Elevation | Construction.1.2.1.EFPC.4 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG6 | 7 | 7 | 0% | 2023-03-11 08:00 | 2023-03-17 17:00 | -4 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.4 | OG6 | OG6 | 01771 | 0 | 0 | OG6-01771 | Construction | West Elevation | Construction.1.2.1.EFPC.4 | Cure slab at Curtain Wall for flood protection (West Side) --> OG6 | 7 | 7 | 0% | 2023-04-20 08:00 | 2023-04-26 17:00 | -6 | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.2.1.EFPC.5 | OG6 | OG6 | 01816 | 0 | 0 | OG6-01816 | Construction | Concrete Shelf Construction | Construction.1.2.1.EFPC.5 | Cure concrete shelf around bldg perimeter --> OG6 | 7 | 7 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 54 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG6
Not Started | CI NYCHA Update #22.Construction.1.3.1.5 | OG1 | OG1 | 01361 | 0 | 0 | OG1-01361 | Construction | Boiler Room Construction | Construction.1.3.1.5 | Cure Concrete boiler room walls --> OG1 | 7 | 7 | 0% | 2022-12-13 08:00 | 2022-12-19 17:00 | 35 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.1 | OG1 | OG1 | 01421 | 0 | 0 | OG1-01421 | Construction | East Elevation | Construction.1.3.1.EFPC.1 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> OG1 | 7 | 0 | 100% | 2022-05-25 13:00 | 2022-05-31 12:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.1 | OG1 | OG1 | 01441 | 0 | 0 | OG1-01441 | Construction | East Elevation | Construction.1.3.1.EFPC.1 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> OG1 | 7 | 0 | 100% | 2022-10-18 08:00 | 2022-10-24 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.2 | OG1 | OG1 | 01521 | 0 | 0 | OG1-01521 | Construction | South Elevation | Construction.1.3.1.EFPC.2 | Cure concrete footings at Curtain Wall for flood protection (South Side) --> OG1 | 7 | 0 | 100% | 2022-03-11 | 2022-03-15 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.2 | OG1 | OG1 | 01541 | 0 | 0 | OG1-01541 | Construction | South Elevation | Construction.1.3.1.EFPC.2 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> OG1 | 7 | 0 | 100% | 2022-09-08 08:00 | 2022-09-14 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.3 | OG1 | OG1 | 01621 | 0 | 0 | OG1-01621 | Construction | North Elevation | Construction.1.3.1.EFPC.3 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> OG1 | 7 | 0 | 100% | 2022-05-25 08:00 | 2022-05-31 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.3 | OG1 | OG1 | 01641 | 0 | 0 | OG1-01641 | Construction | North Elevation | Construction.1.3.1.EFPC.3 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> OG1 | 7 | 0 | 100% | 2022-09-08 08:00 | 2022-09-14 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.4 | OG1 | OG1 | 01721 | 0 | 0 | OG1-01721 | Construction | West Elevation | Construction.1.3.1.EFPC.4 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> OG1 | 7 | 7 | 0% | 2022-12-22 08:00 | 2022-12-28 17:00 | 84 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.4 | OG1 | OG1 | 01741 | 0 | 0 | OG1-01741 | Construction | West Elevation | Construction.1.3.1.EFPC.4 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> OG1 | 7 | 7 | 0% | 2023-01-27 08:00 | 2023-02-02 17:00 | 61 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG1
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.4 | OG1 | OG1 | 01771 | 0 | 0 | OG1-01771 | Construction | West Elevation | Construction.1.3.1.EFPC.4 | Cure slab at Curtain Wall for flood protection (West Side) --> OG1 | 7 | 7 | 0% | 2023-03-09 08:00 | 2023-03-15 17:00 | 60 | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-OG1
Completed | CI NYCHA Update #22.Construction.1.3.1.EFPC.5 | OG1 | OG1 | 01816 | 0 | 0 | OG1-01816 | Construction | Concrete Shelf Construction | Construction.1.3.1.EFPC.5 | Cure concrete shelf around bldg perimeter --> OG1 | 7 | 0 | 100% | 2022-05-27 08:00 | 2022-06-03 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG1
Completed | CI NYCHA Update #22.Construction.4.5.4 | SGS | SGS | 01621 | 0 | 0 | SGS-01621 | Construction | Retaining Walls | Construction.4.5.4 | Cure Retaining wall footing --> SGS Phase 5 | 7 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | MLJ | CONCRETE | SITE CONCRETE | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.4.5.4 | SGS | SGS | 01641 | 0 | 0 | SGS-01641 | Construction | Retaining Walls | Construction.4.5.4 | Cure Retaining wall --> SGS Phase 5 | 7 | 7 | 0% | 2022-12-06 08:00 | 2022-12-12 17:00 | -12 | MLJ | CONCRETE | SITE CONCRETE | 03-2400 | 03-2400-SGS
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01041 | 0 | 0 | SG7-01041 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Cure Plumbing Shafts & Ftgs Below Water Table --> SG7 | 7 | 0 | 100% | 2021-10-10 | 2021-10-17 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01081 | 0 | 0 | SG7-01081 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Cure Remaining Ftgs/Piers/Grade Beams --> SG7 | 7 | 0 | 100% | 2022-05-11 08:00 | 2022-05-17 17:00 |  | 0 | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01116 | 0 | 0 | SG7-01116 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Cure Concrete Stair South Side ---> SG7 | 7 | 7 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 132 | MLJ | Concrete | NB CONCRETE | 03-1900 | 03-1900-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01136 | 0 | 0 | SG7-01136 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Cure First Floor Slab --> SG7 | 7 | 0 | 100% | 2022-06-25 08:00 | 2022-07-01 17:00 |  | MLJ | CONCRETE | NB CONCRETE | 03-1900 | 03-1900-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01176 | 0 | 0 | SG7-01176 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Cure 2nd Floor Slab / First Floor Walls & Col Encasements And 1st Floor Pads --> SG7 | 7 | 0 | 100% | 2022-09-15 08:00 | 2022-09-21 17:00 |  | MLJ | CONCRETE | NB CONCRETE | 03-1900 | 03-1900-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01211 | 0 | 0 | SG7-01211 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Cure Roof Slab and 2nd Floor Conc Pads -->SG7 | 7 | 0 | 100% | 2022-09-15 08:00 | 2022-09-21 17:00 |  | MLJ | CONCRETE | NB CONCRETE | 03-1900 | 03-1900-SG7
Not Started | CI NYCHA Update #22.Construction.4.3.5.5 | SG3 | SG3 | 01361 | 0 | 0 | SG3-01361 | Construction | Boiler Room Construction | Construction.4.3.5.5 | Cure Concrete boiler room walls --> SG3 | 7 | 7 | 0% | 2022-12-13 08:00 | 2022-12-19 17:00 | 118 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.EFPC.1 | SG3 | SG3 | 01421 | 0 | 0 | SG3-01421 | Construction | East Elevation | Construction.4.3.5.EFPC.1 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> SG3 | 7 | 0 | 100% | 2022-09-08 08:00 | 2022-09-14 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.1 | SG3 | SG3 | 01441 | 0 | 0 | SG3-01441 | Construction | East Elevation | Construction.4.3.5.EFPC.1 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG3 | 7 | 7 | 0% | 2022-12-29 08:00 | 2023-01-04 17:00 | -86 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.1 | SG3 | SG3 | 01471 | 0 | 0 | SG3-01471 | Construction | East Elevation | Construction.4.3.5.EFPC.1 | Cure slab at Curtain Wall for flood protection (East Side) --> SG3 | 7 | 7 | 0% | 2023-02-08 08:00 | 2023-02-14 17:00 | -84 | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.2 | SG3 | SG3 | 01521 | 0 | 0 | SG3-01521 | Construction | South Elevation | Construction.4.3.5.EFPC.2 | Cure concrete footings at Curtain Wall for flood protection (South Side) --> SG3 | 7 | 7 | 0% | 2023-01-05 08:00 | 2023-01-11 17:00 | -106 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.2 | SG3 | SG3 | 01541 | 0 | 0 | SG3-01541 | Construction | South Elevation | Construction.4.3.5.EFPC.2 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG3 | 7 | 7 | 0% | 2023-02-08 08:00 | 2023-02-14 17:00 | -127 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.2 | SG3 | SG3 | 01571 | 0 | 0 | SG3-01571 | Construction | South Elevation | Construction.4.3.5.EFPC.2 | Cure slab at Curtain Wall for flood protection (South Side) --> SG3 | 7 | 7 | 0% | 2023-03-21 08:00 | 2023-03-27 17:00 | -125 | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.3 | SG3 | SG3 | 01621 | 0 | 0 | SG3-01621 | Construction | North Elevation | Construction.4.3.5.EFPC.3 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> SG3 | 7 | 7 | 0% | 2022-12-07 08:00 | 2022-12-13 17:00 | -40 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.3 | SG3 | SG3 | 01641 | 0 | 0 | SG3-01641 | Construction | North Elevation | Construction.4.3.5.EFPC.3 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG3 | 7 | 7 | 0% | 2023-01-11 08:00 | 2023-01-17 17:00 | -62 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.4 | SG3 | SG3 | 01721 | 0 | 0 | SG3-01721 | Construction | West Elevation | Construction.4.3.5.EFPC.4 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> SG3 | 7 | 7 | 0% | 2023-04-29 08:00 | 2023-05-05 17:00 | -211 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.4 | SG3 | SG3 | 01741 | 0 | 0 | SG3-01741 | Construction | West Elevation | Construction.4.3.5.EFPC.4 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG3 | 7 | 7 | 0% | 2023-06-02 08:00 | 2023-06-08 17:00 | -225 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.4 | SG3 | SG3 | 01771 | 0 | 0 | SG3-01771 | Construction | West Elevation | Construction.4.3.5.EFPC.4 | Cure slab at Curtain Wall for flood protection (West Side) --> SG3 | 7 | 7 | 0% | 2023-07-06 08:00 | 2023-07-12 17:00 | -230 | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-SG3
Completed | CI NYCHA Update #22.Construction.4.3.5.EFPC.5 | SG3 | SG3 | 01816 | 0 | 0 | SG3-01816 | Construction | Concrete Shelf Construction | Construction.4.3.5.EFPC.5 | Cure concrete shelf around bldg perimeter --> SG3 | 7 | 0 | 100% | 2022-10-01 08:00 | 2022-10-07 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG3
Not Started | CI NYCHA Update #22.Construction.4.7.4.5 | SG1 | SG1 | 01361 | 0 | 0 | SG1-01361 | Construction | Boiler Room Construction | Construction.4.7.4.5 | Cure Concrete boiler room walls --> SG1 | 7 | 7 | 0% | 2022-12-13 08:00 | 2022-12-19 17:00 | 118 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.1 | SG1 | SG1 | 01421 | 0 | 0 | SG1-01421 | Construction | East Elevation | Construction.4.7.4.EFPC.1 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> SG1 | 7 | 0 | 100% | 2022-10-18 08:00 | 2022-10-25 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.1 | SG1 | SG1 | 01441 | 0 | 0 | SG1-01441 | Construction | East Elevation | Construction.4.7.4.EFPC.1 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG1 | 7 | 7 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | -52 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.1 | SG1 | SG1 | 01471 | 0 | 0 | SG1-01471 | Construction | East Elevation | Construction.4.7.4.EFPC.1 | Cure slab at Curtain Wall for flood protection (East Side) --> SG1 | 7 | 7 | 0% | 2023-01-06 08:00 | 2023-01-12 17:00 | -51 | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.2 | SG1 | SG1 | 01521 | 0 | 0 | SG1-01521 | Construction | South Elevation | Construction.4.7.4.EFPC.2 | Cure concrete footings at Curtain Wall for flood protection (South Side) --> SG1 | 7 | 0 | 100% | 2022-11-19 08:00 | 2022-11-24 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.2 | SG1 | SG1 | 01541 | 0 | 0 | SG1-01541 | Construction | South Elevation | Construction.4.7.4.EFPC.2 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG1 | 7 | 0 | 100% | 2022-11-18 08:00 | 2022-11-24 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.3 | SG1 | SG1 | 01621 | 0 | 0 | SG1-01621 | Construction | North Elevation | Construction.4.7.4.EFPC.3 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> SG1 | 7 | 0 | 100% | 2022-09-08 08:00 | 2022-09-14 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.3 | SG1 | SG1 | 01641 | 0 | 0 | SG1-01641 | Construction | North Elevation | Construction.4.7.4.EFPC.3 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG1 | 7 | 0 | 100% | 2022-09-17 08:00 | 2022-09-23 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.4 | SG1 | SG1 | 01721 | 0 | 0 | SG1-01721 | Construction | West Elevation | Construction.4.7.4.EFPC.4 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> SG1 | 7 | 0 | 100% | 2022-10-25 08:00 | 2022-10-31 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.4 | SG1 | SG1 | 01741 | 0 | 0 | SG1-01741 | Construction | West Elevation | Construction.4.7.4.EFPC.4 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG1 | 7 | 0 | 100% | 2022-11-18 08:00 | 2022-11-24 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.4 | SG1 | SG1 | 01771 | 0 | 0 | SG1-01771 | Construction | West Elevation | Construction.4.7.4.EFPC.4 | Cure slab at Curtain Wall for flood protection (West Side) --> SG1 | 7 | 7 | 0% | 2022-12-29 08:00 | 2023-01-04 17:00 | -43 | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-SG1
Completed | CI NYCHA Update #22.Construction.4.7.4.EFPC.5 | SG1 | SG1 | 01816 | 0 | 0 | SG1-01816 | Construction | Concrete Shelf Construction | Construction.4.7.4.EFPC.5 | Cure concrete shelf around bldg perimeter --> SG1 | 7 | 0 | 100% | 2022-09-07 | 2022-09-07 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG1
Not Started | CI NYCHA Update #22.Construction.4.2.1.5 | SG2 | SG2 | 01361 | 0 | 0 | SG2-01361 | Construction | Boiler Room Construction | Construction.4.2.1.5 | Cure Concrete boiler room walls --> SG2 | 7 | 7 | 0% | 2022-12-20 08:00 | 2022-12-26 17:00 | 111 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.1 | SG2 | SG2 | 01421 | 0 | 0 | SG2-01421 | Construction | East Elevation | Construction.4.2.1.EFPC.1 | Cure concrete footings at Curtain Wall for flood protection (East Side) --> SG2 | 7 | 7 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | -63 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.1 | SG2 | SG2 | 01441 | 0 | 0 | SG2-01441 | Construction | East Elevation | Construction.4.2.1.EFPC.1 | Cure concrete walls & shelf at Curtain Wall for flood protection (East Side) --> SG2 | 7 | 7 | 0% | 2022-12-21 08:00 | 2022-12-27 17:00 | -76 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.1 | SG2 | SG2 | 01471 | 0 | 0 | SG2-01471 | Construction | East Elevation | Construction.4.2.1.EFPC.1 | Cure slab at Curtain Wall for flood protection (East Side) --> SG2 | 7 | 7 | 0% | 2023-02-01 08:00 | 2023-02-07 17:00 | -75 | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.2 | SG2 | SG2 | 01521 | 0 | 0 | SG2-01521 | Construction | South Elevation | Construction.4.2.1.EFPC.2 | Cure concrete footings at Curtain Wall for flood protection (South Side) --> SG2 | 7 | 0 | 100% | 2022-09-07 08:00 | 2022-09-13 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.2 | SG2 | SG2 | 01541 | 0 | 0 | SG2-01541 | Construction | South Elevation | Construction.4.2.1.EFPC.2 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Side) --> SG2 | 7 | 0 | 100% | 2022-09-16 08:00 | 2022-09-22 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.3 | SG2 | SG2 | 01621 | 0 | 0 | SG2-01621 | Construction | North Elevation | Construction.4.2.1.EFPC.3 | Cure concrete footings at Curtain Wall for flood protection (North Side) --> SG2 | 7 | 0 | 100% | 2022-09-07 08:00 | 2022-09-13 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.3 | SG2 | SG2 | 01641 | 0 | 0 | SG2-01641 | Construction | North Elevation | Construction.4.2.1.EFPC.3 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Side) --> SG2 | 7 | 0 | 100% | 2022-09-16 08:00 | 2022-09-22 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.4 | SG2 | SG2 | 01721 | 0 | 0 | SG2-01721 | Construction | West Elevation | Construction.4.2.1.EFPC.4 | Cure concrete footings at Curtain Wall for flood protection (West Side) --> SG2 | 7 | 0 | 100% | 2022-10-28 08:00 | 2022-11-03 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.4 | SG2 | SG2 | 01741 | 0 | 0 | SG2-01741 | Construction | West Elevation | Construction.4.2.1.EFPC.4 | Cure concrete walls & shelf at Curtain Wall for flood protection (West Side) --> SG2 | 7 | 0 | 100% | 2022-11-04 08:00 | 2022-11-10 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.4 | SG2 | SG2 | 01771 | 0 | 0 | SG2-01771 | Construction | West Elevation | Construction.4.2.1.EFPC.4 | Cure slab at Curtain Wall for flood protection (West Side) --> SG2 | 7 | 0 | 100% | 2022-11-04 08:00 | 2022-11-10 17:00 |  | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.4.2.1.EFPC.5 | SG2 | SG2 | 01816 | 0 | 0 | SG2-01816 | Construction | Concrete Shelf Construction | Construction.4.2.1.EFPC.5 | Cure concrete shelf around bldg perimeter --> SG2 | 7 | 0 | 100% | 2022-08-24 08:00 | 2022-08-30 17:00 |  | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-SG2
Completed | CI NYCHA Update #22.Construction.8.3.4 | S8 | S8 | 01621 | 0 | 0 | S8-01621 | Construction | Retaining Walls | Construction.8.3.4 | Cure Retaining wall footing --> S8 Phase 6 | 7 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | MLJ | CONCRETE | SITE CONCRETE | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.3.4 | S8 | S8 | 01641 | 0 | 0 | S8-01641 | Construction | Retaining Walls | Construction.8.3.4 | Cure Retaining wall --> S8 Phase 6 | 7 | 0 | 100% | 2022-10-25 08:00 | 2022-10-25 17:00 |  | MLJ | CONCRETE | SITE CONCRETE | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01041 | 0 | 0 | S8A-01041 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Cure Plumbing Shafts & Ftgs Below Water Table --> S8 (Addition) | 7 | 0 | 100% | 2022-05-19 08:00 | 2022-05-25 17:00 |  | MLJ | CONCRETE | NB CONCRETE | 03-1900 | 03-1900-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01081 | 0 | 0 | S8A-01081 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Cure Remaining Ftgs/Piers/Grade Beams --> S8 (Addition) | 7 | 0 | 100% | 2022-05-27 | 2022-06-03 |  | 0 | 0 | 0 | 0 | 0-S8A
Not Started | CI NYCHA Update #22.Construction.8.2.7 | S82 | S8A | 01116 | 0 | 0 | S8A-01116 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Cure Concrete Stair South Side ---> S8 (Addition) | 7 | 7 | 0% | 2022-12-02 08:00 | 2022-12-08 17:00 | 125 | MLJ | Concrete | NB CONCRETE | 03-1900 | 03-1900-S82
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01136 | 0 | 0 | S8A-01136 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Cure First Floor Slab --> S8 (Addition) | 7 | 0 | 100% | 2022-07-16 08:00 | 2022-07-22 17:00 |  | MLJ | CONCRETE | NB CONCRETE | 03-1900 | 03-1900-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01176 | 0 | 0 | S8A-01176 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Cure 2nd Floor Slab / First Floor Walls & Col Encasements And 1st Floor Pads --> S8 (Addition) | 7 | 0 | 100% | 2022-09-28 08:00 | 2022-10-07 17:00 |  | MLJ | CONCRETE | NB CONCRETE | 03-1900 | 03-1900-S8A
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01211 | 0 | 0 | S8A-01211 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Cure Roof Slab and 2nd Floor Conc Pads -->S8 (Addition) | 7 | 0 | 100% | 2022-09-27 08:00 | 2022-10-04 17:00 |  | MLJ | CONCRETE | NB CONCRETE | 03-1900 | 03-1900-S8A
Not Started | CI NYCHA Update #22.Construction.8.1.5.5 | S81 | S8E | 01361 | 0 | 0 | S8E-01361 | Construction | Boiler Room Construction | Construction.8.1.5.5 | Cure Concrete boiler room walls --> S8 (Existing) | 7 | 7 | 0% | 2022-12-13 08:00 | 2022-12-19 17:00 | 118 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.1 | S81 | S8E | 01421 | 0 | 0 | S8E-01421 | Construction | North Wing - North Elevation | Construction.8.1.5.EFPC.1 | Cure concrete footings at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 7 | 7 | 0% | 2023-01-14 08:00 | 2023-01-20 17:00 | -106 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.1 | S81 | S8E | 01441 | 0 | 0 | S8E-01441 | Construction | North Wing - North Elevation | Construction.8.1.5.EFPC.1 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 7 | 7 | 0% | 2023-03-02 08:00 | 2023-03-08 17:00 | -134 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.1 | S81 | S8E | 01471 | 0 | 0 | S8E-01471 | Construction | North Wing - North Elevation | Construction.8.1.5.EFPC.1 | Cure slab at Curtain Wall for flood protection (North Wing - North) --> S8 (Existing) | 7 | 7 | 0% | 2023-04-26 08:00 | 2023-05-02 17:00 | -124 | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.2 | S81 | S8E | 01521 | 0 | 0 | S8E-01521 | Construction | South Wing - East Elevation | Construction.8.1.5.EFPC.2 | Cure concrete footings at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 7 | 7 | 0% | 2023-01-14 08:00 | 2023-01-20 17:00 | -107 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.2 | S81 | S8E | 01541 | 0 | 0 | S8E-01541 | Construction | South Wing - East Elevation | Construction.8.1.5.EFPC.2 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 7 | 7 | 0% | 2023-03-02 08:00 | 2023-03-08 17:00 | -135 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.2 | S81 | S8E | 01571 | 0 | 0 | S8E-01571 | Construction | South Wing - East Elevation | Construction.8.1.5.EFPC.2 | Cure slab at Curtain Wall for flood protection (South Wing - East) --> S8 (Existing) | 7 | 7 | 0% | 2023-04-26 08:00 | 2023-05-02 17:00 | -133 | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.3 | S81 | S8E | 01621 | 0 | 0 | S8E-01621 | Construction | South Wing - West Elevation | Construction.8.1.5.EFPC.3 | Cure concrete footings at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 7 | 7 | 0% | 2022-12-03 08:00 | 2022-12-09 17:00 | -17 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.3 | S81 | S8E | 01641 | 0 | 0 | S8E-01641 | Construction | South Wing - West Elevation | Construction.8.1.5.EFPC.3 | Cure concrete walls & shelf at Curtain Wall for flood protection (South Wing - West) --> S8 (Existing) | 7 | 7 | 0% | 2023-01-20 08:00 | 2023-01-26 17:00 | -46 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.4 | S81 | S8E | 01721 | 0 | 0 | S8E-01721 | Construction | North Wing - South Elevation | Construction.8.1.5.EFPC.4 | Cure concrete footings at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 7 | 7 | 0% | 2022-11-30 08:00 | 2022-12-06 17:00 | -119 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.4 | S81 | S8E | 01741 | 0 | 0 | S8E-01741 | Construction | North Wing - South Elevation | Construction.8.1.5.EFPC.4 | Cure concrete walls & shelf at Curtain Wall for flood protection (North Wing - South) --> S8 (Existing) | 7 | 7 | 0% | 2023-01-10 08:00 | 2023-01-16 17:00 | -139 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Not Started | CI NYCHA Update #22.Construction.8.1.5.EFPC.5 | S81 | S8E | 01816 | 0 | 0 | S8E-01816 | Construction | Concrete Shelf Construction | Construction.8.1.5.EFPC.5 | Cure concrete shelf around bldg perimeter --> S8 (Existing) | 7 | 7 | 0% | 2023-02-24 08:00 | 2023-03-02 17:00 | -125 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-S81
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01107 | 0 | 0 | SG6-01107 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Structural Steel Framing - 2nd Floor --> SG6 | 10 | 0 | 100% | 2021-08-11 08:00 | 2021-08-17 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01107 | 0 | 0 | OG8-01107 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Structural Steel Framing - 2nd Floor --> OG8 | 7 | 0 | 100% | 2022-01-10 | 2022-01-14 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01109 | 0 | 0 | OG8-01109 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install Structural Steel Framing - 3rd Foor --> OG8 | 7 | 0 | 100% | 2022-01-17 | 2022-01-21 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01107 | 0 | 0 | OG9-01107 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install Structural Steel Framing - 2nd Floor --> OG9 | 10 | 0 | 100% | 2021-11-14 | 2021-11-24 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01107 | 0 | 0 | OG10-01107 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Structural Steel Framing - 2nd Floor --> OG10 | 10 | 0 | 100% | 2022-01-14 | 2022-01-21 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01107 | 0 | 0 | SG7-01107 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Install Structural Steel Framing - 2nd Floor --> SG7 | 10 | 0 | 100% | 2022-08-08 08:00 | 2022-08-12 17:00 |  | WEIR | STRUCTURAL STEEL | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01107 | 0 | 0 | S8A-01107 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Install Structural Steel Framing - 2nd Floor --> S8 (Addition) | 10 | 0 | 100% | 2022-09-01 08:00 | 2022-09-09 17:00 |  | WEIR | STRUCTURAL STEEL | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG4 | PERMIT | 03015 | 0 | 0 | PERMIT-03015 | Procurement | Permits | Procurement.Div 1.Permits | File for Alt 2 Permit - SG-4 | 10 | 0 | 100% | 2020-11-01 | 2020-12-01 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG4 | PERMIT | 03020 | 0 | 0 | PERMIT-03020 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Alt 2 Permit - SG-4 | 20 | 0 | 100% | 2020-12-01 | 2020-12-16 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG5 | PERMIT | 03025 | 0 | 0 | PERMIT-03025 | Procurement | Permits | Procurement.Div 1.Permits | File for Alt 2 Permit - SG-5 | 10 | 0 | 100% | 2020-11-01 | 2020-12-01 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG5 | PERMIT | 03030 | 0 | 0 | PERMIT-03030 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Alt 2 Permit - SG-5 | 20 | 0 | 100% | 2020-12-01 | 2020-12-12 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG2 | PERMIT | 03035 | 0 | 0 | PERMIT-03035 | Procurement | Permits | Procurement.Div 1.Permits | File for Alt 2 Permit - OG-2 | 10 | 0 | 100% | 2020-11-01 | 2020-12-01 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG2 | PERMIT | 03040 | 0 | 0 | PERMIT-03040 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Alt 2 Permit - OG-2 | 20 | 0 | 100% | 2020-12-01 | 2020-12-17 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG3 | PERMIT | 03045 | 0 | 0 | PERMIT-03045 | Procurement | Permits | Procurement.Div 1.Permits | File for Alt 2 Permit - OG-3 | 10 | 0 | 100% | 2020-11-01 | 2020-12-01 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG3 | PERMIT | 03050 | 0 | 0 | PERMIT-03050 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Alt 2 Permit - OG-3 | 20 | 0 | 100% | 2020-12-01 | 2021-02-03 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG4 | PERMIT | 03055 | 0 | 0 | PERMIT-03055 | Procurement | Permits | Procurement.Div 1.Permits | File for Alt 2 Permit - OG-4 | 10 | 0 | 100% | 2020-11-01 | 2020-12-01 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG4 | PERMIT | 03060 | 0 | 0 | PERMIT-03060 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Alt 2 Permit - OG-4 | 20 | 0 | 100% | 2020-12-01 | 2020-12-17 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG8 | PERMIT | 03065 | 0 | 0 | PERMIT-03065 | Procurement | Permits | Procurement.Div 1.Permits | File for New building Permit - OG-8 | 10 | 0 | 100% | 2020-11-01 | 2020-12-01 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG8 | PERMIT | 03070 | 0 | 0 | PERMIT-03070 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue New building Permit - OG-8 | 20 | 0 | 100% | 2020-12-01 | 2021-02-03 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG9 | PERMIT | 03075 | 0 | 0 | PERMIT-03075 | Procurement | Permits | Procurement.Div 1.Permits | File for New building Permit - OG-9 | 10 | 0 | 100% | 2020-11-01 | 2020-12-01 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG9 | PERMIT | 03080 | 0 | 0 | PERMIT-03080 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue New building Permit - OG-9 | 20 | 0 | 100% | 2020-12-01 | 2021-06-21 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG1 | PERMIT | 03105 | 0 | 0 | PERMIT-03105 | Procurement | Permits | Procurement.Div 1.Permits | File for Alt 2 Permit - OG-1 | 10 | 0 | 100% | 2020-11-01 | 2020-12-01 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG1 | PERMIT | 03110 | 0 | 0 | PERMIT-03110 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Alt 2 Permit - OG-1 | 20 | 0 | 100% | 2020-12-01 | 2021-02-02 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG5 | PERMIT | 03115 | 0 | 0 | PERMIT-03115 | Procurement | Permits | Procurement.Div 1.Permits | File for Alt 2 Permit - OG-5 | 10 | 0 | 100% | 2020-11-01 | 2020-12-01 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG5 | PERMIT | 03120 | 0 | 0 | PERMIT-03120 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Alt 2 Permit - OG-5 | 20 | 0 | 100% | 2020-12-01 | 2021-05-06 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG6 | PERMIT | 03125 | 0 | 0 | PERMIT-03125 | Procurement | Permits | Procurement.Div 1.Permits | File for Alt 2 Permit - OG-6 | 10 | 0 | 100% | 2020-11-01 | 2020-12-01 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG6 | PERMIT | 03130 | 0 | 0 | PERMIT-03130 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Alt 2 Permit - OG-6 | 20 | 0 | 100% | 2020-12-01 | 2021-06-21 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG10 | PERMIT | 03135 | 0 | 0 | PERMIT-03135 | Procurement | Permits | Procurement.Div 1.Permits | File for New building Permit - OG-10 | 10 | 0 | 100% | 2020-11-01 | 2020-12-01 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG10 | PERMIT | 03140 | 0 | 0 | PERMIT-03140 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue New building Permit - OG-10 | 20 | 0 | 100% | 2020-12-01 | 2021-02-03 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG1 | PERMIT | 03205 | 0 | 0 | PERMIT-03205 | Procurement | Permits | Procurement.Div 1.Permits | File for Alt 2 Permit - SG-1 | 10 | 0 | 100% | 2020-11-01 | 2020-12-01 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG1 | PERMIT | 03210 | 0 | 0 | PERMIT-03210 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Alt 2 Permit - SG-1 | 20 | 0 | 100% | 2020-12-01 | 2020-12-17 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG2 | PERMIT | 03215 | 0 | 0 | PERMIT-03215 | Procurement | Permits | Procurement.Div 1.Permits | File for Alt 2 Permit - SG-2 | 10 | 0 | 100% | 2020-11-01 | 2020-12-01 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG2 | PERMIT | 03220 | 0 | 0 | PERMIT-03220 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Alt 2 Permit - SG-2 | 20 | 0 | 100% | 2020-12-01 | 2020-12-14 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG3 | PERMIT | 03225 | 0 | 0 | PERMIT-03225 | Procurement | Permits | Procurement.Div 1.Permits | File for Alt 2 Permit - SG-3 | 10 | 0 | 100% | 2020-11-01 | 2020-12-01 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG3 | PERMIT | 03230 | 0 | 0 | PERMIT-03230 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Alt 2 Permit - SG-3 | 20 | 0 | 100% | 2020-12-01 | 2020-12-14 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG7 | PERMIT | 03235 | 0 | 0 | PERMIT-03235 | Procurement | Permits | Procurement.Div 1.Permits | File for New building Permit - SG-7 | 10 | 0 | 100% | 2020-11-01 | 2020-12-01 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG7 | PERMIT | 03240 | 0 | 0 | PERMIT-03240 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue New building Permit - SG-7 | 20 | 0 | 100% | 2020-12-01 | 2020-12-17 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | S81 | PERMIT | 03305 | 0 | 0 | PERMIT-03305 | Procurement | Permits | Procurement.Div 1.Permits | File for Alt 2 Permit - S8E | 10 | 0 | 100% | 2020-11-01 | 2020-12-01 |  | 0 | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | S81 | PERMIT | 03310 | 0 | 0 | PERMIT-03310 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Alt 2 Permit - S8E | 20 | 0 | 100% | 2020-12-01 | 2021-06-21 |  | 0 | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | S82 | PERMIT | 03315 | 0 | 0 | PERMIT-03315 | Procurement | Permits | Procurement.Div 1.Permits | File for Alt 1 Permit - S8A | 10 | 0 | 100% | 2020-11-01 | 2020-12-15 |  | 0 | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | S82 | PERMIT | 03320 | 0 | 0 | PERMIT-03320 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Alt 1 Permit - S8a | 20 | 0 | 100% | 2020-12-15 | 2021-05-06 17:00 |  | 0 | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Construction.2.4.7.6 | SG6 | SG6 | 02522 | 0 | 0 | SG6-02522 | Construction | Testing & Start-Up | Construction.2.4.7.6 | Notifcation to 3rd Party for Testing at SG6 | 3 | 0 | 100% | 2022-08-01 15:00 | 2022-08-23 15:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.2.6.4 | SG4 | SG4 | 02512 | 0 | 0 | SG4-02512 | Construction | Testing & Start-Up | Construction.2.2.6.4 | Notifcation to 3rd Party for Testing at SG4 | 3 | 0 | 100% | 2022-06-01 08:00 | 2022-06-01 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.2.3.6.4 | SG5 | SG5 | 02512 | 0 | 0 | SG5-02512 | Construction | Testing & Start-Up | Construction.2.3.6.4 | Notifcation to 3rd Party for Testing at SG5 | 3 | 3 | 0% | 2023-01-13 08:00 | 2023-01-18 17:00 | -38 | UNSURE | STARTUP | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.3.1.6 | OG8 | OG8 | 02707 | 0 | 0 | OG8-02707 | Construction | Testing & Start-Up | Construction.3.1.6 | Notifcation to 3rd Party for Testing at OG8 | 3 | 3 | 0% | 2023-04-05 08:00 | 2023-04-07 17:00 | -80 | UNSURE | STARTUP | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.6.8.4 | OG4 | OG4 | 02507 | 0 | 0 | OG4-02507 | Construction | Testing & Start-Up | Construction.3.6.8.4 | Notifcation to 3rd Party for Testing at OG4 | 3 | 3 | 0% | 2023-03-02 08:00 | 2023-03-06 17:00 | -59 | UNSURE | STARTUP | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Construction.3.3.8.4 | OG5 | OG5 | 02507 | 0 | 0 | OG5-02507 | Construction | Testing & Start-Up | Construction.3.3.8.4 | Notifcation to 3rd Party for Testing at OG5 | 3 | 0 | 100% | 2022-09-10 | 2022-09-10 |  | 0 | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.5.4.6 | OG9 | OG9 | 02507 | 0 | 0 | OG9-02507 | Construction | Testing & Start-Up | Construction.5.4.6 | Notifcation to 3rd Party for Testing at OG9 | 3 | 3 | 0% | 2023-01-20 08:00 | 2023-01-24 17:00 | -36 | UNSURE | STARTUP | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.3.8.4 | OG3 | OG3 | 02507 | 0 | 0 | OG3-02507 | Construction | Testing & Start-Up | Construction.5.3.8.4 | Notifcation to 3rd Party for Testing at OG3 | 3 | 3 | 0% | 2023-01-25 08:00 | 2023-01-27 17:00 | -15 | UNSURE | STARTUP | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.5.2.8.4 | OG2 | OG2 | 02507 | 0 | 0 | OG2-02507 | Construction | Testing & Start-Up | Construction.5.2.8.4 | Notifcation to 3rd Party for Testing at OG2 | 3 | 3 | 0% | 2023-01-27 08:00 | 2023-01-31 17:00 | -49 | UNSURE | STARTUP | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.1.4.6 | OG10 | OG10 | 02507 | 0 | 0 | OG10-02507 | Construction | Testing & Start-Up | Construction.1.4.6 | Notifcation to 3rd Party for Testing at OG10 | 3 | 3 | 0% | 2023-04-13 08:00 | 2023-04-17 17:00 | -47 | UNSURE | STARTUP | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.2.5.4 | OG6 | OG6 | 02507 | 0 | 0 | OG6-02507 | Construction | Testing & Start-Up | Construction.1.2.5.4 | Notifcation to 3rd Party for Testing at OG6 | 3 | 3 | 0% | 2023-05-05 08:00 | 2023-05-09 17:00 | -72 | UNSURE | STARTUP | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.1.3.5.4 | OG1 | OG1 | 02507 | 0 | 0 | OG1-02507 | Construction | Testing & Start-Up | Construction.1.3.5.4 | Notifcation to 3rd Party for Testing at OG1 | 3 | 3 | 0% | 2023-01-20 08:00 | 2023-01-24 17:00 | 19 | UNSURE | STARTUP | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.4.4.5.6 | SG7 | SG7 | 02607 | 0 | 0 | SG7-02607 | Construction | Testing & Start-Up | Construction.4.4.5.6 | Notifcation to 3rd Party for Testing at SG7 | 3 | 3 | 0% | 2023-08-28 08:00 | 2023-08-30 17:00 | -130 | UNSURE | STARTUP | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.3.8.4 | SG3 | SG3 | 02507 | 0 | 0 | SG3-02507 | Construction | Testing & Start-Up | Construction.4.3.8.4 | Notifcation to 3rd Party for Testing at SG3 | 3 | 3 | 0% | 2023-08-25 08:00 | 2023-08-29 17:00 | -134 | UNSURE | STARTUP | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.8.2.5.6 | S82 | S8A | 02517 | 0 | 0 | S8A-02517 | Construction | Testing & Start-Up | Construction.8.2.5.6 | Notifcation to 3rd Party for Testing at S8A | 3 | 3 | 0% | 2023-06-20 08:00 | 2023-06-22 17:00 | -82 | UNSURE | STARTUP | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.7.1.1.1 | SG6 | ABLT | SG6 | 01005 | 0 | ABLT-SG6-01005 | Construction | Building SG-6 | Construction.7.1.1.1 | Prep/Submit Architectural/Civil As-Built Drawings - SG6 | 15 | 15 | 0% | 2022-11-25 08:00 | 2022-12-15 17:00 | 102 | UNSURE | AS-BUILT | ENG | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.7.1.1.1 | SG6 | ABLT | SG6 | 01010 | 0 | ABLT-SG6-01010 | Construction | Building SG-6 | Construction.7.1.1.1 | Review/Approve Architectural/Civil As-Built Drawings - SG6 | 10 | 10 | 0% | 2022-12-16 08:00 | 2022-12-30 17:00 | 102 | UNSURE | AS-BUILT | ENG | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.7.1.1.1 | SG6 | ABLT | SG6 | 01015 | 0 | ABLT-SG6-01015 | Construction | Building SG-6 | Construction.7.1.1.1 | Prep/Submit Electrical As-Built Drawings - SG6 | 15 | 15 | 0% | 2023-06-19 08:00 | 2023-07-10 17:00 | -49 | FSE | 0 | ENG | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.7.1.1.1 | SG6 | ABLT | SG6 | 01020 | 0 | ABLT-SG6-01020 | Construction | Building SG-6 | Construction.7.1.1.1 | Review/Approve Electrical As-Built Drawings - SG6 | 10 | 10 | 0% | 2023-07-11 08:00 | 2023-07-24 17:00 | -49 | FSE | 0 | ENG | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.7.1.1.1 | SG6 | ABLT | SG6 | 01025 | 0 | ABLT-SG6-01025 | Construction | Building SG-6 | Construction.7.1.1.1 | Prep/Submit Mechanical As-Built Drawings - SG6 | 15 | 15 | 0% | 2023-01-17 08:00 | 2023-02-06 17:00 | 58 | UNSURE | AS-BUILT | ENG | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.7.1.1.1 | SG6 | ABLT | SG6 | 01030 | 0 | ABLT-SG6-01030 | Construction | Building SG-6 | Construction.7.1.1.1 | Review/Approve Mechanical As-Built Drawings - SG6 | 10 | 10 | 0% | 2023-02-07 08:00 | 2023-02-21 17:00 | 58 | UNSURE | AS-BUILT | ENG | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.7.1.1.2 | SGN | ABLT | SGN | 01005 | 0 | ABLT-SGN-01005 | Construction | Site Utility Work | Construction.7.1.1.2 | Prep/Submit Site Utility As-Built Drawings - Surfside Gardens North | 15 | 15 | 0% | 2022-11-25 08:00 | 2022-12-15 17:00 | 102 | UNSURE | AS-BUILT | ENG | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.7.1.1.2 | SGN | ABLT | SGN | 01010 | 0 | ABLT-SGN-01010 | Construction | Site Utility Work | Construction.7.1.1.2 | Review/Approve Site Utility As-Built Drawings - Surfside Gardens North | 10 | 10 | 0% | 2022-12-16 08:00 | 2022-12-30 17:00 | 102 | UNSURE | AS-BUILT | ENG | 0 | 0-SGN
Not Started | CI NYCHA Update #22.Construction.7.1.1.3 | SG4 | ABLT | SG4 | 01005 | 0 | ABLT-SG4-01005 | Construction | Building SG-4 | Construction.7.1.1.3 | Prep/Submit Architectural/Civil As-Built Drawings - SG4 | 15 | 15 | 0% | 2023-06-21 08:00 | 2023-07-12 17:00 | -41 | UNSURE | AS-BUILT | ENG | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.7.1.1.3 | SG4 | ABLT | SG4 | 01010 | 0 | ABLT-SG4-01010 | Construction | Building SG-4 | Construction.7.1.1.3 | Review/Approve Architectural/Civil As-Built Drawings - SG4 | 10 | 10 | 0% | 2023-07-13 08:00 | 2023-07-26 17:00 | -41 | UNSURE | AS-BUILT | ENG | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.7.1.1.3 | SG4 | ABLT | SG4 | 01015 | 0 | ABLT-SG4-01015 | Construction | Building SG-4 | Construction.7.1.1.3 | Prep/Submit Electrical As-Built Drawings - SG4 | 15 | 15 | 0% | 2023-03-21 08:00 | 2023-04-10 17:00 | 14 | FSE | 0 | ENG | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.7.1.1.3 | SG4 | ABLT | SG4 | 01020 | 0 | ABLT-SG4-01020 | Construction | Building SG-4 | Construction.7.1.1.3 | Review/Approve Electrical As-Built Drawings - SG4 | 10 | 10 | 0% | 2023-04-11 08:00 | 2023-04-24 17:00 | 14 | FSE | 0 | ENG | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.7.1.1.3 | SG4 | ABLT | SG4 | 01025 | 0 | ABLT-SG4-01025 | Construction | Building SG-4 | Construction.7.1.1.3 | Prep/Submit Mechanical As-Built Drawings - SG4 | 15 | 15 | 0% | 2023-04-12 15:00 | 2023-05-03 15:00 | -3 | UNSURE | AS-BUILT | ENG | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.7.1.1.3 | SG4 | ABLT | SG4 | 01030 | 0 | ABLT-SG4-01030 | Construction | Building SG-4 | Construction.7.1.1.3 | Review/Approve Mechanical As-Built Drawings - SG4 | 10 | 10 | 0% | 2023-05-03 15:00 | 2023-05-17 15:00 | -3 | UNSURE | AS-BUILT | ENG | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.7.1.1.4 | SG5 | ABLT | SG5 | 01005 | 0 | ABLT-SG5-01005 | Construction | Building SG-5 | Construction.7.1.1.4 | Prep/Submit Architectural/Civil As-Built Drawings - SG5 | 15 | 15 | 0% | 2023-01-30 08:00 | 2023-02-17 17:00 | 59 | UNSURE | AS-BUILT | ENG | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.7.1.1.4 | SG5 | ABLT | SG5 | 01010 | 0 | ABLT-SG5-01010 | Construction | Building SG-5 | Construction.7.1.1.4 | Review/Approve Architectural/Civil As-Built Drawings - SG5 | 10 | 10 | 0% | 2023-02-21 08:00 | 2023-03-06 17:00 | 59 | UNSURE | AS-BUILT | ENG | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.7.1.1.4 | SG5 | ABLT | SG5 | 01015 | 0 | ABLT-SG5-01015 | Construction | Building SG-5 | Construction.7.1.1.4 | Prep/Submit Electrical As-Built Drawings - SG5 | 15 | 15 | 0% | 2023-03-21 08:00 | 2023-04-10 17:00 | 14 | FSE | 0 | ENG | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.7.1.1.4 | SG5 | ABLT | SG5 | 01020 | 0 | ABLT-SG5-01020 | Construction | Building SG-5 | Construction.7.1.1.4 | Review/Approve Electrical As-Built Drawings - SG5 | 10 | 10 | 0% | 2023-04-11 08:00 | 2023-04-24 17:00 | 14 | FSE | 0 | ENG | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.7.1.1.4 | SG5 | ABLT | SG5 | 01025 | 0 | ABLT-SG5-01025 | Construction | Building SG-5 | Construction.7.1.1.4 | Prep/Submit Mechanical As-Built Drawings - SG5 | 15 | 15 | 0% | 2023-03-01 08:00 | 2023-03-21 17:00 | 28 | UNSURE | AS-BUILT | ENG | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.7.1.1.4 | SG5 | ABLT | SG5 | 01030 | 0 | ABLT-SG5-01030 | Construction | Building SG-5 | Construction.7.1.1.4 | Review/Approve Mechanical As-Built Drawings - SG5 | 10 | 10 | 0% | 2023-03-22 08:00 | 2023-04-04 17:00 | 28 | UNSURE | AS-BUILT | ENG | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.7.1.5.2 | OGP1 | ABLT | OGP1 | 01005 | 0 | ABLT-OGP1-01005 | Construction | Site Utility Work | Construction.7.1.5.2 | Prep/Submit Site Utility As-Built Drawings - O'Dwyer Gardens Part 1 | 15 | 15 | 0% | 2023-11-01 08:00 | 2023-11-24 17:00 | -133 | UNSURE | AS-BUILT | ENG | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.7.1.5.2 | OGP1 | ABLT | OGP1 | 01010 | 0 | ABLT-OGP1-01010 | Construction | Site Utility Work | Construction.7.1.5.2 | Review/Approve Site Utility As-Built Drawings - O'Dwyer Gardens Part 1 | 10 | 10 | 0% | 2023-11-27 08:00 | 2023-12-08 17:00 | -133 | UNSURE | AS-BUILT | ENG | 0 | 0-OGP1
Not Started | CI NYCHA Update #22.Construction.7.1.5.1 | OG8 | ABLT | OG8 | 01005 | 0 | ABLT-OG8-01005 | Construction | Building OG-8 | Construction.7.1.5.1 | Prep/Submit Architectural/Civil As-Built Drawings - OG8 | 15 | 15 | 0% | 2023-04-11 08:00 | 2023-05-01 17:00 | 9 | UNSURE | AS-BUILT | ENG | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.7.1.5.1 | OG8 | ABLT | OG8 | 01010 | 0 | ABLT-OG8-01010 | Construction | Building OG-8 | Construction.7.1.5.1 | Review/Approve Architectural/Civil As-Built Drawings - OG8 | 10 | 10 | 0% | 2023-05-02 08:00 | 2023-05-15 17:00 | 9 | UNSURE | AS-BUILT | ENG | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.7.1.5.1 | OG8 | ABLT | OG8 | 01015 | 0 | ABLT-OG8-01015 | Construction | Building OG-8 | Construction.7.1.5.1 | Prep/Submit Electrical As-Built Drawings - OG8 | 15 | 15 | 0% | 2023-04-12 08:00 | 2023-05-02 17:00 | -2 | FSE | 0 | ENG | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.7.1.5.1 | OG8 | ABLT | OG8 | 01020 | 0 | ABLT-OG8-01020 | Construction | Building OG-8 | Construction.7.1.5.1 | Review/Approve Electrical As-Built Drawings - OG8 | 10 | 10 | 0% | 2023-05-03 08:00 | 2023-05-16 17:00 | -2 | FSE | 0 | ENG | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.7.1.5.1 | OG8 | ABLT | OG8 | 01025 | 0 | ABLT-OG8-01025 | Construction | Building OG-8 | Construction.7.1.5.1 | Prep/Submit Mechanical As-Built Drawings - OG8 | 15 | 15 | 0% | 2023-04-10 08:00 | 2023-04-28 17:00 | 0 | UNSURE | AS-BUILT | ENG | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.7.1.5.1 | OG8 | ABLT | OG8 | 01030 | 0 | ABLT-OG8-01030 | Construction | Building OG-8 | Construction.7.1.5.1 | Review/Approve Mechanical As-Built Drawings - OG8 | 10 | 10 | 0% | 2023-05-01 08:00 | 2023-05-12 17:00 | 0 | UNSURE | AS-BUILT | ENG | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.7.1.5.3 | OG4 | ABLT | OG4 | 01005 | 0 | ABLT-OG4-01005 | Construction | Building OG-4 | Construction.7.1.5.3 | Prep/Submit Architectural/Civil As-Built Drawings - OG4 | 15 | 15 | 0% | 2023-08-28 08:00 | 2023-09-18 17:00 | -88 | UNSURE | AS-BUILT | ENG | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.7.1.5.3 | OG4 | ABLT | OG4 | 01010 | 0 | ABLT-OG4-01010 | Construction | Building OG-4 | Construction.7.1.5.3 | Review/Approve Architectural/Civil As-Built Drawings - OG4 | 10 | 10 | 0% | 2023-09-19 08:00 | 2023-10-02 17:00 | -88 | UNSURE | AS-BUILT | ENG | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.7.1.5.3 | OG4 | ABLT | OG4 | 01015 | 0 | ABLT-OG4-01015 | Construction | Building OG-4 | Construction.7.1.5.3 | Prep/Submit Electrical As-Built Drawings - OG4 | 15 | 15 | 0% | 2023-03-21 08:00 | 2023-04-10 17:00 | 14 | FSE | 0 | ENG | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.7.1.5.3 | OG4 | ABLT | OG4 | 01020 | 0 | ABLT-OG4-01020 | Construction | Building OG-4 | Construction.7.1.5.3 | Review/Approve Electrical As-Built Drawings - OG4 | 10 | 10 | 0% | 2023-04-11 08:00 | 2023-04-24 17:00 | 14 | FSE | 0 | ENG | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.7.1.5.3 | OG4 | ABLT | OG4 | 01025 | 0 | ABLT-OG4-01025 | Construction | Building OG-4 | Construction.7.1.5.3 | Prep/Submit Mechanical As-Built Drawings - OG4 | 15 | 15 | 0% | 2023-04-05 08:00 | 2023-04-25 17:00 | 3 | UNSURE | AS-BUILT | ENG | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.7.1.5.3 | OG4 | ABLT | OG4 | 01030 | 0 | ABLT-OG4-01030 | Construction | Building OG-4 | Construction.7.1.5.3 | Review/Approve Mechanical As-Built Drawings - OG4 | 10 | 10 | 0% | 2023-04-26 08:00 | 2023-05-09 17:00 | 3 | UNSURE | AS-BUILT | ENG | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.7.1.5.4 | OG5 | ABLT | OG5 | 01005 | 0 | ABLT-OG5-01005 | Construction | Building OG-5 | Construction.7.1.5.4 | Prep/Submit Architectural/Civil As-Built Drawings - OG5 | 15 | 15 | 0% | 2023-12-22 08:00 | 2024-01-15 17:00 | -167 | UNSURE | AS-BUILT | ENG | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.7.1.5.4 | OG5 | ABLT | OG5 | 01010 | 0 | ABLT-OG5-01010 | Construction | Building OG-5 | Construction.7.1.5.4 | Review/Approve Architectural/Civil As-Built Drawings - OG5 | 10 | 10 | 0% | 2024-01-16 08:00 | 2024-01-29 17:00 | -167 | UNSURE | AS-BUILT | ENG | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.7.1.5.4 | OG5 | ABLT | OG5 | 01015 | 0 | ABLT-OG5-01015 | Construction | Building OG-5 | Construction.7.1.5.4 | Prep/Submit Electrical As-Built Drawings - OG5 | 15 | 15 | 0% | 2023-03-21 08:00 | 2023-04-10 17:00 | 14 | FSE | 0 | ENG | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.7.1.5.4 | OG5 | ABLT | OG5 | 01020 | 0 | ABLT-OG5-01020 | Construction | Building OG-5 | Construction.7.1.5.4 | Review/Approve Electrical As-Built Drawings - OG5 | 10 | 10 | 0% | 2023-04-11 08:00 | 2023-04-24 17:00 | 14 | FSE | 0 | ENG | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.7.1.5.4 | OG5 | ABLT | OG5 | 01025 | 0 | ABLT-OG5-01025 | Construction | Building OG-5 | Construction.7.1.5.4 | Prep/Submit Mechanical As-Built Drawings - OG5 | 15 | 15 | 0% | 2023-10-02 08:00 | 2023-10-23 17:00 | -122 | UNSURE | AS-BUILT | ENG | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.7.1.5.4 | OG5 | ABLT | OG5 | 01030 | 0 | ABLT-OG5-01030 | Construction | Building OG-5 | Construction.7.1.5.4 | Review/Approve Mechanical As-Built Drawings - OG5 | 10 | 10 | 0% | 2023-10-24 08:00 | 2023-11-06 17:00 | -122 | UNSURE | AS-BUILT | ENG | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.7.1.2.2 | OGW | ABLT | OGW | 01005 | 0 | ABLT-OGW-01005 | Construction | Site Utility Work | Construction.7.1.2.2 | Prep/Submit Site Utility As-Built Drawings - O'Dwyer Gardens West | 15 | 15 | 0% | 2023-04-24 08:00 | 2023-05-12 17:00 | 0 | UNSURE | AS-BUILT | ENG | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.7.1.2.2 | OGW | ABLT | OGW | 01010 | 0 | ABLT-OGW-01010 | Construction | Site Utility Work | Construction.7.1.2.2 | Review/Approve Site Utility As-Built Drawings - O'Dwyer Gardens West | 10 | 10 | 0% | 2023-05-15 08:00 | 2023-05-26 17:00 | 0 | UNSURE | AS-BUILT | ENG | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.7.1.2.1 | OG9 | ABLT | OG9 | 01005 | 0 | ABLT-OG9-01005 | Construction | Building OG-9 | Construction.7.1.2.1 | Prep/Submit Architectural/Civil As-Built Drawings - OG9 | 15 | 15 | 0% | 2022-12-02 08:00 | 2022-12-22 17:00 | 97 | UNSURE | AS-BUILT | ENG | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.7.1.2.1 | OG9 | ABLT | OG9 | 01010 | 0 | ABLT-OG9-01010 | Construction | Building OG-9 | Construction.7.1.2.1 | Review/Approve Architectural/Civil As-Built Drawings - OG9 | 10 | 10 | 0% | 2022-12-23 08:00 | 2023-01-09 17:00 | 97 | UNSURE | AS-BUILT | ENG | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.7.1.2.1 | OG9 | ABLT | OG9 | 01015 | 0 | ABLT-OG9-01015 | Construction | Building OG-9 | Construction.7.1.2.1 | Prep/Submit Electrical As-Built Drawings - OG9 | 15 | 15 | 0% | 2023-03-21 08:00 | 2023-04-10 17:00 | 14 | FSE | 0 | ENG | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.7.1.2.1 | OG9 | ABLT | OG9 | 01020 | 0 | ABLT-OG9-01020 | Construction | Building OG-9 | Construction.7.1.2.1 | Review/Approve Electrical As-Built Drawings - OG9 | 10 | 10 | 0% | 2023-04-11 08:00 | 2023-04-24 17:00 | 14 | FSE | 0 | ENG | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.7.1.2.1 | OG9 | ABLT | OG9 | 01025 | 0 | ABLT-OG9-01025 | Construction | Building OG-9 | Construction.7.1.2.1 | Prep/Submit Mechanical As-Built Drawings - OG9 | 15 | 15 | 0% | 2023-02-14 08:00 | 2023-03-07 17:00 | 38 | UNSURE | AS-BUILT | ENG | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.7.1.2.1 | OG9 | ABLT | OG9 | 01030 | 0 | ABLT-OG9-01030 | Construction | Building OG-9 | Construction.7.1.2.1 | Review/Approve Mechanical As-Built Drawings - OG9 | 10 | 10 | 0% | 2023-03-08 08:00 | 2023-03-21 17:00 | 38 | UNSURE | AS-BUILT | ENG | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.7.1.2.3 | OG2 | ABLT | OG2 | 01005 | 0 | ABLT-OG2-01005 | Construction | Building OG-2 | Construction.7.1.2.3 | Prep/Submit Architectural/Civil As-Built Drawings - OG2 | 15 | 15 | 0% | 2023-07-17 08:00 | 2023-08-04 17:00 | -58 | UNSURE | AS-BUILT | ENG | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.7.1.2.3 | OG2 | ABLT | OG2 | 01010 | 0 | ABLT-OG2-01010 | Construction | Building OG-2 | Construction.7.1.2.3 | Review/Approve Architectural/Civil As-Built Drawings - OG2 | 10 | 10 | 0% | 2023-08-07 08:00 | 2023-08-18 17:00 | -58 | UNSURE | AS-BUILT | ENG | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.7.1.2.3 | OG2 | ABLT | OG2 | 01015 | 0 | ABLT-OG2-01015 | Construction | Building OG-2 | Construction.7.1.2.3 | Prep/Submit Electrical As-Built Drawings - OG2 | 15 | 15 | 0% | 2023-03-21 08:00 | 2023-04-10 17:00 | 14 | FSE | 0 | ENG | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.7.1.2.3 | OG2 | ABLT | OG2 | 01020 | 0 | ABLT-OG2-01020 | Construction | Building OG-2 | Construction.7.1.2.3 | Review/Approve Electrical As-Built Drawings - OG2 | 10 | 10 | 0% | 2023-04-11 08:00 | 2023-04-24 17:00 | 14 | FSE | 0 | ENG | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.7.1.2.3 | OG2 | ABLT | OG2 | 01025 | 0 | ABLT-OG2-01025 | Construction | Building OG-2 | Construction.7.1.2.3 | Prep/Submit Mechanical As-Built Drawings - OG2 | 15 | 15 | 0% | 2023-03-22 08:00 | 2023-04-11 17:00 | 13 | UNSURE | AS-BUILT | ENG | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.7.1.2.3 | OG2 | ABLT | OG2 | 01030 | 0 | ABLT-OG2-01030 | Construction | Building OG-2 | Construction.7.1.2.3 | Review/Approve Mechanical As-Built Drawings - OG2 | 10 | 10 | 0% | 2023-04-12 08:00 | 2023-04-25 17:00 | 13 | UNSURE | AS-BUILT | ENG | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.7.1.2.4 | OG3 | ABLT | OG3 | 01005 | 0 | ABLT-OG3-01005 | Construction | Building OG-3 | Construction.7.1.2.4 | Prep/Submit Architectural/Civil As-Built Drawings - OG3 | 15 | 15 | 0% | 2024-01-02 08:00 | 2024-01-22 17:00 | -172 | UNSURE | AS-BUILT | ENG | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.7.1.2.4 | OG3 | ABLT | OG3 | 01010 | 0 | ABLT-OG3-01010 | Construction | Building OG-3 | Construction.7.1.2.4 | Review/Approve Architectural/Civil As-Built Drawings - OG3 | 10 | 10 | 0% | 2024-01-23 08:00 | 2024-02-05 17:00 | -172 | UNSURE | AS-BUILT | ENG | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.7.1.2.4 | OG3 | ABLT | OG3 | 01015 | 0 | ABLT-OG3-01015 | Construction | Building OG-3 | Construction.7.1.2.4 | Prep/Submit Electrical As-Built Drawings - OG3 | 15 | 15 | 0% | 2023-03-21 08:00 | 2023-04-10 17:00 | 14 | FSE | 0 | ENG | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.7.1.2.4 | OG3 | ABLT | OG3 | 01020 | 0 | ABLT-OG3-01020 | Construction | Building OG-3 | Construction.7.1.2.4 | Review/Approve Electrical As-Built Drawings - OG3 | 10 | 10 | 0% | 2023-04-11 08:00 | 2023-04-24 17:00 | 14 | FSE | 0 | ENG | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.7.1.2.4 | OG3 | ABLT | OG3 | 01025 | 0 | ABLT-OG3-01025 | Construction | Building OG-3 | Construction.7.1.2.4 | Prep/Submit Mechanical As-Built Drawings - OG3 | 15 | 15 | 0% | 2023-04-05 08:00 | 2023-04-25 17:00 | 3 | UNSURE | AS-BUILT | ENG | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.7.1.2.4 | OG3 | ABLT | OG3 | 01030 | 0 | ABLT-OG3-01030 | Construction | Building OG-3 | Construction.7.1.2.4 | Review/Approve Mechanical As-Built Drawings - OG3 | 10 | 10 | 0% | 2023-04-26 08:00 | 2023-05-09 17:00 | 3 | UNSURE | AS-BUILT | ENG | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.7.1.3.1 | OG10 | ABLT | OG10 | 01005 | 0 | ABLT-OG10-01005 | Construction | Building OG-10 | Construction.7.1.3.1 | Prep/Submit Architectural/Civil As-Built Drawings - OG10 | 15 | 15 | 0% | 2022-12-01 08:00 | 2022-12-21 17:00 | 98 | UNSURE | AS-BUILT | ENG | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.7.1.3.1 | OG10 | ABLT | OG10 | 01010 | 0 | ABLT-OG10-01010 | Construction | Building OG-10 | Construction.7.1.3.1 | Review/Approve Architectural/Civil As-Built Drawings - OG10 | 10 | 10 | 0% | 2022-12-22 08:00 | 2023-01-06 17:00 | 98 | UNSURE | AS-BUILT | ENG | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.7.1.3.1 | OG10 | ABLT | OG10 | 01015 | 0 | ABLT-OG10-01015 | Construction | Building OG-10 | Construction.7.1.3.1 | Prep/Submit Electrical As-Built Drawings - OG10 | 15 | 15 | 0% | 2023-04-20 08:00 | 2023-05-10 17:00 | -8 | FSE | 0 | ENG | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.7.1.3.1 | OG10 | ABLT | OG10 | 01020 | 0 | ABLT-OG10-01020 | Construction | Building OG-10 | Construction.7.1.3.1 | Review/Approve Electrical As-Built Drawings - OG10 | 10 | 10 | 0% | 2023-05-11 08:00 | 2023-05-24 17:00 | -8 | FSE | 0 | ENG | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.7.1.3.1 | OG10 | ABLT | OG10 | 01025 | 0 | ABLT-OG10-01025 | Construction | Building OG-10 | Construction.7.1.3.1 | Prep/Submit Mechanical As-Built Drawings - OG10 | 15 | 15 | 0% | 2023-02-22 08:00 | 2023-03-14 17:00 | 33 | UNSURE | AS-BUILT | ENG | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.7.1.3.1 | OG10 | ABLT | OG10 | 01030 | 0 | ABLT-OG10-01030 | Construction | Building OG-10 | Construction.7.1.3.1 | Review/Approve Mechanical As-Built Drawings - OG10 | 10 | 10 | 0% | 2023-03-15 08:00 | 2023-03-28 17:00 | 33 | UNSURE | AS-BUILT | ENG | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.7.1.3.2 | OG1 | ABLT | OG1 | 01005 | 0 | ABLT-OG1-01005 | Construction | Building OG-1 | Construction.7.1.3.2 | Prep/Submit Architectural/Civil As-Built Drawings - OG1 | 15 | 15 | 0% | 2024-01-09 08:00 | 2024-01-29 17:00 | -177 | UNSURE | AS-BUILT | ENG | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.7.1.3.2 | OG1 | ABLT | OG1 | 01010 | 0 | ABLT-OG1-01010 | Construction | Building OG-1 | Construction.7.1.3.2 | Review/Approve Architectural/Civil As-Built Drawings - OG1 | 10 | 10 | 0% | 2024-01-30 08:00 | 2024-02-12 17:00 | -177 | UNSURE | AS-BUILT | ENG | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.7.1.3.2 | OG1 | ABLT | OG1 | 01015 | 0 | ABLT-OG1-01015 | Construction | Building OG-1 | Construction.7.1.3.2 | Prep/Submit Electrical As-Built Drawings - OG1 | 15 | 15 | 0% | 2023-03-21 08:00 | 2023-04-10 17:00 | 14 | FSE | 0 | ENG | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.7.1.3.2 | OG1 | ABLT | OG1 | 01020 | 0 | ABLT-OG1-01020 | Construction | Building OG-1 | Construction.7.1.3.2 | Review/Approve Electrical As-Built Drawings - OG1 | 10 | 10 | 0% | 2023-04-11 08:00 | 2023-04-24 17:00 | 14 | FSE | 0 | ENG | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.7.1.3.2 | OG1 | ABLT | OG1 | 01025 | 0 | ABLT-OG1-01025 | Construction | Building OG-1 | Construction.7.1.3.2 | Prep/Submit Mechanical As-Built Drawings - OG1 | 15 | 15 | 0% | 2023-03-22 08:00 | 2023-04-11 17:00 | 13 | UNSURE | AS-BUILT | ENG | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.7.1.3.2 | OG1 | ABLT | OG1 | 01030 | 0 | ABLT-OG1-01030 | Construction | Building OG-1 | Construction.7.1.3.2 | Review/Approve Mechanical As-Built Drawings - OG1 | 10 | 10 | 0% | 2023-04-12 08:00 | 2023-04-25 17:00 | 13 | UNSURE | AS-BUILT | ENG | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.7.1.3.3 | OG6 | ABLT | OG6 | 01005 | 0 | ABLT-OG6-01005 | Construction | Building OG-6 | Construction.7.1.3.3 | Prep/Submit Architectural/Civil As-Built Drawings - OG6 | 15 | 15 | 0% | 2024-01-31 08:00 | 2024-02-21 17:00 | -193 | UNSURE | AS-BUILT | ENG | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.7.1.3.3 | OG6 | ABLT | OG6 | 01010 | 0 | ABLT-OG6-01010 | Construction | Building OG-6 | Construction.7.1.3.3 | Review/Approve Architectural/Civil As-Built Drawings - OG6 | 10 | 10 | 0% | 2024-02-22 08:00 | 2024-03-06 17:00 | -193 | UNSURE | AS-BUILT | ENG | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.7.1.3.3 | OG6 | ABLT | OG6 | 01015 | 0 | ABLT-OG6-01015 | Construction | Building OG-6 | Construction.7.1.3.3 | Prep/Submit Electrical As-Built Drawings - OG6 | 15 | 15 | 0% | 2023-05-12 08:00 | 2023-06-02 17:00 | -24 | FSE | 0 | ENG | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.7.1.3.3 | OG6 | ABLT | OG6 | 01020 | 0 | ABLT-OG6-01020 | Construction | Building OG-6 | Construction.7.1.3.3 | Review/Approve Electrical As-Built Drawings - OG6 | 10 | 10 | 0% | 2023-06-05 08:00 | 2023-06-16 17:00 | -24 | FSE | 0 | ENG | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.7.1.3.3 | OG6 | ABLT | OG6 | 01025 | 0 | ABLT-OG6-01025 | Construction | Building OG-6 | Construction.7.1.3.3 | Prep/Submit Mechanical As-Built Drawings - OG6 | 15 | 15 | 0% | 2023-03-27 08:00 | 2023-04-14 17:00 | 10 | UNSURE | AS-BUILT | ENG | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.7.1.3.3 | OG6 | ABLT | OG6 | 01030 | 0 | ABLT-OG6-01030 | Construction | Building OG-6 | Construction.7.1.3.3 | Review/Approve Mechanical As-Built Drawings - OG6 | 10 | 10 | 0% | 2023-04-17 08:00 | 2023-04-28 17:00 | 10 | UNSURE | AS-BUILT | ENG | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.7.1.4.1 | SG7 | ABLT | SG7 | 01005 | 0 | ABLT-SG7-01005 | Construction | Building SG-7 | Construction.7.1.4.1 | Prep/Submit Architectural/Civil As-Built Drawings - SG7 | 15 | 15 | 0% | 2023-04-19 08:00 | 2023-05-09 17:00 | 3 | UNSURE | AS-BUILT | ENG | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.7.1.4.1 | SG7 | ABLT | SG7 | 01010 | 0 | ABLT-SG7-01010 | Construction | Building SG-7 | Construction.7.1.4.1 | Review/Approve Architectural/Civil As-Built Drawings - SG7 | 10 | 10 | 0% | 2023-05-10 08:00 | 2023-05-23 17:00 | 3 | UNSURE | AS-BUILT | ENG | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.7.1.4.1 | SG7 | ABLT | SG7 | 01015 | 0 | ABLT-SG7-01015 | Construction | Building SG-7 | Construction.7.1.4.1 | Prep/Submit Electrical As-Built Drawings - SG7 | 15 | 15 | 0% | 2023-09-05 08:00 | 2023-09-25 17:00 | -103 | FSE | 0 | ENG | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.7.1.4.1 | SG7 | ABLT | SG7 | 01020 | 0 | ABLT-SG7-01020 | Construction | Building SG-7 | Construction.7.1.4.1 | Review/Approve Electrical As-Built Drawings - SG7 | 10 | 10 | 0% | 2023-09-26 08:00 | 2023-10-09 17:00 | -103 | FSE | 0 | ENG | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.7.1.4.1 | SG7 | ABLT | SG7 | 01025 | 0 | ABLT-SG7-01025 | Construction | Building SG-7 | Construction.7.1.4.1 | Prep/Submit Mechanical As-Built Drawings - SG7 | 15 | 15 | 0% | 2023-05-24 08:00 | 2023-06-14 17:00 | -32 | UNSURE | AS-BUILT | ENG | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.7.1.4.1 | SG7 | ABLT | SG7 | 01030 | 0 | ABLT-SG7-01030 | Construction | Building SG-7 | Construction.7.1.4.1 | Review/Approve Mechanical As-Built Drawings - SG7 | 10 | 10 | 0% | 2023-06-15 08:00 | 2023-06-28 17:00 | -32 | UNSURE | AS-BUILT | ENG | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.7.1.4.2 | SG1 | ABLT | SG1 | 01005 | 0 | ABLT-SG1-01005 | Construction | Building SG-1 | Construction.7.1.4.2 | Prep/Submit Architectural/Civil As-Built Drawings - SG1 | 15 | 15 | 0% | 2023-10-31 08:00 | 2023-11-22 17:00 | -132 | UNSURE | AS-BUILT | ENG | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.7.1.4.2 | SG1 | ABLT | SG1 | 01010 | 0 | ABLT-SG1-01010 | Construction | Building SG-1 | Construction.7.1.4.2 | Review/Approve Architectural/Civil As-Built Drawings - SG1 | 10 | 10 | 0% | 2023-11-24 08:00 | 2023-12-07 17:00 | -132 | UNSURE | AS-BUILT | ENG | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.7.1.4.2 | SG1 | ABLT | SG1 | 01015 | 0 | ABLT-SG1-01015 | Construction | Building SG-1 | Construction.7.1.4.2 | Prep/Submit Electrical As-Built Drawings - SG1 | 15 | 15 | 0% | 2023-03-16 08:00 | 2023-04-05 17:00 | 17 | FSE | 0 | ENG | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.7.1.4.2 | SG1 | ABLT | SG1 | 01020 | 0 | ABLT-SG1-01020 | Construction | Building SG-1 | Construction.7.1.4.2 | Review/Approve Electrical As-Built Drawings - SG1 | 10 | 10 | 0% | 2023-04-06 08:00 | 2023-04-19 17:00 | 17 | FSE | 0 | ENG | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.7.1.4.2 | SG1 | ABLT | SG1 | 01025 | 0 | ABLT-SG1-01025 | Construction | Building SG-1 | Construction.7.1.4.2 | Prep/Submit Mechanical As-Built Drawings - SG1 | 15 | 15 | 0% | 2023-06-22 08:00 | 2023-07-13 17:00 | -52 | UNSURE | AS-BUILT | ENG | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.7.1.4.2 | SG1 | ABLT | SG1 | 01030 | 0 | ABLT-SG1-01030 | Construction | Building SG-1 | Construction.7.1.4.2 | Review/Approve Mechanical As-Built Drawings - SG1 | 10 | 10 | 0% | 2023-07-14 08:00 | 2023-07-27 17:00 | -52 | UNSURE | AS-BUILT | ENG | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.7.1.4.3 | SG2 | ABLT | SG2 | 01005 | 0 | ABLT-SG2-01005 | Construction | Building SG-2 | Construction.7.1.4.3 | Prep/Submit Architectural/Civil As-Built Drawings - SG2 | 15 | 15 | 0% | 2023-10-31 08:00 | 2023-11-22 17:00 | -132 | UNSURE | AS-BUILT | ENG | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.7.1.4.3 | SG2 | ABLT | SG2 | 01010 | 0 | ABLT-SG2-01010 | Construction | Building SG-2 | Construction.7.1.4.3 | Review/Approve Architectural/Civil As-Built Drawings - SG2 | 10 | 10 | 0% | 2023-11-24 08:00 | 2023-12-07 17:00 | -132 | UNSURE | AS-BUILT | ENG | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.7.1.4.3 | SG2 | ABLT | SG2 | 01015 | 0 | ABLT-SG2-01015 | Construction | Building SG-2 | Construction.7.1.4.3 | Prep/Submit Electrical As-Built Drawings - SG2 | 15 | 15 | 0% | 2023-03-23 08:00 | 2023-04-12 17:00 | 12 | FSE | 0 | ENG | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.7.1.4.3 | SG2 | ABLT | SG2 | 01020 | 0 | ABLT-SG2-01020 | Construction | Building SG-2 | Construction.7.1.4.3 | Review/Approve Electrical As-Built Drawings - SG2 | 10 | 10 | 0% | 2023-04-13 08:00 | 2023-04-26 17:00 | 12 | FSE | 0 | ENG | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.7.1.4.3 | SG2 | ABLT | SG2 | 01025 | 0 | ABLT-SG2-01025 | Construction | Building SG-2 | Construction.7.1.4.3 | Prep/Submit Mechanical As-Built Drawings - SG2 | 15 | 15 | 0% | 2023-06-28 08:00 | 2023-07-19 17:00 | -56 | UNSURE | AS-BUILT | ENG | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.7.1.4.3 | SG2 | ABLT | SG2 | 01030 | 0 | ABLT-SG2-01030 | Construction | Building SG-2 | Construction.7.1.4.3 | Review/Approve Mechanical As-Built Drawings - SG2 | 10 | 10 | 0% | 2023-07-20 08:00 | 2023-08-02 17:00 | -56 | UNSURE | AS-BUILT | ENG | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.7.1.4.4 | SG3 | ABLT | SG3 | 01005 | 0 | ABLT-SG3-01005 | Construction | Building SG-3 | Construction.7.1.4.4 | Prep/Submit Architectural/Civil As-Built Drawings - SG3 | 15 | 15 | 0% | 2023-11-06 08:00 | 2023-11-29 17:00 | -136 | UNSURE | AS-BUILT | ENG | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.7.1.4.4 | SG3 | ABLT | SG3 | 01010 | 0 | ABLT-SG3-01010 | Construction | Building SG-3 | Construction.7.1.4.4 | Review/Approve Architectural/Civil As-Built Drawings - SG3 | 10 | 10 | 0% | 2023-11-30 08:00 | 2023-12-13 17:00 | -136 | UNSURE | AS-BUILT | ENG | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.7.1.4.4 | SG3 | ABLT | SG3 | 01015 | 0 | ABLT-SG3-01015 | Construction | Building SG-3 | Construction.7.1.4.4 | Prep/Submit Electrical As-Built Drawings - SG3 | 15 | 15 | 0% | 2023-09-01 08:00 | 2023-09-22 17:00 | -102 | FSE | 0 | ENG | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.7.1.4.4 | SG3 | ABLT | SG3 | 01020 | 0 | ABLT-SG3-01020 | Construction | Building SG-3 | Construction.7.1.4.4 | Review/Approve Electrical As-Built Drawings - SG3 | 10 | 10 | 0% | 2023-09-25 08:00 | 2023-10-06 17:00 | -102 | FSE | 0 | ENG | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.7.1.4.4 | SG3 | ABLT | SG3 | 01025 | 0 | ABLT-SG3-01025 | Construction | Building SG-3 | Construction.7.1.4.4 | Prep/Submit Mechanical As-Built Drawings - SG3 | 15 | 15 | 0% | 2023-06-08 08:00 | 2023-06-28 17:00 | -42 | UNSURE | AS-BUILT | ENG | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.7.1.4.4 | SG3 | ABLT | SG3 | 01030 | 0 | ABLT-SG3-01030 | Construction | Building SG-3 | Construction.7.1.4.4 | Review/Approve Mechanical As-Built Drawings - SG3 | 10 | 10 | 0% | 2023-06-29 08:00 | 2023-07-13 17:00 | -42 | UNSURE | AS-BUILT | ENG | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.7.1.6.1 | S82 | ABLT | S8A | 01005 | 0 | ABLT-S8A-01005 | Construction | Building S8-1 | Construction.7.1.6.1 | Prep/Submit Architectural/Civil As-Built Drawings - S8A | 15 | 15 | 0% | 2023-06-16 08:00 | 2023-07-07 17:00 | -38 | UNSURE | AS-BUILT | ENG | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.7.1.6.1 | S82 | ABLT | S8A | 01010 | 0 | ABLT-S8A-01010 | Construction | Building S8-1 | Construction.7.1.6.1 | Review/Approve Architectural/Civil As-Built Drawings - S8A | 10 | 10 | 0% | 2023-07-10 08:00 | 2023-07-21 17:00 | -38 | UNSURE | AS-BUILT | ENG | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.7.1.6.1 | S82 | ABLT | S8A | 01015 | 0 | ABLT-S8A-01015 | Construction | Building S8-1 | Construction.7.1.6.1 | Prep/Submit Electrical As-Built Drawings - S8A | 15 | 15 | 0% | 2023-06-27 08:00 | 2023-07-18 17:00 | -55 | FSE | 0 | ENG | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.7.1.6.1 | S82 | ABLT | S8A | 01020 | 0 | ABLT-S8A-01020 | Construction | Building S8-1 | Construction.7.1.6.1 | Review/Approve Electrical As-Built Drawings - S8A | 10 | 10 | 0% | 2023-07-19 08:00 | 2023-08-01 17:00 | -55 | FSE | 0 | ENG | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.7.1.6.1 | S82 | ABLT | S8A | 01025 | 0 | ABLT-S8A-01025 | Construction | Building S8-1 | Construction.7.1.6.1 | Prep/Submit Mechanical As-Built Drawings - S8A | 15 | 15 | 0% | 2023-06-15 08:00 | 2023-07-06 17:00 | -47 | UNSURE | AS-BUILT | ENG | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.7.1.6.1 | S82 | ABLT | S8A | 01030 | 0 | ABLT-S8A-01030 | Construction | Building S8-1 | Construction.7.1.6.1 | Review/Approve Mechanical As-Built Drawings - S8A | 10 | 10 | 0% | 2023-07-07 08:00 | 2023-07-20 17:00 | -47 | UNSURE | AS-BUILT | ENG | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.7.1.6.3 | S81 | ABLT | S8E | 01005 | 0 | ABLT-S8E-01005 | Construction | Building S8-2 (Existing) | Construction.7.1.6.3 | Prep/Submit Architectural/Civil As-Built Drawings - S8E | 15 | 15 | 0% | 2023-10-26 08:00 | 2023-11-17 17:00 | -129 | UNSURE | AS-BUILT | ENG | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.7.1.6.3 | S81 | ABLT | S8E | 01010 | 0 | ABLT-S8E-01010 | Construction | Building S8-2 (Existing) | Construction.7.1.6.3 | Review/Approve Architectural/Civil As-Built Drawings - S8E | 10 | 10 | 0% | 2023-11-20 08:00 | 2023-12-04 17:00 | -129 | UNSURE | AS-BUILT | ENG | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.7.1.6.3 | S81 | ABLT | S8E | 01015 | 0 | ABLT-S8E-01015 | Construction | Building S8-2 (Existing) | Construction.7.1.6.3 | Prep/Submit Electrical As-Built Drawings - S8E | 15 | 15 | 0% | 2023-07-13 08:00 | 2023-08-02 17:00 | -66 | FSE | 0 | ENG | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.7.1.6.3 | S81 | ABLT | S8E | 01020 | 0 | ABLT-S8E-01020 | Construction | Building S8-2 (Existing) | Construction.7.1.6.3 | Review/Approve Electrical As-Built Drawings - S8E | 10 | 10 | 0% | 2023-08-03 08:00 | 2023-08-16 17:00 | -66 | FSE | 0 | ENG | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.7.1.6.3 | S81 | ABLT | S8E | 01025 | 0 | ABLT-S8E-01025 | Construction | Building S8-2 (Existing) | Construction.7.1.6.3 | Prep/Submit Mechanical As-Built Drawings - S8E | 15 | 15 | 0% | 2023-06-28 08:00 | 2023-07-19 17:00 | -56 | UNSURE | AS-BUILT | ENG | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.7.1.6.3 | S81 | ABLT | S8E | 01030 | 0 | ABLT-S8E-01030 | Construction | Building S8-2 (Existing) | Construction.7.1.6.3 | Review/Approve Mechanical As-Built Drawings - S8E | 10 | 10 | 0% | 2023-07-20 08:00 | 2023-08-02 17:00 | -56 | UNSURE | AS-BUILT | ENG | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.7.1.3.4 | OGE | ABLT | OGE | 01005 | 0 | ABLT-OGE-01005 | Construction | Site Utility Work | Construction.7.1.3.4 | Prep/Submit Site Utility As-Built Drawings - O'Dwyer Gardens East | 15 | 15 | 0% | 2023-05-08 08:00 | 2023-05-26 17:00 | -10 | UNSURE | AS-BUILT | ENG | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.7.1.3.4 | OGE | ABLT | OGE | 01010 | 0 | ABLT-OGE-01010 | Construction | Site Utility Work | Construction.7.1.3.4 | Review/Approve Site Utility As-Built Drawings - O'Dwyer Gardens East | 10 | 10 | 0% | 2023-05-30 08:00 | 2023-06-12 17:00 | -10 | UNSURE | AS-BUILT | ENG | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.7.1.4.5 | SGS | ABLT | SGS | 01005 | 0 | ABLT-SGS-01005 | Construction | Site Utility Work | Construction.7.1.4.5 | Prep/Submit Site Utility As-Built Drawings - Surfside Gardens South | 15 | 15 | 0% | 2023-11-21 08:00 | 2023-12-12 17:00 | -145 | UNSURE | AS-BUILT | ENG | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.7.1.4.5 | SGS | ABLT | SGS | 01010 | 0 | ABLT-SGS-01010 | Construction | Site Utility Work | Construction.7.1.4.5 | Review/Approve Site Utility As-Built Drawings - Surfside Gardens South | 10 | 10 | 0% | 2023-12-13 08:00 | 2023-12-27 17:00 | -145 | UNSURE | AS-BUILT | ENG | 0 | 0-SGS
Not Started | CI NYCHA Update #22.Construction.7.1.6.2 | S8 | ABLT | S8 | 01005 | 0 | ABLT-S8-01005 | Construction | Site Utility Work | Construction.7.1.6.2 | Prep/Submit Site Utility As-Built Drawings - Site 8 | 15 | 15 | 0% | 2024-01-25 08:00 | 2024-02-14 17:00 | -189 | UNSURE | AS-BUILT | ENG | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.7.1.6.2 | S8 | ABLT | S8 | 01010 | 0 | ABLT-S8-01010 | Construction | Site Utility Work | Construction.7.1.6.2 | Review/Approve Site Utility As-Built Drawings - Site 8 | 10 | 10 | 0% | 2024-02-15 08:00 | 2024-02-29 17:00 | -189 | UNSURE | AS-BUILT | ENG | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.7.2.1 | NA | O&M | 01005 | 0 | 0 | O&M-01005 | Construction | Mechanical O&M Manuals | Construction.7.2.1 | Prep/Submit Spray Shower Equipment O&M Manual/Guarantees/Warranties | 30 | 30 | 0% | 2022-11-25 08:00 | 2023-01-09 17:00 | 23 | UNSURE | SUBMITTALS | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Construction.7.2.1 | NA | O&M | 01010 | 0 | 0 | O&M-01010 | Construction | Mechanical O&M Manuals | Construction.7.2.1 | Review/Approve Spray Shower Equipment O&M Manual/Guarantees/Warranties | 15 | 15 | 0% | 2023-01-10 08:00 | 2023-01-31 17:00 | 23 | UNSURE | SUBMITTALS | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Construction.7.2.2 | NA | O&M | 02035 | 0 | 0 | O&M-02035 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Prep/Submit Switchboards O&M Manual/Guarantees/Warranties | 80 | 80 | 0% | 2022-11-25 08:00 | 2023-03-22 17:00 | -114 | UNSURE | SUBMITTALS | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Construction.7.2.2 | NA | O&M | 02040 | 0 | 0 | O&M-02040 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Review/Approve Switchboards O&M Manual/Guarantees/Warranties | 15 | 15 | 0% | 2023-03-23 08:00 | 2023-04-12 17:00 | -114 | UNSURE | SUBMITTALS | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Construction.7.2.2 | NA | O&M | 02050 | 0 | 0 | O&M-02050 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Prep/Submit Smoke/Fire Alarm System O&M Manual/Guarantees/Warranties | 80 | 80 | 0% | 2022-11-25 08:00 | 2023-03-22 17:00 | -9 | UNSURE | SUBMITTALS | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Construction.7.2.2 | NA | O&M | 02055 | 0 | 0 | O&M-02055 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Review/Approve Smoke/Fire Alarm System O&M Manual/Guarantees/Warranties | 15 | 15 | 0% | 2023-03-23 08:00 | 2023-04-12 17:00 | -9 | UNSURE | SUBMITTALS | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Construction.7.2.2 | NA | O&M | 02070 | 0 | 0 | O&M-02070 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Prep/Submit Power & Distribution Panels O&M Manual/Guarantees/Warranties | 80 | 80 | 0% | 2022-11-25 08:00 | 2023-03-22 17:00 | -105 | UNSURE | SUBMITTALS | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Construction.7.2.2 | NA | O&M | 02075 | 0 | 0 | O&M-02075 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Review/Approve Power & Distribution Panels O&M Manual/Guarantees/Warranties | 15 | 15 | 0% | 2023-03-23 08:00 | 2023-04-12 17:00 | -105 | UNSURE | SUBMITTALS | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Construction.7.2.2 | NA | O&M | 02090 | 0 | 0 | O&M-02090 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Prep/Submit Automatic Transfer Switch O&M Manual/Guarantees/Warranties | 80 | 80 | 0% | 2022-11-25 08:00 | 2023-03-22 17:00 | -105 | UNSURE | SUBMITTALS | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Construction.7.2.2 | NA | O&M | 02095 | 0 | 0 | O&M-02095 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Review/Approve Automatic Transfer Switch O&M Manual/Guarantees/Warranties | 15 | 15 | 0% | 2023-03-23 08:00 | 2023-04-12 17:00 | -105 | UNSURE | SUBMITTALS | ENG | 0 | 0-NA
In Progress | CI NYCHA Update #22.Construction.7.2.2 | NA | O&M | 02105 | 0 | 0 | O&M-02105 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Prep/Submit Emergency Lighting O&M Manual/Guarantees/Warranties | 80 | 58 | 27% | 2022-05-02 08:00 | 2023-02-17 17:00 | -92 | UNSURE | SUBMITTALS | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Construction.7.2.2 | NA | O&M | 02110 | 0 | 0 | O&M-02110 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Review/Approve Emergency lighting O&M Manual/Guarantees/Warranties | 15 | 15 | 0% | 2023-02-21 08:00 | 2023-03-13 17:00 | -92 | UNSURE | SUBMITTALS | ENG | 0 | 0-NA
In Progress | CI NYCHA Update #22.Construction.7.2.2 | NA | O&M | 02125 | 0 | 0 | O&M-02125 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Prep/Submit Emergency & Optional Standby Power System (incl Emer Generator) O&M Manual/Guarantees/Warranties | 80 | 72 | 10% | 2021-12-13 | 2023-03-10 17:00 | -101 | UNSURE | SUBMITTALS | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Construction.7.2.2 | NA | O&M | 02130 | 0 | 0 | O&M-02130 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Review/Approve Emergency & Optional Standby Power System (incl Emer Generator) O&M Manual/Guarantees/Warranties | 15 | 15 | 0% | 2023-03-13 08:00 | 2023-03-31 17:00 | -101 | UNSURE | SUBMITTALS | ENG | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG6 | PERMIT | 06005 | 0 | 0 | PERMIT-06005 | Procurement | Permits | Procurement.Div 1.Permits | File for Electrical Permits - SG6 | 10 | 0 | 100% | 2020-11-18 | 2020-11-20 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG6 | PERMIT | 06010 | 0 | 0 | PERMIT-06010 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Electrical Permits - SG6 | 20 | 0 | 100% | 2020-11-23 | 2021-02-05 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.Div 1.GENRAL | 0 | 01512 | 0 | 0 | 0 | 01512 | Procurement | General | Procurement.Div 1.GENRAL | Revise & Re-Submit Safety Plan | 10 | 0 | 100% | 2020-09-16 | 2020-09-16 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.GENRAL | 0 | 01514 | 0 | 0 | 0 | 01514 | Procurement | General | Procurement.Div 1.GENRAL | Review & Approve Safety Plan | 5 | 0 | 100% | 2020-09-17 | 2020-10-01 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG4 | PERMIT | 07005 | 0 | 0 | PERMIT-07005 | Procurement | Permits | Procurement.Div 1.Permits | File for DEP Asbestos Control Program (ACP) - SG4 | 10 | 0 | 100% | 2020-09-04 | 2020-10-07 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG4 | PERMIT | 07010 | 0 | 0 | PERMIT-07010 | Procurement | Permits | Procurement.Div 1.Permits | DEP Issue Asbestos Control Program (ACP) Permit - SG4 | 20 | 0 | 100% | 2020-10-08 | 2020-10-22 |  | 0 | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Procurement.Div. 3 | NA | 03205 | 0 | 0 | 0 | 03205 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Prepare Smooth Concrete Finish Mock-up | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | 122 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 3 | NA | 03210 | 0 | 0 | 0 | 03210 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Review & Approve Smooth Concrete Finish Mock-up | 3 | 3 | 0% | 2022-11-29 08:00 | 2022-12-01 17:00 | 122 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01000 | 0 | 0 | OG10-01000 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Request CSC to Sign off Demolition Plan at OG-7 | 5 | 0 | 100% | 2021-05-25 | 2021-05-25 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01003 | 0 | 0 | OG10-01003 | Construction | Structural/Architectural Construction | Construction.1.4.7 | CSC Sign off Demolition Plan at OG-7 | 3 | 0 | 100% | 2021-05-25 | 2021-05-25 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01008 | 0 | 0 | OG10-01008 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Request CSC for Pre-Demolition Inspection at OG-7 | 5 | 0 | 100% | 2021-06-14 | 2021-06-16 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01010 | 0 | 0 | OG10-01010 | Construction | Structural/Architectural Construction | Construction.1.4.7 | CSC Pre-Demolition Inspection at OG-7 | 3 | 0 | 100% | 2021-06-17 | 2021-06-18 |  | 0 | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Procurement.Div. 3 | NA | 03220 | 0 | 0 | 0 | 03220 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Prepare Architectural Concrete Finish Mock-up | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | 122 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 3 | NA | 03225 | 0 | 0 | 0 | 03225 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Review & Approve Architectural Concrete Finish Mock-up | 3 | 3 | 0% | 2022-11-29 08:00 | 2022-12-01 17:00 | 122 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 3 | NA | 03230 | 0 | 0 | 0 | 03230 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Prepare Textured Concrete for Exterior Pavements Mock-up | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | 52 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 3 | NA | 03235 | 0 | 0 | 0 | 03235 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Review & Approve Textured Concrete for Exterior Pavements Mock-up | 3 | 3 | 0% | 2022-11-29 08:00 | 2022-12-01 17:00 | 52 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Completed | CI NYCHA Update #22.Procurement.Div. 3 | 0 | 03240 | 0 | 0 | 0 | 03240 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Prepare Self Consolidating Concrete Mock-up | 2 | 0 | 100% | 2022-03-15 | 2022-03-15 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 3 | 0 | 03245 | 0 | 0 | 0 | 03245 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Review & Approve Self Consolidating Concrete Mock-up | 3 | 0 | 100% | 2022-03-16 | 2022-03-16 |  | 0 | 0 | ENG | 0 | 0-0
Not Started | CI NYCHA Update #22.Procurement.Div. 3 | NA | 03250 | 0 | 0 | 0 | 03250 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Prepare Floor Concrete Mock-up | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | 107 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 3 | NA | 03255 | 0 | 0 | 0 | 03255 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Review & Approve Floor Concrete Mock-up | 3 | 3 | 0% | 2022-11-29 08:00 | 2022-12-01 17:00 | 107 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Completed | CI NYCHA Update #22.Procurement.Div. 3 | 0 | 03260 | 0 | 0 | 0 | 03260 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Prepare Surface Preparation and Repair Work Mock-up | 2 | 0 | 100% | 2022-08-01 | 2022-08-01 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 3 | 0 | 03265 | 0 | 0 | 0 | 03265 | Procurement | Div. 3 - Concrete | Procurement.Div. 3 | Review & Approve Surface Preparation and Repair Work Mock-up | 3 | 0 | 100% | 2022-08-02 | 2022-08-02 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 4 | 0 | 04205 | 0 | 0 | 0 | 04205 | Procurement | Div. 4 - Masonry | Procurement.Div 4 | Prepare Masonry Sample Panels (A) Mock-up | 2 | 0 | 100% | 2022-03-25 08:00 | 2022-03-28 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 4 | 0 | 04210 | 0 | 0 | 0 | 04210 | Procurement | Div. 4 - Masonry | Procurement.Div 4 | Review & Approve Masonry Sample Panels (A) Mock-up | 3 | 0 | 100% | 2022-04-01 | 2022-04-01 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 4 | 0 | 04220 | 0 | 0 | 0 | 04220 | Procurement | Div. 4 - Masonry | Procurement.Div 4 | Prepare Masonry Sample Panels (B) Mock-up | 2 | 0 | 100% | 2022-03-25 | 2022-03-28 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 4 | 0 | 04225 | 0 | 0 | 0 | 04225 | Procurement | Div. 4 - Masonry | Procurement.Div 4 | Review & Approve Masonry Sample Panels (B) Mock-up | 3 | 0 | 100% | 2022-04-01 | 2022-04-01 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 4 | 0 | 04230 | 0 | 0 | 0 | 04230 | Procurement | Div. 4 - Masonry | Procurement.Div 4 | Prepare Masonry Sample Cleaning Procedure Mock-up | 2 | 0 | 100% | 2022-09-01 08:00 | 2022-09-01 17:00 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 4 | 0 | 04235 | 0 | 0 | 0 | 04235 | Procurement | Div. 4 - Masonry | Procurement.Div 4 | Review & Approve Masonry Sample Cleaning Procedure Mock-up | 3 | 0 | 100% | 2022-09-01 08:00 | 2022-09-01 17:00 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05805 | 0 | 0 | 0 | 05805 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Prepare Railing Form and Finish Mock-ups | 2 | 0 | 100% | 2022-09-01 08:00 | 2022-09-01 17:00 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.div. 5 | 0 | 05810 | 0 | 0 | 0 | 05810 | Procurement | Div. 5 - Metal | Procurement.div. 5 | Review & Approve Railing Form and Finish Mock-ups | 3 | 0 | 100% | 2022-09-01 08:00 | 2022-09-01 17:00 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07405 | 0 | 0 | 0 | 07405 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Prepare Typical Waterproofing Mock-up | 2 | 0 | 100% | 2022-02-16 | 2022-02-16 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07410 | 0 | 0 | 0 | 07410 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Review & Approve Typical Waterproofing Mock-up | 3 | 0 | 100% | 2022-02-18 | 2022-02-18 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07420 | 0 | 0 | 0 | 07420 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Prepare Crystalline Waterproofing Mock-up | 2 | 0 | 100% | 2022-02-16 | 2022-02-16 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07425 | 0 | 0 | 0 | 07425 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Review & Approve Crystalline Waterproofing Mock-up | 3 | 0 | 100% | 2022-02-18 | 2022-02-18 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07430 | 0 | 0 | 0 | 07430 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Prepare Air Barrier Mock-up | 2 | 0 | 100% | 2022-09-01 08:00 | 2022-09-01 17:00 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07435 | 0 | 0 | 0 | 07435 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Review & Approve Air Barrier Mock-up | 3 | 0 | 100% | 2022-09-01 08:00 | 2022-09-01 17:00 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07440 | 0 | 0 | 0 | 07440 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Prepare Roof Mock-up | 2 | 0 | 100% | 2022-07-26 08:00 | 2022-08-01 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 7 | 0 | 07445 | 0 | 0 | 0 | 07445 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Review & Approve Roof Mock-up | 3 | 0 | 100% | 2022-08-02 | 2022-09-22 |  | 0 | 0 | ENG | 0 | 0-0
Not Started | CI NYCHA Update #22.Procurement.Div. 7 | NA | 07450 | 0 | 0 | 0 | 07450 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Prepare Sealant Mock-up | 2 | 2 | 0% | 2022-12-23 08:00 | 2022-12-27 17:00 | 41 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 7 | NA | 07455 | 0 | 0 | 0 | 07455 | Procurement | Div. 7 - Thermal & Moisture Protection | Procurement.Div. 7 | Review & Approve Sealant Mock-up | 3 | 3 | 0% | 2022-12-28 08:00 | 2022-12-30 17:00 | 41 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 9 | NA | 09305 | 0 | 0 | 0 | 09305 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Prepare Cement Plastering Mock-up | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | 80 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 9 | NA | 09310 | 0 | 0 | 0 | 09310 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Review & Approve Cement Plastering Mock-up | 3 | 3 | 0% | 2022-11-29 08:00 | 2022-12-01 17:00 | 80 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09320 | 0 | 0 | 0 | 09320 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Prepare Gypsum Board Mock-up | 2 | 0 | 100% | 2022-07-13 | 2022-07-15 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09325 | 0 | 0 | 0 | 09325 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Review & Approve Gypsum Board Mock-up | 3 | 0 | 100% | 2022-07-18 | 2022-09-14 |  | 0 | 0 | ENG | 0 | 0-0
In Progress | CI NYCHA Update #22.Procurement.Div. 9 | NA | 09330 | 0 | 0 | 0 | 09330 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Prepare Tiling Mock-up | 2 | 1 | 50% | 2022-11-21 | 2022-11-25 17:00 | 104 | FLOORING | 0 | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 9 | NA | 09335 | 0 | 0 | 0 | 09335 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Review & Approve Tiling Mock-up | 3 | 3 | 0% | 2022-11-28 08:00 | 2022-11-30 17:00 | 104 | FLOORING | 0 | ENG | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09340 | 0 | 0 | 0 | 09340 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Prepare Painting Mock-up | 2 | 0 | 100% | 2022-07-01 | 2022-07-15 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 9 | 0 | 09345 | 0 | 0 | 0 | 09345 | Procurement | Div. 9 - Finishes | Procurement.Div. 9 | Review & Approve Painting Mock-up | 3 | 0 | 100% | 2022-07-16 | 2022-11-07 |  | 0 | 0 | ENG | 0 | 0-0
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32805 | 0 | 0 | 0 | 32805 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare Porous Concrete Pavement Test Panel Mock-up | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | 67 | JMC | 0 | ENG | 0 | 0-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 32 | NA | 32810 | 0 | 0 | 0 | 32810 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Porous Concrete Pavement Test Panel Mock-up | 3 | 3 | 0% | 2022-11-29 08:00 | 2022-12-01 17:00 | 67 | JMC | 0 | ENG | 0 | 0-NA
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32820 | 0 | 0 | 0 | 32820 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Prepare Integrally Colored Concrete Mock-up/Field Samples | 2 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 32 | 0 | 32825 | 0 | 0 | 0 | 32825 | Procurement | Div. 32 - Exterior Improvements | Procurement.Div. 32 | Review & Approve Integrally Colored Concrete Mock-up/Field Samples | 3 | 0 | 100% | 2022-03-25 | 2022-03-25 |  | 0 | 0 | ENG | 0 | 0-0
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01072 | 0 | 0 | OG8-01072 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Waterproof/Insulation Below Slab ----> OG8 | 5 | 0 | 100% | 2021-09-20 | 2022-02-25 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01072 | 0 | 0 | SG6-01072 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Waterproof/Insulation Below Slab ----> SG6 | 5 | 0 | 100% | 2021-06-28 | 2021-07-02 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01072 | 0 | 0 | OG9-01072 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Waterproof/Insulation Below Slab ----> OG9 | 5 | 0 | 100% | 2021-10-22 08:00 | 2021-12-14 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01072 | 0 | 0 | OG10-01072 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Waterproof/Insulation Below Slab ----> OG10 | 5 | 0 | 100% | 2021-11-12 08:00 | 2021-11-14 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01072 | 0 | 0 | SG7-01072 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Waterproof/Insulation Below Slab ----> SG7 | 5 | 0 | 100% | 2022-06-14 | 2022-06-15 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01072 | 0 | 0 | S8A-01072 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Waterproof/Insulation Below Slab ----> S8 (Addition) | 5 | 0 | 100% | 2022-07-07 | 2022-07-08 |  | 0 | WATERPROOFING | 0 | 0 | 0-S8A
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.1 | SG1 | SG1 | 01485 | 0 | 0 | SG1-01485 | Construction | East Elevation | Construction.4.7.4.EFPC.1 | Install Aquafence (East Side) --> SG1 | 1 | 1 | 0% | 2023-01-20 08:00 | 2023-01-20 17:00 | -34 | MLJ | AQUAFENCE | INSTALL | 10-1000 | 10-1000-SG1
Not Started | CI NYCHA Update #22.Construction.4.7.4.EFPC.4 | SG1 | SG1 | 01785 | 0 | 0 | SG1-01785 | Construction | West Elevation | Construction.4.7.4.EFPC.4 | Install Aquafence (West Side) --> SG1 | 1 | 1 | 0% | 2023-01-11 08:00 | 2023-01-11 17:00 | -28 | MLJ | AQUAFENCE | INSTALL | 10-1000 | 10-1000-SG1
Not Started | CI NYCHA Update #22.Construction.4.2.1.EFPC.4 | SG2 | SG2 | 01785 | 0 | 0 | SG2-01785 | Construction | West Elevation | Construction.4.2.1.EFPC.4 | Install Aquafence (West Side) --> SG2 | 1 | 1 | 0% | 2022-11-25 08:00 | 2022-11-25 17:00 | 3 | MLJ | AQUAFENCE | INSTALL | 10-1000 | 10-1000-SG2
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.2 | SG3 | SG3 | 01585 | 0 | 0 | SG3-01585 | Construction | South Elevation | Construction.4.3.5.EFPC.2 | Install Aquafence (South Side) --> SG3 | 1 | 1 | 0% | 2023-04-03 08:00 | 2023-04-03 17:00 | -84 | MLJ | AQUAFENCE | INSTALL | 10-1000 | 10-1000-SG3
Not Started | CI NYCHA Update #22.Construction.4.3.5.EFPC.1 | SG3 | SG3 | 01485 | 0 | 0 | SG3-01485 | Construction | East Elevation | Construction.4.3.5.EFPC.1 | Install Aquafence (East Side) --> SG3 | 1 | 1 | 0% | 2023-02-22 08:00 | 2023-02-22 17:00 | -56 | MLJ | AQUAFENCE | INSTALL | 10-1000 | 10-1000-SG3
Not Started | CI NYCHA Update #22.Construction.1.3.1.EFPC.4 | OG1 | OG1 | 01785 | 0 | 0 | OG1-01785 | Construction | West Elevation | Construction.1.3.1.EFPC.4 | Install Aquafence (West Side) --> OG1 | 1 | 1 | 0% | 2023-03-22 08:00 | 2023-03-22 17:00 | 42 | MLJ | AQUAFENCE | INSTALL | 10-1000 | 10-1000-OG1
Not Started | CI NYCHA Update #22.Construction.5.2.5.EFPC.4 | OG2 | OG2 | 01785 | 0 | 0 | OG2-01785 | Construction | West Elevation | Construction.5.2.5.EFPC.4 | Install Aquafence (West Side) --> OG2 | 1 | 1 | 0% | 2023-02-14 08:00 | 2023-02-14 17:00 | 50 | MLJ | AQUAFENCE | INSTALL | 10-1000 | 10-1000-OG2
Not Started | CI NYCHA Update #22.Construction.5.3.5.EFPC.4 | OG3 | OG3 | 01785 | 0 | 0 | OG3-01785 | Construction | West Elevation | Construction.5.3.5.EFPC.4 | Install Aquafence (West Side) --> OG3 | 1 | 1 | 0% | 2022-11-25 08:00 | 2022-11-25 17:00 | 104 | MLJ | AQUAFENCE | INSTALL | 10-1000 | 10-1000-OG3
Not Started | CI NYCHA Update #22.Construction.3.3.5.EFPC.2 | OG5 | OG5 | 01585 | 0 | 0 | OG5-01585 | Construction | South Elevation | Construction.3.3.5.EFPC.2 | Install Aquafence (South Side) --> OG5 | 1 | 1 | 0% | 2022-12-01 08:00 | 2022-12-01 17:00 | 100 | MLJ | AQUAFENCE | INSTALL | 10-1000 | 10-1000-OG5
Not Started | CI NYCHA Update #22.Construction.3.6.5.EFPC.2 | OG4 | OG4 | 01585 | 0 | 0 | OG4-01585 | Construction | South Elevation | Construction.3.6.5.EFPC.2 | Install Aquafence (South Side) --> OG4 | 1 | 1 | 0% | 2023-01-25 08:00 | 2023-01-25 17:00 | 64 | MLJ | AQUAFENCE | INSTALL | 10-1000 | 10-1000-OG4
Not Started | CI NYCHA Update #22.Construction.2.2.5.EFPC.1 | SG4 | SG4 | 01485 | 0 | 0 | SG4-01485 | Construction | East Elevation | Construction.2.2.5.EFPC.1 | Install Aquafence (East Side) --> SG4 | 1 | 1 | 0% | 2022-12-02 08:00 | 2022-12-02 17:00 | 91 | MLJ | AQUAFENCE | INSTALL | 10-1000 | 10-1000-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.5.EFPC.2 | SG4 | SG4 | 01585 | 0 | 0 | SG4-01585 | Construction | South Elevation | Construction.2.2.5.EFPC.2 | Install Aquafence (South Side) --> SG4 | 1 | 1 | 0% | 2022-12-02 08:00 | 2022-12-02 17:00 | 91 | MLJ | AQUAFENCE | INSTALL | 10-1000 | 10-1000-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.5.EFPC.3 | SG4 | SG4 | 01685 | 0 | 0 | SG4-01685 | Construction | North Elevation | Construction.2.2.5.EFPC.3 | Install Aquafence (North Side) --> SG4 | 1 | 1 | 0% | 2022-12-29 08:00 | 2022-12-29 17:00 | 73 | MLJ | AQUAFENCE | INSTALL | 10-1000 | 10-1000-SG4
Not Started | CI NYCHA Update #22.Construction.2.2.5.EFPC.4 | SG4 | SG4 | 01785 | 0 | 0 | SG4-01785 | Construction | West Elevation | Construction.2.2.5.EFPC.4 | Install Aquafence (West Side) --> SG4 | 1 | 1 | 0% | 2022-12-22 08:00 | 2022-12-22 17:00 | 77 | MLJ | AQUAFENCE | INSTALL | 10-1000 | 10-1000-SG4
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.1 | SG5 | SG5 | 01485 | 0 | 0 | SG5-01485 | Construction | East Elevation | Construction.2.3.5.EFPC.1 | Install Aquafence (East Side) --> SG5 | 1 | 1 | 0% | 2022-12-02 08:00 | 2022-12-02 17:00 | 91 | MLJ | AQUAFENCE | INSTALL | 10-1000 | 10-1000-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.2 | SG5 | SG5 | 01585 | 0 | 0 | SG5-01585 | Construction | South Elevation | Construction.2.3.5.EFPC.2 | Install Aquafence (South Side) --> SG5 | 1 | 1 | 0% | 2022-12-29 08:00 | 2022-12-29 17:00 | 73 | MLJ | AQUAFENCE | INSTALL | 10-1000 | 10-1000-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.3 | SG5 | SG5 | 01685 | 0 | 0 | SG5-01685 | Construction | North Elevation | Construction.2.3.5.EFPC.3 | Install Aquafence (North Side) --> SG5 | 1 | 1 | 0% | 2023-01-20 08:00 | 2023-01-20 17:00 | 59 | MLJ | AQUAFENCE | INSTALL | 10-1000 | 10-1000-SG5
Not Started | CI NYCHA Update #22.Construction.2.3.5.EFPC.4 | SG5 | SG5 | 01785 | 0 | 0 | SG5-01785 | Construction | West Elevation | Construction.2.3.5.EFPC.4 | Install Aquafence (West Side) --> SG5 | 1 | 1 | 0% | 2022-12-02 08:00 | 2022-12-02 17:00 | 91 | MLJ | AQUAFENCE | INSTALL | 10-1000 | 10-1000-SG5
Not Started | CI NYCHA Update #22.Procurement.Div. 10 | NA | 10045 | 0 | 0 | 0 | 10045 | Procurement | Div. 10 - Specialties | Procurement.Div. 10 | Prepare Aquafence/Floodbreak Mock-up | 2 | 2 | 0% | 2022-11-25 08:00 | 2022-11-28 17:00 | 91 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Procurement.Div. 10 | NA | 10050 | 0 | 0 | 0 | 10050 | Procurement | Div. 10 - Specialties | Procurement.Div. 10 | Review & Approve Aquafence/Floodbreak Mock-up | 3 | 3 | 0% | 2022-11-29 08:00 | 2022-12-01 17:00 | 91 | MLJ | PROCUREMENT | ENG | NA | NA-NA
Not Started | CI NYCHA Update #22.Construction.3.6.5.EFPC.2 | OG4 | OG4 | 01560 | 0 | 0 | OG4-01560 | Construction | South Elevation | Construction.3.6.5.EFPC.2 | Form for slab at Curtain Wall for flood protection (South Side) --> OG4 | 4 | 4 | 0% | 2022-12-21 08:00 | 2022-12-27 17:00 | 63 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.5.EFPC.2 | OG4 | OG4 | 01565 | 0 | 0 | OG4-01565 | Construction | South Elevation | Construction.3.6.5.EFPC.2 | Rebar & inserts for slab at Curtain Wall for flood protection (South Side) --> OG4 | 6 | 6 | 0% | 2022-12-28 08:00 | 2023-01-05 17:00 | 63 | TONAGE | REBAR | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.5.EFPC.2 | OG4 | OG4 | 01570 | 0 | 0 | OG4-01570 | Construction | South Elevation | Construction.3.6.5.EFPC.2 | Pour slab at Curtain Wall for flood protection (South Side) --> OG4 | 4 | 4 | 0% | 2023-01-06 08:00 | 2023-01-11 17:00 | 63 | MLJ | Concrete | EB CONCRETE | 03-2100 | 03-2100-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.5.EFPC.2 | OG4 | OG4 | 01575 | 0 | 0 | OG4-01575 | Construction | South Elevation | Construction.3.6.5.EFPC.2 | Strip Forms for slab at Curtain Wall for flood protection (South Side) --> OG4 | 2 | 2 | 0% | 2023-01-12 08:00 | 2023-01-13 17:00 | 66 | MLJ | Formwork | EB FORMWORK | 03-1100 | 03-1100-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.5.EFPC.2 | OG4 | OG4 | 01580 | 0 | 0 | OG4-01580 | Construction | South Elevation | Construction.3.6.5.EFPC.2 | Backfill surounding area at Curtain Wall for flood protection (South Side) --> OG4 | 4 | 4 | 0% | 2023-01-19 08:00 | 2023-01-24 17:00 | 64 | MLJ | BACKFILL | BACKFILL EB | 31-1100 | 31-1100-OG4
Not Started | CI NYCHA Update #22.Construction.3.6.5.EFPC.2 | OG4 | OG4 | 01571 | 0 | 0 | OG4-01571 | Construction | South Elevation | Construction.3.6.5.EFPC.2 | Cure slab at Curtain Wall for flood protection (South Side) --> OG4 | 7 | 7 | 0% | 2023-01-12 08:00 | 2023-01-18 17:00 | 91 | MLJ | CONCRETE | EB CONCRETE | 03-2100 | 03-2100-OG4
Completed | CI NYCHA Update #22.Construction.2.1 | SGN | SURV | SGN | P | 01005 | SURV-SGN-P-01005 | Construction | Survey & Mobilization | Construction.2.1 | Conduct Plumbing Site Survey - Surfside Gardens North (SG-4, SG-5, SG-6) - N/A | 20 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.2.1 | SGN | SURV | SGN | M | 01005 | SURV-SGN-M-01005 | Construction | Survey & Mobilization | Construction.2.1 | Conduct Mechanical Site Survey - Surfside Gardens North (SG-4, SG-5, SG-6) | 20 | 0 | 100% | 2020-12-21 | 2021-01-29 17:00 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.3.2 | OGP1 | SURV | OGP1 | P | 01005 | SURV-OGP1-P-01005 | Construction | Mobilization & Survey | Construction.3.2 | Conduct Plumbing Site Survey - Odwyer Gardens - Part 1 (OG-4 & OG-5) - N/A | 20 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.3.2 | OGP1 | SURV | OGP1 | M | 01005 | SURV-OGP1-M-01005 | Construction | Mobilization & Survey | Construction.3.2 | Conduct Mechanical Site Survey - Odwyer Gardens - Part 1 (OG-4 & OG-5) | 20 | 0 | 100% | 2021-01-22 | 2021-01-29 17:00 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.5.1 | OGW | SURV | OGW | P | 01005 | SURV-OGW-P-01005 | Construction | Mobilization & Survey | Construction.5.1 | Conduct Plumbing Site Survey - O'Dwyer Garden - West (OG-2, OG-3 & OG-9) - N/A | 20 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.1 | OGW | SURV | OGW | M | 01005 | SURV-OGW-M-01005 | Construction | Mobilization & Survey | Construction.5.1 | Conduct Mechanical Site Survey - O'Dwyer Garden - West (OG-2, OG-3 & OG-9) | 20 | 0 | 100% | 2021-01-22 | 2021-01-29 17:00 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.1.1 | OGE | SURV | OGE | P | 01005 | SURV-OGE-P-01005 | Construction | Mobilization & Survey | Construction.1.1 | Conduct Plumbing Site Survey - O'Dwyer Garden - East (OG-1, OG-6 & OG-10) - N/A | 20 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.1.1 | OGE | SURV | OGE | M | 01005 | SURV-OGE-M-01005 | Construction | Mobilization & Survey | Construction.1.1 | Conduct Mechanical Site Survey - O'Dwyer Garden - East (OG-1, OG-6 & OG-10) | 20 | 0 | 100% | 2021-01-22 | 2021-01-29 17:00 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.4.1 | SGS | SURV | SGS | P | 01005 | SURV-SGS-P-01005 | Construction | Mobilization & Survey | Construction.4.1 | Conduct Plumbing Site Survey - Surfside Gardens South (SG-1, SG-2, SG-3 & SG-7) - N/A | 20 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.1 | SGS | SURV | SGS | M | 01005 | SURV-SGS-M-01005 | Construction | Mobilization & Survey | Construction.4.1 | Conduct Mechanical Site Survey - Surfside Gardens South (SG-1, SG-2, SG-3 & SG-7) | 20 | 0 | 100% | 2021-01-22 | 2021-01-29 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.8.4 | S8 | SURV | S8 | P | 01005 | SURV-S8-P-01005 | Construction | Mobilization & Survey | Construction.8.4 | Conduct Plumbing Site Survey - Site 8 (S8 & S8-1) - N/A | 20 | 0 | 100% | 2021-01-04 | 2021-01-04 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Construction.8.4 | S8 | SURV | S8 | M | 01005 | SURV-S8-M-01005 | Construction | Mobilization & Survey | Construction.8.4 | Conduct Mechanical Site Survey - Site 8 (S8 & S8-1) | 20 | 0 | 100% | 2021-01-22 | 2021-01-29 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24335 | 0 | 0 | 0 | 24335 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Release Fin Tube Boilers | 1 | 0 | 100% | 2022-01-03 | 2022-01-03 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 10 | 0 | 10085 | 0 | 0 | 0 | 10085 | Procurement | Div. 10 - Specialties | Procurement.Div. 10 | Release Flood Control System - Aquafence/Floodbreak | 0 | 0 | 100% | 2021-09-30 |  |  | 0 | 0 | 0 | 0 | 0-0
Not Started | CI NYCHA Update #22.Construction.1.5.5 | OGE | OGE | 01706 | 0 | 0 | OGE-01706 | Construction | Site Restoration | Construction.1.5.5 | Backfill Trench for ashpalt repairs (Lot near OG5) --> OG Phase 4 | 5 | 5 | 0% | 2023-03-09 08:00 | 2023-03-15 17:00 | 17 | MLJ | BACKFILL | BACKFILL UTILITY | 31-2200 | 31-2200-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.5 | OGE | OGE | 01707 | 0 | 0 | OGE-01707 | Construction | Site Restoration | Construction.1.5.5 | Asphalt Repairs (Lot near OG5) --> OG Phase 4 | 5 | 5 | 0% | 2023-03-16 08:00 | 2023-03-22 17:00 | 17 | ASPHALT | ASPHALT | 0 | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.5 | OGE | OGE | 01708 | 0 | 0 | OGE-01708 | Construction | Site Restoration | Construction.1.5.5 | Excavate & Backfill for Ashpalt (Lot near OG10) --> OG Phase 4 | 15 | 15 | 0% | 2023-03-23 08:00 | 2023-04-12 17:00 | 17 | MLJ | EXCAVATION | ASHPALT | 31-2300 | 31-2300-OGE
Not Started | CI NYCHA Update #22.Construction.1.5.5 | OGE | OGE | 01709 | 0 | 0 | OGE-01709 | Construction | Site Restoration | Construction.1.5.5 | Asphalt and Linemarking (Lot near OG10) --> OG Phase 4 | 10 | 10 | 0% | 2023-04-13 08:00 | 2023-04-26 17:00 | 17 | ASPHALT | ASPHALT | 0 | 0 | 0-OGE
Not Started | CI NYCHA Update #22.Construction.5.6.5 | OGW | OGW | 01708 | 0 | 0 | OGW-01708 | Construction | Site Restoration | Construction.5.6.5 | Excavate & Backfill for Ashpalt --> OG Phase 3A | 15 | 15 | 0% | 2023-09-21 08:00 | 2023-10-11 17:00 | -110 | MLJ | EXCAVATION | ASHPALT | 31-2300 | 31-2300-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.5 | OGW | OGW | 01709 | 0 | 0 | OGW-01709 | Construction | Site Restoration | Construction.5.6.5 | Asphalt and Linemarking --> OG Phase 3A | 10 | 10 | 0% | 2023-10-12 08:00 | 2023-10-26 17:00 | -110 | ASPHALT | ASPHALT | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.8.3.5 | S8 | S8 | 01708 | 0 | 0 | S8-01708 | Construction | Site Restoration | Construction.8.3.5 | Excavate & Backfill for Ashpalt --> S8 Phase 6 | 15 | 15 | 0% | 2023-10-19 08:00 | 2023-11-09 17:00 | -139 | MLJ | EXCAVATION | ASHPALT | 31-2300 | 31-2300-S8
Not Started | CI NYCHA Update #22.Construction.8.3.5 | S8 | S8 | 01709 | 0 | 0 | S8-01709 | Construction | Site Restoration | Construction.8.3.5 | Asphalt and Linemarking --> S8 Phase 6 | 10 | 10 | 0% | 2023-11-13 08:00 | 2023-11-27 17:00 | -139 | ASPHALT | ASPHALT | 0 | 0 | 0-S8
In Progress | CI NYCHA Update #22.Construction.6 | NA | PAY | 01005 | 0 | 0 | PAY-01005 | Construction | Activities for Payment Purposes | Construction.6 | Project Management | 718 | 365 | 49% | 2020-07-13 17:00 | 2024-05-08 17:00 | -238 | MLJ | OVERHEAD | 0 | 99-1000 | 99-1000-NA
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01166 | 0 | 0 | SG6-01166 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Cure Concrete Pads 1st Floor --> SG6 | 7 | 0 | 100% | 2021-10-17 | 2021-10-24 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01166 | 0 | 0 | OG8-01166 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Cure Concrete Pads 1st Floor --> OG8 | 7 | 0 | 100% | 2022-04-02 08:00 | 2022-04-09 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01166 | 0 | 0 | OG9-01166 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Cure Concrete Pads 1st Floor --> OG9 - N/A | 7 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01166 | 0 | 0 | OG10-01166 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Cure Concrete Pads 1st Floor --> OG10 - N/A | 7 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01166 | 0 | 0 | SG7-01166 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Cure Concrete Pads 1st Floor --> SG7 - N/A | 7 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.8.2.7 | S8A | S8A | 01166 | 0 | 0 | S8A-01166 | Construction | Structural/Architectural Construction | Construction.8.2.7 | Cure Concrete Pads 1st Floor --> S8 (Addition) - N/A | 7 | 0 | 100% | 2020-12-25 | 2020-12-25 |  | 0 | 0 | 0 | 0 | 0-S8A
Completed | CI NYCHA Update #22.Construction.Mob | 0 | MOBE | 01010 | 0 | 0 | MOBE-01010 | Construction | Survey & Mobilization | Construction.Mob | Project Surveying | 333 | 0 | 100% | 2020-07-13 17:00 | 2022-11-01 |  | MLJ | 0 | 0 | 0 | 0-0
In Progress | CI NYCHA Update #22.Construction.Mob | NA | MOBE | 01015 | 0 | 0 | MOBE-01015 | Construction | Survey & Mobilization | Construction.Mob | Project Engineering | 718 | 365 | 49% | 2020-07-13 17:00 | 2024-05-08 17:00 | -238 | MLJ | OVERHEAD | 0 | 99-2000 | 99-2000-NA
In Progress | CI NYCHA Update #22.Construction.6 | NA | PAY | 01010 | 0 | 0 | PAY-01010 | Construction | Activities for Payment Purposes | Construction.6 | CPM - Monthly Updates | 718 | 365 | 49% | 2020-07-13 17:00 | 2024-05-08 17:00 | -238 | MLJ | OVERHEAD | 0 | 01-6100 | 01-6100-NA
In Progress | CI NYCHA Update #22.Construction.6 | NA | PAY | 01015 | 0 | 0 | PAY-01015 | Construction | Activities for Payment Purposes | Construction.6 | Field Office - Rent, Maintenance and Supplies | 718 | 365 | 49% | 2020-07-13 17:00 | 2024-05-08 17:00 | -238 | MLJ | OVERHEAD | 0 | 0 | 0-NA
In Progress | CI NYCHA Update #22.Construction.6 | NA | PAY | 01020 | 0 | 0 | PAY-01020 | Construction | Activities for Payment Purposes | Construction.6 | Yard - Maintenance | 718 | 365 | 49% | 2020-07-13 17:00 | 2024-05-08 17:00 | -238 | MLJ | OVERHEAD | 0 | 0 | 0-NA
In Progress | CI NYCHA Update #22.Construction.6 | NA | PAY | 01025 | 0 | 0 | PAY-01025 | Construction | Activities for Payment Purposes | Construction.6 | Progress Photos | 718 | 365 | 49% | 2020-07-13 17:00 | 2024-05-08 17:00 | -238 | MLJ | OVERHEAD | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.Construction.6 | SGN | PAY | 01030 | 0 | 0 | PAY-01030 | Construction | Activities for Payment Purposes | Construction.6 | Equipment Support for Site - SGN | 0 | 0 | 100% | 2021-05-25 | 2022-01-20 |  | 0 | 0 | 0 | 0 | 0-SGN
Completed | CI NYCHA Update #22.Construction.6 | SGS | PAY | 01035 | 0 | 0 | PAY-01035 | Construction | Activities for Payment Purposes | Construction.6 | Equipment Support for Site - SGS | 60 | 0 | 100% | 2022-01-01 | 2022-08-05 |  | MLJ | 0 | 0 | 0 | 0-SGS
In Progress | CI NYCHA Update #22.Construction.6 | OGE | PAY | 01040 | 0 | 0 | PAY-01040 | Construction | Activities for Payment Purposes | Construction.6 | Equipment Support for Site - OGE | 209 | 65 | 68% | 2022-03-02 | 2023-03-01 17:00 | -40 | MLJ | SITE SUPPORT | 0 | 99-8000 | 99-8000-OGE
Completed | CI NYCHA Update #22.Construction.6 | OGW | PAY | 01045 | 0 | 0 | PAY-01045 | Construction | Activities for Payment Purposes | Construction.6 | Equipment Support for Site - OGW | 1 | 0 | 100% | 2021-08-02 17:00 | 2022-03-16 |  | 0 | 0 | 0 | 0 | 0-OGW
In Progress | CI NYCHA Update #22.Construction.6 | S81 | PAY | 01050 | 0 | 0 | PAY-01050 | Construction | Activities for Payment Purposes | Construction.6 | Equipment Support for Site - S8 | 74 | 0 | 100% | 2022-05-11 | 2022-11-25 08:00 | -90 | MLJ | SITE SUPPORT | 0 | 99-8000 | 99-8000-S81
In Progress | CI NYCHA Update #22.Construction.6 | NA | PAY | 01060 | 0 | 0 | PAY-01060 | Construction | Activities for Payment Purposes | Construction.6 | HVAC Project Management/Site Supervision | 718 | 365 | 49% | 2020-07-13 17:00 | 2024-05-08 17:00 | -238 | WELKIN | 0 | 0 | 0 | 0-NA
In Progress | CI NYCHA Update #22.Construction.6 | NA | PAY | 01065 | 0 | 0 | PAY-01065 | Construction | Activities for Payment Purposes | Construction.6 | HVAC Scheduling | 639 | 115 | 82% | 2020-07-13 17:00 | 2023-05-10 17:00 | -60 | WELKIN | 0 | 0 | 0 | 0-NA
Not Started | CI NYCHA Update #22.Construction.2.4.7.6 | SG6 | SG6 | 02501 | 0 | 0 | SG6-02501 | Construction | Testing & Start-Up | Construction.2.4.7.6 | National Grid to Install Meter - SG6 | 1 | 1 | 0% | 2022-11-29 08:00 | 2022-11-29 17:00 | 78 | NATIONAL GRID | 0 | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.3.1.6 | OG8 | OG8 | 02701 | 0 | 0 | OG8-02701 | Construction | Testing & Start-Up | Construction.3.1.6 | National Grid to Install Meter - OG8 | 1 | 1 | 0% | 2023-04-05 08:00 | 2023-04-05 17:00 | 17 | NATIONAL GRID | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.5.4.6 | OG9 | OG9 | 02501 | 0 | 0 | OG9-02501 | Construction | Testing & Start-Up | Construction.5.4.6 | National Grid to Install Meter - OG9 | 1 | 1 | 0% | 2023-01-20 08:00 | 2023-01-20 17:00 | 69 | NATIONAL GRID | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.1.4.6 | OG10 | OG10 | 02501 | 0 | 0 | OG10-02501 | Construction | Testing & Start-Up | Construction.1.4.6 | National Grid to Install Meter - OG10 | 1 | 1 | 0% | 2023-04-13 08:00 | 2023-04-13 17:00 | 11 | NATIONAL GRID | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.4.4.5.6 | SG7 | SG7 | 02601 | 0 | 0 | SG7-02601 | Construction | Testing & Start-Up | Construction.4.4.5.6 | National Grid to Install Meter - SG7 | 1 | 1 | 0% | 2023-08-28 08:00 | 2023-08-28 17:00 | -89 | NATIONAL GRID | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.8.2.5.6 | S82 | S8A | 02501 | 0 | 0 | S8A-02501 | Construction | Testing & Start-Up | Construction.8.2.5.6 | National Grid to Install Meter - S8A | 1 | 1 | 0% | 2023-07-19 08:00 | 2023-07-19 17:00 | -57 | NATIONAL GRID | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.7.2.1 | SG6 | O&M | 01105 | 0 | 0 | O&M-01105 | Construction | Mechanical O&M Manuals | Construction.7.2.1 | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - SG6 | 10 | 10 | 0% | 2023-02-22 08:00 | 2023-03-07 17:00 | 58 | MLJ | TURNOVER | PLAYGROUND | NA | NA-SG6
Not Started | CI NYCHA Update #22.Construction.7.2.1 | SG4 | O&M | 01110 | 0 | 0 | O&M-01110 | Construction | Mechanical O&M Manuals | Construction.7.2.1 | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - SG4 | 10 | 10 | 0% | 2023-05-17 15:00 | 2023-06-01 15:00 | -3 | MLJ | TURNOVER | PLAYGROUND | NA | NA-SG4
Not Started | CI NYCHA Update #22.Construction.7.2.1 | SG5 | O&M | 01115 | 0 | 0 | O&M-01115 | Construction | Mechanical O&M Manuals | Construction.7.2.1 | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - SG5 | 10 | 10 | 0% | 2023-04-05 08:00 | 2023-04-18 17:00 | 28 | MLJ | TURNOVER | PLAYGROUND | NA | NA-SG5
Not Started | CI NYCHA Update #22.Construction.7.2.1 | OG8 | O&M | 01120 | 0 | 0 | O&M-01120 | Construction | Mechanical O&M Manuals | Construction.7.2.1 | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - OG8 | 10 | 10 | 0% | 2023-05-15 08:00 | 2023-05-26 17:00 | 0 | MLJ | TURNOVER | PLAYGROUND | NA | NA-OG8
Not Started | CI NYCHA Update #22.Construction.7.2.1 | OG4 | O&M | 01125 | 0 | 0 | O&M-01125 | Construction | Mechanical O&M Manuals | Construction.7.2.1 | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - OG4 | 10 | 10 | 0% | 2023-05-10 08:00 | 2023-05-23 17:00 | 3 | MLJ | TURNOVER | PLAYGROUND | NA | NA-OG4
Not Started | CI NYCHA Update #22.Construction.7.2.1 | OG5 | O&M | 01130 | 0 | 0 | O&M-01130 | Construction | Mechanical O&M Manuals | Construction.7.2.1 | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - OG5 | 10 | 10 | 0% | 2023-11-08 08:00 | 2023-11-22 17:00 | -122 | MLJ | TURNOVER | PLAYGROUND | NA | NA-OG5
Not Started | CI NYCHA Update #22.Construction.7.2.1 | OG9 | O&M | 01135 | 0 | 0 | O&M-01135 | Construction | Mechanical O&M Manuals | Construction.7.2.1 | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - OG9 | 10 | 10 | 0% | 2023-03-22 08:00 | 2023-04-04 17:00 | 38 | MLJ | TURNOVER | PLAYGROUND | NA | NA-OG9
Not Started | CI NYCHA Update #22.Construction.7.2.1 | OG2 | O&M | 01140 | 0 | 0 | O&M-01140 | Construction | Mechanical O&M Manuals | Construction.7.2.1 | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - OG2 | 10 | 10 | 0% | 2023-04-26 08:00 | 2023-05-09 17:00 | 13 | MLJ | TURNOVER | PLAYGROUND | NA | NA-OG2
Not Started | CI NYCHA Update #22.Construction.7.2.1 | OG3 | O&M | 01145 | 0 | 0 | O&M-01145 | Construction | Mechanical O&M Manuals | Construction.7.2.1 | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - OG3 | 10 | 10 | 0% | 2023-05-10 08:00 | 2023-05-23 17:00 | 3 | MLJ | TURNOVER | PLAYGROUND | NA | NA-OG3
Not Started | CI NYCHA Update #22.Construction.7.2.1 | OG10 | O&M | 01150 | 0 | 0 | O&M-01150 | Construction | Mechanical O&M Manuals | Construction.7.2.1 | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - OG10 | 10 | 10 | 0% | 2023-03-29 08:00 | 2023-04-11 17:00 | 33 | MLJ | TURNOVER | PLAYGROUND | NA | NA-OG10
Not Started | CI NYCHA Update #22.Construction.7.2.1 | OG1 | O&M | 01155 | 0 | 0 | O&M-01155 | Construction | Mechanical O&M Manuals | Construction.7.2.1 | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - OG1 | 10 | 10 | 0% | 2023-04-26 08:00 | 2023-05-09 17:00 | 13 | MLJ | TURNOVER | PLAYGROUND | NA | NA-OG1
Not Started | CI NYCHA Update #22.Construction.7.2.1 | OG6 | O&M | 01160 | 0 | 0 | O&M-01160 | Construction | Mechanical O&M Manuals | Construction.7.2.1 | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - OG6 | 10 | 10 | 0% | 2023-05-01 08:00 | 2023-05-12 17:00 | 10 | MLJ | TURNOVER | PLAYGROUND | NA | NA-OG6
Not Started | CI NYCHA Update #22.Construction.7.2.1 | SG7 | O&M | 01165 | 0 | 0 | O&M-01165 | Construction | Mechanical O&M Manuals | Construction.7.2.1 | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - SG7 | 10 | 10 | 0% | 2023-06-29 08:00 | 2023-07-13 17:00 | -32 | MLJ | TURNOVER | PLAYGROUND | NA | NA-SG7
Not Started | CI NYCHA Update #22.Construction.7.2.1 | SG1 | O&M | 01170 | 0 | 0 | O&M-01170 | Construction | Mechanical O&M Manuals | Construction.7.2.1 | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - SG1 | 10 | 10 | 0% | 2023-07-28 08:00 | 2023-08-10 17:00 | -52 | MLJ | TURNOVER | PLAYGROUND | NA | NA-SG1
Not Started | CI NYCHA Update #22.Construction.7.2.1 | SG2 | O&M | 01175 | 0 | 0 | O&M-01175 | Construction | Mechanical O&M Manuals | Construction.7.2.1 | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - SG2 | 10 | 10 | 0% | 2023-08-03 08:00 | 2023-08-16 17:00 | -56 | MLJ | TURNOVER | PLAYGROUND | NA | NA-SG2
Not Started | CI NYCHA Update #22.Construction.7.2.1 | SG3 | O&M | 01180 | 0 | 0 | O&M-01180 | Construction | Mechanical O&M Manuals | Construction.7.2.1 | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - SG3 | 10 | 10 | 0% | 2023-07-14 08:00 | 2023-07-27 17:00 | -42 | MLJ | TURNOVER | PLAYGROUND | NA | NA-SG3
Not Started | CI NYCHA Update #22.Construction.7.2.1 | S82 | O&M | 01185 | 0 | 0 | O&M-01185 | Construction | Mechanical O&M Manuals | Construction.7.2.1 | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - S8A | 10 | 10 | 0% | 2023-07-21 08:00 | 2023-08-03 17:00 | -47 | MLJ | TURNOVER | PLAYGROUND | NA | NA-S82
Not Started | CI NYCHA Update #22.Construction.7.2.1 | S81 | O&M | 01190 | 0 | 0 | O&M-01190 | Construction | Mechanical O&M Manuals | Construction.7.2.1 | Turnover Final Spray Shower Equipment O&M Manuals w/As-Built Dwgs - S8E | 10 | 10 | 0% | 2023-08-03 08:00 | 2023-08-16 17:00 | -56 | MLJ | TURNOVER | PLAYGROUND | NA | NA-S81
Not Started | CI NYCHA Update #22.Construction.7.2.2 | SG6 | O&M | 02205 | 0 | 0 | O&M-02205 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - SG6 | 10 | 10 | 0% | 2023-07-25 08:00 | 2023-08-07 17:00 | -49 | FSE | 0 | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.7.2.2 | SG4 | O&M | 02210 | 0 | 0 | O&M-02210 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - SG4 | 10 | 10 | 0% | 2023-04-25 08:00 | 2023-05-08 17:00 | 14 | FSE | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Construction.7.2.2 | SG5 | O&M | 02215 | 0 | 0 | O&M-02215 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - SG5 | 10 | 10 | 0% | 2023-04-25 08:00 | 2023-05-08 17:00 | 14 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Construction.7.2.2 | OG8 | O&M | 02220 | 0 | 0 | O&M-02220 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - OG8 | 10 | 10 | 0% | 2023-05-17 08:00 | 2023-05-31 17:00 | -2 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.7.2.2 | OG4 | O&M | 02225 | 0 | 0 | O&M-02225 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - OG4 | 10 | 10 | 0% | 2023-04-25 08:00 | 2023-05-08 17:00 | 14 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Construction.7.2.2 | OG5 | O&M | 02230 | 0 | 0 | O&M-02230 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - OG5 | 10 | 10 | 0% | 2023-04-25 08:00 | 2023-05-08 17:00 | 14 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Construction.7.2.2 | OG9 | O&M | 02235 | 0 | 0 | O&M-02235 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - OG9 | 10 | 10 | 0% | 2023-04-25 08:00 | 2023-05-08 17:00 | 14 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.7.2.2 | OG2 | O&M | 02240 | 0 | 0 | O&M-02240 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - OG2 | 10 | 10 | 0% | 2023-04-25 08:00 | 2023-05-08 17:00 | 14 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Construction.7.2.2 | OG3 | O&M | 02245 | 0 | 0 | O&M-02245 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - OG3 | 10 | 10 | 0% | 2023-04-25 08:00 | 2023-05-08 17:00 | 14 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Construction.7.2.2 | OG10 | O&M | 02250 | 0 | 0 | O&M-02250 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - OG10 | 10 | 10 | 0% | 2023-05-25 08:00 | 2023-06-08 17:00 | -8 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.7.2.2 | OG1 | O&M | 02255 | 0 | 0 | O&M-02255 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - OG1 | 10 | 10 | 0% | 2023-04-25 08:00 | 2023-05-08 17:00 | 14 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Construction.7.2.2 | OG6 | O&M | 02260 | 0 | 0 | O&M-02260 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - OG6 | 10 | 10 | 0% | 2023-06-19 08:00 | 2023-06-30 17:00 | -24 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Construction.7.2.2 | SG7 | O&M | 02265 | 0 | 0 | O&M-02265 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - SG7 | 10 | 10 | 0% | 2023-10-10 08:00 | 2023-10-24 17:00 | -103 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.7.2.2 | SG1 | O&M | 02270 | 0 | 0 | O&M-02270 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - SG1 | 10 | 10 | 0% | 2023-04-20 08:00 | 2023-05-03 17:00 | 17 | FSE | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Construction.7.2.2 | SG2 | O&M | 02275 | 0 | 0 | O&M-02275 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - SG2 | 10 | 10 | 0% | 2023-04-27 08:00 | 2023-05-10 17:00 | 12 | FSE | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Construction.7.2.2 | SG3 | O&M | 02280 | 0 | 0 | O&M-02280 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - SG3 | 10 | 10 | 0% | 2023-10-09 08:00 | 2023-10-23 17:00 | -102 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Construction.7.2.2 | S82 | O&M | 02285 | 0 | 0 | O&M-02285 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - S8A | 10 | 10 | 0% | 2023-08-02 08:00 | 2023-08-15 17:00 | -55 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.7.2.2 | S81 | O&M | 02290 | 0 | 0 | O&M-02290 | Construction | Electrical O&M Manuals | Construction.7.2.2 | Turnover Electrical Equipment O&M Manuals w/As-Built Dwgs - S8E | 10 | 10 | 0% | 2023-08-17 08:00 | 2023-08-30 17:00 | -66 | FSE | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 04000 | 0 | 0 | PERMIT-04000 | Procurement | Permits | Procurement.Div 1.Permits | NYCHA Provide Information for Dewatering Permit (Indemnity Letter) | 42 | 0 | 100% | 2020-09-23 | 2020-11-25 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG4 | PERMIT | 06015 | 0 | 0 | PERMIT-06015 | Procurement | Permits | Procurement.Div 1.Permits | File for Electrical Permits - SG4 | 10 | 0 | 100% | 2021-01-26 | 2021-02-01 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG4 | PERMIT | 06020 | 0 | 0 | PERMIT-06020 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Electrical Permits - SG4 | 20 | 0 | 100% | 2021-02-01 | 2021-02-03 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG5 | PERMIT | 06025 | 0 | 0 | PERMIT-06025 | Procurement | Permits | Procurement.Div 1.Permits | File for Electrical Permits - SG-5 | 10 | 0 | 100% | 2021-01-26 | 2021-02-01 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG5 | PERMIT | 06030 | 0 | 0 | PERMIT-06030 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Electrical Permits - SG-5 | 20 | 0 | 100% | 2021-02-01 | 2021-02-05 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG2 | PERMIT | 06050 | 0 | 0 | PERMIT-06050 | Procurement | Permits | Procurement.Div 1.Permits | File for Electrical Permits - OG-2 | 10 | 0 | 100% | 2021-02-01 | 2021-02-01 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG2 | PERMIT | 06055 | 0 | 0 | PERMIT-06055 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Electrical Permits - OG-2 | 20 | 0 | 100% | 2021-02-01 | 2021-02-12 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG3 | PERMIT | 06060 | 0 | 0 | PERMIT-06060 | Procurement | Permits | Procurement.Div 1.Permits | File for Electrical Permits - OG-3 | 10 | 0 | 100% | 2021-02-01 | 2021-02-01 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG3 | PERMIT | 06065 | 0 | 0 | PERMIT-06065 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Electrical Permits - OG-3 | 20 | 0 | 100% | 2021-02-01 | 2021-02-12 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG4 | PERMIT | 06075 | 0 | 0 | PERMIT-06075 | Procurement | Permits | Procurement.Div 1.Permits | File for Electrical Permits - OG-4 | 10 | 0 | 100% | 2021-01-25 | 2021-02-01 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG4 | PERMIT | 06080 | 0 | 0 | PERMIT-06080 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Electrical Permits - OG-4 | 20 | 0 | 100% | 2021-02-01 | 2021-02-10 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG8 | PERMIT | 06085 | 0 | 0 | PERMIT-06085 | Procurement | Permits | Procurement.Div 1.Permits | File for Electrical Permits - OG-8 | 10 | 0 | 100% | 2021-01-25 | 2021-02-03 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG8 | PERMIT | 06090 | 0 | 0 | PERMIT-06090 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Electrical Permits - OG-8 | 20 | 0 | 100% | 2021-02-03 | 2021-02-10 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG9 | PERMIT | 06095 | 0 | 0 | PERMIT-06095 | Procurement | Permits | Procurement.Div 1.Permits | File for Electrical Permits - OG-9 | 10 | 0 | 100% | 2021-02-01 | 2021-02-05 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG9 | PERMIT | 06100 | 0 | 0 | PERMIT-06100 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Electrical Permits - OG-9 | 20 | 0 | 100% | 2021-02-08 | 2021-02-12 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG1 | PERMIT | 06105 | 0 | 0 | PERMIT-06105 | Procurement | Permits | Procurement.Div 1.Permits | File for Electrical Permits - OG-1 | 10 | 0 | 100% | 2021-02-01 | 2021-02-05 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG1 | PERMIT | 06110 | 0 | 0 | PERMIT-06110 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Electrical Permits - OG-1 | 20 | 0 | 100% | 2021-02-08 | 2021-02-12 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG5 | PERMIT | 06120 | 0 | 0 | PERMIT-06120 | Procurement | Permits | Procurement.Div 1.Permits | File for Electrical Permits - OG-5 | 10 | 0 | 100% | 2021-02-01 | 2021-02-03 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG5 | PERMIT | 06125 | 0 | 0 | PERMIT-06125 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Electrical Permits - OG-5 | 20 | 0 | 100% | 2021-02-03 | 2021-02-10 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG6 | PERMIT | 06130 | 0 | 0 | PERMIT-06130 | Procurement | Permits | Procurement.Div 1.Permits | File for Electrical Permits - OG-6 | 10 | 0 | 100% | 2021-03-01 | 2021-03-05 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG6 | PERMIT | 06135 | 0 | 0 | PERMIT-06135 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Electrical Permits - OG-6 | 20 | 0 | 100% | 2021-03-05 | 2021-03-12 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG10 | PERMIT | 06140 | 0 | 0 | PERMIT-06140 | Procurement | Permits | Procurement.Div 1.Permits | File for Electrical Permits - OG-10 | 10 | 0 | 100% | 2021-03-15 | 2021-03-19 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG10 | PERMIT | 06145 | 0 | 0 | PERMIT-06145 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Electrical Permits - OG-10 | 20 | 0 | 100% | 2021-03-22 | 2021-03-29 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG1 | PERMIT | 06150 | 0 | 0 | PERMIT-06150 | Procurement | Permits | Procurement.Div 1.Permits | File for Electrical Permits - SG-1 | 10 | 0 | 100% | 2021-04-05 | 2021-04-09 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG1 | PERMIT | 06155 | 0 | 0 | PERMIT-06155 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Electrical Permits - SG-1 | 20 | 0 | 100% | 2021-04-09 | 2021-04-12 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG2 | PERMIT | 06160 | 0 | 0 | PERMIT-06160 | Procurement | Permits | Procurement.Div 1.Permits | File for Electrical Permits - SG-2 | 10 | 0 | 100% | 2021-04-05 | 2021-04-09 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG2 | PERMIT | 06165 | 0 | 0 | PERMIT-06165 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Electrical Permits - SG-2 | 20 | 0 | 100% | 2021-04-08 08:00 | 2021-04-12 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG3 | PERMIT | 06170 | 0 | 0 | PERMIT-06170 | Procurement | Permits | Procurement.Div 1.Permits | File for Electrical Permits - SG-3 | 10 | 0 | 100% | 2021-04-05 | 2021-04-09 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG3 | PERMIT | 06175 | 0 | 0 | PERMIT-06175 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Electrical Permits - SG-3 | 20 | 0 | 100% | 2021-04-12 | 2021-04-12 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG7 | PERMIT | 06180 | 0 | 0 | PERMIT-06180 | Procurement | Permits | Procurement.Div 1.Permits | File for Electrical Permits - SG-7 | 10 | 0 | 100% | 2021-04-12 | 2021-04-21 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG7 | PERMIT | 06185 | 0 | 0 | PERMIT-06185 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Electrical Permits - SG-7 | 20 | 0 | 100% | 2021-04-08 08:00 | 2021-04-22 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | S81 | PERMIT | 06190 | 0 | 0 | PERMIT-06190 | Procurement | Permits | Procurement.Div 1.Permits | File for Electrical Permits - S8E | 10 | 0 | 100% | 2021-05-25 08:00 | 2021-06-17 |  | 0 | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | S81 | PERMIT | 06195 | 0 | 0 | PERMIT-06195 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Electrical Permits - S8E | 20 | 0 | 100% | 2021-06-17 | 2021-06-17 |  | 0 | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | S82 | PERMIT | 06205 | 0 | 0 | PERMIT-06205 | Procurement | Permits | Procurement.Div 1.Permits | File for Electrical Permits - S8A | 10 | 0 | 100% | 2021-05-25 08:00 | 2021-06-17 |  | 0 | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | S82 | PERMIT | 06210 | 0 | 0 | PERMIT-06210 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Electrical Permits - S8A | 20 | 0 | 100% | 2021-06-17 | 2021-07-26 17:00 |  | 0 | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05505 | 0 | 0 | PERMIT-05505 | Procurement | Permits | Procurement.Div 1.Permits | File for Temporary Power Permits - Phase 1 | 10 | 0 | 100% | 2020-11-18 | 2020-11-20 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05510 | 0 | 0 | PERMIT-05510 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Temporary Power Permits - Phase 1 | 20 | 0 | 100% | 2020-11-23 | 2020-12-10 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05550 | 0 | 0 | PERMIT-05550 | Procurement | Permits | Procurement.Div 1.Permits | File for Temporary Power Permits - Remaining Phases | 10 | 0 | 100% | 2021-02-01 | 2021-02-26 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05555 | 0 | 0 | PERMIT-05555 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Temporary Power Permits - Remaining Phases | 5 | 0 | 100% | 2021-02-26 | 2021-02-26 |  | 0 | 0 | 0 | 0 | 0-0
Not Started | CI NYCHA Update #22.Interim Milestones.1 | SG6 | SG6 | BOILER | 0 | 0 | SG6-BOILER | Milestones | SG-6 Interim Building Milestones | Interim Milestones.1 | Boiler Commissioned - SG6 | 0 | 0 | 0% |  | 2023-05-16 17:00 | -28 | WELKIN | 0 | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Interim Milestones.1 | SG6 | SG6 | GENERATOR | 0 | 0 | SG6-GENERATOR | Milestones | SG-6 Interim Building Milestones | Interim Milestones.1 | Generator/Switch Gear Commissioned - SG6 | 0 | 0 | 0% |  | 2023-04-25 17:00 | -13 | FSE | 0 | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Interim Milestones.1 | SG6 | SG6 | HVAC | 0 | 0 | SG6-HVAC | Milestones | SG-6 Interim Building Milestones | Interim Milestones.1 | HVAC Commissioned - SG6 | 0 | 0 | 0% |  | 2022-12-22 17:00 | 71 | WELKIN | 0 | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Interim Milestones.1 | SG6 | SG6 | FA | 0 | 0 | SG6-FA | Milestones | SG-6 Interim Building Milestones | Interim Milestones.1 | Fire Alarm System Commissioned - SG6 | 0 | 0 | 0% |  | 2023-05-02 17:00 | -18 | FSE | 0 | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Interim Milestones.1 | SG6 | SG6 | GAS | 0 | 0 | SG6-GAS | Milestones | SG-6 Interim Building Milestones | Interim Milestones.1 | DOB Sign-off for Gas Work - SG6 | 0 | 0 | 0% |  | 2022-12-13 17:00 | 78 | MLJ | MILESTONE | 0 | NA | NA-SG6
Not Started | CI NYCHA Update #22.Interim Milestones.2 | SG4 | SG4 | GENERATOR | 0 | 0 | SG4-GENERATOR | Milestones | SG-4 Interim Building Milestones | Interim Milestones.2 | Generator/Switch Gear Commissioned - SG4 | 0 | 0 | 0% |  | 2023-05-05 17:00 | 5 | FSE | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Interim Milestones.2 | SG4 | SG4 | HVAC | 0 | 0 | SG4-HVAC | Milestones | SG-4 Interim Building Milestones | Interim Milestones.2 | HVAC Commissioned - SG4 | 0 | 0 | 0% |  | 2023-06-08 17:00 | -18 | WELKIN | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Interim Milestones.2 | SG4 | SG4 | FA | 0 | 0 | SG4-FA | Milestones | SG-4 Interim Building Milestones | Interim Milestones.2 | Fire Alarm System Commissioned - SG4 | 0 | 0 | 0% |  | 2023-05-12 17:00 | 0 | FSE | 0 | 0 | 0 | 0-SG4
Not Started | CI NYCHA Update #22.Interim Milestones.3 | SG5 | SG5 | GENERATOR | 0 | 0 | SG5-GENERATOR | Milestones | SG-5 Interim Building Milestones | Interim Milestones.3 | Generator/Switch Gear Commissioned - SG5 | 0 | 0 | 0% |  | 2023-05-25 17:00 | -9 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Interim Milestones.3 | SG5 | SG5 | HVAC | 0 | 0 | SG5-HVAC | Milestones | SG-5 Interim Building Milestones | Interim Milestones.3 | HVAC Commissioned - SG5 | 0 | 0 | 0% |  | 2023-07-11 17:00 | -40 | WELKIN | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Interim Milestones.3 | SG5 | SG5 | FA | 0 | 0 | SG5-FA | Milestones | SG-5 Interim Building Milestones | Interim Milestones.3 | Fire Alarm System Commissioned - SG5 | 0 | 0 | 0% |  | 2023-06-02 17:00 | -14 | FSE | 0 | 0 | 0 | 0-SG5
Not Started | CI NYCHA Update #22.Interim Milestones.4 | OG8 | OG8 | BOILER | 0 | 0 | OG8-BOILER | Milestones | OG-8 Interim Building Milestones | Interim Milestones.4 | Boiler Commissioned - OG8 | 0 | 0 | 0% |  | 2023-07-10 17:00 | -39 | WELKIN | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Interim Milestones.4 | OG8 | OG8 | GENERATOR | 0 | 0 | OG8-GENERATOR | Milestones | OG-8 Interim Building Milestones | Interim Milestones.4 | Generator/Switch Gear Commissioned - OG8 | 0 | 0 | 0% |  | 2023-08-01 17:00 | -55 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Interim Milestones.4 | OG8 | OG8 | HVAC | 0 | 0 | OG8-HVAC | Milestones | OG-8 Interim Building Milestones | Interim Milestones.4 | HVAC Commissioned - OG8 | 0 | 0 | 0% |  | 2023-08-01 17:00 | -55 | WELKIN | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Interim Milestones.4 | OG8 | OG8 | FA | 0 | 0 | OG8-FA | Milestones | OG-8 Interim Building Milestones | Interim Milestones.4 | Fire Alarm System Commissioned - OG8 | 0 | 0 | 0% |  | 2023-04-27 17:00 | 11 | FSE | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Interim Milestones.4 | OG8 | OG8 | GAS | 0 | 0 | OG8-GAS | Milestones | OG-8 Interim Building Milestones | Interim Milestones.4 | DOB Sign-off for Gas Work - OG8 | 0 | 0 | 0% |  | 2023-04-19 17:00 | 17 | MLJ | MILESTONE | 0 | NA | NA-OG8
Not Started | CI NYCHA Update #22.Interim Milestones.5 | OG4 | OG4 | GENERATOR | 0 | 0 | OG4-GENERATOR | Milestones | OG-4 Interim Building Milestones | Interim Milestones.5 | Generator/Switch Gear Commissioned - OG4 | 0 | 0 | 0% |  | 2023-05-02 17:00 | 8 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Interim Milestones.5 | OG4 | OG4 | HVAC | 0 | 0 | OG4-HVAC | Milestones | OG-4 Interim Building Milestones | Interim Milestones.5 | HVAC Commissioned - OG4 | 0 | 0 | 0% |  | 2023-08-01 17:00 | -55 | WELKIN | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Interim Milestones.5 | OG4 | OG4 | FA | 0 | 0 | OG4-FA | Milestones | OG-4 Interim Building Milestones | Interim Milestones.5 | Fire Alarm System Commissioned - OG4 | 0 | 0 | 0% |  | 2023-05-09 17:00 | 3 | FSE | 0 | 0 | 0 | 0-OG4
Not Started | CI NYCHA Update #22.Interim Milestones.6 | OG5 | OG5 | GENERATOR | 0 | 0 | OG5-GENERATOR | Milestones | OG-5 Interim Building Milestones | Interim Milestones.6 | Generator/Switch Gear Commissioned - OG5 | 0 | 0 | 0% |  | 2023-05-08 17:00 | 4 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Interim Milestones.6 | OG5 | OG5 | HVAC | 0 | 0 | OG5-HVAC | Milestones | OG-5 Interim Building Milestones | Interim Milestones.6 | HVAC Commissioned - OG5 | 0 | 0 | 0% |  | 2023-11-27 17:00 | -134 | WELKIN | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Interim Milestones.6 | OG5 | OG5 | FA | 0 | 0 | OG5-FA | Milestones | OG-5 Interim Building Milestones | Interim Milestones.6 | Fire Alarm System Commissioned - OG5 | 0 | 0 | 0% |  | 2023-05-15 17:00 | -1 | FSE | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.Interim Milestones.7 | OG9 | OG9 | GENERATOR | 0 | 0 | OG9-GENERATOR | Milestones | OG-9 Interim Building Milestones | Interim Milestones.7 | Generator/Switch Gear Commissioned - OG9 | 0 | 0 | 0% |  | 2023-12-18 17:00 | -149 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Interim Milestones.7 | OG9 | OG9 | HVAC | 0 | 0 | OG9-HVAC | Milestones | OG-9 Interim Building Milestones | Interim Milestones.7 | HVAC Commissioned - OG9 | 0 | 0 | 0% |  | 2023-12-18 17:00 | -149 | WELKIN | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Interim Milestones.7 | OG9 | OG9 | FA | 0 | 0 | OG9-FA | Milestones | OG-9 Interim Building Milestones | Interim Milestones.7 | Fire Alarm System Commissioned - OG9 | 0 | 0 | 0% |  | 2023-04-26 17:00 | 12 | FSE | 0 | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Interim Milestones.7 | OG9 | OG9 | GAS | 0 | 0 | OG9-GAS | Milestones | OG-9 Interim Building Milestones | Interim Milestones.7 | DOB Sign-off for Gas Work - OG9 | 0 | 0 | 0% |  | 2023-02-03 17:00 | 69 | MLJ | MILESTONE | 0 | NA | NA-OG9
Not Started | CI NYCHA Update #22.Interim Milestones.8 | OG3 | OG3 | GENERATOR | 0 | 0 | OG3-GENERATOR | Milestones | OG-3 Interim Building Milestones | Interim Milestones.8 | Generator/Switch Gear Commissioned - OG3 | 0 | 0 | 0% |  | 2023-05-02 17:00 | 8 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Interim Milestones.8 | OG3 | OG3 | HVAC | 0 | 0 | OG3-HVAC | Milestones | OG-3 Interim Building Milestones | Interim Milestones.8 | HVAC Commissioned - OG3 | 0 | 0 | 0% |  | 2023-12-18 17:00 | -149 | WELKIN | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Interim Milestones.8 | OG3 | OG3 | FA | 0 | 0 | OG3-FA | Milestones | OG-3 Interim Building Milestones | Interim Milestones.8 | Fire Alarm System Commissioned - OG3 | 0 | 0 | 0% |  | 2023-05-09 17:00 | 3 | FSE | 0 | 0 | 0 | 0-OG3
Not Started | CI NYCHA Update #22.Interim Milestones.9 | OG2 | OG2 | GENERATOR | 0 | 0 | OG2-GENERATOR | Milestones | OG-2 Interim Building Milestones | Interim Milestones.9 | Generator/Switch Gear Commissioned - OG2 | 0 | 0 | 0% |  | 2023-05-04 17:00 | 6 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Interim Milestones.9 | OG2 | OG2 | HVAC | 0 | 0 | OG2-HVAC | Milestones | OG-2 Interim Building Milestones | Interim Milestones.9 | HVAC Commissioned - OG2 | 0 | 0 | 0% |  | 2023-06-19 17:00 | -25 | WELKIN | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Interim Milestones.9 | OG2 | OG2 | FA | 0 | 0 | OG2-FA | Milestones | OG-2 Interim Building Milestones | Interim Milestones.9 | Fire Alarm System Commissioned - OG2 | 0 | 0 | 0% |  | 2023-05-11 17:00 | 1 | FSE | 0 | 0 | 0 | 0-OG2
Not Started | CI NYCHA Update #22.Interim Milestones.10 | OG10 | OG10 | GENERATOR | 0 | 0 | OG10-GENERATOR | Milestones | OG-10 Interim Building Milestones | Interim Milestones.10 | Generator/Switch Gear Commissioned - OG10 | 0 | 0 | 0% |  | 2023-04-25 17:00 | 13 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Interim Milestones.10 | OG10 | OG10 | HVAC | 0 | 0 | OG10-HVAC | Milestones | OG-10 Interim Building Milestones | Interim Milestones.10 | HVAC Commissioned - OG10 | 0 | 0 | 0% |  | 2024-01-10 17:00 | -164 | WELKIN | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Interim Milestones.10 | OG10 | OG10 | FA | 0 | 0 | OG10-FA | Milestones | OG-10 Interim Building Milestones | Interim Milestones.10 | Fire Alarm System Commissioned - OG10 | 0 | 0 | 0% |  | 2023-05-02 17:00 | 8 | FSE | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Interim Milestones.10 | OG10 | OG10 | GAS | 0 | 0 | OG10-GAS | Milestones | OG-10 Interim Building Milestones | Interim Milestones.10 | DOB Sign-off for Gas Work - OG10 | 0 | 0 | 0% |  | 2023-04-27 17:00 | 11 | MLJ | MILESTONE | 0 | NA | NA-OG10
Not Started | CI NYCHA Update #22.Interim Milestones.11 | OG6 | OG6 | GENERATOR | 0 | 0 | OG6-GENERATOR | Milestones | OG-6 Interim Building Milestones | Interim Milestones.11 | Generator/Switch Gear Commissioned - OG6 | 0 | 0 | 0% |  | 2023-06-02 17:00 | -14 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Interim Milestones.11 | OG6 | OG6 | HVAC | 0 | 0 | OG6-HVAC | Milestones | OG-6 Interim Building Milestones | Interim Milestones.11 | HVAC Commissioned - OG6 | 0 | 0 | 0% |  | 2024-01-04 17:00 | -160 | WELKIN | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Interim Milestones.11 | OG6 | OG6 | FA | 0 | 0 | OG6-FA | Milestones | OG-6 Interim Building Milestones | Interim Milestones.11 | Fire Alarm System Commissioned - OG6 | 0 | 0 | 0% |  | 2023-06-09 17:00 | -19 | FSE | 0 | 0 | 0 | 0-OG6
Not Started | CI NYCHA Update #22.Interim Milestones.12 | OG1 | OG1 | GENERATOR | 0 | 0 | OG1-GENERATOR | Milestones | OG-1 Interim Building Milestones | Interim Milestones.12 | Generator/Switch Gear Commissioned - OG1 | 0 | 0 | 0% |  | 2023-06-08 17:00 | -18 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Interim Milestones.12 | OG1 | OG1 | HVAC | 0 | 0 | OG1-HVAC | Milestones | OG-1 Interim Building Milestones | Interim Milestones.12 | HVAC Commissioned - OG1 | 0 | 0 | 0% |  | 2023-12-11 17:00 | -144 | WELKIN | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Interim Milestones.12 | OG1 | OG1 | FA | 0 | 0 | OG1-FA | Milestones | OG-1 Interim Building Milestones | Interim Milestones.12 | Fire Alarm System Commissioned - OG1 | 0 | 0 | 0% |  | 2023-06-15 17:00 | -23 | FSE | 0 | 0 | 0 | 0-OG1
Not Started | CI NYCHA Update #22.Interim Milestones.13 | SG7 | SG7 | GENERATOR | 0 | 0 | SG7-GENERATOR | Milestones | SG-7 Interim Building Milestones | Interim Milestones.13 | Generator/Switch Gear Commissioned - SG7 | 0 | 0 | 0% |  | 2023-09-25 17:00 | -98 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Interim Milestones.13 | SG7 | SG7 | HVAC | 0 | 0 | SG7-HVAC | Milestones | SG-7 Interim Building Milestones | Interim Milestones.13 | HVAC Commissioned - SG7 | 0 | 0 | 0% |  | 2023-10-03 17:00 | -104 | WELKIN | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Interim Milestones.13 | SG7 | SG7 | FA | 0 | 0 | SG7-FA | Milestones | SG-7 Interim Building Milestones | Interim Milestones.13 | Fire Alarm System Commissioned - SG7 | 0 | 0 | 0% |  | 2023-09-28 17:00 | -101 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Interim Milestones.13 | SG7 | SG7 | GAS | 0 | 0 | SG7-GAS | Milestones | SG-7 Interim Building Milestones | Interim Milestones.13 | DOB Sign-off for Gas Work - SG7 | 0 | 0 | 0% |  | 2023-09-12 17:00 | -89 | MLJ | MILESTONE | 0 | NA | NA-SG7
Not Started | CI NYCHA Update #22.Interim Milestones.14 | SG3 | SG3 | GENERATOR | 0 | 0 | SG3-GENERATOR | Milestones | SG-3 Interim Building Milestones | Interim Milestones.14 | Generator/Switch Gear Commissioned - SG3 | 0 | 0 | 0% |  | 2023-09-25 17:00 | -97 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Interim Milestones.14 | SG3 | SG3 | HVAC | 0 | 0 | SG3-HVAC | Milestones | SG-3 Interim Building Milestones | Interim Milestones.14 | HVAC Commissioned - SG3 | 0 | 0 | 0% |  | 2023-10-09 17:00 | -107 | WELKIN | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Interim Milestones.14 | SG3 | SG3 | FA | 0 | 0 | SG3-FA | Milestones | SG-3 Interim Building Milestones | Interim Milestones.14 | Fire Alarm System Commissioned - SG3 | 0 | 0 | 0% |  | 2023-10-02 17:00 | -102 | FSE | 0 | 0 | 0 | 0-SG3
Not Started | CI NYCHA Update #22.Interim Milestones.15 | SG1 | SG1 | GENERATOR | 0 | 0 | SG1-GENERATOR | Milestones | SG-1 Interim Building Milestones | Interim Milestones.15 | Generator/Switch Gear Commissioned - SG1 | 0 | 0 | 0% |  | 2023-09-15 17:00 | -90 | FSE | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Interim Milestones.15 | SG1 | SG1 | HVAC | 0 | 0 | SG1-HVAC | Milestones | SG-1 Interim Building Milestones | Interim Milestones.15 | HVAC Commissioned - SG1 | 0 | 0 | 0% |  | 2023-10-03 17:00 | -102 | WELKIN | 0 | 0 | 0 | 0-SG1
Not Started | CI NYCHA Update #22.Interim Milestones.16 | SG2 | SG2 | GENERATOR | 0 | 0 | SG2-GENERATOR | Milestones | SG-2 Interim Building Milestones | Interim Milestones.16 | Generator/Switch Gear Commissioned - SG2 | 0 | 0 | 0% |  | 2023-09-19 17:00 | -91 | FSE | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Interim Milestones.16 | SG2 | SG2 | HVAC | 0 | 0 | SG2-HVAC | Milestones | SG-2 Interim Building Milestones | Interim Milestones.16 | HVAC Commissioned - SG2 | 0 | 0 | 0% |  | 2023-10-03 17:00 | -101 | WELKIN | 0 | 0 | 0 | 0-SG2
Not Started | CI NYCHA Update #22.Interim Milestones.17 | S82 | S8A | GENERATOR | 0 | 0 | S8A-GENERATOR | Milestones | S-8 Interim Building Milestones | Interim Milestones.17 | Generator/Switch Gear Commissioned - S8A | 0 | 0 | 0% |  | 2023-07-18 17:00 | -46 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Interim Milestones.17 | S82 | S8A | HVAC | 0 | 0 | S8A-HVAC | Milestones | S-8 Interim Building Milestones | Interim Milestones.17 | HVAC Commissioned - S8A | 0 | 0 | 0% |  | 2023-08-01 17:00 | -56 | WELKIN | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Interim Milestones.17 | S82 | S8A | FA | 0 | 0 | S8A-FA | Milestones | S-8 Interim Building Milestones | Interim Milestones.17 | Fire Alarm System Commissioned - S8A | 0 | 0 | 0% |  | 2023-07-25 17:00 | -51 | FSE | 0 | 0 | 0 | 0-S82
Not Started | CI NYCHA Update #22.Interim Milestones.17 | S82 | S8A | GAS | 0 | 0 | S8A-GAS | Milestones | S-8 Interim Building Milestones | Interim Milestones.17 | DOB Sign-off for Gas Work - S8A | 0 | 0 | 0% |  | 2023-08-02 17:00 | -57 | MLJ | MILESTONE | 0 | NA | NA-S82
Not Started | CI NYCHA Update #22.Interim Milestones.18 | S81 | S8E | GENERATOR | 0 | 0 | S8E-GENERATOR | Milestones | S8-Existing Interim Building Milestones | Interim Milestones.18 | Generator/Switch Gear Commissioned - S8E | 0 | 0 | 0% |  | 2023-07-12 17:00 | -41 | FSE | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Interim Milestones.18 | S81 | S8E | HVAC | 0 | 0 | S8E-HVAC | Milestones | S8-Existing Interim Building Milestones | Interim Milestones.18 | HVAC Commissioned - S8E | 0 | 0 | 0% |  | 2023-07-26 17:00 | -51 | WELKIN | 0 | 0 | 0 | 0-S81
Not Started | CI NYCHA Update #22.Construction.2.4.7.6 | SG6 | SG6 | 02502 | 0 | 0 | SG6-02502 | Construction | Testing & Start-Up | Construction.2.4.7.6 | DOB Inspection and issue permit - SG6 | 10 | 10 | 0% | 2022-11-30 08:00 | 2022-12-13 17:00 | 78 | UNSURE | INSPECTION | INSPECTION | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.2.4.7.6 | SG6 | SG6 | 02503 | 0 | 0 | SG6-02503 | Construction | Testing & Start-Up | Construction.2.4.7.6 | National Grid Approval - SG6 | 10 | 10 | 0% | 2022-11-30 08:00 | 2022-12-13 17:00 | 78 | UNSURE | STARTUP | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.3.1.6 | OG8 | OG8 | 02702 | 0 | 0 | OG8-02702 | Construction | Testing & Start-Up | Construction.3.1.6 | DOB Inspection and issue permit - OG8 | 10 | 10 | 0% | 2023-04-06 08:00 | 2023-04-19 17:00 | 17 | UNSURE | INSPECTION | INSPECTION | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.6 | OG8 | OG8 | 02703 | 0 | 0 | OG8-02703 | Construction | Testing & Start-Up | Construction.3.1.6 | National Grid Approval - OG8 | 10 | 10 | 0% | 2023-04-06 08:00 | 2023-04-19 17:00 | 17 | UNSURE | STARTUP | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.5.4.6 | OG9 | OG9 | 02502 | 0 | 0 | OG9-02502 | Construction | Testing & Start-Up | Construction.5.4.6 | DOB Inspection and issue permit - OG9 | 10 | 10 | 0% | 2023-01-23 08:00 | 2023-02-03 17:00 | 69 | UNSURE | INSPECTION | INSPECTION | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.5.4.6 | OG9 | OG9 | 02503 | 0 | 0 | OG9-02503 | Construction | Testing & Start-Up | Construction.5.4.6 | National Grid Approval - OG9 | 10 | 10 | 0% | 2023-01-23 08:00 | 2023-02-03 17:00 | 69 | UNSURE | STARTUP | 0 | 0 | 0-OG9
Not Started | CI NYCHA Update #22.Construction.1.4.6 | OG10 | OG10 | 02502 | 0 | 0 | OG10-02502 | Construction | Testing & Start-Up | Construction.1.4.6 | DOB Inspection and issue permit - OG10 | 10 | 10 | 0% | 2023-04-14 08:00 | 2023-04-27 17:00 | 11 | UNSURE | INSPECTION | INSPECTION | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.1.4.6 | OG10 | OG10 | 02503 | 0 | 0 | OG10-02503 | Construction | Testing & Start-Up | Construction.1.4.6 | National Grid Approval - OG10 | 10 | 10 | 0% | 2023-04-14 08:00 | 2023-04-27 17:00 | 11 | UNSURE | STARTUP | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.4.4.5.6 | SG7 | SG7 | 02602 | 0 | 0 | SG7-02602 | Construction | Testing & Start-Up | Construction.4.4.5.6 | DOB Inspection and issue permit - SG7 | 10 | 10 | 0% | 2023-08-29 08:00 | 2023-09-12 17:00 | -89 | UNSURE | INSPECTION | INSPECTION | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.4.4.5.6 | SG7 | SG7 | 02603 | 0 | 0 | SG7-02603 | Construction | Testing & Start-Up | Construction.4.4.5.6 | National Grid Approval - SG7 | 10 | 10 | 0% | 2023-08-29 08:00 | 2023-09-12 17:00 | -89 | UNSURE | STARTUP | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.8.2.5.6 | S82 | S8A | 02502 | 0 | 0 | S8A-02502 | Construction | Testing & Start-Up | Construction.8.2.5.6 | DOB Inspection and issue permit - S8A | 10 | 10 | 0% | 2023-07-20 08:00 | 2023-08-02 17:00 | -57 | UNSURE | INSPECTION | INSPECTION | 0 | 0-S82
Not Started | CI NYCHA Update #22.Construction.8.2.5.6 | S82 | S8A | 02503 | 0 | 0 | S8A-02503 | Construction | Testing & Start-Up | Construction.8.2.5.6 | National Grid Approval - S8A | 10 | 10 | 0% | 2023-07-20 08:00 | 2023-08-02 17:00 | -57 | UNSURE | STARTUP | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 02000 | 0 | 0 | PERMIT-02000 | Procurement | Permits | Procurement.Div 1.Permits | Await Receipt of DPL1, CCD1 and TPP1 from NYCHA to Pull Fence Permit (Should have been at NTP) | 53 | 0 | 100% | 2020-07-13 | 2020-09-24 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG4 | PERMIT | 02015 | 0 | 0 | PERMIT-02015 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Fence Permit - SG-4 | 20 | 0 | 100% | 2020-09-28 | 2020-12-15 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG5 | PERMIT | 02020 | 0 | 0 | PERMIT-02020 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Fence Permit - SG-5 | 20 | 0 | 100% | 2020-09-28 | 2020-12-14 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG2 | PERMIT | 02025 | 0 | 0 | PERMIT-02025 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Fence Permit - OG-2 | 20 | 0 | 100% | 2020-09-28 | 2020-12-14 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG3 | PERMIT | 02030 | 0 | 0 | PERMIT-02030 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Fence Permit - OG-3 | 20 | 0 | 100% | 2020-09-28 | 2020-12-14 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG4 | PERMIT | 02035 | 0 | 0 | PERMIT-02035 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Fence Permit - OG-4 | 20 | 0 | 100% | 2020-09-28 | 2020-12-14 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG8 | PERMIT | 02040 | 0 | 0 | PERMIT-02040 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Fence Permit - OG-8 | 20 | 0 | 100% | 2020-09-28 | 2020-12-14 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG9 | PERMIT | 02045 | 0 | 0 | PERMIT-02045 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Fence Permit - OG-9 | 20 | 0 | 100% | 2020-09-28 | 2020-12-14 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG1 | PERMIT | 02050 | 0 | 0 | PERMIT-02050 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Fence Permit - OG-1 | 20 | 0 | 100% | 2020-09-28 | 2020-12-11 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG5 | PERMIT | 02055 | 0 | 0 | PERMIT-02055 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Fence Permit - OG-5 | 20 | 0 | 100% | 2020-09-28 | 2021-01-06 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG6 | PERMIT | 02060 | 0 | 0 | PERMIT-02060 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Fence Permit - OG-6 | 20 | 0 | 100% | 2020-09-28 | 2021-01-06 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG10 | PERMIT | 02065 | 0 | 0 | PERMIT-02065 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Fence Permit - OG-10 | 20 | 0 | 100% | 2020-09-28 | 2021-01-15 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG1 | PERMIT | 02070 | 0 | 0 | PERMIT-02070 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Fence Permit - SG-1 | 20 | 0 | 100% | 2020-09-28 | 2020-12-14 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG2 | PERMIT | 02075 | 0 | 0 | PERMIT-02075 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Fence Permit - SG-2 | 20 | 0 | 100% | 2020-09-28 | 2020-12-14 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG3 | PERMIT | 02080 | 0 | 0 | PERMIT-02080 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Fence Permit - SG-3 | 20 | 0 | 100% | 2020-09-28 | 2020-12-14 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG7 | PERMIT | 02085 | 0 | 0 | PERMIT-02085 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Fence Permit - SG-7 | 20 | 0 | 100% | 2020-09-28 | 2020-12-14 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | S81 | PERMIT | 02090 | 0 | 0 | PERMIT-02090 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Fence Permit - S8E | 20 | 0 | 100% | 2020-09-28 | 2020-12-14 |  | 0 | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | S82 | PERMIT | 02095 | 0 | 0 | PERMIT-02095 | Procurement | Permits | Procurement.Div 1.Permits | DOB Issue Fence Permit - S8A | 20 | 0 | 100% | 2020-09-28 | 2020-12-14 |  | 0 | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG6 | PERMIT | 02002 | 0 | 0 | PERMIT-02002 | Procurement | Permits | Procurement.Div 1.Permits | DOB Notifies MLJ of need for L2 Forms for OG5 & OG6 due to Previous Fine | 1 | 0 | 100% | 2020-12-11 | 2020-12-11 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG6 | PERMIT | 02003 | 0 | 0 | PERMIT-02003 | Procurement | Permits | Procurement.Div 1.Permits | NYCHA Provide L2 Forms for OG5 and OG6 | 5 | 0 | 100% | 2020-12-14 | 2020-12-31 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01860 | 0 | 0 | 0 | 01860 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Prepare & Submit Fence Subcontractor | 1 | 0 | 100% | 2020-07-13 | 2020-07-13 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Subcont | 0 | 01865 | 0 | 0 | 0 | 01865 | Procurement | Subcontractors & Vendors | Procurement.Div 1.Subcont | Review & Approve Fence Subcontractor | 10 | 0 | 100% | 2020-07-14 | 2021-08-02 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05000 | 0 | 0 | PERMIT-05000 | Procurement | Permits | Procurement.Div 1.Permits | Request NYCHA for Documentation for Demolition Permit Filing | 1 | 0 | 100% | 2020-09-16 08:00 | 2020-09-16 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05001 | 0 | 0 | PERMIT-05001 | Procurement | Permits | Procurement.Div 1.Permits | NYCHA Provide Notarized Letters, Notifications and Forms to MLJ for Demo Permit Application | 20 | 0 | 100% | 2020-11-25 08:00 | 2021-03-15 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05005 | 0 | 0 | PERMIT-05005 | Procurement | Permits | Procurement.Div 1.Permits | File for Demolition Permit (Requires forms from NYCHA) | 10 | 0 | 100% | 2021-03-16 | 2021-03-16 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01002 | 0 | 0 | SG6-01002 | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install SOE For Plumbing Shaft & Ftgs/Piers Below Water Table --> SG6 | 4 | 0 | 100% | 2021-03-26 | 2021-04-01 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Procurement.Div. 31 | 0 | 31205 | 0 | 0 | 0 | 31205 | Procurement | Div. 31 - Earthwork | Procurement.Div. 31 | Prepare & Submit Methods of Excavation | 20 | 0 | 100% | 2020-12-01 | 2020-12-18 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 31 | 0 | 31210 | 0 | 0 | 0 | 31210 | Procurement | Div. 31 - Earthwork | Procurement.Div. 31 | Review & Approve Methods of Excavation | 10 | 0 | 100% | 2020-12-21 | 2021-02-12 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Construction.3.1.7 | OG8 | OG8 | 01002 | 0 | 0 | OG8-01002 | Construction | Structural/Architectural Construction | Construction.3.1.7 | Install SOE For Plumbing Shaft & Ftgs/Piers Below Water Table --> OG8 | 5 | 0 | 100% | 2021-04-02 | 2021-04-06 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.5.4.7 | OG9 | OG9 | 01002 | 0 | 0 | OG9-01002 | Construction | Structural/Architectural Construction | Construction.5.4.7 | Install SOE For Plumbing Shaft & Ftgs/Piers Below Water Table --> OG9 | 5 | 0 | 100% | 2021-07-07 | 2021-07-09 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01005 | 0 | 0 | DELAY-01005 | Delays | Project Delays | 19 | Site closure due to shooting - January 8, 2021 | 1 | 0 | 100% | 2021-01-08 | 2021-01-08 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01010 | 0 | 0 | DELAY-01010 | Delays | Project Delays | 19 | Site closure due to shooting - January 19 - 22, 2021 | 4 | 0 | 100% | 2021-01-19 | 2021-01-22 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | SG4 | DELAY | 01050 | 0 | 0 | DELAY-01050 | Delays | Project Delays | 19 | Basement not in a suitable condition to commence work - SG4 | 0 | 0 | 100% | 2020-07-13 | 2021-01-12 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.19 | SG5 | DELAY | 01055 | 0 | 0 | DELAY-01055 | Delays | Project Delays | 19 | Basement not in a suitable condition to commence work - SG5 | 0 | 0 | 100% | 2020-07-13 08:00 | 2021-04-02 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.19 | OG4 | DELAY | 01060 | 0 | 0 | DELAY-01060 | Delays | Project Delays | 19 | Basement not in a suitable condition to commence work - OG4 | 160 | 0 | 100% | 2020-07-13 08:00 | 2021-05-18 17:00 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.19 | OG5 | DELAY | 01065 | 0 | 0 | DELAY-01065 | Delays | Project Delays | 19 | Basement not in a suitable condition to commence work - OG5 | 160 | 0 | 100% | 2020-07-13 08:00 | 2021-10-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.19 | OG3 | DELAY | 01070 | 0 | 0 | DELAY-01070 | Delays | Project Delays | 19 | Basement not in a suitable condition to commence work - OG3 | 160 | 0 | 100% | 2020-07-13 08:00 | 2022-02-28 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.19 | OG2 | DELAY | 01075 | 0 | 0 | DELAY-01075 | Delays | Project Delays | 19 | Basement not in a suitable condition to commence work - OG2 | 0 | 0 | 100% | 2020-07-13 08:00 | 2021-05-17 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.19 | OG6 | DELAY | 01080 | 0 | 0 | DELAY-01080 | Delays | Project Delays | 19 | Basement not in a suitable condition to commence work - OG6 | 146 | 0 | 100% | 2020-07-13 08:00 | 2021-02-12 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.19 | OG1 | DELAY | 01085 | 0 | 0 | DELAY-01085 | Delays | Project Delays | 19 | Basement not in a suitable condition to commence work - OG1 | 146 | 0 | 100% | 2020-07-13 08:00 | 2021-02-12 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.19 | SG3 | DELAY | 01090 | 0 | 0 | DELAY-01090 | Delays | Project Delays | 19 | Basement not in a suitable condition to commence work - SG3 | 0 | 0 | 100% | 2020-07-13 08:00 | 2022-09-30 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.19 | SG1 | DELAY | 01095 | 0 | 0 | DELAY-01095 | Delays | Project Delays | 19 | Basement not in a suitable condition to commence work - SG1 | 150 | 0 | 100% | 2020-07-13 08:00 | 2021-02-19 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.19 | SG2 | DELAY | 01100 | 0 | 0 | DELAY-01100 | Delays | Project Delays | 19 | Basement not in a suitable condition to commence work - SG2 | 0 | 0 | 100% | 2020-07-13 08:00 | 2021-05-18 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.19 | S81 | DELAY | 01105 | 0 | 0 | DELAY-01105 | Delays | Project Delays | 19 | Basement not in a suitable condition to commence work - S8E | 0 | 0 | 100% | 2020-07-13 08:00 | 2021-03-25 |  | 0 | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01215 | 0 | 0 | DELAY-01215 | Delays | Project Delays | 19 | Redesign Site Fencing due to Conflict with Specifications | 50 | 0 | 100% | 2020-11-11 | 2021-02-08 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01205 | 0 | 0 | DELAY-01205 | Delays | Project Delays | 19 | RFI #152 - Temp Site Fencing Design Discrepency - Submit | 1 | 0 | 100% | 2020-11-03 | 2020-11-03 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01210 | 0 | 0 | DELAY-01210 | Delays | Project Delays | 19 | RFI #152 - Temp Site Fencing Design Discrepency - Response | 5 | 0 | 100% | 2020-11-04 | 2020-11-10 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG5 | PERMIT | 07015 | 0 | 0 | PERMIT-07015 | Procurement | Permits | Procurement.Div 1.Permits | File for DEP Asbestos Control Program (ACP) - SG5 | 10 | 0 | 100% | 2020-09-04 | 2020-10-06 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG5 | PERMIT | 07020 | 0 | 0 | PERMIT-07020 | Procurement | Permits | Procurement.Div 1.Permits | DEP Issue Asbestos Control Program (ACP) Permit - SG5 | 20 | 0 | 100% | 2020-10-07 | 2020-10-26 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG2 | PERMIT | 07025 | 0 | 0 | PERMIT-07025 | Procurement | Permits | Procurement.Div 1.Permits | File for DEP Asbestos Control Program (ACP) - OG2 | 10 | 0 | 100% | 2020-09-04 | 2020-10-06 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG2 | PERMIT | 07030 | 0 | 0 | PERMIT-07030 | Procurement | Permits | Procurement.Div 1.Permits | DEP Issue Asbestos Control Program (ACP) Permit - OG2 | 20 | 0 | 100% | 2020-10-07 | 2020-11-19 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG3 | PERMIT | 07035 | 0 | 0 | PERMIT-07035 | Procurement | Permits | Procurement.Div 1.Permits | File for DEP Asbestos Control Program (ACP) - OG3 | 10 | 0 | 100% | 2020-09-04 | 2020-10-06 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG3 | PERMIT | 07040 | 0 | 0 | PERMIT-07040 | Procurement | Permits | Procurement.Div 1.Permits | DEP Issue Asbestos Control Program (ACP) Permit - OG3 | 20 | 0 | 100% | 2020-10-07 | 2020-10-15 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG4 | PERMIT | 07045 | 0 | 0 | PERMIT-07045 | Procurement | Permits | Procurement.Div 1.Permits | File for DEP Asbestos Control Program (ACP) - OG4 | 10 | 0 | 100% | 2020-09-04 | 2020-10-06 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG4 | PERMIT | 07050 | 0 | 0 | PERMIT-07050 | Procurement | Permits | Procurement.Div 1.Permits | DEP Issue Asbestos Control Program (ACP) Permit - OG4 | 20 | 0 | 100% | 2020-10-07 | 2020-11-19 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG5 | PERMIT | 07055 | 0 | 0 | PERMIT-07055 | Procurement | Permits | Procurement.Div 1.Permits | File for DEP Asbestos Control Program (ACP) - OG5 | 10 | 0 | 100% | 2020-09-04 | 2020-10-06 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG5 | PERMIT | 07060 | 0 | 0 | PERMIT-07060 | Procurement | Permits | Procurement.Div 1.Permits | DEP Issue Asbestos Control Program (ACP) Permit - OG5 | 20 | 0 | 100% | 2020-10-07 | 2020-11-17 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG6 | PERMIT | 07065 | 0 | 0 | PERMIT-07065 | Procurement | Permits | Procurement.Div 1.Permits | File for DEP Asbestos Control Program (ACP) - OG6 | 10 | 0 | 100% | 2020-09-04 | 2020-10-06 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG6 | PERMIT | 07070 | 0 | 0 | PERMIT-07070 | Procurement | Permits | Procurement.Div 1.Permits | DEP Issue Asbestos Control Program (ACP) Permit - OG6 | 20 | 0 | 100% | 2020-10-07 | 2020-11-10 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG1 | PERMIT | 07075 | 0 | 0 | PERMIT-07075 | Procurement | Permits | Procurement.Div 1.Permits | File for DEP Asbestos Control Program (ACP) - OG1 | 10 | 0 | 100% | 2020-09-04 | 2020-10-06 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | OG1 | PERMIT | 07080 | 0 | 0 | PERMIT-07080 | Procurement | Permits | Procurement.Div 1.Permits | DEP Issue Asbestos Control Program (ACP) Permit - OG1 | 20 | 0 | 100% | 2020-10-07 | 2020-11-06 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG3 | PERMIT | 07085 | 0 | 0 | PERMIT-07085 | Procurement | Permits | Procurement.Div 1.Permits | File for DEP Asbestos Control Program (ACP) - SG3 | 10 | 0 | 100% | 2021-02-05 08:00 | 2021-02-15 17:00 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG3 | PERMIT | 07090 | 0 | 0 | PERMIT-07090 | Procurement | Permits | Procurement.Div 1.Permits | DEP Issue Asbestos Control Program (ACP) Permit - SG3 | 20 | 0 | 100% | 2021-04-30 | 2021-05-14 17:00 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG1 | PERMIT | 07095 | 0 | 0 | PERMIT-07095 | Procurement | Permits | Procurement.Div 1.Permits | File for DEP Asbestos Control Program (ACP) - SG1 | 10 | 0 | 100% | 2021-02-05 08:00 | 2021-02-15 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG1 | PERMIT | 07100 | 0 | 0 | PERMIT-07100 | Procurement | Permits | Procurement.Div 1.Permits | DEP Issue Asbestos Control Program (ACP) Permit - SG1 | 20 | 0 | 100% | 2021-04-30 | 2021-05-14 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG2 | PERMIT | 07105 | 0 | 0 | PERMIT-07105 | Procurement | Permits | Procurement.Div 1.Permits | File for DEP Asbestos Control Program (ACP) - SG2 | 10 | 0 | 100% | 2021-02-05 08:00 | 2021-02-15 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | SG2 | PERMIT | 07110 | 0 | 0 | PERMIT-07110 | Procurement | Permits | Procurement.Div 1.Permits | DEP Issue Asbestos Control Program (ACP) Permit - SG2 | 20 | 0 | 100% | 2021-04-30 | 2021-05-14 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | S81 | PERMIT | 07115 | 0 | 0 | PERMIT-07115 | Procurement | Permits | Procurement.Div 1.Permits | File for DEP Asbestos Control Program (ACP) - S8E | 10 | 0 | 100% | 2021-02-05 08:00 | 2021-02-15 17:00 |  | 0 | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | S81 | PERMIT | 07120 | 0 | 0 | PERMIT-07120 | Procurement | Permits | Procurement.Div 1.Permits | DEP Issue Asbestos Control Program (ACP) Permit - S8E | 20 | 0 | 100% | 2022-02-16 08:00 | 2022-04-20 |  | 0 | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.Construction.1.5.Removals1 | OGE | OGE | 01007 | 0 | 0 | OGE-01007 | Construction | Site Protection & Removals | Construction.1.5.Removals1 | Install Site Fencing - O'Dwyer Gardens - East - @ OG10 & OG7 Only | 10 | 0 | 100% | 2021-02-24 | 2021-02-26 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Construction.5.6.Removals1 | OGW | OGW | 01006 | 0 | 0 | OGW-01006 | Construction | Site Protection & Removals | Construction.5.6.Removals1 | Install Site Fencing - O'Dwyer Gardens - West (Central) | 5 | 0 | 100% | 2022-02-10 | 2022-02-15 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.6.Removals1 | OGW | OGW | 01007 | 0 | 0 | OGW-01007 | Construction | Site Protection & Removals | Construction.5.6.Removals1 | Clear & Grub and Demo Playground (Central) | 5 | 0 | 100% | 2022-02-16 | 2022-02-21 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 03999 | 0 | 0 | PERMIT-03999 | Procurement | Permits | Procurement.Div 1.Permits | Request Indemnity Letter from NYCHA for Dewatering Permit | 1 | 0 | 100% | 2020-09-23 | 2020-09-23 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Construction.2.4.7.5 | SG6 | SG6 | 03000 | 0 | 0 | SG6-03000 | Construction | Foundation/Plumbing Shaft | Construction.2.4.7.5 | Rough-In Mechanical Piping & Appurtenances - Plumbing Shaft | 5 | 0 | 100% | 2022-03-23 | 2022-05-31 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.3.1.8.4 | OG8 | OG8 | 03000 | 0 | 0 | OG8-03000 | Construction | Foundation | Construction.3.1.8.4 | Rough-In Mechanical Piping & Appurtenances - Plumbing Shaft | 5 | 0 | 100% | 2022-08-01 08:00 | 2022-09-26 12:00 |  | WELKIN | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.5.4.5.4 | OG9 | OG9 | 03000 | 0 | 0 | OG9-03000 | Construction | Foundation | Construction.5.4.5.4 | Rough-In Mechanical Piping & Appurtenances - Plumbing Shaft | 5 | 0 | 100% | 2022-08-01 08:00 | 2022-10-25 |  | WELKIN | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Construction.1.4.5.4 | OG10 | OG10 | 03000 | 0 | 0 | OG10-03000 | Construction | Foundation | Construction.1.4.5.4 | Rough-In Mechanical Piping & Appurtenances - Plumbing Shaft | 5 | 0 | 100% | 2022-07-25 08:00 | 2022-09-24 |  | WELKIN | 0 | 0 | 0 | 0-OG10
Not Started | CI NYCHA Update #22.Construction.4.4.5.4 | SG7 | SG7 | 03000 | 0 | 0 | SG7-03000 | Construction | Foundation | Construction.4.4.5.4 | Rough-In Mechanical Piping & Appurtenances - Plumbing Shaft | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | -74 | WELKIN | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.Construction.8.2.5.4 | S82 | S8A | 03000 | 0 | 0 | S8A-03000 | Construction | Foundation | Construction.8.2.5.4 | Rough-In Mechanical Piping & Appurtenances - Plumbing Shaft | 5 | 5 | 0% | 2022-12-16 08:00 | 2022-12-22 17:00 | -49 | WELKIN | 0 | 0 | 0 | 0-S82
Completed | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 03132 | 0 | 0 | SG6-03132 | Construction | 1st Floor | Construction.2.4.7.1 | Install and terminate wires - FOT Controls - 1st Floor | 10 | 0 | 100% | 2022-08-08 08:00 | 2022-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
In Progress | CI NYCHA Update #22.Construction.2.4.7.2 | SG6 | SG6 | 03232 | 0 | 0 | SG6-03232 | Construction | 2nd Floor | Construction.2.4.7.2 | Install & Terminate Wires for Boiler Controls - 2nd Floor | 10 | 2 | 85% | 2022-08-22 08:00 | 2022-11-28 12:00 | -14 | MEP | 0 | 0 | 0 | 0-SG6
Not Started | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 03132 | 0 | 0 | OG8-03132 | Construction | 1st Floor | Construction.3.1.8.1 | Install Wire & Terminate FOT Controls - 1st Floor | 20 | 20 | 0% | 2022-12-19 08:00 | 2023-01-18 17:00 | -43 | MEP | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.3.1.8.2 | OG8 | OG8 | 03232 | 0 | 0 | OG8-03232 | Construction | 2nd Floor | Construction.3.1.8.2 | Install Wire & Terminate for Boiler Controls - 2nd Floor | 20 | 20 | 0% | 2023-01-19 08:00 | 2023-02-15 17:00 | -65 | MEP | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 03108 | 0 | 0 | SG6-03108 | Construction | 1st Floor | Construction.2.4.7.1 | Install Ductwork - 1st Floor | 5 | 0 | 100% | 2022-01-19 | 2022-01-28 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.2 | SG6 | SG6 | 03208 | 0 | 0 | SG6-03208 | Construction | 2nd Floor | Construction.2.4.7.2 | Install Ductwork - 2nd Floor | 5 | 0 | 100% | 2022-02-04 | 2022-02-18 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 03305 | 0 | 0 | SG6-03305 | Construction | Roof | Construction.2.4.7.3 | Install Ductwork & Appurtenances - Roof - N/A | 4 | 0 | 100% | 2021-02-01 | 2021-02-01 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.7.3 | SG6 | SG6 | 03310 | 0 | 0 | SG6-03310 | Construction | Roof | Construction.2.4.7.3 | Install & Connect Exhaust Fans - Roof - N/A | 6 | 0 | 100% | 2021-02-01 | 2021-02-01 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01002a | 0 | 0 | SG6-01002a | Construction | Structural/Architectural Construction | Construction.2.4.4 | Excavate High Level & Lagging | 5 | 0 | 100% | 2021-02-25 | 2021-03-11 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.2.4.4 | SG6 | SG6 | 01002b | 0 | 0 | SG6-01002b | Construction | Structural/Architectural Construction | Construction.2.4.4 | Install Sheet Piles | 3 | 0 | 100% | 2021-03-11 | 2021-03-30 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.Construction.3.2 | OGP1 | SURV | OGP1 | E | 01001 | SURV-OGP1-E-01001 | Construction | Mobilization & Survey | Construction.3.2 | Cleaning & Pipe Repairs (Disputed Work) | 5 | 0 | 100% | 2022-09-01 | 2022-09-03 |  | 0 | 0 | 0 | 0 | 0-OGP1
Completed | CI NYCHA Update #22.Construction.5.1 | OGW | SURV | OGW | E | 01001 | SURV-OGW-E-01001 | Construction | Mobilization & Survey | Construction.5.1 | Cleaning & Pipe Repairs (Disputed Work) - OG-3 | 5 | 0 | 100% | 2022-09-01 08:00 | 2022-09-01 17:00 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.5.1 | OGW | SURV | OGW | E | 01016 | SURV-OGW-E-01016 | Construction | Mobilization & Survey | Construction.5.1 | Conduct Electrical Site Survey - O'Dwyer Garden - Part 2 (OG-2) | 15 | 0 | 100% | 2020-09-08 | 2021-06-08 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Construction.4.1 | SGS | SURV | SGS | E | 01031 | SURV-SGS-E-01031 | Construction | Mobilization & Survey | Construction.4.1 | Conduct Electrical Site Survey - Surfside Gardens South (SG-2) | 10 | 0 | 100% | 2021-06-01 | 2021-07-21 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Construction.4.1 | SGS | SURV | SGS | E | 01032 | SURV-SGS-E-01032 | Construction | Mobilization & Survey | Construction.4.1 | Conduct Electrical Site Survey - Surfside Gardens South (SG-3) | 10 | 0 | 100% | 2021-06-01 | 2021-09-17 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.19 | SG6 | DELAY | 01305 | 0 | 0 | DELAY-01305 | Delays | Project Delays | 19 | DELAY - Discrepancies between Internal and External MEP Drawings - SG6 (RFI #135) | 128 | 0 | 100% | 2020-09-01 | 2021-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.19 | SG4 | DELAY | 01310 | 0 | 0 | DELAY-01310 | Delays | Project Delays | 19 | DELAY - Discrepancies between Internal and External MEP Drawings - SG4 | 128 | 0 | 100% | 2020-09-01 | 2021-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.19 | SG5 | DELAY | 01315 | 0 | 0 | DELAY-01315 | Delays | Project Delays | 19 | DELAY - Discrepancies between Internal and External MEP Drawings - SG5 | 128 | 0 | 100% | 2020-09-01 | 2021-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.19 | OG8 | DELAY | 01320 | 0 | 0 | DELAY-01320 | Delays | Project Delays | 19 | DELAY - Discrepancies between Internal and External MEP Drawings - OG8 (RFI 92, 111) | 22 | 0 | 100% | 2021-02-23 | 2021-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.19 | OG5 | DELAY | 01325 | 0 | 0 | DELAY-01325 | Delays | Project Delays | 19 | DELAY - Discrepancies between Internal and External MEP Drawings - OG5 (RFI 92, 111) | 22 | 0 | 100% | 2021-02-23 | 2021-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.19 | OG4 | DELAY | 01330 | 0 | 0 | DELAY-01330 | Delays | Project Delays | 19 | DELAY - Discrepancies between Internal and External MEP Drawings - OG4 | 22 | 0 | 100% | 2021-02-23 | 2021-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.19 | OG9 | DELAY | 01335 | 0 | 0 | DELAY-01335 | Delays | Project Delays | 19 | DELAY - Discrepancies between Internal and External MEP Drawings - OG9 (RFI 92) | 32 | 0 | 100% | 2021-02-23 | 2021-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.19 | OG3 | DELAY | 01340 | 0 | 0 | DELAY-01340 | Delays | Project Delays | 19 | DELAY - Discrepancies between Internal and External MEP Drawings - OG3 | 32 | 0 | 100% | 2021-02-23 | 2021-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.19 | OG2 | DELAY | 01345 | 0 | 0 | DELAY-01345 | Delays | Project Delays | 19 | DELAY - Discrepancies between Internal and External MEP Drawings - OG2 (RFI 92) | 32 | 0 | 100% | 2021-02-23 | 2021-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.19 | OG10 | DELAY | 01350 | 0 | 0 | DELAY-01350 | Delays | Project Delays | 19 | DELAY - Discrepancies between Internal and External MEP Drawings - OG10 | 37 | 0 | 100% | 2021-02-16 | 2021-09-14 17:00 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.19 | OG6 | DELAY | 01355 | 0 | 0 | DELAY-01355 | Delays | Project Delays | 19 | DELAY - Discrepancies between Internal and External MEP Drawings - OG6 | 37 | 0 | 100% | 2021-02-16 | 2021-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.19 | OG1 | DELAY | 01360 | 0 | 0 | DELAY-01360 | Delays | Project Delays | 19 | DELAY - Discrepancies between Internal and External MEP Drawings - OG1 | 37 | 0 | 100% | 2021-02-16 | 2021-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.19 | SG7 | DELAY | 01365 | 0 | 0 | DELAY-01365 | Delays | Project Delays | 19 | DELAY - MEP Discrepancies - SG7 | 37 | 0 | 100% | 2021-02-23 | 2022-03-24 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.19 | SG3 | DELAY | 01370 | 0 | 0 | DELAY-01370 | Delays | Project Delays | 19 | DELAY - MEP Discrepancies - SG3 | 32 | 0 | 100% | 2021-02-23 | 2022-03-24 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.19 | SG1 | DELAY | 01375 | 0 | 0 | DELAY-01375 | Delays | Project Delays | 19 | DELAY - MEP Discrepancies - SG1 | 32 | 0 | 100% | 2021-02-23 | 2022-03-24 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.19 | SG2 | DELAY | 01380 | 0 | 0 | DELAY-01380 | Delays | Project Delays | 19 | DELAY - MEP Discrepancies - SG2 | 32 | 0 | 100% | 2021-02-23 | 2022-03-24 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.Construction.1.4.7 | OG10 | OG10 | 01019 | 0 | 0 | OG10-01019 | Construction | Structural/Architectural Construction | Construction.1.4.7 | Install Sheeting/SOE --> OG10 | 10 | 0 | 100% | 2021-06-30 | 2021-07-06 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.19 | OG8 | DELAY | 01405 | 0 | 0 | DELAY-01405 | Delays | Project Delays | 19 | DELAY - OG8 Obstructions in Ground | 35 | 0 | 100% | 2021-04-07 | 2021-06-11 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01410 | 0 | 0 | DELAY-01410 | Delays | Project Delays | 19 | DELAY - Asbestos Abatement Additional Review and Property Management Coordination | 20 | 0 | 100% | 2021-05-07 | 2021-06-11 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01415 | 0 | 0 | DELAY-01415 | Delays | Project Delays | 19 | DELAY - Paint Removal Additional Review and Property Management Coordination (Notified by E-Mail) | 22 | 0 | 100% | 2021-05-07 | 2021-06-11 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | 0 | CO007 | 01005 | 0 | 0 | CO007-01005 | Change Order | Project Change Orders | 1 | Submit RFI 116 - Boiler Accessories | 1 | 0 | 100% | 2020-09-25 | 2020-09-25 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | 0 | CO007 | 01010 | 0 | 0 | CO007-01010 | Change Order | Project Change Orders | 1 | Response RFI 116 - Boiler Accessories | 5 | 0 | 100% | 2020-09-28 | 2020-10-12 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | 0 | CO007 | 01015 | 0 | 0 | CO007-01015 | Change Order | Project Change Orders | 1 | MLJ Await Receipt of Change Order #7 | 150 | 0 | 100% | 2020-10-13 08:00 | 2022-03-15 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | 0 | CO007 | 01020 | 0 | 0 | CO007-01020 | Change Order | Project Change Orders | 1 | Prep/Submit Boiler Accessories | 20 | 0 | 100% | 2022-03-16 | 2022-03-25 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | 0 | CO007 | 01025 | 0 | 0 | CO007-01025 | Change Order | Project Change Orders | 1 | Review/Approve Boiler Accessories | 10 | 0 | 100% | 2022-03-26 | 2022-04-12 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | 0 | CO007 | 01030 | 0 | 0 | CO007-01030 | Change Order | Project Change Orders | 1 | Fab/Deliver Boiler Accessories | 60 | 0 | 100% | 2022-04-01 | 2022-09-09 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | 0 | CO003 | 01005 | 0 | 0 | CO003-01005 | Change Order | Project Change Orders | 1 | National Grid Revised Allowance | 120 | 0 | 100% | 2020-12-01 | 2021-10-25 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | OG10 | DELAY | 01420 | 0 | 0 | DELAY-01420 | Delays | Project Delays | 19 | Delay - Removal of Cars in OG Parking Lot 3 (OG10 and OG7) | 20 | 0 | 100% | 2021-04-25 | 2021-05-11 |  | 0 | 0 | 0 | 0 | 0-OG10
Completed | CI NYCHA Update #22.19 | OG9 | DELAY | 01425 | 0 | 0 | DELAY-01425 | Delays | Project Delays | 19 | DELAY - Waiting on Revised TR From DOB for OG9 Permit | 5 | 0 | 100% | 2021-06-09 08:00 | 2021-06-14 |  | 0 | 0 | 0 | 0 | 0-OG9
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05001a | 0 | 0 | PERMIT-05001a | Procurement | Permits | Procurement.Div 1.Permits | MLJ Provide Rodent Control Plan | 10 | 0 | 100% | 2021-02-01 | 2021-02-17 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05001b | 0 | 0 | PERMIT-05001b | Procurement | Permits | Procurement.Div 1.Permits | MLJ/FSE Provide Electric Cut-Off Letter | 10 | 0 | 100% | 2021-02-01 | 2021-02-07 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05001c | 0 | 0 | PERMIT-05001c | Procurement | Permits | Procurement.Div 1.Permits | MLJ Provide SRO Intake Form | 10 | 0 | 100% | 2021-02-01 | 2021-02-11 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05001d | 0 | 0 | PERMIT-05001d | Procurement | Permits | Procurement.Div 1.Permits | MLJ Provide Photographs | 10 | 0 | 100% | 2020-08-03 | 2020-08-24 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05001e | 0 | 0 | PERMIT-05001e | Procurement | Permits | Procurement.Div 1.Permits | MLJ Provide Separate Fence Application | 10 | 0 | 100% | 2020-12-01 | 2020-12-14 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05001f | 0 | 0 | PERMIT-05001f | Procurement | Permits | Procurement.Div 1.Permits | MLJ Request Gas Cut-off Letter | 10 | 0 | 100% | 2020-10-19 | 2020-10-30 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05001f5 | 0 | 0 | PERMIT-05001f5 | Procurement | Permits | Procurement.Div 1.Permits | NYCHA Provide Gas Cut-Off Letter | 90 | 0 | 100% | 2020-10-30 | 2021-03-15 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05001g | 0 | 0 | PERMIT-05001g | Procurement | Permits | Procurement.Div 1.Permits | MLJ Request Sewer Cut-off Letter | 10 | 0 | 100% | 2020-10-19 | 2020-10-30 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05001g5 | 0 | 0 | PERMIT-05001g5 | Procurement | Permits | Procurement.Div 1.Permits | NYCHA Provide Sewer Cut-Off Letter | 90 | 0 | 100% | 2020-10-30 | 2021-03-15 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05001h | 0 | 0 | PERMIT-05001h | Procurement | Permits | Procurement.Div 1.Permits | MLJ Request Water Cut-off Letter | 10 | 0 | 100% | 2020-10-19 | 2020-10-30 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05001h5 | 0 | 0 | PERMIT-05001h5 | Procurement | Permits | Procurement.Div 1.Permits | NYCHA Provide Water Cut-Off Letter | 90 | 0 | 100% | 2020-10-30 | 2021-03-15 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05001i | 0 | 0 | PERMIT-05001i | Procurement | Permits | Procurement.Div 1.Permits | MLJ Request 5-Day Notice Letter to adjoining Owners | 10 | 0 | 100% | 2020-10-19 | 2020-10-30 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05001i5 | 0 | 0 | PERMIT-05001i5 | Procurement | Permits | Procurement.Div 1.Permits | NYCHA Provide 5-Day Notice Letter to adjoining Owners | 80 | 0 | 100% | 2020-10-30 | 2021-03-01 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05001j | 0 | 0 | PERMIT-05001j | Procurement | Permits | Procurement.Div 1.Permits | MLJ Request Community Board Notification | 10 | 0 | 100% | 2020-10-19 | 2020-10-30 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05001j5 | 0 | 0 | PERMIT-05001j5 | Procurement | Permits | Procurement.Div 1.Permits | NYCHA Provide Community Board Notification | 80 | 0 | 100% | 2020-10-30 | 2021-03-01 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05001k | 0 | 0 | PERMIT-05001k | Procurement | Permits | Procurement.Div 1.Permits | MLJ Request Asbestos Report (of all Sides/Facades) | 10 | 0 | 100% | 2020-10-19 | 2020-10-30 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div 1.Permits | 0 | PERMIT | 05001k5 | 0 | 0 | PERMIT-05001k5 | Procurement | Permits | Procurement.Div 1.Permits | NYCHA Provide Asbestos Report (of all Sides/Facades) | 90 | 0 | 100% | 2020-10-30 | 2021-03-15 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | OG8 | DELAY | 01407 | 0 | 0 | DELAY-01407 | Delays | Project Delays | 19 | Install Remaining SOE after removal of Obstructions - OG-8 | 5 | 0 | 100% | 2021-06-17 | 2021-06-29 |  | 0 | 0 | 0 | 0 | 0-OG8
Not Started | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01350 | 0 | 0 | OGW-01350 | Construction | Site Utilities | Construction.5.6.6 | Excavate for Steam & HW OG3--> Street | 5 | 5 | 0% | 2023-08-14 08:00 | 2023-08-18 17:00 | -197 | MLJ | EXCAVATION | UTILITY EXC | 33-3100 | 33-3100-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01355 | 0 | 0 | OGW-01355 | Construction | Site Utilities | Construction.5.6.6 | Install Steam and HW piping OG3--> Street | 5 | 5 | 0% | 2023-08-21 08:00 | 2023-08-25 17:00 | -197 | WELKIN | UG PIPE | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01360 | 0 | 0 | OGW-01360 | Construction | Site Utilities | Construction.5.6.6 | Test Steam & HW Piping OG3--> Street | 5 | 5 | 0% | 2023-08-28 08:00 | 2023-09-01 17:00 | -197 | WELKIN | UG PIPE | 0 | 0 | 0-OGW
Not Started | CI NYCHA Update #22.Construction.5.6.6 | OGW | OGW | 01365 | 0 | 0 | OGW-01365 | Construction | Site Utilities | Construction.5.6.6 | Backfill Steam & HW Piping OG3--> Street | 5 | 5 | 0% | 2023-09-05 08:00 | 2023-09-11 17:00 | -197 | MLJ | BACKFILL | BACKFILL UTILITY | 31-2200 | 31-2200-OGW
Not Started | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01280 | 0 | 0 | S8-01280 | Construction | Site Utilities | Construction.8.3.6 | Excavate for Steam Piping - Street -> S8.1 | 5 | 5 | 0% | 2023-08-14 08:00 | 2023-08-18 17:00 | -202 | MLJ | EXCAVATION | UTILITY EXC | 33-3100 | 33-3100-S8
Not Started | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01285 | 0 | 0 | S8-01285 | Construction | Site Utilities | Construction.8.3.6 | Install Steam Piping - Street -> S8.1 | 5 | 5 | 0% | 2023-08-21 08:00 | 2023-08-25 17:00 | -202 | WELKIN | UG PIPE | 0 | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01290 | 0 | 0 | S8-01290 | Construction | Site Utilities | Construction.8.3.6 | Test Steam Piping - Street -> S8.1 | 5 | 5 | 0% | 2023-08-28 08:00 | 2023-09-01 17:00 | -202 | WELKIN | UG PIPE | 0 | 0 | 0-S8
Not Started | CI NYCHA Update #22.Construction.8.3.6 | S8 | S8 | 01295 | 0 | 0 | S8-01295 | Construction | Site Utilities | Construction.8.3.6 | Backfill Steam Piping - Street -> S8.1 | 5 | 5 | 0% | 2023-09-05 08:00 | 2023-09-11 17:00 | -202 | MLJ | BACKFILL | BACKFILL UTILITY | 31-2200 | 31-2200-S8
Completed | CI NYCHA Update #22.19 | S8 | DELAY | 01110 | 0 | 0 | DELAY-01110 | Delays | Project Delays | 19 | Basement not in a suitable condition to commence work - Site 8 | 0 | 0 | 100% | 2020-07-13 08:00 | 2022-02-21 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.19 | SG7 | DELAY | 01450 | 0 | 0 | DELAY-01450 | Delays | Project Delays | 19 | DELAY - Exisiting Interfering Gas Line at SG7 | 5 | 0 | 100% | 2021-05-19 | 2021-07-27 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01455 | 0 | 0 | DELAY-01455 | Delays | Project Delays | 19 | DELAY - Building Color Change for All New Buildings | 20 | 0 | 100% | 2021-04-27 | 2021-09-21 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | SG1, SG2, SG3, SG7 | DELAY | 01385 | 0 | 0 | DELAY-01385 | Delays | Project Delays | 19 | DELAY - SG-South (Bulletin #3) - Con-Edison Changes - SG1,2,3,7 (RFI 219 & 370) | 90 | 0 | 100% | 2021-02-08 | 2021-10-20 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1, SG2, SG3, SG7
Completed | CI NYCHA Update #22.19 | SG5 | DELAY | 01460 | 0 | 0 | DELAY-01460 | Delays | Project Delays | 19 | DELAY - Awaiting Access to First Floor Room - SG5 | 10 | 0 | 100% | 2020-07-13 08:00 | 2021-10-18 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.19 | SG4 | DELAY | 01465 | 0 | 0 | DELAY-01465 | Delays | Project Delays | 19 | DELAY - Awaiting Access to First Floor Room - SG4 | 10 | 0 | 100% | 2020-07-13 08:00 | 2021-09-22 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.19 | OG1 | DELAY | 01470 | 0 | 0 | DELAY-01470 | Delays | Project Delays | 19 | DELAY - Awaiting Access to First Floor Room - OG1 | 20 | 0 | 100% | 2020-07-13 08:00 | 2021-12-27 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.19 | OG2 | DELAY | 01475 | 0 | 0 | DELAY-01475 | Delays | Project Delays | 19 | DELAY - Awaiting Access to First Floor Room - OG2 | 20 | 0 | 100% | 2020-07-13 08:00 | 2021-12-27 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.19 | OG3 | DELAY | 01480 | 0 | 0 | DELAY-01480 | Delays | Project Delays | 19 | DELAY - Awaiting Access to First Floor Room - OG3 | 20 | 0 | 100% | 2020-07-13 08:00 | 2021-12-28 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.19 | OG4 | DELAY | 01485 | 0 | 0 | DELAY-01485 | Delays | Project Delays | 19 | DELAY - Awaiting Access to First Floor Room - OG4 | 20 | 0 | 100% | 2020-07-13 08:00 | 2021-12-27 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.19 | OG5 | DELAY | 01490 | 0 | 0 | DELAY-01490 | Delays | Project Delays | 19 | DELAY - Awaiting Access to First Floor Room - OG5 | 20 | 0 | 100% | 2020-07-13 08:00 | 2021-12-27 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.19 | OG6 | DELAY | 01495 | 0 | 0 | DELAY-01495 | Delays | Project Delays | 19 | DELAY - Awaiting Access to First Floor Room - OG6 | 20 | 0 | 100% | 2020-07-13 08:00 | 2022-11-07 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.19 | SG3 | DELAY | 01500 | 0 | 0 | DELAY-01500 | Delays | Project Delays | 19 | DELAY - Awaiting Access to First Floor Room - SG3 | 20 | 0 | 100% | 2020-07-13 08:00 | 2022-06-03 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.19 | SG5 | DELAY | 01505 | 0 | 0 | DELAY-01505 | Delays | Project Delays | 19 | DELAY - Tenants vacate 2nd Floor Apartment - SG5 | 20 | 0 | 100% | 2020-07-13 | 2022-08-26 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.19 | OG8 | DELAY | 01510 | 0 | 0 | DELAY-01510 | Delays | Project Delays | 19 | DELAY - OG8 Obstructions in Ground #2 - Underground Tank | 35 | 0 | 100% | 2021-07-28 | 2021-08-25 17:00 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01515 | 0 | 0 | DELAY-01515 | Delays | Project Delays | 19 | DELAY - Underground HW & CW Plumbing Permit | 25 | 0 | 100% | 2021-07-26 | 2021-09-23 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | OGE | 22911 | 0 | 0 | 0 | 22911 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. Underground Domestic Cold and Hot Water Distribution Piping - OGE | 40 | 0 | 100% | 2021-08-13 | 2021-09-26 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Procurement.Div. 22 | OGW | 22912 | 0 | 0 | 0 | 22912 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. Underground Domestic Cold and Hot Water Distribution Piping - OGW | 40 | 0 | 100% | 2021-06-21 | 2021-08-24 17:00 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Procurement.Div. 22 | 0 | 22913 | 0 | 0 | 0 | 22913 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. Underground Domestic Cold and Hot Water Distribution Piping - OGP1 | 40 | 0 | 100% | 2021-08-12 | 2021-09-26 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 22 | SGS | 22914 | 0 | 0 | 0 | 22914 | Procurement | Div. 22 - Plumbing | Procurement.Div. 22 | Fab/Del. Underground Domestic Cold and Hot Water Distribution Piping - SGS | 40 | 0 | 100% | 2021-10-05 | 2021-11-15 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.Procurement.Div. 23 | 0 | 24201 | 0 | 0 | 0 | 24201 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Steam and Condensate Piping - OGP1 | 35 | 0 | 100% | 2021-08-16 08:00 | 2021-09-22 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OGE | 24202 | 0 | 0 | 0 | 24202 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Steam and Condensate Piping - OGE | 35 | 0 | 100% | 2021-08-02 08:00 | 2021-09-26 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.Procurement.Div. 23 | OGW | 24203 | 0 | 0 | 0 | 24203 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Steam and Condensate Piping - OGW | 35 | 0 | 100% | 2021-03-25 08:00 | 2021-09-22 17:00 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.Procurement.Div. 23 | SGS | 24204 | 0 | 0 | 0 | 24204 | Procurement | Div. 23 - Heating Ventilating & Air Conditioning | Procurement.Div. 23 | Fab/Del. Steam and Condensate Piping - SGS | 35 | 0 | 100% | 2021-09-24 08:00 | 2021-09-26 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01605 | 0 | 0 | DELAY-01605 | Delays | Project Delays | 19 | DELAY - RFI #325 - Regarding Light Fixtures in all existing Cellars - Submit | 5 | 0 | 100% | 2021-07-29 08:00 | 2021-07-30 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01610 | 0 | 0 | DELAY-01610 | Delays | Project Delays | 19 | DELAY - RFI #325 - Regarding Light Fixtures in all existing Cellars - Response | 15 | 0 | 100% | 2021-07-30 | 2021-09-20 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01520 | 0 | 0 | DELAY-01520 | Delays | Project Delays | 19 | DELAY - UG plumbing pipe Inspection failure due to pipe type - Eng to Re-file Dwgs/OTCR | 10 | 0 | 100% | 2021-09-23 | 2022-06-24 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01525 | 0 | 0 | DELAY-01525 | Delays | Project Delays | 19 | DELAY - OG Fence Change required by residents | 20 | 0 | 100% | 2021-09-16 | 2021-12-02 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01530 | 0 | 0 | DELAY-01530 | Delays | Project Delays | 19 | DELAY - Existing Pipe under W33rd | 75 | 0 | 100% | 2021-06-22 | 2022-08-12 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01535 | 0 | 0 | DELAY-01535 | Delays | Project Delays | 19 | DELAY - Condition of existing basement walls preventing waterproofing (RFI 302 & RFI 311) | 75 | 0 | 100% | 2021-07-08 | 2022-07-10 |  | 0 | 0 | 0 | 0 | 0-0
In Progress | CI NYCHA Update #22.1 | NA | CO008 | 01005 | 0 | 0 | CO008-01005 | Change Order | Project Change Orders | 1 | Bulletin #1 - PCO #44 Civil Work | 120 | 60 | 50% | 2021-05-05 | 2023-02-22 17:00 | -56 | MLJ | CHANGE ORDER | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01060 | 0 | 0 | SG7-01060 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Abate asbestos on Existing Steam Line --> SG7 | 3 | 0 | 100% | 2022-03-28 | 2022-04-15 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.Construction.4.4.7 | SG7 | SG7 | 01062 | 0 | 0 | SG7-01062 | Construction | Structural/Architectural Construction | Construction.4.4.7 | Relocate Existing steam --> SG7 | 5 | 0 | 100% | 2022-04-18 | 2022-04-18 |  | 0 | 0 | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01705 | 0 | 0 | DELAY-01705 | Delays | Project Delays | 19 | DELAY - RFI's 242,365 &381 - Fire Standpipe CO21 - Submit | 5 | 0 | 100% | 2021-05-05 08:00 | 2021-10-01 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01710 | 0 | 0 | DELAY-01710 | Delays | Project Delays | 19 | DELAY - RFI's 242,365 &381 - Fire Standpipe CO21 - Response | 5 | 0 | 100% | 2021-09-25 | 2021-10-22 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | S8 | DELAY | 01715 | 0 | 0 | DELAY-01715 | Delays | Project Delays | 19 | CO #21 - MLJ Awaits Receipt of CO21 Fire Standpipe Relocation - Site 8 | 10 | 0 | 100% | 2021-10-23 | 2022-03-14 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01720 | 0 | 0 | DELAY-01720 | Delays | Project Delays | 19 | CO #21 - Fire Standpipe Relocation (Incl Shutdown and Testing) | 15 | 0 | 100% | 2022-03-14 | 2022-04-05 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01805 | 0 | 0 | DELAY-01805 | Delays | Project Delays | 19 | DELAY - AWP Approved by Saban | 1 | 0 | 100% | 2021-02-08 08:00 | 2021-02-08 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01810 | 0 | 0 | DELAY-01810 | Delays | Project Delays | 19 | DELAY - Additional review and change to formatting requried by CSQ | 188 | 0 | 100% | 2021-02-09 | 2022-02-11 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01905 | 0 | 0 | DELAY-01905 | Delays | Project Delays | 19 | CO- ACM Found on Exterior of Foundation Wall @ Existing Buildings | 1 | 0 | 100% | 2021-10-06 08:00 | 2021-10-06 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01910 | 0 | 0 | DELAY-01910 | Delays | Project Delays | 19 | CO - Expose, Test and confirm quantities | 25 | 0 | 100% | 2021-10-07 08:00 | 2021-11-18 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | SG1 | DELAY | 01915 | 0 | 0 | DELAY-01915 | Delays | Project Delays | 19 | CO #55 - Abate ACM for Underground utilities - SG-1 | 2 | 0 | 100% | 2021-12-20 08:00 | 2021-12-21 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.19 | SG1 | DELAY | 01920 | 0 | 0 | DELAY-01920 | Delays | Project Delays | 19 | CO #54 - Abate ACM for masonry foundation - SG-1 | 5 | 0 | 100% | 2022-08-15 | 2022-08-19 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01015 | 0 | 0 | DELAY-01015 | Delays | Project Delays | 19 | Site closure due to shooting - June 11, 2021 | 1 | 0 | 100% | 2021-06-11 08:00 | 2021-06-11 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01020 | 0 | 0 | DELAY-01020 | Delays | Project Delays | 19 | Site closure due to shooting - June 29, 2021 | 1 | 0 | 100% | 2021-06-29 08:00 | 2021-06-29 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01025 | 0 | 0 | DELAY-01025 | Delays | Project Delays | 19 | Site closure due to shooting - June 30, 2021 | 1 | 0 | 100% | 2021-06-30 08:00 | 2021-06-30 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01030 | 0 | 0 | DELAY-01030 | Delays | Project Delays | 19 | Site closure due to shooting - August 19, 2021 | 1 | 0 | 100% | 2021-08-19 08:00 | 2021-08-19 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 01035 | 0 | 0 | DELAY-01035 | Delays | Project Delays | 19 | Site closure due to shooting - October 25, 2021 | 1 | 0 | 100% | 2021-10-25 08:00 | 2021-10-25 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | SG2 | DELAY | 01925 | 0 | 0 | DELAY-01925 | Delays | Project Delays | 19 | CO #55 - Abate ACM for Underground utilities - SG-2 | 2 | 0 | 100% | 2021-12-13 08:00 | 2021-12-14 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.19 | SG2 | DELAY | 01930 | 0 | 0 | DELAY-01930 | Delays | Project Delays | 19 | CO #54 - Abate ACM for masonry foundation - SG-2 | 5 | 0 | 100% | 2022-08-15 | 2022-08-19 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.19 | SG3 | DELAY | 01935 | 0 | 0 | DELAY-01935 | Delays | Project Delays | 19 | CO #55 - Abate ACM for Underground utilities - SG-3 | 2 | 0 | 100% | 2021-12-14 08:00 | 2021-12-16 17:00 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.19 | SG3 | DELAY | 01940 | 0 | 0 | DELAY-01940 | Delays | Project Delays | 19 | CO #54 - Abate ACM for masonry foundation - SG-3 | 5 | 0 | 100% | 2022-08-29 | 2022-08-31 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.19 | SG4 | DELAY | 01950 | 0 | 0 | DELAY-01950 | Delays | Project Delays | 19 | CO #54 - Abate ACM for masonry foundation - SG-4 | 5 | 0 | 100% | 2022-03-10 | 2022-03-11 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.19 | SG5 | DELAY | 01960 | 0 | 0 | DELAY-01960 | Delays | Project Delays | 19 | CO #54 - Abate ACM for masonry foundation - SG-5 | 5 | 0 | 100% | 2022-02-16 08:00 | 2022-02-18 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.19 | OG1 | DELAY | 01965 | 0 | 0 | DELAY-01965 | Delays | Project Delays | 19 | CO #55 - Abate ACM for Underground utilities - OG-1 | 2 | 0 | 100% | 2021-11-16 08:00 | 2021-11-17 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.19 | OG1 | DELAY | 01970 | 0 | 0 | DELAY-01970 | Delays | Project Delays | 19 | CO #54 - Abate ACM for masonry foundation - OG-1 | 5 | 0 | 100% | 2022-04-21 | 2022-05-05 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.19 | OG2 | DELAY | 01975 | 0 | 0 | DELAY-01975 | Delays | Project Delays | 19 | CO #55 - Abate ACM for Underground utilities - OG-2 | 2 | 0 | 100% | 2021-12-02 | 2022-04-12 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.19 | OG2 | DELAY | 01980 | 0 | 0 | DELAY-01980 | Delays | Project Delays | 19 | CO #54 - Abate ACM for masonry foundation - OG-2 | 5 | 0 | 100% | 2022-04-26 | 2022-04-29 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.19 | OG3 | DELAY | 01985 | 0 | 0 | DELAY-01985 | Delays | Project Delays | 19 | CO #55 - Abate ACM for Underground utilities - OG-3 | 2 | 0 | 100% | 2021-11-26 | 2022-04-13 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.19 | OG3 | DELAY | 01990 | 0 | 0 | DELAY-01990 | Delays | Project Delays | 19 | CO #54 - Abate ACM for masonry foundation - OG-3 | 5 | 0 | 100% | 2022-05-19 | 2022-09-30 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.19 | OG4 | DELAY | 01995 | 0 | 0 | DELAY-01995 | Delays | Project Delays | 19 | CO #55 - Abate ACM for Underground utilities - OG-4 | 2 | 0 | 100% | 2021-10-25 08:00 | 2021-10-26 17:00 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.19 | OG4 | DELAY | 02000 | 0 | 0 | DELAY-02000 | Delays | Project Delays | 19 | CO #54 - Abate ACM for masonry foundation - OG-4 | 5 | 0 | 100% | 2022-06-03 08:00 | 2022-10-07 17:00 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.19 | OG5 | DELAY | 02005 | 0 | 0 | DELAY-02005 | Delays | Project Delays | 19 | CO #55 - Abate ACM for Underground utilities - OG-5 | 2 | 0 | 100% | 2022-01-06 | 2022-04-14 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.19 | OG5 | DELAY | 02010 | 0 | 0 | DELAY-02010 | Delays | Project Delays | 19 | CO #54 - Abate ACM for masonry foundation - OG-5 | 5 | 0 | 100% | 2022-05-20 | 2022-09-28 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.19 | OG6 | DELAY | 02015 | 0 | 0 | DELAY-02015 | Delays | Project Delays | 19 | CO #55 - Abate ACM for Underground utilities - OG-6 | 2 | 0 | 100% | 2021-11-17 08:00 | 2021-11-18 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.19 | OG6 | DELAY | 02020 | 0 | 0 | DELAY-02020 | Delays | Project Delays | 19 | CO #54 - Abate ACM for masonry foundation - OG-6 | 5 | 0 | 100% | 2022-09-01 | 2022-09-03 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.19 | S8 | DELAY | 02025 | 0 | 0 | DELAY-02025 | Delays | Project Delays | 19 | CO #55 - Abate ACM for Underground utilities - Site 8 | 2 | 0 | 100% | 2022-02-18 | 2022-10-24 |  | 0 | 0 | 0 | 0 | 0-S8
Not Started | CI NYCHA Update #22.19 | S8 | DELAY | 02030 | 0 | 0 | DELAY-02030 | Delays | Project Delays | 19 | CO #54 - Abate ACM for masonry foundation - Site 8 | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | -86 | ATCO | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.1 | 0 | CO007 | 01035 | 0 | 0 | CO007-01035 | Change Order | Project Change Orders | 1 | Install Boiler Accessories | 10 | 0 | 100% | 2022-09-14 | 2022-10-14 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | DELAY | 03005 | 0 | 0 | DELAY-03005 | Delays | Project Delays | 19 | DELAY - Manufacturing Supply/Chain Issues for ATS Equipment | 40 | 0 | 100% | 2021-10-11 | 2021-12-17 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | OG1 | CO016 | 01005 | 0 | 0 | CO016-01005 | Change Order | Project Change Orders | 1 | Relocate Obstructions in 1st Floor - OG1 | 10 | 0 | 100% | 2022-04-15 | 2022-04-20 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.1 | OG2 | CO016 | 01010 | 0 | 0 | CO016-01010 | Change Order | Project Change Orders | 1 | Relocate Obstructions in 1st Floor - OG2 | 10 | 0 | 100% | 2022-04-25 | 2022-04-28 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.1 | OG3 | CO016 | 01015 | 0 | 0 | CO016-01015 | Change Order | Project Change Orders | 1 | Relocate Obstructions in 1st Floor - OG3 | 10 | 0 | 100% | 2022-04-22 | 2022-04-28 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.1 | OG4 | CO016 | 01020 | 0 | 0 | CO016-01020 | Change Order | Project Change Orders | 1 | Relocate Obstructions in 1st Floor - OG4 | 10 | 0 | 100% | 2022-04-18 | 2022-04-21 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.1 | OG5 | CO016 | 01025 | 0 | 0 | CO016-01025 | Change Order | Project Change Orders | 1 | Relocate Obstructions in 1st Floor - OG5 | 10 | 0 | 100% | 2022-04-25 | 2022-04-28 |  | 0 | 0 | 0 | 0 | 0-OG5
Not Started | CI NYCHA Update #22.1 | OG6 | CO016 | 01030 | 0 | 0 | CO016-01030 | Change Order | Project Change Orders | 1 | Relocate Obstructions in 1st Floor - OG6 | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | -69 | MLJ | CHANGE ORDER | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.1 | SG3 | CO016 | 01035 | 0 | 0 | CO016-01035 | Change Order | Project Change Orders | 1 | Relocate Obstructions in 1st Floor - SG3 | 10 | 0 | 100% | 2022-10-03 | 2022-10-10 17:00 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.1 | SG5 | CO016 | 01040 | 0 | 0 | CO016-01040 | Change Order | Project Change Orders | 1 | Relocate Obstructions in 1st Floor - SG5 | 10 | 0 | 100% | 2022-04-07 | 2022-04-15 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.19 | SG1 | DELAY | 01911 | 0 | 0 | DELAY-01911 | Delays | Project Delays | 19 | CO #55 - NYCHA Instruct PCO 55 - SG-1 | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-12-21 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.19 | SG1 | DELAY | 01912 | 0 | 0 | DELAY-01912 | Delays | Project Delays | 19 | CO #55 - Filing with DEP - SG-1 | 10 | 0 | 100% | 2021-11-18 08:00 | 2021-12-13 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1
Completed | CI NYCHA Update #22.19 | SG2 | DELAY | 01922 | 0 | 0 | DELAY-01922 | Delays | Project Delays | 19 | CO #55 - NYCHA Instruct PCO 55 - SG-2 | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-12-21 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.19 | SG2 | DELAY | 01923 | 0 | 0 | DELAY-01923 | Delays | Project Delays | 19 | CO #55 - Filing with DEP - SG-2 | 10 | 0 | 100% | 2021-11-18 08:00 | 2021-12-06 17:00 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.19 | SG3 | DELAY | 01932 | 0 | 0 | DELAY-01932 | Delays | Project Delays | 19 | CO #55 - NYCHA Instruct PCO 55 - SG-3 | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-12-21 17:00 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.19 | SG3 | DELAY | 01933 | 0 | 0 | DELAY-01933 | Delays | Project Delays | 19 | CO #55 - Filing with DEP- SG-3 | 10 | 0 | 100% | 2021-11-18 08:00 | 2021-12-07 17:00 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.19 | SG4 | DELAY | 01942 | 0 | 0 | DELAY-01942 | Delays | Project Delays | 19 | CO #55 - NYCHA Instruct PCO 55 - SG-4 | 20 | 0 | 100% | 2021-11-25 | 2021-12-21 17:00 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.19 | SG4 | DELAY | 01943 | 0 | 0 | DELAY-01943 | Delays | Project Delays | 19 | CO #55 - Filing with DEP- SG-4 | 10 | 0 | 100% | 2022-01-03 08:00 | 2022-01-14 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.19 | SG5 | DELAY | 01952 | 0 | 0 | DELAY-01952 | Delays | Project Delays | 19 | CO #55 - NYCHA Instruct PCO 55 - SG-5 | 20 | 0 | 100% | 2021-11-25 | 2021-12-21 17:00 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.19 | SG5 | DELAY | 01953 | 0 | 0 | DELAY-01953 | Delays | Project Delays | 19 | CO #55 - Filing with DEP- SG-5 | 10 | 0 | 100% | 2022-01-03 08:00 | 2022-01-14 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.19 | OG1 | DELAY | 01962 | 0 | 0 | DELAY-01962 | Delays | Project Delays | 19 | CO #55 - NYCHA Instruct PCO 55 - OG-1 | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-12-21 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.19 | OG1 | DELAY | 01963 | 0 | 0 | DELAY-01963 | Delays | Project Delays | 19 | CO #55 - Filing with DEP- OG-1 | 10 | 0 | 100% | 2021-10-27 08:00 | 2021-11-10 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.19 | OG2 | DELAY | 01972 | 0 | 0 | DELAY-01972 | Delays | Project Delays | 19 | CO #55 - NYCHA Instruct PCO 55 - OG-2 | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-12-21 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.19 | OG2 | DELAY | 01973 | 0 | 0 | DELAY-01973 | Delays | Project Delays | 19 | CO #55 - Filing with DEP- OG-2 | 10 | 0 | 100% | 2021-11-18 08:00 | 2021-11-23 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.19 | OG3 | DELAY | 01982 | 0 | 0 | DELAY-01982 | Delays | Project Delays | 19 | CO #55 - NYCHA Instruct PCO 55 - OG-3 | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-12-21 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.19 | OG3 | DELAY | 01983 | 0 | 0 | DELAY-01983 | Delays | Project Delays | 19 | CO #55 - Filing with DEP- OG-3 | 10 | 0 | 100% | 2021-11-02 08:00 | 2021-11-10 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.19 | OG4 | DELAY | 01992 | 0 | 0 | DELAY-01992 | Delays | Project Delays | 19 | CO #55 - NYCHA Instruct PCO 55 - OG-4 | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-12-21 17:00 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.19 | OG4 | DELAY | 01993 | 0 | 0 | DELAY-01993 | Delays | Project Delays | 19 | CO #55 - Filing with DEP- OG-4 | 10 | 0 | 100% | 2021-10-11 08:00 | 2021-10-14 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.19 | OG5 | DELAY | 02002 | 0 | 0 | DELAY-02002 | Delays | Project Delays | 19 | CO #55 - NYCHA Instruct PCO 55 - OG-5 | 20 | 0 | 100% | 2021-11-25 08:00 | 2021-12-21 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.19 | OG5 | DELAY | 02003 | 0 | 0 | DELAY-02003 | Delays | Project Delays | 19 | CO #55 - Filing with DEP- OG-5 | 10 | 0 | 100% | 2021-11-18 08:00 | 2021-12-03 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.19 | OG6 | DELAY | 02012 | 0 | 0 | DELAY-02012 | Delays | Project Delays | 19 | CO #55 - NYCHA Instruct PCO 55 - OG-6 | 20 | 0 | 100% | 2021-11-25 | 2021-12-21 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.19 | OG6 | DELAY | 02013 | 0 | 0 | DELAY-02013 | Delays | Project Delays | 19 | CO #55 - Filing with DEP- OG-6 | 10 | 0 | 100% | 2021-10-27 08:00 | 2021-11-10 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.19 | S8 | DELAY | 02022 | 0 | 0 | DELAY-02022 | Delays | Project Delays | 19 | CO #55 - NYCHA Instruct PCO 55 - Site 8 | 20 | 0 | 100% | 2021-11-25 | 2021-12-21 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.19 | S8 | DELAY | 02023 | 0 | 0 | DELAY-02023 | Delays | Project Delays | 19 | CO #55 - Filing with DEP- Site 8 | 10 | 0 | 100% | 2021-11-18 08:00 | 2021-12-20 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.1.1 | SGS | CO059 | 01005 | 0 | 0 | CO059-01005 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Instruction - SGS and OGW Electrical Feeder Changes (RFI #370) | 8 | 0 | 100% | 2021-12-21 | 2021-12-21 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.19 | SG5 | DELAY | 01115 | 0 | 0 | DELAY-01115 | Delays | Project Delays | 19 | Basement not in a suitable condition to continue work (Steam) - SG5 | 20 | 0 | 100% | 2022-01-11 | 2022-04-01 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.19 | OG4 | DELAY | 01120 | 0 | 0 | DELAY-01120 | Delays | Project Delays | 19 | Basement not in a suitable condition to continue work (Flooding) - OG4 | 20 | 0 | 100% | 2022-01-11 | 2022-04-01 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.19 | OG4 | DELAY | 01125 | 0 | 0 | DELAY-01125 | Delays | Project Delays | 19 | Basement not in a suitable condition to continue work (Sewage) - OG4 | 20 | 0 | 100% | 2022-01-11 | 2022-04-01 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.19 | 0 | RFI462 | 01005 | 0 | 0 | RFI462-01005 | Delays | Project Delays | 19 | 2nd floor apartment DOB Plumbing Drawings - Submit | 1 | 0 | 100% | 2021-12-27 08:00 | 2021-12-27 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | RFI462 | 01010 | 0 | 0 | RFI462-01010 | Delays | Project Delays | 19 | 2nd floor apartment DOB Plumbing Drawings - Response | 10 | 0 | 100% | 2021-12-28 | 2022-04-12 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | RFI302 | 01005 | 0 | 0 | RFI302-01005 | Delays | Project Delays | 19 | RFI 302, 311 & 483 - Waterproofing to existing buildings - Submit | 1 | 0 | 100% | 2021-07-13 08:00 | 2022-01-24 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | RFI302 | 01010 | 0 | 0 | RFI302-01010 | Delays | Project Delays | 19 | RFI 302, 311 & 483 - Waterproofing to existing buildings - Response | 10 | 0 | 100% | 2021-07-14 08:00 | 2022-07-10 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | SG4, SG5 | RFI408 | 01005 | 0 | 0 | RFI408-01005 | Delays | Project Delays | 19 | RFI 408 - Existing Building Masonry interferences - Submit (SG4,5) | 5 | 0 | 100% | 2021-10-15 | 2021-10-20 |  | 0 | 0 | 0 | 0 | 0-SG4, SG5
Completed | CI NYCHA Update #22.19 | SG4, SG5 | RFI408 | 01010 | 0 | 0 | RFI408-01010 | Delays | Project Delays | 19 | RFI 408 - Existing Building Masonry interferences - Response (SG4,5) | 10 | 0 | 100% | 2021-10-21 | 2022-05-12 |  | 0 | 0 | 0 | 0 | 0-SG4, SG5
Completed | CI NYCHA Update #22.19 | OG5 OG6 | RFI473 | 01005 | 0 | 0 | RFI473-01005 | Delays | Project Delays | 19 | RFI #473 - Fuel Oil Tank between OG5&OG6 - Submit | 1 | 0 | 100% | 2022-01-19 08:00 | 2022-01-19 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5 OG6
Completed | CI NYCHA Update #22.19 | OG5 OG6 | RFI473 | 01010 | 0 | 0 | RFI473-01010 | Delays | Project Delays | 19 | RFI #473 - Fuel Oil Tank between OG5&OG6 - Response | 10 | 0 | 100% | 2022-01-20 | 2022-02-14 |  | 0 | 0 | 0 | 0 | 0-OG5 OG6
Completed | CI NYCHA Update #22.1 | OG5 OG6 | CO046 | 01005 | 0 | 0 | CO046-01005 | Change Order | Project Change Orders | 1 | CO #46 - Scope Development - OG5 & OG6 Sanitary Vent Connections | 1 | 0 | 100% | 2021-10-06 08:00 | 2021-10-06 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5 OG6
Completed | CI NYCHA Update #22.19 | OG5 | RFI294 | 01005 | 0 | 0 | RFI294-01005 | Delays | Project Delays | 19 | RFI #294 - OG5 Existing Vents - Submit | 5 | 0 | 100% | 2021-07-01 | 2021-07-01 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.19 | OG5 | RFI294 | 01010 | 0 | 0 | RFI294-01010 | Delays | Project Delays | 19 | RFI #294 - OG5 Existing Vents - Response | 10 | 0 | 100% | 2021-07-02 | 2021-08-05 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.1 | OG5 OG6 | CO046 | 01010 | 0 | 0 | CO046-01010 | Change Order | Project Change Orders | 1 | CO #46 - Scope Agreement - OG5 & OG6 Sanitary Vent Connections | 65 | 0 | 100% | 2021-10-07 | 2022-01-13 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5 OG6
Completed | CI NYCHA Update #22.1 | OG5 OG6 | CO046 | 01015 | 0 | 0 | CO046-01015 | Change Order | Project Change Orders | 1 | CO #46 - Submit Price - OG5 & OG6 Sanitary Vent Connections | 5 | 0 | 100% | 2022-01-14 | 2022-01-18 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5 OG6
Completed | CI NYCHA Update #22.1 | OG5 OG6 | CO046 | 01020 | 0 | 0 | CO046-01020 | Change Order | Project Change Orders | 1 | CO #46 - Negotiate/Instruction - OG5 & OG6 Sanitary Vent Connections | 20 | 0 | 100% | 2022-01-19 | 2022-08-23 |  | 0 | 0 | 0 | 0 | 0-OG5 OG6
Completed | CI NYCHA Update #22.1 | OG5 | CO046 | 01025 | 0 | 0 | CO046-01025 | Change Order | Project Change Orders | 1 | CO #46 - Sanitary Vent Connections @ OG-5 | 10 | 0 | 100% | 2022-09-06 08:00 | 2022-09-16 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.1 | OG6 | CO046 | 01030 | 0 | 0 | CO046-01030 | Change Order | Project Change Orders | 1 | CO #46 - Sanitary Vent Connections @ OG-6 | 10 | 0 | 100% | 2022-09-06 08:00 | 2022-09-16 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.1 | 0 | CO052 | 01005 | 0 | 0 | CO052-01005 | Change Order | Project Change Orders | 1 | CO #52 - Scope Development - Playground removal (RFI 375) | 5 | 0 | 100% | 2021-10-26 08:00 | 2021-10-26 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | 0 | CO052 | 01010 | 0 | 0 | CO052-01010 | Change Order | Project Change Orders | 1 | CO #52 - Scope Agreement - Playground removal (RFI 375) | 5 | 0 | 100% | 2021-10-27 | 2022-01-06 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | 0 | CO052 | 01015 | 0 | 0 | CO052-01015 | Change Order | Project Change Orders | 1 | CO #52 - Submit Price - Playground removal (RFI 375) | 5 | 0 | 100% | 2022-01-06 | 2022-01-06 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | 0 | CO052 | 01020 | 0 | 0 | CO052-01020 | Change Order | Project Change Orders | 1 | CO #52 - Negotiate/Instruction - Playground removal (RFI 375) | 20 | 0 | 100% | 2022-01-07 | 2022-08-23 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | 0 | CO052 | 01025 | 0 | 0 | CO052-01025 | Change Order | Project Change Orders | 1 | CO #52 - Remove Playround - OG East | 5 | 0 | 100% | 2022-02-07 | 2022-02-09 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | OGE | RFI375 | 01005 | 0 | 0 | RFI375-01005 | Delays | Project Delays | 19 | RFI #375 - OGE Playground Clash with ductbank - Submit | 5 | 0 | 100% | 2021-09-29 | 2021-09-29 17:00 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.19 | OGE | RFI375 | 01010 | 0 | 0 | RFI375-01010 | Delays | Project Delays | 19 | RFI #375 - OGE Playground Clash with ductbank - Response | 10 | 0 | 100% | 2021-09-30 | 2021-10-22 17:00 |  | 0 | 0 | 0 | 0 | 0-OGE
Completed | CI NYCHA Update #22.1 | SG6, OG8 | CO053 | 01005 | 0 | 0 | CO053-01005 | Change Order | Project Change Orders | 1 | CO #53 - Scope Development - SG6 and OG8 boiler stack support (RFI #213) | 5 | 0 | 100% | 2021-04-13 08:00 | 2021-10-29 |  | 0 | 0 | 0 | 0 | 0-SG6, OG8
Completed | CI NYCHA Update #22.1 | SG6, OG8 | CO053 | 01010 | 0 | 0 | CO053-01010 | Change Order | Project Change Orders | 1 | CO #53 - Scope Agreement - - SG6 and OG8 boiler stack support (RFI #213) | 20 | 0 | 100% | 2021-11-01 | 2022-02-10 |  | 0 | 0 | 0 | 0 | 0-SG6, OG8
Completed | CI NYCHA Update #22.1 | SG6, OG8 | CO053 | 01015 | 0 | 0 | CO053-01015 | Change Order | Project Change Orders | 1 | CO #53 - Submit Price - SG6 and OG8 boiler stack support (RFI #213) | 5 | 0 | 100% | 2022-02-10 | 2022-02-11 |  | 0 | 0 | 0 | 0 | 0-SG6, OG8
Completed | CI NYCHA Update #22.1 | SG6, OG8 | CO053 | 01020 | 0 | 0 | CO053-01020 | Change Order | Project Change Orders | 1 | CO #53 - Negotiate/Instruction - SG6 and OG8 boiler stack support (RFI #213) | 20 | 0 | 100% | 2022-02-24 08:00 | 2022-08-23 17:00 |  | 0 | 0 | 0 | 0 | 0-SG6, OG8
Completed | CI NYCHA Update #22.19 | 0 | RFI213 | 01005 | 0 | 0 | RFI213-01005 | Delays | Project Delays | 19 | RFI #213 - Boiler Stack Support - Submit | 5 | 0 | 100% | 2021-03-31 | 2021-03-31 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | RFI213 | 01010 | 0 | 0 | RFI213-01010 | Delays | Project Delays | 19 | RFI #213 - Boiler Stack Support - Response | 10 | 0 | 100% | 2021-04-01 | 2021-04-12 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | SG6 | CO053 | 01025 | 0 | 0 | CO053-01025 | Change Order | Project Change Orders | 1 | CO #53 - Install Additional Boiler Stack Supports - SG6 | 10 | 0 | 100% | 2022-04-26 | 2022-04-26 |  | 0 | 0 | 0 | 0 | 0-SG6
Completed | CI NYCHA Update #22.1 | OG8 | CO053 | 01030 | 0 | 0 | CO053-01030 | Change Order | Project Change Orders | 1 | CO #53 - Install Additional Boiler Stack Supports - OG8 | 10 | 0 | 100% | 2022-04-27 | 2022-04-29 |  | 0 | 0 | 0 | 0 | 0-OG8
Completed | CI NYCHA Update #22.1 | SG1, SG2, SG3 | RFI189 | 01005 | 0 | 0 | RFI189-01005 | Change Order | Project Change Orders | 1 | RFI #189 - Ammendments to SG1, 2 & 3 Duct Bank - Submit | 5 | 0 | 100% | 2021-03-04 | 2021-03-04 |  | 0 | 0 | 0 | 0 | 0-SG1, SG2, SG3
Completed | CI NYCHA Update #22.1 | SG1, SG2, SG3 | RFI189 | 01010 | 0 | 0 | RFI189-01010 | Change Order | Project Change Orders | 1 | RFI #189 - Ammendments to SG1, 2 & 3 Duct Bank - Response | 10 | 0 | 100% | 2021-03-05 | 2021-03-08 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1, SG2, SG3
Completed | CI NYCHA Update #22.1 | SG1, SG2, SG3 | RFI205 | 01005 | 0 | 0 | RFI205-01005 | Change Order | Project Change Orders | 1 | RFI #205 - Ammendments to SG1, 2 & 3 Duct Bank - Submit | 5 | 0 | 100% | 2021-03-15 | 2021-03-15 |  | 0 | 0 | 0 | 0 | 0-SG1, SG2, SG3
Completed | CI NYCHA Update #22.1 | SG1, SG2, SG3 | RFI205 | 01010 | 0 | 0 | RFI205-01010 | Change Order | Project Change Orders | 1 | RFI #205 - Ammendments to SG1, 2 & 3 Duct Bank - Response | 10 | 0 | 100% | 2021-03-16 | 2021-03-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1, SG2, SG3
Completed | CI NYCHA Update #22.1 | SG1, SG2, SG3 | RFI219 | 01005 | 0 | 0 | RFI219-01005 | Change Order | Project Change Orders | 1 | RFI #219 - Ammendments to SG1, 2 & 3 Duct Bank - Submit | 5 | 0 | 100% | 2021-04-06 | 2021-04-06 |  | 0 | 0 | 0 | 0 | 0-SG1, SG2, SG3
Completed | CI NYCHA Update #22.1 | SG1, SG2, SG3 | RFI219 | 01010 | 0 | 0 | RFI219-01010 | Change Order | Project Change Orders | 1 | RFI #219 - Ammendments to SG1, 2 & 3 Duct Bank - Response | 10 | 0 | 100% | 2021-04-07 | 2021-05-12 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1, SG2, SG3
Completed | CI NYCHA Update #22.1 | SG1, SG2, SG3 | RFI276 | 01005 | 0 | 0 | RFI276-01005 | Change Order | Project Change Orders | 1 | RFI #276 - Ammendments to SG1, 2 & 3 Duct Bank - Submit | 5 | 0 | 100% | 2021-06-09 | 2021-06-09 |  | 0 | 0 | 0 | 0 | 0-SG1, SG2, SG3
Completed | CI NYCHA Update #22.1 | SG1, SG2, SG3 | RFI276 | 01010 | 0 | 0 | RFI276-01010 | Change Order | Project Change Orders | 1 | RFI #276 - Ammendments to SG1, 2 & 3 Duct Bank - Response | 10 | 0 | 100% | 2021-06-10 | 2021-10-01 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1, SG2, SG3
Completed | CI NYCHA Update #22.19 | SG1, SG2, SG3 | RFI355 | 01005 | 0 | 0 | RFI355-01005 | Delays | Project Delays | 19 | RFI #355 - Ammendments to SG1, 2 & 3 Duct Bank - Submit | 5 | 0 | 100% | 2021-09-13 | 2021-09-13 |  | 0 | 0 | 0 | 0 | 0-SG1, SG2, SG3
Completed | CI NYCHA Update #22.19 | SG1, SG2, SG3 | RFI355 | 01010 | 0 | 0 | RFI355-01010 | Delays | Project Delays | 19 | RFI #355 - Ammendments to SG1, 2 & 3 Duct Bank - Response | 10 | 0 | 100% | 2021-09-14 | 2021-10-01 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1, SG2, SG3
Completed | CI NYCHA Update #22.1 | SG1, SG2, SG3 | RFI370 | 01005 | 0 | 0 | RFI370-01005 | Change Order | Project Change Orders | 1 | RFI #370 - Ammendments to SG1, 2 & 3 Duct Bank - Submit | 5 | 0 | 100% | 2021-09-27 | 2021-09-27 |  | 0 | 0 | 0 | 0 | 0-SG1, SG2, SG3
Completed | CI NYCHA Update #22.1 | SG1, SG2, SG3 | RFI370 | 01010 | 0 | 0 | RFI370-01010 | Change Order | Project Change Orders | 1 | RFI #370 - Ammendments to SG1, 2 & 3 Duct Bank - Response | 10 | 0 | 100% | 2021-09-28 | 2021-10-20 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1, SG2, SG3
Completed | CI NYCHA Update #22.1.1 | SGS | CO059 | 01000 | 0 | 0 | CO059-01000 | Change Order | Change Order #59 | 1.1 | CO #59 - Scope Development - SGS and OGW Electrical Feeder Changes (RFI #370) | 5 | 0 | 100% | 2021-10-21 08:00 | 2021-11-03 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.1.1 | SGS | CO059 | 01001 | 0 | 0 | CO059-01001 | Change Order | Change Order #59 | 1.1 | CO #59 - Scope Agreement - SGS and OGW Electrical Feeder Changes (RFI #370) | 20 | 0 | 100% | 2021-11-01 | 2021-12-17 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.1.1 | SGS | CO059 | 01002 | 0 | 0 | CO059-01002 | Change Order | Change Order #59 | 1.1 | CO #59 - Submit Price - SGS and OGW Electrical Feeder Changes (RFI #370) | 5 | 0 | 100% | 2021-12-20 08:00 | 2021-12-28 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.1.1 | SGS | CO059 | 01010 | 0 | 0 | CO059-01010 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Perform Engineering Coordination - SGS - (FSE CO: 18-0016) | 30 | 0 | 100% | 2021-12-22 08:00 | 2022-05-13 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.1.1 | OGW | CO059 | 01015 | 0 | 0 | CO059-01015 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Perform Engineering Coordination - OGW | 30 | 0 | 100% | 2022-02-07 08:00 | 2022-02-28 17:00 |  | 0 | 0 | 0 | 0 | 0-OGW
Completed | CI NYCHA Update #22.1.1 | SGS | CO059 | 01020 | 0 | 0 | CO059-01020 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Excavate for electric Existing Manhole to SG3 (PDLCO1) | 3 | 0 | 100% | 2022-03-07 08:00 | 2022-08-18 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.1.1 | SGS | CO059 | 01025 | 0 | 0 | CO059-01025 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Install Electrical conduit Existing Manhole to SG3 (PDLCO1) | 2 | 0 | 100% | 2022-08-23 | 2022-08-23 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.1.1 | SGS | CO059 | 01030 | 0 | 0 | CO059-01030 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Encase conduit in concrete Existing Manhole to SG3 (PDLCO1) | 1 | 0 | 100% | 2022-08-23 08:00 | 2022-08-24 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.1.1 | SGS | CO059 | 01035 | 0 | 0 | CO059-01035 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Backfill Electrical Existing Manhole to SG3 (PDLCO1) | 2 | 0 | 100% | 2022-08-25 08:00 | 2022-08-25 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
In Progress | CI NYCHA Update #22.1.1 | NA | CO059 | 01050 | 0 | 0 | CO059-01050 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Excavate for New MH to existing MH (PDLCO1) | 3 | 2 | 33% | 2022-03-07 08:00 | 2023-01-05 17:00 | 9 | FSE | 0 | 0 | 0 | 0-NA
Not Started | CI NYCHA Update #22.1.1 | NA | CO059 | 01055 | 0 | 0 | CO059-01055 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Install Electrical conduit for New MH to existing MH (PDLCO1) | 2 | 2 | 0% | 2023-01-09 08:00 | 2023-01-10 17:00 | 9 | FSE | 0 | 0 | 0 | 0-NA
Not Started | CI NYCHA Update #22.1.1 | NA | CO059 | 01060 | 0 | 0 | CO059-01060 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Backfill conduit New MH to Existing Manhole (PDLCO1) | 1 | 1 | 0% | 2023-01-11 08:00 | 2023-01-11 17:00 | 9 | FSE | 0 | 0 | 0 | 0-NA
Not Started | CI NYCHA Update #22.1.1 | NA | CO059 | 01065 | 0 | 0 | CO059-01065 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Pull Cable - New MH to Existing Manhole (PDLCO1) | 2 | 2 | 0% | 2023-01-12 08:00 | 2023-01-13 17:00 | 9 | FSE | 0 | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.1.1 | SGS | CO059 | 01018 | 0 | 0 | CO059-01018 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Install Temp Electrical conduit MH to SG3 (PDLCO1) | 10 | 0 | 100% | 2022-08-11 08:00 | 2022-08-24 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.1.1 | OG6 | CO059 | 02005 | 0 | 0 | CO059-02005 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Excavate for electric Existing Manhole to OG6 (PDLCO1) | 5 | 0 | 100% | 2022-03-01 08:00 | 2022-03-04 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.1.1 | OG6 | CO059 | 02010 | 0 | 0 | CO059-02010 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Install Electrical conduit Existing Manhole to OG6 (PDLCO1) | 5 | 0 | 100% | 2022-04-04 08:00 | 2022-05-19 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.1.1 | OG6 | CO059 | 02015 | 0 | 0 | CO059-02015 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Encase conduit in concrete Existing Manhole to OG6 (PDLCO1) | 2 | 0 | 100% | 2022-05-20 08:00 | 2022-05-23 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.1.1 | OG6 | CO059 | 02020 | 0 | 0 | CO059-02020 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Backfill Electrical Existing Manhole to OG6 (PDLCO1) | 5 | 0 | 100% | 2022-05-24 08:00 | 2022-05-27 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.1 | S8 | CO039 | 01005 | 0 | 0 | CO039-01005 | Change Order | Project Change Orders | 1 | CO #39 - Scope Development - Site 8 Electrical Repairs | 5 | 0 | 100% | 2021-08-30 | 2021-08-31 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.1 | S8 | CO039 | 01010 | 0 | 0 | CO039-01010 | Change Order | Project Change Orders | 1 | CO #39 - Scope Agreement - Site 8 Electrical Repairs | 20 | 0 | 100% | 2021-09-01 | 2021-12-13 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.1 | S8 | CO039 | 01015 | 0 | 0 | CO039-01015 | Change Order | Project Change Orders | 1 | CO #39 - Submit Price - Site 8 Electrical Repairs | 5 | 0 | 100% | 2021-12-14 08:00 | 2021-12-20 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.1 | S8 | CO039 | 01020 | 0 | 0 | CO039-01020 | Change Order | Project Change Orders | 1 | CO #39 - Negotiate/Instruction - Site 8 Electrical Repairs | 20 | 0 | 100% | 2021-12-21 08:00 | 2022-01-26 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.1 | S8 | CO039 | 01025 | 0 | 0 | CO039-01025 | Change Order | Project Change Orders | 1 | CO #39 - Perform Electrical Repairs - Site 8 Basement | 10 | 0 | 100% | 2022-02-14 08:00 | 2022-02-21 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.1 | S8 | CO071 | 01005 | 0 | 0 | CO071-01005 | Change Order | Project Change Orders | 1 | CO #71 (PDLCO3) - Scope Development - Site 8 Basement Cleaning | 5 | 0 | 100% | 2021-12-17 | 2021-12-17 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.1 | S8 | CO071 | 01010 | 0 | 0 | CO071-01010 | Change Order | Project Change Orders | 1 | CO #71 (PDLCO3) - Scope Agreement - Site 8 Basement Cleaning | 20 | 0 | 100% | 2021-12-20 | 2021-12-30 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.1 | S8 | CO071 | 01015 | 0 | 0 | CO071-01015 | Change Order | Project Change Orders | 1 | CO #71 (PDLCO3) - Submit Price - Site 8 Basement Cleaning | 5 | 0 | 100% | 2021-12-31 08:00 | 2022-01-05 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.1 | S8 | CO071 | 01020 | 0 | 0 | CO071-01020 | Change Order | Project Change Orders | 1 | CO #71 (PDLCO3) - Negotiate/Instruction - Site 8 Basement Cleaning | 20 | 0 | 100% | 2022-01-06 08:00 | 2022-01-18 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.1 | S8 | CO071 | 01025 | 0 | 0 | CO071-01025 | Change Order | Project Change Orders | 1 | CO #71 (PDLCO3) - Perform Site 8 Cleaning - Site 8 Basement | 10 | 0 | 100% | 2022-02-11 08:00 | 2022-02-14 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.1.1 | SGS | CO059 | 01006 | 0 | 0 | CO059-01006 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Negotiate - SGS and OGW Electrical Feeder Changes (RFI #370) | 8 | 0 | 100% | 2021-12-29 08:00 | 2022-02-21 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.1 | SG1, SG2, SG3, SG7 | RFI469 | 01005 | 0 | 0 | RFI469-01005 | Change Order | Project Change Orders | 1 | RFI #469 - SG1,2,3, & 7 Electrical Diagrams - Submit | 5 | 0 | 100% | 2021-12-22 | 2022-01-11 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1, SG2, SG3, SG7
Completed | CI NYCHA Update #22.1 | SG1, SG2, SG3, SG7 | RFI469 | 01010 | 0 | 0 | RFI469-01010 | Change Order | Project Change Orders | 1 | RFI #469 - SG1,2,3, & 7 Electrical Diagrams - Response (Inadequate) | 10 | 0 | 100% | 2022-01-12 | 2022-01-20 |  | 0 | 0 | 0 | 0 | 0-SG1, SG2, SG3, SG7
Not Started | CI NYCHA Update #22.1.1 | NA | CO059 | 01052 | 0 | 0 | CO059-01052 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Coring for New MH to existing MH (PDLCO1) | 1 | 1 | 0% | 2023-01-06 08:00 | 2023-01-06 17:00 | 9 | MLJ | CHANGE ORDER | 0 | 0 | 0-NA
Completed | CI NYCHA Update #22.1.1 | SG7 | CO059 | 01090 | 0 | 0 | CO059-01090 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Excavate for New MH to SG7 (PDLCO1) | 2 | 0 | 100% | 2022-02-21 08:00 | 2022-02-24 17:00 |  | 0 | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.1.1 | SG7 | CO059 | 01100 | 0 | 0 | CO059-01100 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Install Electrical conduit for New MH to SG7 (PDLCO1) | 2 | 2 | 0% | 2023-01-18 08:00 | 2023-01-19 17:00 | 9 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.1.1 | SG7 | CO059 | 01105 | 0 | 0 | CO059-01105 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Backfill conduit New MH to SG7 (PDLCO1) | 1 | 1 | 0% | 2023-01-20 08:00 | 2023-01-20 17:00 | 9 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.1.1 | SG7 | CO059 | 01110 | 0 | 0 | CO059-01110 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Pull Cable - New MH to SG7 (PDLCO1) | 2 | 2 | 0% | 2023-01-23 08:00 | 2023-01-24 17:00 | 9 | FSE | 0 | 0 | 0 | 0-SG7
Not Started | CI NYCHA Update #22.1.1 | SG7 | CO059 | 01095 | 0 | 0 | CO059-01095 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Coring for New MH to SG7 (PDLCO1) | 1 | 1 | 0% | 2023-01-17 08:00 | 2023-01-17 17:00 | 9 | MLJ | CHANGE ORDER | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.1.1 | SGS | CO059 | 01022 | 0 | 0 | CO059-01022 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Coring for Existing MH to SG3 (PDLCO1) | 1 | 0 | 100% | 2022-08-19 08:00 | 2022-08-19 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.1.1 | SGS | CO059 | 01023 | 0 | 0 | CO059-01023 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Formwork for Existing MH to SG3 (PDLCO1) | 1 | 0 | 100% | 2022-08-22 08:00 | 2022-08-22 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
In Progress | CI NYCHA Update #22.1.1 | SGS | CO059 | 01040 | 0 | 0 | CO059-01040 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Pull/Terminate/Energize Cable - Existing Manhole to SG3 (PDLCO1) | 20 | 23 | 0% | 2022-08-26 | 2022-12-28 17:00 | 9 | FSE | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.1.1 | SGS | CO059 | 02050 | 0 | 0 | CO059-02050 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Additional Time for Excavation (SGS-01205) | 2 | 0 | 100% | 2022-06-28 08:00 | 2022-06-29 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.1.1 | SGS | CO059 | 02055 | 0 | 0 | CO059-02055 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Additional Time for Backfill (SGS-01220) | 1 | 0 | 100% | 2022-07-05 08:00 | 2022-07-05 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.1 | S81 | CO021 | 01005 | 0 | 0 | CO021-01005 | Change Order | Project Change Orders | 1 | CO #21 - Prep and Submit S8 Fire Standpipe Submittals | 47 | 0 | 100% | 2021-11-24 | 2022-01-27 |  | 0 | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.1 | S81 | CO021 | 01010 | 0 | 0 | CO021-01010 | Change Order | Project Change Orders | 1 | CO #21 - Review/Approve S8 Fire Standpipe Submittals | 10 | 0 | 100% | 2022-01-28 | 2022-02-07 |  | 0 | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.1 | 0 | CO021 | 01015 | 0 | 0 | CO021-01015 | Change Order | Project Change Orders | 1 | CO #21 - Asbestos Abatement including Preparation and Completion of work | 6 | 0 | 100% | 2022-02-08 | 2022-02-18 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | 0 | CO021 | 01020 | 0 | 0 | CO021-01020 | Change Order | Project Change Orders | 1 | CO #21 - DOB ACP 20 | 3 | 0 | 100% | 2022-02-09 | 2022-02-24 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | S81 | CO021 | 01025 | 0 | 0 | CO021-01025 | Change Order | Project Change Orders | 1 | CO #21 - S8 Fire Stand Pipe Relocation Filings | 5 | 0 | 100% | 2022-02-10 | 2022-02-24 |  | 0 | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.1 | S81 | CO021 | 01030 | 0 | 0 | CO021-01030 | Change Order | Project Change Orders | 1 | CO #21 - Initial S8 Fire Stand Pipe Relocation Filing and DOB comments | 55 | 0 | 100% | 2021-11-23 | 2022-02-24 |  | 0 | 0 | 0 | 0 | 0-S81
Completed | CI NYCHA Update #22.1 | SG1, SG2, SG3, SG7 | RFI519 | 01005 | 0 | 0 | RFI519-01005 | Change Order | Project Change Orders | 1 | RFI #519 - SG1,2,3, & 7 Crab Details - Submit | 1 | 0 | 100% | 2022-03-02 | 2022-03-02 17:00 |  | 0 | 0 | 0 | 0 | 0-SG1, SG2, SG3, SG7
Completed | CI NYCHA Update #22.1 | SG1, SG2, SG3, SG7 | RFI519 | 01010 | 0 | 0 | RFI519-01010 | Change Order | Project Change Orders | 1 | RFI #519 - SG1,2,3, & 7 Crab Details - Response (Inadequate) | 10 | 0 | 100% | 2022-03-03 | 2022-03-08 |  | 0 | 0 | 0 | 0 | 0-SG1, SG2, SG3, SG7
Completed | CI NYCHA Update #22.1 | SG1, SG2, SG3, SG7 | RFI540 | 01005 | 0 | 0 | RFI540-01005 | Change Order | Project Change Orders | 1 | RFI #540 - SG1,2,3, & 7 Request for Missing information regd. MH Termination in RFI #519 - Submit | 10 | 0 | 100% | 2022-03-21 | 2022-03-22 |  | 0 | 0 | 0 | 0 | 0-SG1, SG2, SG3, SG7
Completed | CI NYCHA Update #22.1 | SG1, SG2, SG3, SG7 | RFI540 | 01010 | 0 | 0 | RFI540-01010 | Change Order | Project Change Orders | 1 | RFI #540 - SG1,2,3, & 7 Request for Missing information regd. MH Termination in RFI #519 - Response | 10 | 0 | 100% | 2022-03-23 | 2022-04-19 |  | 0 | 0 | 0 | 0 | 0-SG1, SG2, SG3, SG7
Completed | CI NYCHA Update #22.Construction.2.3.5.1 | SG5 | SG5 | 01031 | 0 | 0 | SG5-01031 | Construction | Asbestos Abatement | Construction.2.3.5.1 | Test for Asbestos - 2nd Foor --> SG5 | 10 | 0 | 100% | 2022-08-24 | 2022-08-30 |  | ATCO | ABESTOS | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.1 | SG5 | SG5 | 01032 | 0 | 0 | SG5-01032 | Construction | Asbestos Abatement | Construction.2.3.5.1 | File for Asbestos Abatement- 2nd Foor --> SG5 | 10 | 0 | 100% | 2022-08-30 | 2022-09-05 |  | ATCO | ABESTOS | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.Construction.2.3.5.1 | SG5 | SG5 | 01033 | 0 | 0 | SG5-01033 | Construction | Asbestos Abatement | Construction.2.3.5.1 | Asbestos Abatement - 2nd Foor --> SG5 | 5 | 0 | 100% | 2022-09-06 | 2022-09-09 |  | ATCO | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.1 | 0 | RFI519 | 01015 | 0 | 0 | RFI519-01015 | Change Order | Project Change Orders | 1 | RFI #519 - MLJ Perform Survey & Excavation | 5 | 0 | 100% | 2022-03-21 | 2022-03-21 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | 0 | RFI512 | 01005 | 0 | 0 | RFI512-01005 | Change Order | Project Change Orders | 1 | RFI #512 - SG 1-3 Steam Tunnel Abatement - Submit | 1 | 0 | 100% | 2022-02-24 | 2022-02-24 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | 0 | RFI512 | 01010 | 0 | 0 | RFI512-01010 | Change Order | Project Change Orders | 1 | RFI #512 - SG 1-3 Steam Tunnel Abatement - Response | 10 | 0 | 100% | 2022-02-25 | 2022-03-02 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | 0 | RFI446 | 01005 | 0 | 0 | RFI446-01005 | Change Order | Project Change Orders | 1 | RFI #446 - SG 1-3 Steam Tunnel Abatement - Submit | 1 | 0 | 100% | 2021-10-11 | 2021-10-11 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | 0 | RFI446 | 01010 | 0 | 0 | RFI446-01010 | Change Order | Project Change Orders | 1 | RFI #446 - SG 1-3 Steam Tunnel Abatement - Response | 10 | 0 | 100% | 2021-10-12 | 2021-10-22 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | 0 | RFI389 | 01005 | 0 | 0 | RFI389-01005 | Change Order | Project Change Orders | 1 | RFI #389 - SG 1-3 Steam Tunnel Abatement - Submit | 1 | 0 | 100% | 2021-12-08 | 2021-12-08 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | 0 | RFI389 | 01010 | 0 | 0 | RFI389-01010 | Change Order | Project Change Orders | 1 | RFI #389 - SG 1-3 Steam Tunnel Abatement - Response | 10 | 0 | 100% | 2021-10-11 | 2021-10-11 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.1 | SGS | CO077 | 01005 | 0 | 0 | CO077-01005 | Change Order | Project Change Orders | 1 | CO #77 - Scope Development - SG1-3 Steam Tunnel Abatement (RFI's 389,446,512) | 5 | 0 | 100% | 2022-03-03 08:00 | 2022-03-07 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.1 | SGS | CO077 | 01010 | 0 | 0 | CO077-01010 | Change Order | Project Change Orders | 1 | CO #77 - Scope Agreement - SG1-3 Steam Tunnel Abatement (RFI's 389,446,512) | 20 | 0 | 100% | 2022-03-08 | 2022-03-16 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.1 | SGS | CO077 | 01015 | 0 | 0 | CO077-01015 | Change Order | Project Change Orders | 1 | CO #77 - Submit Price - SG1-3 Steam Tunnel Abatement (RFI's 389,446,512) | 5 | 0 | 100% | 2022-03-17 08:00 | 2022-03-17 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
In Progress | CI NYCHA Update #22.1 | SGS | CO077 | 01020 | 0 | 0 | CO077-01020 | Change Order | Project Change Orders | 1 | CO #77 - Negotiate/Instruction - SG1-3 Steam Tunnel Abatement (RFI's 389,446,512) | 20 | 30 | 0% | 2022-03-18 08:00 | 2023-01-09 17:00 | 97 | MLJ | CHANGE ORDER | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.1 | SGS | CO077 | 01025 | 0 | 0 | CO077-01025 | Change Order | Project Change Orders | 1 | CO #77 - SG1-3 Steam Tunnel Abatement (RFI's 389,446,512) | 12 | 0 | 100% | 2022-03-28 | 2022-04-15 |  | 0 | 0 | 0 | 0 | 0-SGS
Not Started | CI NYCHA Update #22.1.1 | SG7 | CO059 | 01045 | 0 | 0 | CO059-01045 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Remove Existing Ductbank East of SG7 | 3 | 3 | 0% | 2022-12-29 08:00 | 2023-01-03 17:00 | 9 | MLJ | CHANGE ORDER | 0 | 0 | 0-SG7
Completed | CI NYCHA Update #22.19 | OG1 | RFI462 | 01015 | 0 | 0 | RFI462-01015 | Delays | Project Delays | 19 | RFI #462 - Second Floor Apt Gas Riser Relocation - OG1 - Submit | 1 | 0 | 100% | 2021-12-20 08:00 | 2021-12-27 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.19 | 0 | RFI462 | 01020 | 0 | 0 | RFI462-01020 | Delays | Project Delays | 19 | RFI #462 - Second Floor Apt Gas Riser Relocation - Response | 10 | 0 | 100% | 2021-12-28 | 2022-04-12 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | RFI548 | 01005 | 0 | 0 | RFI548-01005 | Delays | Project Delays | 19 | RFI #548 - Second Floor Apt Gas Riser Relocation - Submit | 1 | 0 | 100% | 2022-04-04 08:00 | 2022-04-08 17:00 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | RFI548 | 01010 | 0 | 0 | RFI548-01010 | Delays | Project Delays | 19 | RFI #548 - Second Floor Apt Gas Riser Relocation - Response | 10 | 0 | 100% | 2022-04-09 | 2022-04-13 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | OG1 | RFI548 | 01015 | 0 | 0 | RFI548-01015 | Delays | Project Delays | 19 | RFI #548 - Second Floor Apt Gas Riser Relocation - OG1 | 3 | 0 | 100% | 2022-04-14 08:00 | 2022-04-18 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.19 | OG1 | RFI548 | 01020 | 0 | 0 | RFI548-01020 | Delays | Project Delays | 19 | RFI #548 - Second Floor Apt Gas Riser Relocation - OG1 DOB Inspection Failed | 3 | 0 | 100% | 2022-04-19 | 2022-04-21 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.19 | OG1 | RFI548 | 01025 | 0 | 0 | RFI548-01025 | Delays | Project Delays | 19 | RFI #548 - Second Floor Apt Gas Riser Relocation by NYCHA - OG1 | 25 | 0 | 100% | 2022-11-03 | 2022-11-03 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.19 | SG4 | RFI548 | 01030 | 0 | 0 | RFI548-01030 | Delays | Project Delays | 19 | RFI #548 - Second Floor Apt Gas Riser Relocation by NYCHA - SG4 | 25 | 0 | 100% | 2022-11-03 | 2022-11-03 |  | 0 | 0 | 0 | 0 | 0-SG4
Completed | CI NYCHA Update #22.19 | SG5 | RFI548 | 01035 | 0 | 0 | RFI548-01035 | Delays | Project Delays | 19 | RFI #548 - Second Floor Apt Gas Riser Relocation by NYCHA - SG5 | 25 | 0 | 100% | 2022-11-03 | 2022-11-03 |  | 0 | 0 | 0 | 0 | 0-SG5
Completed | CI NYCHA Update #22.19 | SG3 | RFI548 | 01040 | 0 | 0 | RFI548-01040 | Delays | Project Delays | 19 | RFI #548 - Second Floor Apt Gas Riser Relocation by NYCHA - SG3 | 25 | 0 | 100% | 2022-11-03 | 2022-11-03 |  | 0 | 0 | 0 | 0 | 0-SG3
Completed | CI NYCHA Update #22.19 | OG2 | RFI548 | 01045 | 0 | 0 | RFI548-01045 | Delays | Project Delays | 19 | RFI #548 - Second Floor Apt Gas Riser Relocation by NYCHA - OG2 | 25 | 0 | 100% | 2022-11-03 | 2022-11-03 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.19 | OG3 | RFI548 | 01050 | 0 | 0 | RFI548-01050 | Delays | Project Delays | 19 | RFI #548 - Second Floor Apt Gas Riser Relocation by NYCHA - OG3 | 25 | 0 | 100% | 2022-11-03 | 2022-11-03 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.19 | OG4 | RFI548 | 01055 | 0 | 0 | RFI548-01055 | Delays | Project Delays | 19 | RFI #548 - Second Floor Apt Gas Riser Relocation by NYCHA - OG4 | 25 | 0 | 100% | 2022-11-03 | 2022-11-03 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.19 | OG5 | RFI548 | 01060 | 0 | 0 | RFI548-01060 | Delays | Project Delays | 19 | RFI #548 - Second Floor Apt Gas Riser Relocation by NYCHA - OG5 | 25 | 0 | 100% | 2022-11-03 | 2022-11-03 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.19 | OG6 | RFI548 | 01065 | 0 | 0 | RFI548-01065 | Delays | Project Delays | 19 | RFI #548 - Second Floor Apt Gas Riser Relocation by NYCHA - OG6 | 25 | 0 | 100% | 2022-11-03 | 2022-11-03 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.1.1 | SGS | CO059 | 01011 | 0 | 0 | CO059-01011 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Provide Proposal inc pricing on alternatives - SGS - (FSE CO: 18-0016) | 5 | 0 | 100% | 2022-04-29 08:00 | 2022-05-13 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.1.1 | SGS | CO059 | 01012 | 0 | 0 | CO059-01012 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - NYCHA Confirm Scope - SGS - (FSE CO: 18-0016) | 10 | 0 | 100% | 2022-05-06 08:00 | 2022-05-13 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.1 | #N/A | #N/A | #N/A | #N/A | #N/A | CO063-01005 | Change Order | Project Change Orders | 1 | CO #63 - Scope Development - Support for Electrical Conduit Concrete Encasements | 10 | 0 | 100% | 2021-11-01 08:00 | 2021-11-15 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | #N/A | #N/A | #N/A | #N/A | #N/A | CO063-01010 | Change Order | Project Change Orders | 1 | CO #63 - Scope Agreement - Support for Electrical Conduit Concrete Encasements | 15 | 0 | 100% | 2021-11-16 08:00 | 2022-09-27 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | #N/A | #N/A | #N/A | #N/A | #N/A | CO063-01015 | Change Order | Project Change Orders | 1 | CO #63 - Submit Price - Support for Electrical Conduit Concrete Encasements | 10 | 0 | 100% | 2022-09-28 | 2022-09-29 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | #N/A | #N/A | #N/A | #N/A | #N/A | CO063-01020 | Change Order | Project Change Orders | 1 | CO #63 - Negotiate/Instruction - Support for Electrical Conduit Concrete Encasements | 30 | 0 | 100% | 2022-09-30 | 2022-10-19 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #22.Construction.2.4.7.1 | SG6 | SG6 | 02112 | 0 | 0 | SG6-02112 | Construction | 1st Floor | Construction.2.4.7.1 | Encase Electrical Conduits - 1st Floor | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | -29 | MLJ | CONCRETE | CONDUIT ENCASE | 03-1105 | 03-1105-SG6
Not Started | CI NYCHA Update #22.Construction.2.2.6.1 | SG4 | SG4 | 02232 | 0 | 0 | SG4-02232 | Construction | Cellar | Construction.2.2.6.1 | Encase Electrical Conduits - Cellar | 10 | 10 | 0% | 2022-11-30 08:00 | 2022-12-13 17:00 | -28 | MLJ | CONCRETE | CONDUIT ENCASE | 03-1105 | 03-1105-SG4
Not Started | CI NYCHA Update #22.Construction.2.3.6.1 | SG5 | SG5 | 02217 | 0 | 0 | SG5-02217 | Construction | Cellar | Construction.2.3.6.1 | Encase Electrical Conduits - Cellar | 10 | 10 | 0% | 2022-12-22 08:00 | 2023-01-06 17:00 | -36 | MLJ | CONCRETE | CONDUIT ENCASE | 03-1105 | 03-1105-SG5
Not Started | CI NYCHA Update #22.Construction.3.1.8.1 | OG8 | OG8 | 02117 | 0 | 0 | OG8-02117 | Construction | 1st Floor | Construction.3.1.8.1 | Encase Electrical Conduits - 1st Floor | 10 | 10 | 0% | 2022-11-28 08:00 | 2022-12-09 17:00 | -4 | MLJ | CONCRETE | CONDUIT ENCASE | 03-1105 | 03-1105-OG8
Not Started | CI NYCHA Update #22.Construction.3.6.8.1 | OG4 | OG4 | 02022 | 0 | 0 | OG4-02022 | Construction | Cellar | Construction.3.6.8.1 | Encase Electrical Conduits - Cellar | 10 | 10 | 0% | 2022-12-09 08:00 | 2022-12-22 17:00 | -16 | MLJ | CONCRETE | CONDUIT ENCASE | 03-1105 | 03-1105-OG4
Not Started | CI NYCHA Update #22.Construction.3.3.8.1 | OG5 | OG5 | 02017 | 0 | 0 | OG5-02017 | Construction | Cellar | Construction.3.3.8.1 | Encase Electrical Conduits - Cellar | 10 | 10 | 0% | 2022-12-08 13:00 | 2022-12-22 12:00 | -10 | MLJ | CONCRETE | CONDUIT ENCASE | 03-1105 | 03-1105-OG5
Not Started | CI NYCHA Update #22.Construction.5.4.5.1 | OG9 | OG9 | 02117 | 0 | 0 | OG9-02117 | Construction | 1st Floor | Construction.5.4.5.1 | Encase Electrical Conduits - 1st Floor | 10 | 10 | 0% | 2022-11-29 08:00 | 2022-12-12 17:00 | -13 | MLJ | CONCRETE | CONDUIT ENCASE | 03-1105 | 03-1105-OG9
Not Started | CI NYCHA Update #22.Construction.5.3.8.1 | OG3 | OG3 | 02022 | 0 | 0 | OG3-02022 | Construction | Cellar | Construction.5.3.8.1 | Encase Electrical Conduits - Cellar | 10 | 10 | 0% | 2022-12-23 11:12 | 2023-01-10 11:12 | -7 | MLJ | CONCRETE | CONDUIT ENCASE | 03-1105 | 03-1105-OG3
Not Started | CI NYCHA Update #22.Construction.5.2.8.1 | OG2 | OG2 | 02022 | 0 | 0 | OG2-02022 | Construction | Cellar | Construction.5.2.8.1 | Encase Electrical Conduits - Cellar | 10 | 10 | 0% | 2022-12-06 08:00 | 2022-12-19 17:00 | -26 | MLJ | CONCRETE | CONDUIT ENCASE | 03-1105 | 03-1105-OG2
Not Started | CI NYCHA Update #22.Construction.1.4.5.1 | OG10 | OG10 | 02117 | 0 | 0 | OG10-02117 | Construction | 1st Floor | Construction.1.4.5.1 | Encase Electrical Conduits - 1st Floor | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | 36 | MLJ | CONCRETE | CONDUIT ENCASE | 03-1105 | 03-1105-OG10
Not Started | CI NYCHA Update #22.Construction.1.2.5.1 | OG6 | OG6 | 02022 | 0 | 0 | OG6-02022 | Construction | Cellar | Construction.1.2.5.1 | Encase Electrical Conduits - Cellar | 10 | 10 | 0% | 2023-01-24 08:00 | 2023-02-06 17:00 | -12 | MLJ | CONCRETE | CONDUIT ENCASE | 03-1105 | 03-1105-OG6
Not Started | CI NYCHA Update #22.Construction.1.3.5.1 | OG1 | OG1 | 02017 | 0 | 0 | OG1-02017 | Construction | Cellar | Construction.1.3.5.1 | Encase Electrical Conduits - Cellar | 10 | 10 | 0% | 2022-12-07 08:00 | 2022-12-20 17:00 | 36 | MLJ | CONCRETE | CONDUIT ENCASE | 03-1105 | 03-1105-OG1
Not Started | CI NYCHA Update #22.Construction.4.4.5.1 | SG7 | SG7 | 02117 | 0 | 0 | SG7-02117 | Construction | 1st Floor | Construction.4.4.5.1 | Encase Electrical Conduits - 1st Floor | 10 | 10 | 0% | 2022-12-15 08:00 | 2022-12-29 17:00 | 34 | MLJ | CONCRETE | CONDUIT ENCASE | 03-1105 | 03-1105-SG7
Not Started | CI NYCHA Update #22.Construction.4.3.8.1 | SG3 | SG3 | 02017 | 0 | 0 | SG3-02017 | Construction | Cellar | Construction.4.3.8.1 | Encase Electrical Conduits - Cellar | 10 | 10 | 0% | 2022-12-13 08:00 | 2022-12-27 17:00 | 31 | MLJ | CONCRETE | CONDUIT ENCASE | 03-1105 | 03-1105-SG3
Not Started | CI NYCHA Update #22.Construction.4.7.8.1 | SG1 | SG1 | 02037 | 0 | 0 | SG1-02037 | Construction | Cellar | Construction.4.7.8.1 | Encase Electrical Conduits - Cellar | 10 | 10 | 0% | 2023-02-03 08:00 | 2023-02-16 17:00 | 10 | MLJ | CONCRETE | CONDUIT ENCASE | 03-1105 | 03-1105-SG1
Not Started | CI NYCHA Update #22.Construction.4.2.4.1 | SG2 | SG2 | 02022 | 0 | 0 | SG2-02022 | Construction | Cellar | Construction.4.2.4.1 | Encase Electrical Conduits - Cellar | 10 | 10 | 0% | 2023-02-27 08:00 | 2023-03-10 17:00 | -5 | MLJ | CONCRETE | CONDUIT ENCASE | 03-1105 | 03-1105-SG2
Not Started | CI NYCHA Update #22.Construction.8.2.5.1 | S82 | S8A | 02142 | 0 | 0 | S8A-02142 | Construction | 1st Floor | Construction.8.2.5.1 | Encase Electrical Conduits - 1st Floor | 10 | 10 | 0% | 2022-12-06 13:00 | 2022-12-20 12:00 | 41 | MLJ | CONCRETE | CONDUIT ENCASE | 03-1105 | 03-1105-S82
Not Started | CI NYCHA Update #22.Construction.8.1.8.1 | S81 | S8E | 02032 | 0 | 0 | S8E-02032 | Construction | Cellar | Construction.8.1.8.1 | Encase Electrical Conduits - Cellar | 10 | 10 | 0% | 2023-01-09 08:00 | 2023-01-23 17:00 | 28 | MLJ | CONCRETE | CONDUIT ENCASE | 03-1105 | 03-1105-S81
Completed | CI NYCHA Update #22.19 | 0 | RFI546 | 01005 | 0 | 0 | RFI546-01005 | Delays | Project Delays | 19 | RFI 546 - Tree Clash with Underground Steam OG East - Submit | 5 | 0 | 100% | 2022-04-01 | 2022-04-01 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | 0 | RFI546 | 01010 | 0 | 0 | RFI546-01010 | Delays | Project Delays | 19 | RFI 546 - Tree Clash with Underground Steam OG East - Response | 10 | 0 | 100% | 2022-04-04 | 2022-05-17 |  | 0 | 0 | 0 | 0 | 0-0
Completed | CI NYCHA Update #22.19 | OG4 | DELAY | 02105 | 0 | 0 | DELAY-02105 | Delays | Project Delays | 19 | Delay - Unable to Pull Permit due to NYCHA Violations - OG4 | 20 | 0 | 100% | 2022-05-27 | 2022-06-20 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.19 | OG5 | DELAY | 02110 | 0 | 0 | DELAY-02110 | Delays | Project Delays | 19 | Delay - Unable to Pull Permit due to NYCHA Violations - OG5 | 20 | 0 | 100% | 2022-05-27 | 2022-06-20 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.1.1 | SGS | CO059 | 01007 | 0 | 0 | CO059-01007 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Neg Revised Scope - SGS and OGW Electrical Feeder Changes (RFI #370) - N/A (Replaced w/1000a-1000k) | 10 | 0 | 100% | 2022-02-22 08:00 | 2022-06-24 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.1.1 | SGS | CO059 | 01008 | 0 | 0 | CO059-01008 | Change Order | Change Order #59 | 1.1 | CO #59 (PDLCO1) - Issue Instruction - SGS and OGW Electrical Feeder Changes (RFI #370) - N/A (Replaced w/1000a-1000k) | 20 | 0 | 100% | 2022-06-24 08:00 | 2022-06-24 17:00 |  | 0 | 0 | 0 | 0 | 0-SGS
Completed | CI NYCHA Update #22.19 | S8 | RFI589 | 01015 | 0 | 0 | RFI589-01015 | Delays | Project Delays | 19 | RFI #589 - Site 8 Access Space - Response | 25 | 0 | 100% | 2022-06-20 | 2022-07-22 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.19 | S8 | RFI589 | 01010 | 0 | 0 | RFI589-01010 | Delays | Project Delays | 19 | RFI #589 - Site 8 Access Space - Submit | 25 | 0 | 100% | 2022-06-01 | 2022-06-17 17:00 |  | 0 | 0 | 0 | 0 | 0-S8
Completed | CI NYCHA Update #22.19 | OG4 | DELAY | 04005 | 0 | 0 | DELAY-04005 | Delays | Project Delays | 19 | Remove AC units from First floor apartments OG4 | 20 | 0 | 100% | 2022-08-09 08:00 | 2022-08-19 17:00 |  | 0 | 0 | 0 | 0 | 0-OG4
Completed | CI NYCHA Update #22.19 | OG5 | DELAY | 04010 | 0 | 0 | DELAY-04010 | Delays | Project Delays | 19 | Remove AC units from First floor apartments OG5 | 20 | 0 | 100% | 2022-08-09 08:00 | 2022-08-19 17:00 |  | 0 | 0 | 0 | 0 | 0-OG5
Completed | CI NYCHA Update #22.19 | OG3 | DELAY | 04015 | 0 | 0 | DELAY-04015 | Delays | Project Delays | 19 | Remove AC units from First floor apartments OG3 | 20 | 0 | 100% | 2022-08-09 08:00 | 2022-08-19 17:00 |  | 0 | 0 | 0 | 0 | 0-OG3
Completed | CI NYCHA Update #22.19 | OG2 | DELAY | 04020 | 0 | 0 | DELAY-04020 | Delays | Project Delays | 19 | Remove AC units from First floor apartments OG2 | 20 | 0 | 100% | 2022-08-09 08:00 | 2022-08-19 17:00 |  | 0 | 0 | 0 | 0 | 0-OG2
Completed | CI NYCHA Update #22.19 | OG6 | DELAY | 04025 | 0 | 0 | DELAY-04025 | Delays | Project Delays | 19 | Remove AC units from First floor apartments OG6 | 20 | 0 | 100% | 2022-08-09 08:00 | 2022-08-19 17:00 |  | 0 | 0 | 0 | 0 | 0-OG6
Completed | CI NYCHA Update #22.19 | OG1 | DELAY | 04030 | 0 | 0 | DELAY-04030 | Delays | Project Delays | 19 | Remove AC units from First floor apartments OG1 | 20 | 0 | 100% | 2022-08-09 08:00 | 2022-08-19 17:00 |  | 0 | 0 | 0 | 0 | 0-OG1
Completed | CI NYCHA Update #22.19 | SG2 | DELAY | 05005 | 0 | 0 | DELAY-05005 | Delays | Project Delays | 19 | NYCHA Relocate Tenant Association Plants --> SG1 & SG2 | 20 | 0 | 100% | 2022-06-01 08:00 | 2022-06-24 |  | 0 | 0 | 0 | 0 | 0-SG2
Completed | CI NYCHA Update #22.1.1 | 0 | CO059 | 01000a | 0 | 0 | CO059-01000a | Change Order | Change Order #59 | 1.1 | CO #PCO 59 Rev 1 Issued 12/20/21 | 31 | 0 | 100% | 2021-11-04 | 2021-12-20 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1.1 | 0 | CO059 | 01000b | 0 | 0 | CO059-01000b | Change Order | Change Order #59 | 1.1 | CO #PCO 59 Rev 2 Issued 1/10/22 | 13 | 0 | 100% | 2021-12-21 | 2022-01-10 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1.1 | 0 | CO059 | 01000c | 0 | 0 | CO059-01000c | Change Order | Change Order #59 | 1.1 | CO #PCO 59 Initial Negotiation agreed 3/4/22 | 37 | 0 | 100% | 2022-01-11 | 2022-03-04 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1.1 | 0 | CO059 | 01000d | 0 | 0 | CO059-01000d | Change Order | Change Order #59 | 1.1 | CO #PCO 59 Rev 3 Issued 3/25/22 | 15 | 0 | 100% | 2022-03-07 | 2022-03-25 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1.1 | 0 | CO059 | 01000e | 0 | 0 | CO059-01000e | Change Order | Change Order #59 | 1.1 | CO #PCO 59 Rev 4 Issued 5/20 | 40 | 0 | 100% | 2022-03-28 | 2022-05-20 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1.1 | 0 | CO059 | 01000f | 0 | 0 | CO059-01000f | Change Order | Change Order #59 | 1.1 | CO #PCO 59 Rev 5 issued 5/27 | 5 | 0 | 100% | 2022-05-23 | 2022-05-27 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1.1 | 0 | CO059 | 01000g | 0 | 0 | CO059-01000g | Change Order | Change Order #59 | 1.1 | CO #PCO 59 Rev 6 issued 7/13 | 31 | 0 | 100% | 2022-05-31 | 2022-07-13 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1.1 | 0 | CO059 | 01000h | 0 | 0 | CO059-01000h | Change Order | Change Order #59 | 1.1 | CO #PCO 59 - Meeting with EOR on 7/14 | 1 | 0 | 100% | 2022-07-14 08:00 | 2022-07-14 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1.1 | 0 | CO059 | 01000i | 0 | 0 | CO059-01000i | Change Order | Change Order #59 | 1.1 | CO #PCO 59 Rev 7 issued 7/19 (2 options for EOR comments) | 3 | 0 | 100% | 2022-07-15 08:00 | 2022-07-19 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1.1 | 0 | CO059 | 01000j | 0 | 0 | CO059-01000j | Change Order | Change Order #59 | 1.1 | CO #PCO 59 Rev 8 issued 7/26 | 5 | 0 | 100% | 2022-07-20 08:00 | 2022-07-26 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1.1 | 0 | CO059 | 01000k | 0 | 0 | CO059-01000k | Change Order | Change Order #59 | 1.1 | CO #PCO 59 - PCO 59 Scope Agreed 7/26 | 1 | 0 | 100% | 2022-07-26 08:00 | 2022-07-26 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.19 | S8 | DELAY | 01111 | 0 | 0 | DELAY-01111 | Delays | Project Delays | 19 | Basement not in a suitable condition for Engineering - Site 8 | 90 | 0 | 100% | 2020-06-14 08:00 | 2022-03-25 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | 0 | COXXX | 01005 | 0 | 0 | COXXX-01005 | Change Order | Project Change Orders | 1 | CO #XX (TBD) - SWO Issued for waterproofing existing buildings | 20 | 0 | 100% | 2022-06-20 08:00 | 2022-07-22 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | SGS | #N/A | #N/A | #N/A | #N/A | CO102-01005 | Change Order | Project Change Orders | 1 | CO #102 - Scope Development - SGS Shutdown Temp Power | 5 | 0 | 100% | 2022-07-25 08:00 | 2022-07-28 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | SGS | #N/A | #N/A | #N/A | #N/A | CO102-01010 | Change Order | Project Change Orders | 1 | CO #102 - Scope Agreement - SGS Shutdown Temp Power | 10 | 0 | 100% | 2022-07-29 08:00 | 2022-08-25 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | SGS | #N/A | #N/A | #N/A | #N/A | CO102-01015 | Change Order | Project Change Orders | 1 | CO #102 - Submit Price - SGS Shutdown Temp Power | 10 | 0 | 100% | 2022-08-25 08:00 | 2022-09-01 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | SGS | #N/A | #N/A | #N/A | #N/A | CO102-01020 | Change Order | Project Change Orders | 1 | CO #102 - Negotiate/Instruction - SGS Shutdown Temp Power | 160 | 0 | 100% | 2022-09-02 | 2022-09-30 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #22.1 | NA | #N/A | #N/A | #N/A | #N/A | CO102-01025 | Change Order | Project Change Orders | 1 | CO #102 - Provide Temp Power for Shutdown | 1 | 1 | 0% | 2022-11-25 08:00 | 2022-11-25 17:00 | 31 | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | SG7, OG8, OG9, OG10, Site 8 | #N/A | #N/A | #N/A | #N/A | CO100-01005 | Change Order | Project Change Orders | 1 | CO #100 - Scope Development - Exterior Metal Panel Support SG7,OG8,OG9 OG10, Site 8 | 5 | 0 | 100% | 2022-06-25 08:00 | 2022-07-25 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | SG7, OG8, OG9, OG10, Site 8 | #N/A | #N/A | #N/A | #N/A | CO100-01010 | Change Order | Project Change Orders | 1 | CO #100 - Scope Agreement - Exterior Metal Panel Support SG7,OG8,OG9 OG10, Site 8 | 15 | 0 | 100% | 2022-07-26 | 2022-10-05 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | SG7, OG8, OG9, OG10, Site 8 | #N/A | #N/A | #N/A | #N/A | CO100-01015 | Change Order | Project Change Orders | 1 | CO #100 - Submit Price - Exterior Metal Panel Support SG7,OG8,OG9 OG10, Site 8 | 10 | 0 | 100% | 2022-10-05 | 2022-10-05 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | SG7, OG8, OG9, OG10, Site 8 | #N/A | #N/A | #N/A | #N/A | CO100-01020 | Change Order | Project Change Orders | 1 | CO #100 - Negotiate/Instruction - Exterior Metal Panel Support SG7,OG8,OG9 OG10, Site 8 | 30 | 0 | 100% | 2022-10-05 | 2022-10-05 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #22.1 | SG7 | #N/A | #N/A | #N/A | #N/A | CO100-01025 | Change Order | Project Change Orders | 1 | CO #100 - Install Additional Metal Panel Support SG7 | 20 | 20 | 0% | 2022-11-25 08:00 | 2022-12-22 17:00 | -20 | #N/A | #N/A | #N/A | #N/A | #N/A
In Progress | CI NYCHA Update #22.1 | OG8 | #N/A | #N/A | #N/A | #N/A | CO100-01030 | Change Order | Project Change Orders | 1 | CO #100 - Install Additional Metal Panel Support OG8 | 20 | 15 | 25% | 2022-09-23 | 2022-12-15 17:00 | 56 | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | OG9 | #N/A | #N/A | #N/A | #N/A | CO100-01035 | Change Order | Project Change Orders | 1 | CO #100 - Install Additional Metal Panel Support OG9 | 20 | 0 | 100% | 2022-07-05 | 2022-08-15 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | OG10 | #N/A | #N/A | #N/A | #N/A | CO100-01040 | Change Order | Project Change Orders | 1 | CO #100 - Install Additional Metal Panel Support OG10 | 20 | 0 | 100% | 2022-08-10 | 2022-10-14 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #22.1 | S82 | #N/A | #N/A | #N/A | #N/A | CO100-01045 | Change Order | Project Change Orders | 1 | CO #100 - Install Additional Metal Panel Support S8A | 20 | 20 | 0% | 2022-11-25 08:00 | 2022-12-22 17:00 | 55 | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | OG6 | #N/A | #N/A | #N/A | #N/A | CO098-01005 | Change Order | Project Change Orders | 1 | CO #98 - Scope Development - OG6 Structural Steel Interference | 5 | 0 | 100% | 2022-06-18 | 2022-07-18 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | OG6 | #N/A | #N/A | #N/A | #N/A | CO098-01010 | Change Order | Project Change Orders | 1 | CO #98 - Scope Agreement - OG6 Structural Steel Interference | 30 | 0 | 100% | 2022-07-19 | 2022-11-17 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | OG6 | #N/A | #N/A | #N/A | #N/A | CO098-01015 | Change Order | Project Change Orders | 1 | CO #98 - Submit Price - OG6 Structural Steel Interference | 10 | 0 | 100% | 2022-11-17 | 2022-11-17 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | OG6 | #N/A | #N/A | #N/A | #N/A | CO098-01020 | Change Order | Project Change Orders | 1 | CO #98 - Negotiate/Instruction - OG6 Structural Steel Interference | 30 | 0 | 100% | 2022-11-17 | 2022-11-17 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #22.1 | NA | #N/A | #N/A | #N/A | #N/A | CO098-01025 | Change Order | Project Change Orders | 1 | CO #98 - Make changes to structural steel supports | 10 | 10 | 0% | 2022-11-25 08:00 | 2022-12-08 17:00 | -74 | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | #N/A | #N/A | #N/A | #N/A | #N/A | CO093-01005 | Change Order | Project Change Orders | 1 | CO #93 - Scope Development - Roof Access and ATS Room Door Issue | 5 | 0 | 100% | 2022-05-15 08:00 | 2022-06-15 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | #N/A | #N/A | #N/A | #N/A | #N/A | CO093-01010 | Change Order | Project Change Orders | 1 | CO #93 - Scope Agreement - Roof Access and ATS Room Door Issue | 30 | 0 | 100% | 2022-06-16 | 2022-06-27 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | #N/A | #N/A | #N/A | #N/A | #N/A | CO093-01015 | Change Order | Project Change Orders | 1 | CO #93 - Submit Price - Roof Access and ATS Room Door Issue | 10 | 0 | 100% | 2022-06-28 08:00 | 2022-07-13 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | #N/A | #N/A | #N/A | #N/A | #N/A | CO093-01020 | Change Order | Project Change Orders | 1 | CO #93 - Negotiate/Instruction - Roof Access and ATS Room Door Issue | 160 | 0 | 100% | 2022-07-13 08:00 | 2022-10-04 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | SG6 | #N/A | #N/A | #N/A | #N/A | CO093-01025 | Change Order | Project Change Orders | 1 | CO #93 - Manufacture Steel - SG6 | 20 | 0 | 100% | 2022-10-04 | 2022-10-07 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.1 | SG6 | #N/A | #N/A | #N/A | #N/A | CO093-01030 | Change Order | Project Change Orders | 1 | CO #93 - Remove Blockwork and protect equipment - SG6 | 5 | 0 | 100% | 2022-10-04 | 2022-10-07 |  | #N/A | #N/A | #N/A | #N/A | #N/A
In Progress | CI NYCHA Update #22.1 | SG6 | #N/A | #N/A | #N/A | #N/A | CO093-01035 | Change Order | Project Change Orders | 1 | CO #93 - Install Steel Supports - SG6 | 5 | 2 | 60% | 2022-10-09 | 2022-11-28 17:00 | 103 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #22.1 | SG6 | #N/A | #N/A | #N/A | #N/A | CO093-01040 | Change Order | Project Change Orders | 1 | CO #93 - Fireproof Steel Supports - SG6 | 5 | 5 | 0% | 2022-11-29 08:00 | 2022-12-05 17:00 | 103 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #22.1 | OG8 | #N/A | #N/A | #N/A | #N/A | CO093-01105 | Change Order | Project Change Orders | 1 | CO #93 - Manufacture Steel - OG8 | 20 | 20 | 0% | 2022-11-25 08:00 | 2022-12-22 17:00 | 41 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #22.1 | OG8 | #N/A | #N/A | #N/A | #N/A | CO093-01110 | Change Order | Project Change Orders | 1 | CO #93 - Remove Blockwork and protect equipment - OG8 | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | 41 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #22.1 | OG8 | #N/A | #N/A | #N/A | #N/A | CO093-01115 | Change Order | Project Change Orders | 1 | CO #93 - Install Steel Supports - OG8 | 5 | 5 | 0% | 2023-01-03 08:00 | 2023-01-09 17:00 | 41 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #22.1 | OG8 | #N/A | #N/A | #N/A | #N/A | CO093-01120 | Change Order | Project Change Orders | 1 | CO #93 - Fireproof Steel Supports - OG8 | 5 | 5 | 0% | 2023-01-10 08:00 | 2023-01-17 17:00 | 41 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #22.1 | OG10 | #N/A | #N/A | #N/A | #N/A | CO093-01205 | Change Order | Project Change Orders | 1 | CO #93 - Manufacture Steel - OG10 | 20 | 20 | 0% | 2022-11-25 08:00 | 2022-12-22 17:00 | 36 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #22.1 | OG10 | #N/A | #N/A | #N/A | #N/A | CO093-01210 | Change Order | Project Change Orders | 1 | CO #93 - Remove Blockwork and protect equipment - OG10 | 5 | 5 | 0% | 2022-12-23 08:00 | 2022-12-30 17:00 | 36 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #22.1 | OG10 | #N/A | #N/A | #N/A | #N/A | CO093-01215 | Change Order | Project Change Orders | 1 | CO #93 - Install Steel Supports - OG10 | 5 | 5 | 0% | 2023-01-03 08:00 | 2023-01-09 17:00 | 36 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #22.1 | OG10 | #N/A | #N/A | #N/A | #N/A | CO093-01220 | Change Order | Project Change Orders | 1 | CO #93 - Fireproof Steel Supports - OG10 | 5 | 5 | 0% | 2023-01-10 08:00 | 2023-01-17 17:00 | 36 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #22.1 | OG9 | #N/A | #N/A | #N/A | #N/A | CO093-01315 | Change Order | Project Change Orders | 1 | CO #93 - Cut Steel and blockwork and protect equipment - OG9 | 5 | 5 | 0% | 2022-11-25 08:00 | 2022-12-01 17:00 | 53 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #22.1 | OG9 | #N/A | #N/A | #N/A | #N/A | CO093-01320 | Change Order | Project Change Orders | 1 | CO #93 - Fireproof Steel Supports - OG9 | 5 | 5 | 0% | 2022-12-02 08:00 | 2022-12-08 17:00 | 53 | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.19 | S8 | #N/A | #N/A | #N/A | #N/A | RFI589-01005 | Delays | Project Delays | 19 | RFI #589 - Site 8 Access Space - Submit | 1 | 0 | 100% | 2022-06-17 08:00 | 2022-06-17 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.19 | S8 | #N/A | #N/A | #N/A | #N/A | RFI589-01020 | Delays | Project Delays | 19 | RFI #589 - Site 8 Access Space - Response | 5 | 0 | 100% | 2022-06-20 08:00 | 2022-07-22 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.19 | S8 | #N/A | #N/A | #N/A | #N/A | RFI625-01005 | Delays | Project Delays | 19 | RFI #625 - Site 8 Access Space - Submit | 10 | 0 | 100% | 2022-07-25 08:00 | 2022-08-08 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #22.19 | S8 | #N/A | #N/A | #N/A | #N/A | RFI625-01010 | Delays | Project Delays | 19 | RFI #625 - Site 8 Access Space - Response | 15 | 0 | 100% | 2022-08-09 08:00 | 2022-09-06 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #23.19 |  | x |  |  |  | RFI557-01005 |  |  |  | RFI #557 - 2nd FL Electrical Room Lockable Gas Valve - Submit | 5 | 0 | 100% | 2022-04-22 | 2022-04-27 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #23.19 |  | x |  |  |  | RFI557-01010 |  |  |  | RFI #557 - 2nd FL Electrical Room Lockable Gas Valve - Response | 10 | 0 | 100% | 2022-04-28 | 2022-06-09 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #23.19 |  | x |  |  |  | RFI557-01015 |  |  |  | RFI #557 - Weekly Progress Meeting Item 68.2 - 2nd Floor Apt DOB Approved Plumbing Dwgs - NYCHA Rev. Schedule B | 60 | 0 | 100% | 2022-06-10 08:00 | 2022-11-03 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.1 |  | x |  |  |  | CO108-01005 |  |  |  | CO #108 - Scope Development - Replace Steam & Water Pipe under W33rd | 5 | 0 | 100% | 2022-08-12 08:00 | 2022-09-11 |  | #N/A | #N/A | #N/A | #N/A | #N/A
In Progress | CI NYCHA Update #25.1 | NA | x |  |  |  | CO108-01010 | Change Order | Project Change Orders |  | CO #108 - Scope Agreement - Replace Steam & Water Pipe under W33rd | 10 | 20 | 0% | 2022-09-12 08:00 | 2022-12-22 17:00 | -193 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1 | NA | x |  |  |  | CO108-01015 | Change Order | Project Change Orders |  | CO #108 - Submit Price - Replace Steam & Water Pipe under W33rd | 10 | 10 | 0% | 2022-12-23 08:00 | 2023-01-09 17:00 | -193 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1 | NA | x |  |  |  | CO108-01020 | Change Order | Project Change Orders |  | CO #108 - Negotiate/Instruction - Replace Steam & Water Pipe under W33rd | 30 | 30 | 0% | 2023-01-10 08:00 | 2023-02-22 17:00 | -193 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1 | NA | x |  |  |  | CO108-01025 | Change Order | Project Change Orders |  | CO #108 - Prepare Shop Drawings | 10 | 10 | 0% | 2023-02-23 08:00 | 2023-03-08 17:00 | -193 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1 | NA | x |  |  |  | CO108-01030 | Change Order | Project Change Orders |  | CO #108 - Review/Approve Shop Drawings | 10 | 10 | 0% | 2023-03-09 08:00 | 2023-03-22 17:00 | -193 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1 | NA | x |  |  |  | CO108-01035 | Change Order | Project Change Orders |  | CO #108 - Procure Pipe | 60 | 60 | 0% | 2023-03-23 08:00 | 2023-06-15 17:00 | -193 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1 | NA | x |  |  |  | CO108-01040 | Change Order | Project Change Orders |  | CO #108 - Perform Pipe Replacement | 30 | 30 | 0% | 2023-06-16 08:00 | 2023-07-28 17:00 | -193 | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG5, OG8 | x |  |  |  | RFI628-01005 |  |  |  | RFI #628 - Underground Steam Piping Route from OG8 to OG5 Street Crossing - Submit | 1 | 0 | 100% | 2022-08-12 08:00 | 2022-08-12 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG5, OG8 | x |  |  |  | RFI628-01010 |  |  |  | RFI #628 - Underground Steam Piping Route from OG8 to OG5 Street Crossing - Response | 24 | 0 | 100% | 2022-08-15 | 2022-09-16 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 |  | x |  |  |  | RFI518-01005 |  |  |  | RFI #518 PCOCO 68 Expose Existing Underground Pipe Under W33rd & W35th St - Submit | 1 | 0 | 100% | 2022-03-02 08:00 | 2022-03-02 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 |  | x |  |  |  | RFI518-01010 |  |  |  | RFI #518 PCOCO 68 Expose Existing Underground Pipe Under W33rd & W35th St - Response | 11 | 0 | 100% | 2022-03-03 | 2022-03-17 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG5 | x |  |  |  | RFI501-01005 |  |  |  | RFI #501 - Underground Pipe Street Crossing at OG-5 - Submit | 1 | 0 | 100% | 2022-02-09 08:00 | 2022-02-09 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG5 | x |  |  |  | RFI501-01010 |  |  |  | RFI #501 - Underground Pipe Street Crossing at OG-5 - Response | 99 | 0 | 100% | 2022-02-10 | 2022-06-30 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG5 | x |  |  |  | RFI428-01005 |  |  |  | RFI #428 - Underground Pipe Street Crossing at OG-5 - Submit | 1 | 0 | 100% | 2021-11-17 08:00 | 2021-11-17 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG5 | x |  |  |  | RFI428-01010 |  |  |  | RFI #428 - Underground Pipe Street Crossing at OG-5 - Response | 267 | 0 | 100% | 2021-11-18 | 2021-12-13 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG5 | x |  |  |  | RFI426-01005 |  |  |  | RFI #426 - Underground Pipe insulation Street Crossing at OG-5, OG-3 & S8 - Submit | 1 | 0 | 100% | 2021-11-15 08:00 | 2021-11-15 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG5 | x |  |  |  | RFI426-01010 |  |  |  | RFI #426 - Underground Pipe insulation Street Crossing at OG-5, OG-3 & S8 - Response | 11 | 0 | 100% | 2021-11-16 | 2021-12-01 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 |  | x |  |  |  | RFI422-01005 |  |  |  | RFI #422 - Underground Pipe Street Crossing at 33rd St - Submit | 1 | 0 | 100% | 2021-11-08 08:00 | 2021-11-08 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 |  | x |  |  |  | RFI422-01010 |  |  |  | RFI #422 - Underground Pipe Street Crossing at 33rd St - Response | 2 | 0 | 100% | 2021-11-09 | 2021-11-11 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG5 | x |  |  |  | RFI398-01005 |  |  |  | RFI #398 - OG-5 Underground Street Crossing Electrical - Submit | 1 | 0 | 100% | 2021-10-15 08:00 | 2021-10-15 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG5 | x |  |  |  | RFI398-01010 |  |  |  | RFI #398 - OG-5 Underground Street Crossing Electrical - Response | 2 | 0 | 100% | 2021-10-18 | 2021-10-19 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG8 | x |  |  |  | RFI332-01005 |  |  |  | RFI #332 - OG8 Underground Pre-Engineered Pipe Layout & POE - Submit | 1 | 0 | 100% | 2021-08-06 08:00 | 2021-08-06 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG8 | x |  |  |  | RFI332-01010 |  |  |  | RFI #332 - OG8 Underground Pre-Engineered Pipe Layout & POE - Response | 9 | 0 | 100% | 2021-08-09 | 2021-08-19 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 |  | x |  |  |  | RFI304-01005 |  |  |  | RFI #304 - Potential Deterioration to underground pipe installed under previous contract - Submit | 1 | 0 | 100% | 2021-07-15 08:00 | 2021-07-15 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 |  | x |  |  |  | RFI304-01010 |  |  |  | RFI #304 - Potential Deterioration to underground pipe installed under previous contract - Response | 54 | 0 | 100% | 2021-07-16 | 2021-09-30 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 |  | x |  |  |  | RFI301-01005 |  |  |  | RFI #301 - Underground Pre-installed utilities - Package 2 - Submit | 1 | 0 | 100% | 2021-07-02 08:00 | 2021-07-02 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 |  | x |  |  |  | RFI301-01010 |  |  |  | RFI #301 - Underground Pre-installed utilities - Package 2 - Response | 6 | 0 | 100% | 2021-07-05 | 2021-07-13 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG8 | x |  |  |  | RFI283-01005 |  |  |  | RFI #283 - Revised OG8 Foundation Drawings - Submit | 1 | 0 | 100% | 2021-06-21 08:00 | 2021-06-21 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG8 | x |  |  |  | RFI283-01010 |  |  |  | RFI #283 - Revised OG8 Foundation Drawings - Response | 9 | 0 | 100% | 2021-06-22 | 2021-07-02 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG8 | x |  |  |  | RFI281-01005 |  |  |  | RFI #281 - OG-8 into OG-5 UG LPS POE connecting to interior new LPS routing / design - Submit | 1 | 0 | 100% | 2021-06-21 08:00 | 2021-06-21 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG8 | x |  |  |  | RFI281-01010 |  |  |  | RFI #281 - OG-8 into OG-5 UG LPS POE connecting to interior new LPS routing / design - Response | 4 | 0 | 100% | 2021-06-22 | 2021-06-25 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 |  | x |  |  |  | RFI200-01005 |  |  |  | RFI #200 - Package 2 Discrepancies with Electrical - Submit | 1 | 0 | 100% | 2021-03-11 08:00 | 2021-03-11 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 |  | x |  |  |  | RFI200-01010 |  |  |  | RFI #200 - Package 2 Discrepancies with Electrical - Response | 7 | 0 | 100% | 2021-03-12 | 2021-03-22 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 |  | x |  |  |  | RFI194-01005 |  |  |  | RFI #194 - Package 2 As-built Drawings - Submit | 1 | 0 | 100% | 2021-03-05 08:00 | 2021-03-05 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 |  | x |  |  |  | RFI194-01010 |  |  |  | RFI #194 - Package 2 As-built Drawings - Response | 1 | 0 | 100% | 2021-03-08 | 2021-03-08 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG8 | x |  |  |  | RFI111-01005 |  |  |  | RFI #111 - OG-5 to OG-8 Underground Electrical Conduit Ductbank - Submit | 1 | 0 | 100% | 2020-09-22 08:00 | 2020-09-22 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG8 | x |  |  |  | RFI111-01010 |  |  |  | RFI #111 - OG-5 to OG-8 Underground Electrical Conduit Ductbank - Response | 16 | 0 | 100% | 2020-09-23 | 2020-10-15 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | S8 | x |  |  |  | RFI506-01005 |  |  |  | RFI #506 - Site 8 Underground Steam POE to Street Connection - Submit (CO #60) | 5 | 0 | 100% | 2022-02-16 08:00 | 2022-02-16 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | S8 | x |  |  |  | RFI506-01010 |  |  |  | RFI #506 - Site 8 Underground Steam POE to Street Connection - Response (CO #60) | 5 | 0 | 100% | 2022-02-17 | 2022-03-22 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.1.2 |  | x |  |  |  | CO060-01005 |  |  |  | CO #60 - Scope Development - Replace Steam & Water Pipe under W35th Street | 5 | 0 | 100% | 2021-10-06 08:00 | 2021-11-06 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.1.2 |  | x |  |  |  | CO060-01010 |  |  |  | CO #60 - Scope Agreement - Replace Steam & Water Pipe under W35th Street | 20 | 0 | 100% | 2021-11-08 | 2022-01-13 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.1.2 |  | x |  |  |  | CO060-01015 |  |  |  | CO #60 - Submit Price - Replace Steam & Water Pipe under W35th Street | 5 | 0 | 100% | 2022-01-14 08:00 | 2022-02-11 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.1.2 |  | x |  |  |  | CO060-01020 |  |  |  | CO #60 - Negotiate - Replace Steam & Water Pipe under W35th Street | 8 | 0 | 100% | 2022-02-14 08:00 | 2022-11-03 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
In Progress | CI NYCHA Update #25.1.2 | NA | x |  |  |  | CO060-01025 | Change Order | Project Change Orders |  | CO #60 - Revise Scope - Replace Steam & Water Pipe under W35th Street | 30 | 10 | 66% | 2022-11-04 | 2022-12-08 17:00 | -202 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1.2 | NA | x |  |  |  | CO060-01030 | Change Order | Project Change Orders |  | CO #60 - Revised Scope Agreement - Replace Steam & Water Pipe under W35th Street | 20 | 20 | 0% | 2022-12-09 08:00 | 2023-01-09 17:00 | -202 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1.2 | NA | x |  |  |  | CO060-01035 | Change Order | Project Change Orders |  | CO #60 - Submit Revised Price - Replace Steam & Water Pipe under W35th Street | 10 | 10 | 0% | 2023-01-10 08:00 | 2023-01-24 17:00 | -202 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1.2 | NA | x |  |  |  | CO060-01040 | Change Order | Project Change Orders |  | CO #60 - Negotiate Revised Scope - Replace Steam & Water Pipe under W35th Street | 30 | 30 | 0% | 2023-01-25 08:00 | 2023-03-08 17:00 | -202 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1.2 | NA | x |  |  |  | CO060-01045 | Change Order | Project Change Orders |  | CO #60 - Prepare Drawings - Replace Steam & Water Pipe under W35th Street | 10 | 10 | 0% | 2023-03-09 08:00 | 2023-03-22 17:00 | -202 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1.2 | NA | x |  |  |  | CO060-01050 | Change Order | Project Change Orders |  | CO #60 - Review/Approve Drawings - Replace Steam & Water Pipe under W35th Street | 10 | 10 | 0% | 2023-03-23 08:00 | 2023-04-05 17:00 | -202 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1.2 | NA | x |  |  |  | CO060-01055 | Change Order | Project Change Orders |  | CO #60 - Procure Pipe - Replace Steam & Water Pipe under W35th Street | 60 | 60 | 0% | 2023-04-06 08:00 | 2023-06-29 17:00 | -202 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1.2 | NA | x |  |  |  | CO060-01060 | Change Order | Project Change Orders |  | CO #60 - Perform Pipe Replacement - Replace Steam & Water Pipe under W35th Street | 30 | 30 | 0% | 2023-06-30 08:00 | 2023-08-11 17:00 | -202 | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG3 | x |  |  |  | RFI421-01005 |  |  |  | RFI #421 Underground Pipe Street Crossing at OG-3 - Submit (CO #60) | 5 | 0 | 100% | 2021-11-05 08:00 | 2021-11-05 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG3 | x |  |  |  | RFI421-01010 |  |  |  | RFI #421 Underground Pipe Street Crossing at OG-3 - Response (CO #60) | 5 | 0 | 100% | 2021-11-08 | 2021-12-23 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.1.3 | SG3 | x |  |  |  | CO122-01005 |  |  |  | CO #122 - Scope Development - SG3 AC Units & Window Guards | 5 | 0 | 100% | 2022-11-07 08:00 | 2022-11-13 |  | #N/A | #N/A | #N/A | #N/A | #N/A
In Progress | CI NYCHA Update #25.1.3 | SG3 | x |  |  |  | CO122-01010 | Change Order | Project Change Orders |  | CO #122 - Scope Agreement - SG3 AC Units & Window Guards | 30 | 20 | 33% | 2022-11-14 | 2022-12-22 17:00 | -157 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1.3 | SG3 | x |  |  |  | CO122-01015 | Change Order | Project Change Orders |  | CO #122 - Submit Price - SG3 AC Units & Window Guards | 10 | 10 | 0% | 2022-12-23 08:00 | 2023-01-09 17:00 | -157 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1.3 | SG3 | x |  |  |  | CO122-01020 | Change Order | Project Change Orders |  | CO #122 - Negotiate - SG3 AC Units & Window Guards | 30 | 30 | 0% | 2023-01-10 08:00 | 2023-02-22 17:00 | -157 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1.3 | SG3 | x |  |  |  | CO122-01025 | Change Order | Project Change Orders |  | CO #122 - Perform Work - SG3 AC Units & Window Guards | 20 | 20 | 0% | 2023-02-23 08:00 | 2023-03-22 17:00 | -157 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1.3 | NA | x |  |  |  | CO122-01030 | Change Order | Project Change Orders |  | CO #122 - Additional Time for Heating under Low Temperatures | 10 | 10 | 0% | 2023-03-23 08:00 | 2023-04-05 17:00 | -141 | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.1.4 | SG7, OG8, OG9, OG10, Site 8 | x |  |  |  | CO123-01005 |  |  |  | CO #123 - Scope Development - Substitute for Cladding Design OG9, OG10, SG7, S8 | 5 | 0 | 100% | 2022-11-18 08:00 | 2022-11-22 |  | #N/A | #N/A | #N/A | #N/A | #N/A
In Progress | CI NYCHA Update #25.1.4 | SG7, OG8, OG9, OG10, Site 8 | x |  |  |  | CO123-01010 | Change Order | Project Change Orders |  | CO #123 - Scope Agreement - Substitute for Cladding Design OG9, OG10, SG7, S8 | 30 | 20 | 33% | 2022-11-23 | 2022-12-22 17:00 | -15 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1.4 | SG7, OG8, OG9, OG10, Site 8 | x |  |  |  | CO123-01015 | Change Order | Project Change Orders |  | CO #123 - Submit Price - Substitute for Cladding Design OG9, OG10, SG7, S8 | 10 | 10 | 0% | 2022-12-23 08:00 | 2023-01-09 17:00 | -15 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1.4 | SG7, OG8, OG9, OG10, Site 8 | x |  |  |  | CO123-01020 | Change Order | Project Change Orders |  | CO #123 - Negotiate - Substitute for Cladding Design OG9, OG10, SG7, S8 | 30 | 30 | 0% | 2023-01-10 08:00 | 2023-02-22 17:00 | -15 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1.4 | SG7, OG8, OG9, OG10, Site 8 | x |  |  |  | CO123-01025 | Change Order | Project Change Orders |  | CO #123 - Procure Materials - Substitute for Cladding Design OG9, OG10, SG7, S8 | 10 | 10 | 0% | 2023-02-23 08:00 | 2023-03-08 17:00 | -15 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1.4 | OG9 | x |  |  |  | CO123-01030 | Change Order | Project Change Orders |  | CO #123 - Perform Work @ OG9 | 10 | 10 | 0% | 2023-03-09 08:00 | 2023-03-22 17:00 | -15 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1.4 | OG10 | x |  |  |  | CO123-01040 | Change Order | Project Change Orders |  | CO #123 - Perform Work @ OG10 | 10 | 10 | 0% | 2023-03-23 08:00 | 2023-04-05 17:00 | -15 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1.4 | SG7 | x |  |  |  | CO123-01050 | Change Order | Project Change Orders |  | CO #123 - Perform Work @ SG7 | 10 | 10 | 0% | 2023-04-06 08:00 | 2023-04-19 17:00 | -15 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1.4 | S8 | x |  |  |  | CO123-01060 | Change Order | Project Change Orders |  | CO #123 - Perform Work @ Site 8 | 10 | 10 | 0% | 2023-04-20 08:00 | 2023-05-03 17:00 | -15 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1 | OG8 | x |  |  |  | CO007-01037 | Change Order | Project Change Orders |  | Install Boiler Accessories - OG8 | 15 | 15 | 0% | 2022-12-12 08:00 | 2023-01-03 17:00 | -65 | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG9 | x |  |  |  | RFI127-01005 |  |  |  | RFI #127 - OG9 Structural Steel missing dimensions - Submit | 1 | 0 | 100% | 2020-10-30 08:00 | 2020-10-30 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG9 | x |  |  |  | RFI127-01010 |  |  |  | RFI #127 - OG9 Structural Steel missing dimensions - Response | 5 | 0 | 100% | 2020-11-02 | 2020-11-09 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG9 | x |  |  |  | RFI166-01005 |  |  |  | RFI #166 - Follow up RFI for RFI #127 - OG9 Missing Dimensions - Submit | 1 | 0 | 100% | 2021-01-04 08:00 | 2021-01-04 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG9 | x |  |  |  | RFI166-01010 |  |  |  | RFI #166 - Follow up RFI for RFI #127 - OG9 Missing Dimensions - Response | 16 | 0 | 100% | 2021-01-05 | 2021-01-27 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG9 | x |  |  |  | RFI619-01005 |  |  |  | RFI #619 - OG9 Windscreen vs Metal Panel - Submit | 1 | 0 | 100% | 2022-08-05 08:00 | 2022-08-05 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG9 | x |  |  |  | RFI619-01010 |  |  |  | RFI #619 - OG9 Windscreen vs Metal Panel - Response | 7 | 0 | 100% | 2022-08-08 | 2022-08-16 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 |  | x |  |  |  | RFI656-01005 |  |  |  | RFI #656 - Metal panel vs wind screen issue - Submit | 1 | 0 | 100% | 2022-09-29 08:00 | 2022-09-29 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 |  | x |  |  |  | RFI656-01010 |  |  |  | RFI #656 - Metal panel vs wind screen issue - Response | 11 | 0 | 100% | 2022-09-30 | 2022-10-17 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 |  | x |  |  |  | RFI672-01005 |  |  |  | RFI #672 - Follow Up to RFI 656: Metal Panel vs Wind Screen Issue - Submit | 1 | 0 | 100% | 2022-10-24 08:00 | 2022-10-24 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 |  | x |  |  |  | RFI672-01010 |  |  |  | RFI #672 - Follow Up to RFI 656: Metal Panel vs Wind Screen Issue - Response | 16 | 0 | 100% | 2022-10-25 | 2022-11-17 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 |  | x |  |  |  | RFI619-01015 |  |  |  | RFI #619 - Designer Review Options and provide direction to cut panels | 38 | 0 | 100% | 2022-08-16 08:00 | 2022-10-07 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | SG3 | x |  |  |  | RFI663-01005 |  |  |  | RFI #663 - SG3 AC Units & Window Guards - Submit | 1 | 0 | 100% | 2022-10-12 | 2022-10-12 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | SG3 | x |  |  |  | RFI663-01010 |  |  |  | RFI #663 - SG3 AC Units & Window Guards - Response | 16 | 0 | 100% | 2022-10-13 | 2022-10-31 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | SG3 | x |  |  |  | RFI681-01005 |  |  |  | RFI #681 - SG3 Window Guards (Follow up to RFI 663) - Submit | 1 | 0 | 100% | 2022-11-01 08:00 | 2022-11-01 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | SG3 | x |  |  |  | RFI681-01010 |  |  |  | RFI #681 - SG3 Window Guards (Follow up to RFI 663) - Response | 6 | 0 | 100% | 2022-11-02 | 2022-11-09 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | SG3 | x |  |  |  | RFI690-01005 |  |  |  | RFI #690 - SG3 Window Guards (Follow up to RFI 663 & 681) - Submit | 1 | 0 | 100% | 2022-11-17 08:00 | 2022-11-17 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | SG3 | x |  |  |  | RFI690-01010 |  |  |  | RFI #690 - SG3 Window Guards (Follow up to RFI 663 & 681) - Response | 3 | 0 | 100% | 2022-11-18 | 2022-11-22 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG5 | x |  |  |  | RFI628-01015 |  |  |  | RFI #628 - Weekly Meeting Topic 68.12 OG5 to Street Connection (33rd Street Crossing) | 5 | 0 | 100% | 2022-01-26 | 2022-09-14 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.1.2 | OG3 | x |  |  |  | CO060-02030 |  |  |  | CO #60 - Weekly Meeting Topic 68.11 OG3 & Site 8 Existing/New (35th Street Crossing) | 5 | 0 | 100% | 2022-01-26 08:00 | 2022-09-14 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
In Progress | CI NYCHA Update #25.1.1 | NA | x |  |  |  | CO059-01037 | Change Order | Project Change Orders |  | CO #59 (PDLCO1) - Con Ed Price and Schedule Shutdown | 20 | 10 | 50% | 2022-08-26 08:00 | 2022-12-08 17:00 | 22 | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1.2 | NA | x |  |  |  | CO060-01065 | Change Order | Project Change Orders |  | Complete Remaining Curtain Wall affected by Change Order #60 | 20 | 20 | 0% | 2023-09-12 08:00 | 2023-10-09 17:00 | -202 | #N/A | #N/A | #N/A | #N/A | #N/A
Completed | CI NYCHA Update #25.19 | OG3 | x |  |  |  | RFI421-01015 |  |  |  | RFI #421 - Weekly Meeting Topic 68.11 OG3 & Site 8 Existing/New (35th Street Crossing) | 5 | 0 | 100% | 2022-01-26 | 2022-09-14 17:00 |  | #N/A | #N/A | #N/A | #N/A | #N/A
Not Started | CI NYCHA Update #25.1 |  | x |  |  |  | CO108-01045 | Change Order | Project Change Orders |  | CO #108 - Complete Remaining Curtain Wall affected by Change Order #108 | 10 | 10 | 0% | 2023-09-26 08:00 | 2023-10-09 17:00 | -185 | #N/A | #N/A | #N/A | #N/A | #N/A

## Count
|  | Activity Status | (Multiple Items)
Row Labels | Count of Activity ID | Row Labels | Count of Activity ID
Completed | 3707 | NA | 120
In Progress | 307 | OG1 | 118
Not Started | 2244 | OG10 | 92
Grand Total | 6258 | OG2 | 114
|  | OG3 | 105
|  | OG4 | 111
|  | OG5 | 108
|  | OG6 | 178
|  | OG8 | 132
|  | OG9 | 99
|  | OGE | 58
|  | OGP1 | 45
|  | OGW | 55
|  | S8 | 48
|  | S81 | 162
|  | S82 | 127
|  | SG1 | 88
|  | SG2 | 87
|  | SG3 | 187
|  | SG4 | 81
|  | SG5 | 109
|  | SG6 | 68
|  | SG7 | 155
|  | SG7, OG8, OG9, OG10, Site 8 | 4
|  | SGN | 33
|  | SGS | 66
|  | (blank) | 1
|  | Grand Total | 2551